Memo to:

Lynn Blair

Mike Stage

Sherry Forbish

Randy Janzen

Shelley Corman
Larry Berger

Joe Linhart

Steve Weller

Chris Greaney

2/20 Meeting:

Dana Kirk

Larry Berger

Joe Linhart



Alex Brinis

Sherry Forbish

Steve Weller

Michael Rodriguez
Randy Janzen

Meeting “To Do” List:

Steve is to contact Transok, specifically Michael Walker, Bill Culbertson and Tracie Dobbs, to arrange a meeting of all parties (NNG, FPL, and AEP), to discuss procedures for reporting volumes timely and maximum length of time for reallocation of volumes.  It presently takes a significant number of days to receive Transok’s allocation for the prior production month.  Further, Transok has made a reallocation as late as eight months after the production month.   To be done by Feb. 26th.
Steve is to contact AEP to discuss volumes (and corresponding dollars due) currently on AEP’s pipe.  These monies will be collected from AEP and then disbursed to FPL. 

Call was made to AEP on 20th, waiting for return call.  To be done by Feb. 26th.
Randy is to provide a copy of the FPL A/R – this has been accomplished.

Randy is to provide a procedure for communicating monthly volumes to Michael Rodriguez and Jamie Schnorf, FPL; Tracie Dobbs, Transok; Howard Camp, AEP, after Transok’s monthly allocation.  The intent is to have all parties “sign off” on the volumes allocated.  Jan 2002 will be done by Feb. 28th.

Michael Rodriguez is to request access to NNG’s Flowing Gas so he may view volumes online.  Be done by Feb. 22nd.
Howard Camp is to request access to NNG’s Flowing Gas so he may view volumes online.  Be done by Feb. 22nd.

Per Lynn:

Dates are to be assigned to each task.

Weekly updates are to be provided to her attention.

Randy is to accompany Steve to meet with both Transok and AEP.

It is critical to detail all volumes correctly to minimize confusion and error.

