TIMELINE

Red = State Proceedings

Green = FERC

Blue = HSR, NRC, OREFSC

Plum = SEC

	
	Action
	Resonsible 
	participants

	8.29 (AM)
	OPUC all hands meeting in Portland.  
	Enron
	Ackerman, Lesh, Kaufman, Morgan, NNG Counsel.

	8.30 (PM)
	WUTC all hands meeting in Portland.
	Enron
	Ackerman, Lesh, Kaufman, Morgan, NNG Counsel.

	9.4
	FERC all hands meeting in Portland.  
	Enron
	Susan Ackerman, Pamela Lesh, Mike Morgan, Paul Kaufman, Julie Solomon (or Bill Hieronymous), Adam Wenner, NNG FERC Counsel … ?

	9.5 (AM)
	SEC all hands meeting in Portland.  
	Enron
	Ackerman, Lesh, Kaufman, Morgan, Wenner, Joann Rutkowski, NNG SEC Counsel

	9.6
	Meeting with Chairman Hemmingway and Comm’r Beyer
	NNG
	Mark Dodson, Peggy Fowler, Kaufman

	9.6
	Meeting with Comm’r Smith.
	NNG
	Dodson, Fowler, Ackerman, Lesh

	9.7
	PR all hands meeting in Portland.  
	Enron
	Dodson, Greg Kantor, Kaufman, Mark Palmer …?

	9.8
	Meetings with Governor’s office, Sen. Doerfler, Simmons
	NNG
	Dodson, Fowler, Kaufman

	9.8
	Phone call to WUTC Chair Showalter, Comm’r Hemstad, Oshie
	NNG
	Dodson

	9.8
	Phone calls to OR Congressional Delegation
	NNG
	Dodson

	9.10

	Meeting with Sparling, Helman, Nyegaard
	NNG
	Ackerman, Lesh, Kaufman

	9.10
	Phone calls to Cannon and Pyron
	NNG
	Dodson and Fowler

	9.10
	Follow-up with Congressional Offices—Press packet
	
	

	9.10
	Phone call to Jenks
	NNG
	Ackerman and Lesh

	9.10
	Phone call to Lott
	NNG
	Ackerman

	9.10
	Phone call to Public Counsel
	NNG
	Ackerman and NNG WA Counsel

	9.10
	Phone call to Mayor Katz
	NNG
	Dodson and Fowler

	9.10
	Press-release after market closes
	NNG/Enron/PGE
	Kantor, Palmer

	9.10
	Phone call to FERC Chairman and Comm’r Brownell
	Enron
	Rick Shapiro and Dodson

	9.10
	Phone call to FERC Merger Staff
	Enron
	Wenner and NNG Counsel

	9.10
	Phone call to SEC Staff
	Enron
	Rutkowski and NNG Counsel

	9.11
	Follow-up meeting with ICNU, CUB, NWIGU
	NNG
	Ackerman, Lesh, Kaufman

	9.21
	Draft WUTC/OPUC testimony due
	NNG and PGE
	Ackerman, Lesh, Kaufman, Morgan and NNG Counsel

	9.21
	Draft NRC and OREFSC
	NNG and PGE
	Ackerman, Lesh, Kaufman

	10.3
	All hands FERC meeting in D.C.
	Enron
	Ackerman, Lesh, PGE Team, Kaufman, Solomon (or Hieronymous), Wenner, NNG FERC Counsel … ?

	10.4
	All hands SEC meeting in D.C.
	Enron
	Ackerman, Lesh, Kaufman, Wenner, Rutkowski, NNG SEC Counsel … ?

	10.5
	Revised draft of WUTC/OPUC testimony 
	NNG and PGE
	Ackerman, Lesh, Kaufman, Morgan and NNG Counsel

	10.5
	File WUTC/OPUC testimony and applications
	NNG and PGE
	Morgan and NNG Counsel

	10.5
	Open Data Room
	NNG and PGE
	

	10.8
	Draft FERC filing
	Enron
	Ackerman, Lesh, PGE Team, Kaufman, Solomon (or Hieronymous), Wenner, NNG FERC Counsel … ?

	10.11
	Pre-filing meeting with FERC Staff
	Enron
	Ackerman, PGE Representative, Kaufman, Solomon (or Hieronymous), Wenner, NNG FERC Counsel …

	10.12
	Draft SEC Filing
	Enron
	Ackerman, Lesh, Kaufman, Wenner, Rutkowski, NNG SEC Counsel … ?

	10.16
	Special Meeting of OPUC
	NNG and PGE
	

	10.17
	FERC all hands meeting in D.C.
	Enron
	Ackerman, Lesh, PGE Team, Kaufman, Solomon (or Hieronymous), Wenner, NNG FERC Counsel …

	10.18
	SEC all hands meeting in D.C.
	Enron
	Ackerman, Lesh, Kaufman, Wenner, Rutkowski, NNG SEC Counsel …

	10.19
	File NRC and OREFSEC
	NNG and PGE
	Ackerman, Lesh, Kaufman

	10.22
	OPUC Prehearing Conference
	NNG and PGE
	Ackerman, Lesh, Kaufman, Morgan, NNG Counsel

	10.22
	File FERC
	NNG, PGE, Enron
	Wenner and NNG FERC Counsel

	10.23
	WUTC Prehearing Conference
	NNG, Enron
	Ackerman, NNG Counsel, Morgan

	10.26
	File SEC
	NNG, PGE, Enron
	Rutkowski and NNG SEC Counsel

	10.26
	Assumed date for FERC notice
	
	

	11.16
	Draft OPUC NNG/PGE Rebuttal 
	
	

	11.23
	OPUC—NNG/PGE file Rebuttal
	NNG, PGE
	Ackerman, Lesh, Kaufman, Morgan, NNG Counsel

	11.30
	OPUC—NNG/PGE, Staff/Intervenors Surrebuttal
	
	

	11.9
	OPUC—Staff/Intervenors File Reply Testimony
	
	

	12.17
	Draft HSR Filing Due
	NNG, Enron
	

	12.21
	FERC approximate date for comments/protests
	NNG, Enron
	Wenner, NNG FERC Counsel

	12.3
	OPUC Hearings
	NNG, PGE
	Ackerman, Lesh, Kaufman, Morgan, NNG Counsel

	1.07.02
	FERC approximate date for NNG/Enron/PGE response to comments.
	
	

	1.16.02
	HSR Filing 
	NNG, Enron
	

	2.16.02
	HSR approximate date for second request.
	
	

	
	
	
	


Decision time frames

3.02
FERC Decision—assuming no hearing

7.02
OPUC Decision

8.02
HSR Completion

10.02
SEC Decision—2 months after final state decision

