Management Coordination Meeting Minutes

March 1, 2001


[image: image1.wmf]
WEEKLY SUMMARY

SEPTEMBER 28 – OCTOBER 4, 2001

1. Aconcagua (Deepwater) (Mississippi Canyon 305) (25% WI) – Mariner has accepted Nippons bid for 25% WI.  Expect to close November 1. 

2. Yosemite (Deepwater) (Green Canyon 516) (50% WI) – The Yosemite well was completed and tested successfully at rates up to 110 MMCFPD combined from two zones.  The manifold has been run and tested.  The process equipment has been successfully installed on the Allegheny host platform.  Umbilical lay starts next week. 

3. Falcon (Deepwater) (East Breaks 690) (50% WI) – Evaluating a lump sum proposal for project.  Meeting with pipeline companies to access interest in building and owning the host platform and export system.  Plan to begin ordering long lead items in October. 
4. Swordfish (Deepwater) (Viosca Knoll 917, 961, 962) (Planned WI 30% BCP, 15% ACP) - Received board approval on this opportunity.  Mariner has laid off a portion of its 50% BCP, 25% ACP working interest.  Burlington has committed to WI 50% BCP, 25% ACP and Samedan has committed to WI 20% BCP, 10% ACP.  BP will retain a WI 50% ACP.

5. Roaring Fork (Shelf - 450' WD) (South Timbalier 316) (Planned WI 40% BCP, 20% ACP) - Received management approval on this Westport operated shelf opportunity to participate in drilling a 13,500' PTD well ($6.5MM DHC).  The well is currently at 4,400’ prepped to drill out of 16” csg. The primary target is a Trim 'B' seismic amplitude anomaly at 12,100'. 

[image: image2.wmf]
CONFIDENTIAL

MANAGEMENT COORDINATION MEETING OF OCTOBER 4, 2001

HELD AT 580 WESTLAKE PARK BLVD., SUITE 1300

HOUSTON, TEXAS

PRESENT

C.
K.
Burgess

R.
R.
Clark

D.
M. 
Clement

G. 
K.  
Harless

D.
S. 
Huber

A. 
D.
Keel

S.
D.
Josey

M.
A.
Wichterich

M.
C.
van den Bold

T.
E. 
Young

K. 
D. 
Zelikovitz

cc:
M. 
A.
Altobelli

cc:
J. 
S. 
Hudson

cc: 
D.
cc:
C.
L.
Loegering



cc:
R. 
Bowen – ENAC

cc:
C.
Fox – ENAC

cc:
J.
Melendrez – ENAC

cc:
T.
Proffitt – ENAC

cc:
J.  
Sherrick – EGEP

cc:
J.
Thompson – ENAC

cc:
G.
Whalley – EWS

Note:

ENAC – Enron North America Corp.

EWS – Enron Wholesale Services

EGEP – Enron Global E&P

1. OPERATIONS

1.1
Development/Key Producing Fields
a. Aconcagua (Deepwater) (Mississippi Canyon 305) (25% WI) – Mariner has accepted Nippons bid for 25% WI.  Expect to close November 1. 
b. Pluto (Deepwater) (Mississippi Canyon 674/718) (51% WI) – Performed flowline blow-down and paraffin treatment. Brought well back on line with 5.0 MMCFPD increase in production. Recovered a small amount of paraffin. Repaired inlet flowline shut down valves.

c. Yosemite (Deepwater) (Green Canyon 516) (50% WI) – The Yosemite well was completed and tested successfully at rates up to 110 MMCFPD combined from two zones.  The manifold has been run and tested.  The process equipment has been successfully installed on the Allegheny host platform.  Umbilical lay starts next week. 

d. Falcon (Deepwater) (East Breaks 690) (50% WI) – Evaluating a lump sum proposal for project.  Meeting with pipeline companies to access interest in building and owning the host platform and export system.  Plan to begin ordering long lead items in October. 

2. EXPLORATION & LAND
2.1 Swordfish (Deepwater) (Viosca Knoll 917, 961, 962) (Planned WI 30% BCP, 15% ACP) - Received board approval on this opportunity.  Mariner has laid off a portion of its 50% BCP, 25% ACP working interest.  Burlington has committed to WI 50% BCP, 25% ACP and Samedan has committed to WI 20% BCP, 10% ACP.  BP will retain a WI 50% ACP.

2.2 Roaring Fork (Shelf - 450' WD) (South Timbalier 316) (Planned WI 40% BCP, 20% ACP) - Received management approval on this Westport operated shelf opportunity to participate in drilling a 13,500' PTD well ($6.5MM DHC).  The well is currently at 4,400’ prepped to drill out of 16” csg. The primary target is a Trim 'B' seismic amplitude anomaly at 12,100'. 

2.3 Texaco Farmout - East Breaks - Finalizing agreements.

2.4 Western Gulf of Mexico Lease Sale - OCS Sale 180 - Mariner was the high bidder on 13 deepwater blocks.  Twelve of the bids were with Pioneer 50% and the remaining bid was 100% Mariner.  As of today, three blocks have been awarded with the remaining ten blocks moving into phase 2 of the MMS’ evaluation.

3.
FINANCE & ADMINISTRATION

3.1 Revolver Debt - At October 4, 2001, we continue to have no borrowings against our $80 million Bank of America-led revolving credit facility, and we had short-term investments of $0.1 million.

Our mid-year borrowing base redetermination is currently in progress.  We have requested no change to the $80 million borrowing base at this time. 

3.2 Accounts Payable Imaging System – We are beginning implementation of a system to image and further automate our accounts payable processing system.  System is expected to be operational in the fourth quarter of 2001. 

3.3 Budget – Distributed budget timing with kickoff meeting scheduled October 15, 2001.

3.
FINANCE & ADMINISTRATION

3.4 Insurance – Finalized Pluto tree builders risk claim and forwarded final proof of loss to underwriters.  Should receive check in September.  Continue to gather information and invoices on Pluto umbilical claim.  All claims continue to work well. 

Working with TotalFinaElf on outstanding builders risk coverage on Canyon Express.  

Working with Burlington on Monet/Hells Canyon claim. 

3.5
Document Retention Policy – Distributed document retention policy for comments due October 11, 2001.

4.
LEGAL
4.1 Roaring Fork – Working on Participation Agreement(s) with Westport and Samedan.  

4.2 TGS Seismic Acquisition Agreement – Finalized agreement terms; execution of agreement is subject to board approval. 

4.3 Aconcagua – Revised Purchase and Sale Agreement  to respond to Nippon’s comments. 

4.4 Falcon – Finalizing today a purchase order for the purchase of the umbilical and 10” pipeline (long-lead items) from Coflexip and working with the Falcon team and Pioneer on a potential turnkey contract with Coflexip covering additional aspects of the Falcon development project. 

4.5 Swordfish – Finalizing participation agreement with Burlington. 

4.6 McClelland – Working with Land to finalize Farmin Agreement with Texaco/TFE.

4.7 Dulcimer Litigation – Kelly Zelikovitz to testify on October 9 at hearing on motion to enforce prior settlement. 

5.
GAS & OIL SALES

5.1 West Texas Intermediate posted prices:

WTI moved from $18.50 - $19.00 effective September 26.

WTI moved from $19.00 - $19.50 effective September 27.

WTI moved from $1.505 - $20.25 effective September 28.

5.2 NYMEX Gas.  The 12 month forward Nymex price as of October 3 is $2.82 per MMBTU; quotes by month are as follows:

NOV.
DEC.
JAN.
FEB.
MAR.
APR.

$2.32
$2.68
$2.89
$2.88
$2.84
$2.75

6.
PRODUCTION

Mariner’s oil and gas prices (restated net of transportation) and production are as follows:


Jan

Actual
Feb.

Actual
March

Actual
April

Actual
May

Actual
June

Actual

Monthly Pre-Hedge Prices:

Oil ($/bbl)
$25.61
$25.30
$23.51
$23.04
$24.69
$24.15

Gas ($/mcf)
$10.38
$6.59
$5.42
$5.70
$4.97
$3.80

Year-to-Date Weighted Average Gas Prices ($/MCF):

W/O Hedge
$10.38
$8.50
$7.52
$7.02
$6.59
$6.21

With Hedge
$6.60
$5.84
$5.56
$5.36
$5.15
$4.96

Production:

Oil (bbl/d)
8,941
8,125
8,848
8,735
8,433
7,791

Gas (mmcf/d)
56.9
64.2
62.2
67.9
63.9
49.4

*Gas production decline in June reflects watering out of Apia field.

� EMBED CorelDraw.Graphic.8  ���





� EMBED CorelDraw.Graphic.8  ���








H:\Word\Minutes\Mgmt Mtg\10-4-01.doc

[image: image3.wmf]_1047130911.unknown

