[image: image1.png]E CALIFORNIA ISO





DRAFT (8/29/00)

Software Implementation Release for

ADS, BBS, MDAS, SI/SA

INSTALLATION SCHEDULE

SCHEDULE OF EVENTS:

#
Time
Task
Responsibility

Monday, August 28, 2000

1. 

Alert Market Participants' metering contacts that STAR will be unavailable during the upgrade on 8/29/00.
MDAS System Admin

Tuesday, August 29, 2000

2. 
By 1300
Send Installation Schedule to Market Participants, TSWG and Settlement Contacts
CRCommunications

3. 
1200 - COB
Begin configuring STAR metering systems for trade date 8/31.
MDAS Team

By COB Wednesday, August 30, 2000

4. 
1330
Conference Call to discuss Implementation
10-Min Team/SCs

5. 

Complete deployment of Final ADS Client to MP’s.  Verify connectivity and stability.
ADS Team

6. 
by COB
Complete configuration of STAR metering systems for trade date 8/31.
MDAS Team

Thursday, August 31, 2000

7. 
by COB
Clear up all MV90 communication problems with meters
MDAS Technical Analyst

8. 
by COB
Send all available hourly data for 8/30/00 to STAR
MDAS Technical Analyst

9. 
by COB
Remind MP's to manually read all appropriate meters on 9/1/00
MDAS Technical Analyst

10. 
2200 -- 2245
Run Markets for HE 0100 AND 0200

Close Real – Time Market for 2400

Put Real-Time Market for HE 0100 on HOLD.
HA GRC

Market Ops

11. 
2245 – 2300
SI Unavailable to Market


12. 
2245
Download all supplemental energy intertie schedules for HE 0100 and 0200 (minimum – the rest of hours  needs to be done after on-line) and convert to new format.  Default all PRE_DISP_FLG to “YES”.
Market Ops

13. 
2245 – 2300
Apply upgraded SI Software to Production System
Market Ops

14. 
2245 – 2300
Upload all supplemental energy intertie schedules for HE 0100 and 0200.
Market Ops

15. 
2300
SI Available to Market


16. 
2300
Remind SCs to submit Intertie supplemental bids in new format (w/ PRE_DISP_FLG)


17. 
2315
Close Supplemental Market for HE 0100
Market Ops

18. 
2400
Begin dispatching real-time markets using new 10-minute BEEP for HE 01 9/1/2000
RT GRC

Friday, September 1

19. 

Upgrade MDAS Online DB and Code
Structure Consulting

Coordinated by MDAS System Admin

Tuesday, September 5, 2000

20. 
by COB
Import manually read files from SC's into MV90.  Totalize data and send to STAR
MDAS Technical Analyst

21. 
by COB
Change Summary Maps in MV90 to 10 Minute intervals (except for those to remain hourly and the outstanding ID's)
MDAS System Admin

Wednesday, September 6, 2000

22. 
by COB
Start automatic 10 minute totalization in MV90
MDAS Team

23. 
by COB
Start automatic transfer of 10 minute data to STAR
MDAS Team

September 1 + 25 days

24. 
TBD
Run a “trial push” of a sample trade days with 10-minute energy calcs to Settlements.  Run settlements batch for sample trade days.
DBA

Market Ops

Settlements

Monday, October 9, 2000

25. 
by COB
Notify Market Participants that T+45 SQMD will be due on Monday, October 16, 2000
MDAS System Admin

Monday, October 16, 2000

26. 

SQMD data due for trade date 9/1/2000.   
Market Participants

September 1 + 50 days

27. 
1300
Push September 1 trade day to Settlements
DBA

28. 

Run Preliminary Settlements for September 1
Settlements

Septemeber 1 + ? days

29. 

Preliminary Settlements for Septmeber 1 Available







ISO Market Operations 

Last Revision:  08/29/00 1:03 PM
10-min Installation Schedule External.doc

