
Summary of Contract Terms

1 General Electric Frame 7EA Combustion Gas Turbine

Delivery Point:
Shall mean either (i) in the case of the turbine the Seller’s manufacturing facility in Greenville, South Carolina; (ii) in the case of material ship direct items, Vendor’s manufacturing facilities; or (iii) in the case of the generator, Purchaser designated U.S. Port of Import, as applicable.

Optional Delivery Point:
In the event Purchaser elects by Change Order to have a Unit delivered to a Site.

Delivery Date(s):
Gas Turbine and Generator
March 11, 2001





Remaining Major Components
March 31, 2001

Payment terms:
ENA shall assume the obligations of all remaining payments related to the turbine purchase price (including change orders), except those obligations arising after the closing date of the proposed transaction.
Retention Letter of Credit:
In the amount of $965,855, to be held by purchaser until final acceptance of the unit.  GE may replace with letter of credit in like amount.

Correction of Equipment:
GE is responsible for replacing or correcting any defective work or conditions prior to acceptance of the Unit.  GE must also correct punchlist items to Purchaser’s satisfaction not later than the Primary Warranty Period, or Purchaser may draw on Retention Letter of credit.

Document Liquidated 

Damages
1-30 days late
$500.00/day


31-90 days late
$1,000.00/day


91+ days late
$5,000.00/day

Delivery of Final

O&M Instructions 

Liquidated Damages
1-30 days late
$500.00/day


31-90 days late
$1,000.00/day


91+ days late
$5,000.00/day

if not delivered within 90 days after site delivery date of the Unit.

Delivery Liquidated Damages
day 1+

$14,500.00/day

Takeover Liquidated Damages
day 1+ 

$14,500 per day 

Specific Performance

Near Source Sound Level

Guarantee
Near field average A-weighted sound pressure levels for each Unit < 85dB(A) (referenced to 20 micropascals) when measured at 1.5 meters above any working elevation and 1 meter from the surface.

Specific Performance 

Exhaust Emissions Guarantee
Category

Load

Units of Measure
100%


NOx


9

ppmvd @ 15% O2
CO


25

ppmvd

Particulates (TSP)
5

lb/hr





PM10


n/a

lb/hr

UHC


7

ppmvw





VOC


n/a

ppmvw

Electrical Output Guarantee
Adjusted Electrical Output > 77,800 kW (net of Unit auxiliary loads).

Specific Performance Electrical

Output Guarantee
Adjusted Electrical Output > 75,466 kW (net of Unit auxiliary loads)

Heat Rate Guarantee
Adjusted Heat Rate not to exceed 10,720 BTU/kWh (LHV).

Specific Performance Heat

Rate Guarantee
Adjusted Heat Rate not to exceed 11,042 BTU/kWh (LHV).

Output Liquidated Damages
If the Unit achieves the Specific Performance Electrical Output Guarantee during Performance Test, but fails to achieve the Electrical Output Guarantee, that amount which is equal to the positive difference between the Electrical Output Guarantee and the Adjusted Electrical Output of the Unit multiplied by $708/kW.

Heat Rate Liquidated Damages
That amount which is equal to the positive difference between the Adjusted Heat Rate of the Unit and the Heat Rate Guarantee multiplied by $14,650 per BTU/kWh (LHV).

Maximum Document

Liquidated Damages
$100,000 per Unit

Max. Delivery Liquidated

Damages
 $1,931,710 per Unit

Max. Takeover Liquidated

Damages
$1,931,710 per Unit

Max. Output Liquidated 

Damages
$1,931,710 per Unit

Max. Heat Rate Liquidated

Damages
$2,897,565 per Unit

Max. Aggregate Liquidated

Damages
$5,795,130 per Unit

Overall Liability Cap
$19,317,100

[Remainder of page left intentionally blank]

