NETCO Structuring Re-Start/Integration Plan

	Action Items
	Person Responsible
	Estimated Date of Completion
	Issues/Comments
	

	Structuring Model Capabilities

	1. Identify model templates for potential NETCO business and transfer to common drive


	Power – Jim Meyn

Gas – Mark Breese
	Complete
	Location of files:

Power (Basic Swap/Option) – M:\power2\pricing\Pwr_strc97.xls

Other Power Models – M:\user_pub\todd\models

Gas – O:\Gas Structuring\Requested files
	

	2. Coordinate with Research and/or IT to ensure proper technical support for models at time of restart
	Berney Aucoin

Vince Kaminski

IT Rep – NETCO?
	Week of Jan. 7th
	Research has historically provided technical support/maintenance for EXOTICA library functions. We need to identify an IT/quant person with Visual Basic coding skills to maintain this library. Ideally, the same person supporting the code for the risk books would  maintain this library in the new company. Meeting to be set up for week of 1/7 to coordinate/transfer this capability from Research to NETCO.
	

	3. Transfer models into new IT domain.
	Jay Webb
	TBD
	In coordination with overall NETCO file transfer date
	

	4. Test models to risk systems
	Power – Berney (or designee)

Gas – Mark Breese
	TBD – should take a day or two
	Once #3 is complete, this process can begin. The timeframe is contingent on number of issues identified.
	


	Deal Processes/Controls

	1. Establish standard contract forms for identified commodity products
	Legal, Credit, Commercial Teams
	TBD
	
	

	2. Establish deal approval process.
	Office of Chairman, Commercial Teams
	TBD
	Will there be a RAC-like entity for NETCO?
	

	Back Office Execution/Reporting Capability

	1. Formalize deal capture process for deals from marketing.
	Commercial Leads,

Structuring

Power/Gas Risk Leads
	TBD
	Will there be a deal ticket process or automatic entry into risk system?
	

	2. Address P&L reporting standards
	Accounting
	TBD
	Accural vs. MTM? ; Origination?
	

	3. Develop Cash Flow reporting mechanisms
	Risk/Accounting, Structuring, Credit
	TBD
	Tilted Swaps, Option premiums, etc.
	


