Knowledge Management Pilot Charter


Knowledge Management

Pilot Project Charter

Table of Contents

Purpose of Document
3

Charter Purpose
3

Purpose of the Project
3

Business Drivers
3

Project Objectives
3

Expected Benefits
4

Project Scope (SCOPE dEFINITIONS)
4

Definitions
4

Objective 1 - Portal Pilot
5

Objective 2 - Prototype/Pilot Unstructured Data Management Tool
6

Objective 3 - Proposed Strategy for Knowledge Management
6

Deliverables
6

Estimated Project Activities and Timeline
6

Estimated Activities and Timeline
6

Risks AND DEPENDENCIES
7

Risks
7

Dependencies
9

project organization
10

Project Organization Chart
10

roles and responsibilities
11

APPendices
12

Appendix A - Background
12

Appendix B - Project Charter Sign Off
15




Purpose of Document

Charter Purpose

This project charter has been created for the knowledge management pilot project.  Its purpose is to foster an understanding of the project objectives, scope, and underlying assumptions upon which the project plan is based. The intent of this document is to provide additional depth and clarification to the project in total.  It also provides a baseline for scope control, describes the project organization, deliverables and schedule.  

This project charter also serves as the contract between all parties involved in the knowledge management pilot – the project sponsors, the project chair, and the task force.  Sign-off of this document indicates each party’s understanding of and agreement with the objectives, scope, deliverables, and schedule of the project.

Purpose of the Project

Business Drivers 

There currently exists within Enron multiple efforts aimed at improving access to information and sharing knowledge.  One business driver for this pilot is to identify ways to improve efficiencies and productivity levels by uniting multiple, independent data systems and reducing and/or eliminating redundant efforts.

Second, to remain the most innovative company on the globe, Enron needs to provide the culture and tools for rapidly sharing information.  Given this opportunity, employees will be best positioned to engage and reflect the greater intellectual collective of Enron experts worldwide. 

Project Objectives

The primary objectives of this project are to:

1. Implement a web entry point (portal) with the following characteristics:

· A clear, accessible yahoo-like web entry point to Enron’s universe of intranets, internal and external search tools and extranet sites  
· A maintenance standardized, easily accessible portal to eventually front certain Enron intranets, search tools and engines, and other systems

2. Develop a pilot/prototype of a qualitative data retrieval tool:

· An unobtrusive method of retrieving qualitative data and making this easily available 

3. Document a proposed strategy for Knowledge Management

· A definition of KM for Enron  

· Propose KM scope and objectives

· A recommendation on how to coordinate multiple KM BU initiatives

· An analysis of the costs and benefits

· A longer term vision for Knowledge Management 

· System requirements (high level)

· Cultural issues and recommendations

· Organizational structure recommendations

· Change management plan

Expected benefits upon completion of this project

1. Reduction of redundant efforts

2. Coordinated development efforts 

3. The first step towards tools and processes, which, if effectively implemented, could:  

· Increase efficiency in accessing data

· Make impromptu queries easier

· Improve product to market efficiencies

· Possibly increase revenues

· Create potential new sources of market opportunities 

· Enhance shareholder value 

Project Scope 

Definitions

	Scope
	Definition 

	Business Units, Functional Areas
	· Global Accounting

· RAC

· Government Affairs

· EBS

· IT

· Global HR

· Global Strategic Sourcing

	Knowledge Management
	· Coordinated effort across Enron 

· Increased ability to extract quantitative and qualitative data from existing systems

· Built with business purpose in mind

· Focused on culture, people, process, and technology

	Unstructured data management search tool
	A search tool potentially capable of the following (for qualitative data only):

· Automation of the search process

· Multiple doors entry to search process

· Automation of the retrieval process

· Unlimited interfaces through which search information is retrieved

· Automation of the information sharing process

· Automation of tagging information as proprietary process

· Automation of expert identification

· Automation of sourcing expert information 

· Mapping of users with needs to users with information

	Portal prototype
	A single web entry point fronting certain Enron intranet sites and applications  


Objective 1 – Portal Pilot

	In Scope
	Not in Scope

	· Developing, testing, and implementing a pilot for a yahoo-like prototype knowledge management portal 
	· Implementation of a portal to provide the only point of access to intranet sites, databases, applications, etc. 

· Implementation of a data warehouse, data storage facility

	*Selected Enron intranet sites and applications

· Peoplefinder

· eThink

· **ibuyit

· HR Web

      Global Compensation

      Performance Management

      eHRonline

· Pilot Unstructured Data Management Tool (available post UDM selection process)

· rac.enron.com

· A variety of feeds such as (Dow Jones feeds, market feeds, etc.)

· One of Rick Causey’s Four Buttons

Counterparty exposure button

*Will deliver if content/product is available

**Portal under continuous development
	· External sites or data feeds not defined at the time of implementation

· Internal sites not identified at the time of implementation

· Expertfinder

· eMail 

· Documents Repositories

LiveLink

      Lotus Notes Databases

· Expense Reporting

· Online Travel Booking Solution

· Corporate Risk Systems

      Risk Track & Credit Aggregation System

· Data warehouses

Trading systems (i.e. Enron Risk Management System)

Trading Support Systems

Pipeline Noms

Global Counterparty

SAP

· Three of Global Accounting’s Four Buttons

Cost Center

P&L

Cash

· Backweb


Objective 2 - Prototype/Pilot of Unstructured Data Management Tool (UDM)

	In Scope
	Not in Scope

	· Investigating UDM tools such as 80-20, Autonomy, Knowmatic, TACIT, and Vignette, selecting the tool of choice, then testing and piloting that tool
	· Implementation of a pilot for every search tool investigated

	· Implementing UDM pilot to allow employees increased ability to extract quantitative and qualitative data from existing systems 
	· Implementation of a UDM pilot which forces people to document their experience and best practices at a detail level

	· Implementing UDM pilot which retrieves knowledge by “spidering” the information
	· Implementation of a UDM pilot which replicates the data in an additional server


Objective 3 - Proposed Strategy for Knowledge Management

	In Scope
	Not in Scope

	· Preparation and proposal of strategy to project sponsors
	· Implementation of proposed strategy


Deliverables

1. Detailed project work plan

2. Unstructured Data Management Tool product selection criteria

3. UDM Tool product selection

4. UDM Pilot definition

5. UDM Pilot implementation

6. Measured results

7. Project report

8. Go/No Go decision

9. Limited project communications to select audiences
10. Limited project marketing to select audiences
11. Portal “pilot” 
12. Proposed KM strategy document (presentation format)
Estimated Project Activities and Timeline

Estimated Activities and Timeline

Phase I  - Beginning 11/03 through First Quarter 2001

· Business Analyst requirements report



Week of 12/11/00

· UDM tool evaluation and selection completed 


Week of 1/5/01

· Portal prototype evaluation and development


Completed

· Portal prototype unveiling at technology conference

Completed

· Portal prototype availability to selected audience


Completed

· Portal pilot communications to all employees of HR, Net Works, and GSS


Week of 12/11/00

· Portal pilot availability to all employees of HR, Net Works, and GSS



Week of 12/11/00

· Executive sponsor review of portal pilot



Week of 12/11/00

· UDM tool prototype contract negotiated (business terms)
Week of 1/19/01

· UDM tool prototype contract legal review



Week of 1/30/01

· UDM tool prototype contract fully executed


Week of 2/06/01

· UDM tool implementation for pilot
begins



Week of 2/08/01

· UDM tool prototype evaluation and development


Week of 2/22/01

· UDM tool prototype unveiling




Week of 2/26/01

· UDM tool availability to selected audience


Week of 3/01/01
· UDM tool pilot communications




Week of 3/01/01

· UDM tool pilot availability to all employees of HR, Net Works, and GSS



Week of 3/01/01

· Executive sponsor review of UDM pilot



Week of 3/01/01

· First draft of KM strategy review




Week of 2/01/01

· Final draft of KM strategy 





Week of 3/01/01

· Portal and UDM tool pilots completed



Week of 3/16/01

· Executive sponsor review of project



Week of 3/19/01

Risks and Dependencies

Risks

Listed below are the major risks that are facing the project team and the strategies for managing the risks:

1. Availability of Business Analyst – In order to determine the business requirements for the Unstructured Data Management tool, Peggy Alix will need to assign a Business Analyst to scope the business requirements to meet business problems. 
Strategy – Identify a Business Analyst.  Establish regular review as part of project management process.  Negotiate full-time participation.  If full-time participation is not possible, establish clear part-time commitment parameters – days/week, schedule, etc.

2. Challenges to complete the software selection process in a timely fashion – After the business requirements for the Unstructured Data Management tool are determined, John Simmons’ architecture team will need to identify the unstructured data management tool of choice which meets the identified business requirements.  John will need to assign resources to analyze the UDM tools. 
Strategy – Identify a software selection team to start after the BA completes his responsibilities.  Establish regular review as part of project management process.  Negotiate full-time participation.  If full-time participation is not possible, establish clear part-time commitment parameters – days/week, schedule, etc.

3. Availability of SME – In order to determine if the unstructured data management tool meets the identified business requirements, Subject Matter Expert, John Norden will need to analyze the UDM tools and companies within the above timeframes. 

Strategy – Establish regular review as part of project management process.  Negotiate full-time participation.  If full-time participation is not possible, establish clear part-time commitment parameters – days/week, schedule, etc.

4. Availability of task force members  – Due to the upcoming holidays in November and December, the risk associated with the unavailability of some of the staff is high, and could result in the postponement of the implementation of the pilot and prototype.
Strategy – Establish a holiday calendar for task force chair to reference task force members’ schedules.  Plan in advance to deal with task force members’ vacation schedules. 

5. Scoped as Enron-wide.  The portal has been scoped as an Enron wide tool, however, the task force resources do not represent all Enron business units.
Strategy –Review as part of project management process, the charter and work plan with key business unit leaders.

6. Challenges surrounding unveiling the new pilot portal 11/3 without a communication/marketing strategy implemented.  The IT organization will be unveiling a pilot version of a personalized portal when Corp has already released myhome.enron.com and EBS released wEBSource.  There does not appear to be a synchronized front on portal delivery.  This may be confusing for employees.  
Strategy – Provide limited communications surrounding the pilot portal release.  Before releasing the final version of the portal (not the portal pilot), a communication/marketing effort must be planned and executed.
7. Managing Expectations.  Project addresses front-end portal and qualitative search tool only.  Much will need to be built in addition to these tools to truly access Enron-wide information (e.g. quantitative search tools, data warehouses, etc.)  People may expect much more than can actually be delivered in a short timeframe.  
Strategy  - Review as part of the Proposed Strategy for Knowledge Management, future considerations for Phase II of this project.  Perform limited communication.

8. Enron culture not consistent with knowledge sharing.  Rollout of tools for knowledge sharing does not mean people will use them.  In fact, we are aware of several instances where sharing knowledge or resources with another Business Unit has been discouraged.
Strategy - Provide a communication/marketing effort to address this concern.
9. UDM prototype scope.  The time allotted for the evaluation and development of the UDM tool prototype may not be sufficient.   
Strategy - The scope of the UDM prototype will be determined by the time allotted for the development phase as defined in the timeline.
Dependencies


The project timeline contains the following dependencies:

· Resources required (Subject Matter Experts, TIBCO Technical Resources, project team members) will be available when requested.

· Support from Business Unit IT groups will be forthcoming.

· Team members have communicated their roles to their management and have received authorization to support project. 

· Security tags for proprietary information will provide Enron confidential information remains within defined confines.

Project Organization

Project Organization Chart



Roles and Responsibilities

Chair




Marie Hejka 

Task Force Members

Technical Delivery


Bryan Powell  
Customers 



Melissa Becker 

Debbie Brackett 

John Gillespie


Anthony Mends

Pegi Newhouse

Andrea Yowman 

Executive Contact


George Wasaff 


Project Chair – Responsible for day-to-day management of the overall Task Force.  Serves as the primary liaison between the Task Force and the Project Sponsors.  Facilitates coordination between the Task Force and the other integration teams.  Manages the project work plan and reports status against that plan.  Responsible for managing project resources, requests and overall project costs.

Task Force Members –Responsible for developing, testing and documenting the structure and functionality of any new system or new functionality of an existing system within the scope of the project. Task force members acting as customers will provide input and requirements for Subject Matter Expert evaluations and technical delivery.

Executive Contact – Responsible for day-to-day executive sponsor duties.  Serves to support Task Force decisions on a daily basis.

Project Sponsors – Provide project sponsorship and confirm overall scope and direction for the project.  Assist in resolving issues elevated by the Task Force.

IT Technology Subject Matter Expert - Responsible for providing subject matter expertise to the Task Force, Technical Team and Project Sponsors.  Responsible for validating whether or not the identified business requirements can be met through a given unstructured data management tool.

Technical Team –Define the technical requirements for the pilot/prototype implementation and deliver these requirements.  Responsible for assessing information provided by the SME.  Will create a final UDM tool selection report. Responsible for building the portal.

Content Strategy – Responsible for providing content strategy support to the Technical Team.  Ensure the portal unveiled reflects knowledge gained from releasing myhome.enron, mywEBSource and other personalized portals.

Appendix A

Background

Overview

October 10, 2000 Melissa Becker, Philippe Bibi, Rick Buy, Rick Causey, Marie Hejka, Steve Kean, Cindy Olson, and Andrea Yowman met to discuss knowledge management at Enron.  Current Knowledge Management initiatives were discussed.  Philippe, Rick, Rick, Steve, and Cindy concluded a task force chaired by Marie Hejka comprised of Melissa Becker, Debbie Brackett, Bryan Powell, and Andrea Yowman would develop two tactical KM tools:  a portal prototype to front Enron intranet sites and a pilot for a knowledge retrieval tool.  

Those assembled at the meeting did not identify an Enron overall leader for KM to define and obtain agreement on the KM scope and objectives and to coordinate multiple BU initiatives.  While the chair and task force agree to undertake the charge of developing the portal prototype and pilot, they also intend to establish the KM strategy required to make these tactical developments successful.  Therefore, the task force plans to identify a KM strategy by which KM tools, initially the portal and pilot, will be successful.

Current Situation (Where we are now, who is doing what.)


Knowledge Management Task Force Initiatives

Philippe Bibi, Rick Buy, Rick Causey, Steve Kean, and Cindy Olson each support efforts to improve access to information.  Listed below are some of these initiatives.

Melissa Becker.  Melissa is coordinating across seven teams focusing on filling the process, data and reporting gaps still existing after the implementation of SAP.  As part of this, there are multiple web initiatives that need to be coordinated.

Debbie Brackett.  Debbie is coordinating RAC IT requirements for all in the RAC group.  Her organization aggregates worldwide market and counterparty credit risk.  This information is available through various applications and is published through the rac.enron.com website. It is published nightly for RAC, and other Enron users. 

John Gillespie.  John Gillespie is a member of George Wasaff’s Global Strategic Sourcing group.  John participated in the Accounting group’s Accelerated Solution Environment offsite.  John helped define portal characteristics at that event.  

Marie Hejka.  Marie leads the grassroots Knowledge Management forum and is chairing the Knowledge Management task force analyzing “access to information.”

Anthony Mends.  wEBSource, EBS” personalized web portal, was released in August, 2000.  Anthony is continuing to support ongoing efforts to manage knowledge by introducing new, web based Knowledge Management applications.

Pegi Newhouse.  Pegi, a member of the KM Forum, has led several Intranet efforts at ENA and Azurix’s Oasis. Oasis features KM tools such as communities and utilizes Interwoven content management.

Bryan Powell.  Philippe Bibi has sponsored the development of a standardized, TIBCO-based portal that will consolidate the mynetwork portals and at home portals.  The portal is well along in development.  Powell has interfaced with GSS and HR to ensure the portal reflects the greater Enron communities.  

Andrea Yowman.  Andrea is coordinating HR’s data repository and the development of HR related applications for Enron Corp.

George Wasaff.  George Wasaff is responsible for the Global Strategic Sourcing unit for Enron. George participated in the Accounting group’s Accelerated Solution Environment offsite meeting.  George and his team identified portal characteristics essential for the new portal.  

Initiatives Outside the Task Force

Brandon Rigney.  Developed, unveiled, and implemented the portal myhome.enron.com. 

wEBSource.  In August, EBS launched wEBSource, a TIBCO-developed, personalized web entry portal for EBS.
Business Challenges and Requirements (Requirements will be based on business problems to solve, these will be prioritized.)

Access to information - There is an overarching problem growing at Enron:  information is challenging, at best, to get. Below is a list of the business requirements resulting from challenges Enron employees encounter.  

	Reality 

(What is the current situation?)
	Challenge

(What challenges does this provide the employee)
	Business Requirement

	1.  No shared KM strategy across Enron
	Multiple, uncoordinated initiatives result in duplication of efforts (labor and IT costs)

Employees are confused about who’s doing what and how the initiatives relate
	Develop a shared understanding of Enron’s KM strategy including who owns it

	2. No single common web entry point for all Enron. 

No centralized area to find credible, reliable, accessible information 


	Cannot access the whole of Enron intranets without accessing each site individually.  

Users do not know where to begin information searches


	Develop a web entry point as a portal to front all Enron intranet sites.  Develop a system which provides users direction in initiating information searches

	3. No common search engine capable of accessing all Enron systems 


	Information residing in the individual business units systems (websites, databases, etc.) can only be searched online via that business units website search engine 
	Implement an engine capable of searching all Enron systems

	4. No unobtrusive method for capturing, qualitative  data to share or retrieve 


	Sharing information requires effort on the part of the individual, this effort often precludes the dissemination of information
	Identify an unobtrusive method for capturing qualitative data to share and/or retrieve.  This system must inherent reflect security parameters defined by the task force

	5. No intelligence inherent in the architecture of our intranet system.  The system remembers nothing about a user’s web activity


	Users are provided no direction when conducting searches
	Build intelligence in to the Enron web platform

	Knowledge sharing is not a priority at Enron


	Entrepreneurial culture creates “do-ers” not always inclined to ask “where have we done this before”
	Implement measures to encourage sharing intellectual capital, knowledge and resources


Appendix B

Project Charter Sign-Off

	Philippe Bibi

	

	

	

	

	Rick Buy

	

	

	

	

	Rick Causey

	

	

	

	

	Steve Kean

	

	

	

	

	Cindy Olson

	

	

	

	George Wasaff
	
	

	
	
	

	
	
	

	
	
	

	

	Marie Hejka
	
	

	
	
	

	
	
	

	
	
	

	Melissa Becker


	
	

	
	
	

	
	
	

	
	
	

	Debbie Brackett


	
	

	
	
	

	
	
	

	
	
	

	Anthony Mends


	
	

	
	
	

	
	
	

	
	
	

	Pegi Newhouse


	
	

	
	
	

	
	
	

	
	
	

	Bryan Powell


	
	

	
	
	

	
	
	

	
	
	

	Andrea Yowman


	
	

	
	
	

	
	
	

	
	
	




















































































































Project Sponsors:


Philippe Bibi


Rick Buy


Rick Causey


Steve Kean


Cindy Olson





Project Chair:


Marie Hejka





Task Force:


Melissa Becker


Debbie Brackett


John Gillespie


Anthony Mends


Pegi Newhouse


Bryan Powell


Andrea Yowman





Executive Contact:


George Wasaff














Content Strategy:


Brandon Rigney


Anthony Mends





Technical Team: 


Ryan Orsak











IT Technology SME:


Peggy Alix


John Norden


John Simmons


*Kent Morrison





 


*Consultant














Page 16


