RAC Deal Approval Sheet
                                                                                                                       Deal Name: Columbia


ENRON RISK ASSESSMENT AND CONTROL

DEAL APPROVAL SHEET

	DEAL NAME:  Columbia I
Counterparty:  TBD

Business Unit:  EWS/Americas/West Power

Business Unit Originator:  Jake Thomas/Laura Wente

Public
Private

Merchant
Strategic

FMV                  Accrual

Conforming
Nonconforming
	Date DASH Completed:  02/16/2001

RAC Underwriter/Analyst:  Chip Schneider/NA
Investment Type:  Generation Asset

Capital Funding Source(s):  Balance Sheet/Off-Balance Sheet

Expected Closing Date:   08/01/2001

Expected Funding Date:  02/21/2001

Board Approval: Pending  Received  Denied  N/A


RAC Recommendation: 
Proceed with Transaction
Returns below Capital Price
Do not Proceed

APPROVAL AMOUNT REQUESTED ($ millions)


TOTAL




$16.5
EXPOSURE SUMMARY ($ millions)*


This Request



$16.5
        
TOTAL




$16.5
* Subsequent approval required by 08/01/2001 for balance of project costs.
DEAL DESCRIPTION

Enron North America (“ENA”), through its wholly-owned subsidiary, Longview Energy Development, LLC (“LED” or “Columbia”) requests $16.5 million to begin developing a combined-cycle, natural gas-fired power plant and to have E-Next Generation (“E-NEXT”) make six months of progress payments to GE on a newly procured 7FA gas turbine. The project will be located on a 20-acre industrial site at the Port of Longview (“Port”) in unincorporated Cowlitz County, Washington.   While a 7FA turbine could produce as much as 270 megawatts (“MW”), the plant would be designed to produce 249 MW in order to qualify for an exemption from the Washington Energy Facility Site Evaluation Council (“EFSEC”) approval.  If legislation is adopted increasing the 250MW threshold or if the owner of the plant chooses in the future to pursue the EFSEC permit, the plant could be modified to increase plant capacity to a higher output rating as approved by EFSEC.  This DASH requests approval for turbine progress payments to be made by “E-NEXT” of up to $10 million as well as developments costs, interest and fee payments to be made through 08/01/2001, at which time, a sale of LED is expected to be complete.  The total cost of the turbine is $40 million.  If ENA chooses to terminate its agreement with GE in August 2001, Enron will forfeit $8 million of the $10 million paid-in at that point in time.

ENA plans to sell LED to a third-party prior to the start of construction or commence construction of the facility with funding from E-Next Generation.  ENA has begun marketing LED to independent power producers (“IPP’s”), investor-owned utilities (“IOU’s”), public power agencies, and industrials. It is expected that the LED project, including the GE 7FA gas turbine, will be sold prior to construction for an estimated $10 million to $15 million promote fee and reimbursement of development costs incurred up to the closing.

During project development, ENA will incur soft costs such as permitting and early-stage engineering.  All hard costs for the project will be financed through E-Next Generation.  Negotiation of the third-party EPC contract is anticipated to be complete by July 31, 2001 and construction is expected to begin sometime in August 2001. The project will interconnect to the Bonneville Power Authority (“BPA”) transmission system at BPA’s existing Longview substation.  Commercial operation is expected by September 1, 2003.

TRANSACTION SOURCES AND USES OF FUNDS ($000)

	
	Sources
	
	
	Uses

	Enron Development Costs
	3,200
	
	Power Plant Development
	3,200

	E-Next Generation 
	13,300
	
	Turbine Progress Payments
	10,000

	
	
	
	Equipment Contingency
	2,800

	 
	
	
	Interest, Fees & Legal 
	500

	Total
	16,500
	
	Total
	16,500


TRANSACTION UPSIDES/OPTIONALITY
The design output of LED will be 249 MW, but the plant could be modified to achieve up to 270MW if an EFSEC siting permit is obtained and if additional capital investments are made to the plant.  Primarily due to the energy crisis that has occurred in California and the Pacific Northwest, the Washington legislature is currently discussing modification of the EFSEC limit and its review process.  ENA supports raising the EFSEC limit to approximately 300 MW given the increased efficiency and reduced emissions of newer turbine technology today.  ENA will also support legislation that would allow commencement of permitting for a Phase II project expansion during the construction of the first phase.
EXIT STRATEGY 

West Origination’s exit strategy is to sell LED to a third-party investor on or before the start of construction.  A non-binding letter of intent for the sale of the facility has been signed with McCook Metals.  West Origination estimates that the gain on the sale of LED would be approximately $10 million to $15 million.  The estimated gain is based on Pastoria and Coyote Springs 2, two comparable combined-cycle frame technology projects.  Coyote Springs 2 was developed and sold for a promote fee of approximately $16.5 MM.  ENA is currently negotiating with Calpine for the sale of Pastoria; subject to the resolution of outstanding issues (i.e. water), a promote fee in excess of $30 MM is expected.  In addition, ENA has recently entered into a Purchase and Sales Agreement with Black Hills Energy Capital for the sale of Fountain Valley Power, a 240MW peaking facility in Colorado Springs, Co. which, when closed, will provide ENA a $15MM promote plus recovery of ENA development dollars invested.  A non-binding letter of intent has been signed with McCook Metals, LLC, an industrial company in the process of purchasing an aluminum smelter in Longview, Washington.  The dollars per kW listed below for LED reflect a conservative EPC estimate of $142 million versus $126 million EPC cost for Coyote Springs 2 and also assume that negotiations with Cascade Natural Gas will be successful, thus eliminating the need for construction of a bypass pipeline to the facility.  
	
	Pastoria
	Coyote Springs 2
	Longview

	Capacity
	750 MW
	280 MW
	249 MW

	$/kW w/o Development Fee
	$730
	$580
	$769

	Development Fee
	$30 MM
	$16.5 MM
	$10MM to $15MM

	$/kW w/ Development Fee
	$770
	$640
	$830

	Fixed O&M $/MWh
	$1.80
	$1.50
	$1.90

	Non-Fuel Variable O&M $/MWh
	$2.76
	$2.51
	$2.50

	Status
	Negotiating
	Sold
	Under Development


RISK MATRIX 
	 DESCRIPTION
	MITIGATION/COMMENTS

	Merchant/Commodity Risk
	Reserve margins in the Western Systems Coordinating Council (“WSCC”) are forecast to continue declining over the next 2-3 years as load grows and insufficient, additional generation is added.  In particular, capacity additions in the Pacific Northwest are projected to be the lowest of any region in the WSCC.  Also, the marginal system heat rate is higher at Mid-Columbia for a 10-year period starting July 1, 2002, than at any other pricing point in the West according to both ENA curves (12,411 Btu/kWh) and Henwood (13,032 Btu/kWh).  With a 6900 Btu/kWh heat rate and a favorable grid location, the plant will be attractive to asset-focused industry players.

	Development Cost Risk/ Potential for Project Termination 
	Approximately $.4 MM in development costs has been incurred to date.  An Option to Lease Agreement and an underlying Ground Lease have been substantially negotiated with the Port of Longview (the “Port”).  An Option to enter into an Agreement to acquire water from the Port has also been substantially negotiated for the part of the water supply will be obtained from the Port’s well source.  LED anticipates that the remainder of the water will come from treated effluent from the nearby sewer treatment plant owned by Cowlitz County.  LED is in negotiations with the County to obtain a contract for that water supply and for a permit to discharge plant wastewater to the sewer treatment plant’s outfall to the Columbia River.  ENA is currently in the process of negotiating a reduced tariff rate from Cascade Natural Gas for gas interconnection.  The plant will be electrically interconnected to BPA’s transmission system.  

	Permit Risk
	The air permit application has been filed with the Washington State Southwest Clean Air Agency (“SWCAA”).   The air permit is expected by April 2001.  As a 249 MW facility, the project does not require approval from the Washington State Energy Facilities Site Evaluation Council (“EFSEC”).  The application process for a wastewater disposal permit is currently in progress.  Initial meetings with the Department of Ecology indicate favorable results.  Environmental work and BPA’s supplemental analysis of environmental information is currently on track.  Full permitting is expected by 07/15/2001.

	Regulatory Risk
	If ENA sells the project to an investor-owned utility or other regulated entity, approval from the WUTC or other state public utility commission may be required.

	Construction Cost Risk
	ENA expects to sell LED with a fully-executed EPC contract in place.  The process of choosing an EPC contractor is progressing.  Based on the $126 MM cost of Coyote Springs 2’s EPC contract, estimates from NEPCO and PB Power for this project, and subject to the current estimates for the cost of a early delivered GE 7FA turbine, LED has estimated a cost of $142 million for a fully-wrapped turnkey contract for the project.

	Equity Syndication Risk
	Market transactions indicate a seller’s market for assets and the existence of buyers with higher power price expectations than those implied by the ENA curves or lower cost of capital than Enron. A fully developed project offers significant early-mover advantage to an asset player and the location of the plant west of the Cascades and south of the John Day cut plane provides a competitive advantage.  ENA intends to complete the sale of LED prior to construction.


KEY SUCCESS FACTORS

	
	NA
	Poor
	Excellent

	Core Business
	
	                                             
	            X

	Strategic Fit
	
	                                                
	       X

	Upside Potential
	
	
	       X 

	Management
	X
	
	      

	Risk Mitigation
	
	                             X
	 


OTHER RAC COMMENTS: 
On very short notice, GE has offered ENA a 7FA turbine for October 2002 delivery.  Due to the demand for 7FA turbines, GE requires commitment from E-NEXT by Friday, February 16, 2001.  Given this, RAC has not had an opportunity to review the assumptions contained in the economic model and therefore is unable to validate the returns expected to be generated by LED.  This DASH will enable the deal team to commit E-NEXT to purchase the turbine and make progress payments through July 2001.  If the project has not been sold by August 1, 2001, the deal team will be required to submit a new DASH requesting approval for the balance of the plant cost.

Project Columbia is in very early stages of development and has not yet secured a site or the necessary permits, interconnects, rights-of-way and water supply, or negotiated an EPC Contract.  Although many of these items are in process and prospects for the project are good, there remains substantial risk that the project will not complete development or be developed in a timely manner.  Nevertheless, given the tight supply of GE 7FA turbines, securing a 7FA may prove advantageous as ENA continues to selectively develop projects throughout the west and southeast.  The present demand for gas turbines, particularly 7FAs, would suggest that the downside of acquiring a 7FA is minimal and, therefore, does not place all of E-NEXT’s investment at risk.

Over the past six months, ENA has been able to deploy or dispose of many turbines held in off-balance sheet vehicles.  Only four of the original twenty-four LM6000s remain and these have been earmarked for ENA’s Las Vegas Cogen II project or sale to a third party.  Other remaining equipment includes two 7EA turbines, one Siemens/Westinghouse 501D (with a damaged generator) and two ABB/Alstom 11N1s (held by Enron Canada).  Enron South America also maintains responsibility for four Siemens/Westinghouse-design 501F turbines manufactured by Mitsubishi Heavy Industries (MHI).
Other than the turbine purchase order discussed herein, no contracts/agreements with ongoing irrevocable monetary obligations may be executed until approval for 100% of project costs is obtained.  All expenditures not specifically referred to in this DASH must be approved by Americas Finance 10 business days prior to initial payment.
See Appendix I for the status of critical path items.

MILESTONES

1. Begin EPC contractor selection process



03/07/2001

2. Execute Option to Lease Agreement for site


03/15/2001

3. Execute Option and Agreement to Acquire Water

03/30/2001

4. Finalize gas interconnection plan



03/31/2001

5. 
6. Receive SIS and IFS from BPA



04/30/2001
7. Receive air permit from SWCAA



04/30/2001

8. Finalize wastewater disposal plan



06/30/2001

9. Complete Power Transmission Services Agreement

06/30/2001

10. 

11. Complete EPC Contract negotiations



07/31/2001

12. Complete Ground Lease negotiations



07/31/2001

13. Sell project or circulate new DASH



08/01/2001
	APPROVALS
	
	Name
	
	Signature
	
	Date

	Originator
	
	Jake Thomas
	
	
	
	

	West Regional Mgmt.
	
	Chris Calger
	
	
	
	

	Americas Legal
	
	Mark Haedicke
	
	
	
	

	Americas Tech Services
	
	Brian Redmond
	
	
	
	

	Americas Accounting
	
	Herman Manis
	
	
	
	

	Americas Executive
	
	John Lavarato/Louise Kitchen
	
	
	
	

	EWS Executive
	
	Mark Frevert
	
	
	
	

	RAC Management
	
	Rick Buy/David Gorte
	
	
	
	

	Enron Capital Management
	
	Andy Fastow/Ben Glisan
	
	
	
	


Global Finance Summary (addendum to DASH)

1. Transaction Summary


	
	Amount ($000)

	Total Deal/Project Capital Commitment
	16,000

	Less: Financing
	

	Less: Syndications
	

	Net Enron Investment
	16,000

	
	

	
	



2. Investment terms and pricing:

( Market
x Above Market

( Below Market

Describe (if necessary):




3. Financing terms and pricing:


x Market
( Above Market

( Below Market

Describe (if necessary):




4. Legal or practical liquidity restrictions:
x Unrestricted
( Legally Restricted
( Practically Restricted

Describe (if necessary):




5. Any recourse to Enron (other than investment):

( Recourse

x No Recourse

Describe (if any):




6a. Business unit intent to syndicate:

( None

( Partial

x All

Describe (if necessary):




6b. Intended Enron hold period:


ENA Intends to sell LED by August 2001.




6c. Likely Syndication Market:


x Industry/Strategic Partner
( Direct Private Equity

( Capital Markets

( JEDI 1

( JEDI 2


( Enserco

( LJM 1 or 2


( Condor

( Other:



( Margaux

6d. Is this a JEDI 2 “Qualified Investment”?
( Yes


x No




	
	Signature
	Name
	Date

	Americas Finance 
	
	
	

	Americas Finance - Legal
	
	
	


Appendix I - Status of Critical Path Items
	Item
	Status

	Air Permit
	ENA expects the air permit to be issued by April 2001. 

	Site
	The Option to Lease Agreement will be entered into in February 2001.  The underlying ground lease, which has been substantially negotiated, will be included as an attachment to the Option to Lease Agreement. It would be finalized and entered into upon the exercise of the option at start of construction.

	Gas Interconnection
	ENA is currently working with Cascade Natural Gas to negotiate a special tariff and contract. The contract is expected to be complete by the end of March 2001 and then requires WUTC approval. The ruling is expected by early May 2001. Although the risk of WUTC rejection is considered small, ENA, on behalf of E-NEXT, is prepared to bypass Cascade Natural Gas and build a parallel pipeline to interconnect with NW Pipeline directly.  The estimated cost of the pipeline is approximately $5.5 million.

	Electrical Interconnection
	The project will interconnect with BPA’s transmission system at the Longview substation. To interconnect the project, an approximately ¼ mile transmission line will be built and a 4-mile existing single 115 kV line will be replaced with a double-circuit 230 kW line.  Approximately $5 MM in transmission upgrades will be required.

	Water Supply
	ENA has substantially negotiated an Option to enter into an Agreement to Acquire Water with the Port.  LED will pay the Port well water rate of $0.54/ 100 cu. ft. for the portion of water obtained from the Port, and is in the process of negotiating with the County to acquire  effluent from the sewer treatment plant. The Option to enter into an Agreement to Acquire Water is expected to be executed with the Port in March 2001.

	Wastewater Disposal
	LED is currently negotiating with the Cowlitz county sewer treatment plant to dispose waste water to the sewer plant outfall on the Columbia River. The permit for this wastewater disposal option is expected on or before June 30, 2001.  

	Power Transmission
	BPA is currently undertaking an Interconnection Facilities Study (“IFS”) and System Impact Study (“SIS”) to determine available transmission for the project.  As part of these studies BPA will also determine what system-wide benefits may accrue to their transmission system from the favorable location of this project.  The results of the studies are expected March 2001 and April 2001 respectively.  A Transmission Services Agreement with BPA will be executed by June 30, 2001.

	EPC Contract 
	LED is close to finalizing the Design Basis Document for negotiation with two or three EPC contractors.  LED expects to have an EPC contract negotiated by July 31, 2001.
































C:\personal\ENA\West\DASH_Columbia1_021601.doc

Page 7

