Project Development Agreements

Contracts
Fixed Price, Turn Key, Date Certain 

Payment
[ ? ]

Guaranteed Completion Date
Las Vegas Cogeneration II ______, 2002 Pastoria                               ______, 2003

Moore                                  ______, 200_

Delay Liquidated Damages
[ ? ]

Non Completion LD’s
100% of contract price for each project if project not completed within 2 years after Guaranteed Completion Date

Asset Transfer
[Transfer LLC’s immediately upon close, title to equipment transfers on or before it is delivered on site.?]

Performance Tests [Minimum Performance Levels?]
Output, Heat Rate performed when 100% of facility is complete

Operation before Completion
[Developer allowed to operate before complete, performance tests get adjusted for degradation]

Acceptance Tests
Plant emissions, reliability, other capability and sound, if applicable

Performance LD’s 


Output



% below guaranteed output  x contract price

Subject  to a cap of 10% of contract price per plant

Heat Rate
[$_________] per Btu/kWh

Subject to a cap of 10% of contract price per plant

Overall maximum cap on Performance LD’s = 15% of contract price per plant

Performance Bonuses


Output

[$_________] per kw

Heat Rate
[$_________] per Btu/kWh

Limitation of Liability
100% of contract price (for each plant) until air permits received + turbines transferred

25% of contract price (for each plant) aggregate limit thereafter +

Environmental Indemnification

Environmental Indemnification
100% for hazards caused by Developer up to six (6) months after commercial operation.  No cap.

Purchaser Approvals
Purchaser approves plans and specifications, then substantial completion, then punch list completion, then performance tests.

Alternative Project

[NEED TO RE-THINK AND DISCUSS THE CRITERIA]
· IRR Keep Whole clause

· Utilize the gas turbines

· [1200] operating hours

· Electrical and gas interconnects

· Same NERC subregion or transmission control area



Redesign of Facility

[NEED TO RE-THINK AND DISCUSS THE CRITERIA]
· Operating cost keep whole clause

· Utilize the gas turbines

· [1200] operating hours

· Electrical and gas interconnects

· Same operating parameters

· Within [20] miles of proposed location

· No additional operating resources 

Warranty
12 months from the date of substantial completion for good workmanship

\\Ect\houston\common\Legal\Szisman\Misc\E2 PDA TERM SHEET.doc

