DRAFT: FOR REVIEW AND DISCUSSION PURPOSES ONLY


Project Development Agreements

	Project Developer
	Enron North America Corp.

	Contracts
	Fixed price, turn key, date certain 

	Payment
	Amount and timing to be agreed upon (expected to have some portion payable up front with subsequent payments made on certain specified dates)

	Guaranteed Completion Date
	Moore                                         June, 2001

Las Vegas Cogeneration II      March, 2002 Pastoria                                      June, 2003

	Delay Liquidated Damages
	A daily liquidated damage amount to be agreed upon by the parties and paid for failure to deliver on the Guaranteed Completion Date

	Non Completion Liquidated Damages
	100% of contract price for each project if project not completed within 2 years after Guaranteed Completion Date

	Performance Tests 
	Output, Heat Rate tests will be performed when 100% of facility is complete

	Operation before Completion
	Developer allowed to operate before complete, performance tests get adjusted for degradation

	Acceptance Tests
	Plant emissions, reliability, other capability and sound, if applicable

	Performance Liquidated Damages 


	Output:  % below guaranteed output x contract price

Subject to a cap of 10% of contract price per plant

Heat Rate:  [$_________] per Btu/kWh

Subject to a cap of 10% of contract price per plant

Overall maximum cap on Performance LD’s = 15% of contract price per plant

	Performance Bonuses


	Output

[$_________] per kw

Heat Rate
[$_________] per Btu/kWh

	Limitation of Liability
	100% of contract price (for each plant) until air permits received + turbines transferred

25% of contract price (for each plant) aggregate limit thereafter +

Environmental Indemnification

	Environmental Indemnification
	100% for hazards caused by Developer up to six (6) months after commercial operation.  No cap.

	Purchaser Approvals
	Purchaser approves plans and specifications, then substantial completion, then punch list completion, then performance tests.

	Alternative Project


	Project Developer shall have the right to substitute an alternative project (“AP”) if it is reasonably necessary to do so.  The AP would be subject to the terms above would also have to meet certain mutually agreed upon parameters including, without limitation, the following:

The AP would have to:

· Yield an internal rate of return greater than or equal to the rate of return expected for the original project

· Utilize the same gas turbines

· Be permitted to operate for an agreed upon minimum number of operating hours

· Have the electrical and gas interconnection agreements in place 

· Be located in the same NERC subregion or transmission control area


	Redesign of Facility


	Project Developer shall have the right to institute changes in the physical equipment or operating design of a facility provided that the performance guarantees remain the same and the revised facility meets certain mutually agreed upon parameters including, without limitation, the following:

The revised facility would have to: 

· Utilize the same gas turbines

· Be permitted to operate for an agreed upon minimum number of operating hours

· Have the electrical and gas interconnection agreements in place

· Have the same operating parameters

· Be located within a certain agreed upon distance from the originally proposed location

In addition, the fixed price payable to the Project Developer shall be reduced to the extent necessary to compensate for any increase in operating costs which arises from the redesign.

	Warranty
	12 months from the date of substantial completion for good workmanship


O:\Legal\Szisman\Misc\E2 PDA TERM SHEET v2.doc

