Summary of Assumptions for Fuel Cost Overrun and Penalty Cases

Case A(1): Original Base Case Presented to Lenders in July

· Lender Model from 4/24/00

· Full pass through, e.g. full CCC reimbursement by Aneel

· Generating 150 MW from 4/99 – 3/01

· Generating 238 MW from 4/01 – 7/01

· Generating 238 MW from 8/01 onward

Case A(2): Revised Base Case To be Presented to Lenders in December

· Lender Model from 12/15/00

· Full pass through, e.g. full CCC reimbursement by Aneel

· Combined cycle commissioning on diesel began 10/00

· Gas at plant Apr. 7, 2000

· Generating 150 MW from 4/99 – 5/00

· Generating 300 MW from 6/00 – 4/01

· Generating 311 MW during 5/01

· Generating 480 MW beginning 6/01

· Furnas pays Phase I (or Phase II?) Tariff (Per Letter) for full 300 MW between 6/00 – 4/01
· Furnas accepts FM claim and no penalties due for delay in Phase II
· Note: additional diesel consumed during CC Commissioning of $6.8 MM not covered by Eletrobras or CCC and is included as “Contingency” in budget.

· Note: 150 MW from the gas turbine on diesel can result in up to 75 MW from the steam turbine for a total of 225 MW, thus we only burn 150 MW “worth” of diesel.

· Note: if we get dispatched for the second gas turbine (above 150 MW), we might as well shut down the plant unless we get covered for the fuel cost by Furnas. I don’t think it is possible that we could be forced to dispatch (by Furnas) for 300 MW and not be reimbursed for Diesel. (?)
(Note: all cases below are mutually exclusive, and thus there is no cumulative Delta effect)
Case B: Phase II Delay

· Phase I tariff on 150 MW of generation through 7/1/01 (post-gas commissioning) Or 4/7/01?
· Diesel Fuel generation through 4/7/01

· Partial CCC paid on 1st 150 MW through 6/30/01, whether in combined or simple cycle

· Eletrobras guarantee only assures partial CCC reimbursement above (e.g. no additional guarantee)

· Because Furnas will not pay for capacity > 150 MW, generate 150 MW until 7/1/00 Or 4/7/01?
· Furnas Penalties for Phase II and Phase III (Furnas does not accept FM claim and demands penalties due for delay in Phase II)

Case C: Partial CCC, paid whether in combined or simple cycle

· Same as A(2) assumptions, except:

· Partial pass through, e.g. 150 MW CCC reimbursement whether in SC or CC

· Note: Costs split due to the fact that 300 MW is obtained in combined cycle (2x100 MW Gas Turbine+1x100 MW Steam Turbine). This assumes CCC for only one turbine.

Other D: Only Partial CCC paid only when in simple cycle

· Same as A(2) assumptions, except:

· No Pipeline Delay

· Partial pass through, e.g. 150 MW CCC reimbursement when in simple cycle

· E.g. ANEEL will not reimburse us for the gas turbine while in CC commissioning. (Note: there is a $6 MM “diesel contingency” calculated in the budget)

Case E: Pipeline delayed 

· Same as A(2) assumptions, except:

· Gas Pipeline delayed from Apr. 7, 2000 until 7/1/01

· Partial pass through, e.g. 150 MW CCC reimbursement when in simple or CC
Other: Improved Efficiency

· Same as A(2) assumptions, except:

· Partial pass through, e.g. 150 MW CCC reimbursement when in simple cycle

· Instead of generating 300 MW from 6/00 – 4/01, we generate 450 MW on diesel, in CC for 2/01 – 3/01 (2 months)

· Furnas pays capacity tariff for full 450 MW produced (per Aditivo 2, clause 8)

