The attached table summarizes the capital and operating cost estimate for the proposed 5 and 10 million gallon Butane and Natural Gasoline atmospheric storage tanks.  These costs are based on the following data:

· Tanks containing butane will be insulated with 3 inches of polyisocyanurate foam in two layers with a polar white metal jacket to maintain mechanical integrity of the foam and provide a vapor barrier.  The  gasoline tanks will be insulated similarly with 1 ½” of foam.

· Tanks will be designed, constructed (near Bakersfield CA) and tested to API Standard 620.

· Manways, stairway and platform,  nozzles, hatches, level indicator and controls and instrumentation to protect against over/under pressure is included.

· The foundation will comply with API standard 650 and the Butane tank foundation will be designed to prevent “heaving” due to water freezing.

·  Cathodic protection (internal and external) will be provided.

· Gasoline and Butane will be delivered to the tank (and withdrawn) at a rate of 100,000 GPD for 180 days per year equating to 18 million gallons of product being stored.

· The product cooling system design inlet temperature is 120(F for both butane and NGL and a storage temperature is 25 (F and 70(F respectively.

· Total Capital costs include installation.

· No costs for permitting are included.

· Operating costs are based on $2.50/MCF and $.08/KWH. 

[image: image1.wmf]Tank Size >>>

Service >>>

Butane

Gasoline

Butane

Gasoline

Dimensions >>>

135' Dia.X 48'

135' Dia.X 48'

164' Dia X 64'

164' Dia X 64'

Tank

710,000

710,000

1,200,000

1,200,000

Paint

47,000

47,000

68,000

68,000

Insulation

310,000

270,000

442,000

360,000

Foundation

95,000

95,000

120,000

120,000

Cathodic Protection

100,000

100,000

140,000

140,000

Recompression System

187,500

135,000

187,500

135,000

Product Recirculation System

20,000

20,000

20,000

20,000

Inlet Cooling System

487,500

412,500

487,500

412,500

Product Heating System

40,000

0

40,000

0

Instrumentation/Controls

190,000

114,000

275,000

165,000

Contingency (10%)

199,700

178,950

270,500

245,550

Tax (7.25%)

103,821

90,587

141,397

124,673

Total Capital

2,490,521

2,173,037

3,391,897

2,990,723

Fuel/Electric Op cost

53,000

25,000

58,000

30,000

Non Fuel Op Cost

20,000

15,000

20,000

15,000

Contingency (10%)

7,300

4,000

7,800

4,500

Total Annual Op Cost

80,300

44,000

85,800

49,500

Capital Costs

Operating Costs

5,000,000 Gallon

10,000,000 Gallon

EOTT STORAGE TANK - CAPITAL & OPERATING COST ESTIMATE


