ETC Survey

Update

Following are:

1. An overview of how agreement on the next iteration of the ETC survey process might be generated

2. A summary of the key items for consideration by the V&V group related to the next iteration of the ETC survey

3. A few questions that could serve as the basis for discussion of the ETC survey process at the next V&V meeting

1. Process for Generating Agreement

· V&V members poll their senior management on a few key elements of the survey process (4/5-4/18)

· Importance of HR role/responsibility in generating results reconfirmed with  to HR executives by Cindy Olson (4/5-4/18)

· V&V members report back to V&V group on the outcome of those polls/conversations (4/19)

· Summary of those conversations generated and distributed to V&V members (4/21)

· Outcomes reviewed with senior HR executives from each organization (4/21-4/25)

· Feedback of senior HR executives integrated into the decision mix (4/26-4/28)

· A “going forward” strategy developed based on this data (5/5)

· Strategy reviewed with HR executives and V&V group to gain ratification (5/8-5/12)

· Overall plan for next iteration based on this strategy generated (5/23)

· Meeting of next iteration planning group (5/25)

2. ETC Survey Process Key Items for Consideration

Original View  




Last Implementation

Intended to be:





Last iteration:

· Fast (to take)




- Fast to take (based on general feedback)

· Easy (to take)




- Easy to take (based on general feedback)

· Simple (to understand & implement)

- Customization of questions and

demographics, a desire to make this a global survey, along with organizational    changes have made this a relatively complex process on a Corporation wide basis

· Quick Response to Employees (3-4 weeks)
- Longer than anticipated (up to 3 months)

· Frequently Updated



- Once a year, rather than monthly/quarterly

-     Lower cost than historical surveys

- Higher overall cost due to

  customization/complexity

· Less administration required by all

- Administratively complex coordination

· Ownership by OpCo’s



- Still the focus of the effort, but with an

increasing need to identify 

roles/responsibilities/measures and

 consequences for accomplishing

 improvement

3. Key Questions for Line Management

The overall objectives of the survey were to:

· Provide useful information and insight into the health of the organization as perceived by employees at all levels

· Provide useful insight into the areas employees perceive as hindering their personal performance and effectiveness

· Provide a barometer for measuring perceived change in key areas of employee perception that affect commitment and productivity

· Provide the basis for actionable items on the part of management & employees

Based on these objectives and the observations in item #2 above, line management answers to the following few questions would yield useful information in guiding the next iteration of the survey:

Executive’s Name:_________________________________________

· To what degree has the overall survey yielded information useful to you in identifying areas for improvement in employee perceptions affecting your organization?  

      1            2             3             4             5             6             7              8             9              10

Not At All









     Quite A Bit

Example/Why:

· What, if anything could be done to improve the overall usefulness of the data you receive from the survey?

· To what degree did your custom questions (if you had them) satisfy your need for information in those areas?

     1            2             3             4             5             6             7              8             9              10

Not At All









    Quite A Bit

Example:

· Do you feel the investment (time/energy/cost) in those questions compared what you learned, warrants asking such custom questions in the next edition of the survey?

Yes______________




No________________

Why? 

· If one thing could be done to make the entire survey process more useful to you in leading your organization forward, what would it be?

Rwa mydocuments/ETC V&V Update 4-5-00.doc  


