[image: image1.png]


[image: image2.wmf]
Highly Confidential

Commercial Nuclear Power Plant Monitoring & Support Services

[image: image3.wmf]
Weekly Monitoring Report For Requested Commercial Nuclear Power Plants

12/6/00 – 12/13/00


Report #:
WE001213-111

Unit:

Beaver Valley 2

[image: image4.png]


NERC Region:

ECAR

Mwe:

833
Type:

Pressurized Water Reactor (PWR)
Operator:
FirstEnergy Nuclear Operating Company


Owners:

FirstEnergy Corp.


Cleveland Electric Illuminating Co.
  24.47%



Ohio Edison




  41.88%



Pennsylvania Power Company

  13.74%




Toledo Edison Company


  19.91%









100.00%

COD:

11/87
EOL:

5/2027

Current Operating Status:

As of 12/13/00, Beaver Valley 2 is shutdown in a forced outage.

Recent Events:

On 12/11/00, Unit 2 received indications of a primary leak in containment that exceeded allowable values in Tech Specs.  The plant began a controlled shutdown.

Upcoming Events:

The forced outage is expected to complete by 12/17/00.
Our Opinion:

The licensee is attempting to repair the leak but is not certain of when the leak will be controlled allowing the unit to restart.  Current estimates are that restart should commence sometime this weekend.  That estimate is consistent (perhaps a little lengthy) with historical RCS leaks in containment.  We will continue to monitor the situation and inform you of more definitive estimates as work proceeds. 

Report #:
WE001213-112

NERC Region:

ECAR

Unit:

Cook 1

Mwe:

1,000
Type:

Pressurized Water Reactor (PWR)
Operator:
Indiana Michigan Power Corp. 

Owners:

Indiana Michigan Power Corp.


100%

COD:

8/75
EOL:

10/2014
Current Operating Status:

As of 12/13/00, Cook 1 is shut down in an extended maintenance outage. 

Recent Events:

No new event has been reported to the NRC since the 12/6/00 report.

Upcoming Events:

Cook 1 is expected to complete its regulatory outage by 12/16/00. 

Our Opinion:
Cook 1 has progressed through Mode 4 hot shutdown (entered on 12/7/00) and into Mode 3 hot standby (entered on 12/13/00).  This advance is consistent with expectations for a 12/16/00 restart of the unit.  Power ascension after the restart should be conservatively slow to ensure function of all systems.  Possible delays and/or shutdowns may occur due to leaking systems that have not operated for some time.  Full power, however, is expected to be reached by 12/26/00.  

Report #:
WE001213-113

NERC Region:

ECAR

Unit:

Perry

Mwe:

1,205
Type:

Boiling Water Reactor (BWR)
Operator:
FirstEnergy
Owners:

FirstEnergy


100.00%
COD:

11/87
EOL:

3/2026

Current Operating Status:
As of 12/13/00, Perry is operating at 95% power in a coastdown to a refueling outage.

Recent Events:

No new event has been reported to the NRC since the 12/6/00 report.

Upcoming Events:

The next refueling outage is expected to begin on 2/17/01.

Our Opinion:

Perry continues to report a coastdown to their refueling outage.  It should be a long, slow coastdown since the refueling outage start date continues to be affirmed as 2/17/01.  

Report #:
WE001213-121

NERC Region:

MAIN

Unit:

Kewaunee

Mwe:

503
Type:

Pressurized Water Reactor (PWR)
Operator:
Nuclear Management Company
Owners:

Wisconsin Public Service Corp.
  
  41.2%


Wisconsin Power & Light


  41.0%



Madison Gas & Electric Co.

  17.8%









100.0%
COD:

6/74

EOL:

12/2013
Current Operating Status:

As of 12/13/00, Kewaunee is operating at 96% power.

Recent Events
No new event has been reported to the NRC since the 12/6/00 report.

Upcoming Events:

The next refueling outage is expected to begin on 10/13/01.

Our Opinion:

Kewaunee continues to operate fairly consistently at the 96% power level.  We expect continued performance at this level unless significant steam generator leaks occur.  The risk with this unit is not as much for derates or short term forced outages as it is for a steam generator tube problem forcing a long term outage.  No indications currently exist that the risk is any more elevated than it had been for the past few months.

Report #:
WE001213-122

NERC Region:

MAIN

Unit:

Point Beach 2

Mwe:

485

Type:

Pressurized Water Reactor (PWR)
Operator:
Nuclear Management Company 

Owners:

Wisconsin Electric Power Company

100%

COD:

10/72

EOL:

3/2013

Current Operating Status:

As of 12/13/00, Point Beach 2 is shut down in a refueling outage.

Recent Events:

No new event has been reported to the NRC since the 12/6/00 report.

Upcoming Events:

The refueling outage is expected to end by 12/16/00.

Our Opinion:

Point Beach 2 has advanced once again to hot shutdown after completing some minor maintenance.  We expect restart to occur by sometime this weekend, 12/16/00-12/17/00.  The unit has operated well over the past couple of years, and we expect a capacity factor of about 96-97% over the coming cycle.

Report #:
WE001213-131

NERC Region:

MAPP

Unit:

Prairie Island 1

Mwe:

513
Type:

Pressurized Water Reactor (PWR)
Operator:
Nuclear Management Company

Owners:

Northern States Power Company

100%

COD:

12/73
EOL:

8/2013

Current Operating Status:

As of 12/13/00, Prairie Island 1 is shut down in a forced outage.

Recent Events:

No new event has been reported to the NRC since the 12/6/00 report.   

Upcoming Events:

The next refueling outage is expected to begin on 1/20/01.  

Our Opinion:

Prairie Island 1 has completed maintenance on a reactor coolant pump.  The unit is moving toward restart, and we expect that to occur by 12/14/00.  The maintenance outage should not affect the start of the refueling which is scheduled for 1/20/01.  The unit has performed very well over the past couple of years.  

Report #:
WE001213-231

NERC Region:

SERC

Unit:

Oconee 1

Mwe:

846
Type:

Pressurized Water Reactor (PWR)
Operator:
Duke Power Company
Owners:

Duke Power Company

100%

COD:

7/73

EOL:

2/2013

Current Operating Status:

As of 12/13/00, Oconee 1 is shut down in a refueling outage.

Recent Events:

No new event has been reported to the NRC since the 12/6/00 report.  

Upcoming Events:

The refueling outage is expected to complete by 1/7/01.

Our Opinion:
Oconee 1 continues in a defueled condition in the middle of their refueling outage.   No significant problems have occurred so far that would jeopardize the 1/7/01 restart date.  

Report #:
WE001213-232
NERC Region:

SERC
Unit:

Summer

Mwe:

885
Type:

Pressurized Water Reactor (PWR)
Operator:
South Carolina Electric and Gas (SCE&G)

 

Owners:

SCE&G


  66.67%



Santee Cooper

  33.33%






100.00%

COD:

1/84

EOL:

8/2022

Current Operating Status:

As of 12/13/00, Summer is shut down in a refueling outage.  

Recent Events:

No new event has been reported to the NRC since the 11/29/00 report.
Upcoming Events:

The refueling outage is expected to end by 1/1/01.

Our Opinion:

Restart of the unit has moved out to mid January 2001 (1/12/01-1/15/01).  Site personnel continue to report slow but consistent progress in the welding of the replacement pipe.   The possibility continues to exist that improvement in the timing of the welding could improve the targeted restart date.  

Report #:
WE001213-241
NERC Region:

SPP

Unit:

ANO 2 

Mwe:

858
Type:

Pressurized Water Reactor (PWR)
Operator:
Entergy Operations, Inc.
Owners:

Entergy Arkansas, Inc.
100%
COD:

3/80
EOL:

9/2018
Current Operating Status:

As of 12/13/00, Arkansas Nuclear One 2 is in power ascension after completing its refueling/steam generator replacement outage.    

Recent Events:

No new event has been reported to the NRC since the 12/6/00 report.

Upcoming Events:

On 12/20/00, a meeting will be held with the NRC to discuss the results of the first license renewal inspection.

Full power is expected to be reached by 12/17/00. 

Our Opinion:

The turbine testing has completed and the unit synchronized with the grid.  ANO 2 is in the process of power ascension and should reach full power by the end of the week.  ANO 2 is an average performing plant.  We expect a capacity factor in the low 90s over the coming cycle.

Report #:
WE001213-321

NERC Region:

NPCC
Unit:

FitzPatrick

Mwe:

785
Type:

Boiling Water Reactor (BWR)
Operator:
New York Power Authority
Owners:

New York Power Authority
100%
COD:

7/75

EOL:

10/2014

Current Operating Status:

As of 12/13/00, FitzPatrick is operating at 55% power while performing feedwater pump repair. 

Recent Events:

On 11/21/00, a snowstorm caused the loss of power to the Emergency Operations Facility.
Upcoming Events:

The next refueling outage is expected to start on 10/6/02.

Our Opinion:

The unit is struggling with the repair of a feedwater pump which it is performing while the unit is online.  The removal of the feedwater pump from service, however, has required the unit to derate to about 55% power while the repairs are being made.  Completion of the repair and return to full power should occur soon within the next day or two.

Report #:
WE001213-322

NERC Region:

NPCC
Unit:

Indian Point 2

Mwe:

975
Type:

Pressurized Water Reactor (PWR)
Operator:
Consolidated Edison of New York


Owners:

Consolidated Edison of New York

100%
COD:

8/74
EOL:

9/2013
Current Operating Status:

As of 12/6/00, Indian Point 2 is shut down in a regulatory/steam generator replacement outage that began on 2/15/00.  

Recent Events:

No new events have been reported to the NRC since the 12/6/00 report.  

Upcoming Events:

The steam generator replacement outage is expected to complete by 12/11/00.

Our Opinion:

The licensee has made progress toward completing the Indian Point 2 outage.  The unit has moved to hot shutdown and is expected to restart by 12/17/00.  Full power should then be reached by 12/22/00 or 12/23/00.    

Report #:
WE001213-323

NERC Region:

NPCC
Unit:

Seabrook

Mwe:

1,158
Type:

Pressurized Water Reactor (PWR)
Operator:
North Atlantic Energy Service Corporation 

Owners:

North Atlantic Energy Corp.



 35.98201%



United Illuminating Co.




 17.50000%



Great Bay Power Corp.




 15.03229%



Massachusetts Municipal Wholesale Electric Co.
 
 11.59340%



National Grid





   9.95766%



Connecticut Light & Power Co.



    4.05985%



NSTAR






    3.52317%



New Hampshire Electric Cooperative, Inc.

    
    2.17391%



Taunton Municipal Light Plant



    0.10034%



Hudson Light & Power Dept.



    0.07737%











100.00000%

COD:

7/90

EOL:

10/2026
Current Operating Status:

As of 12/13/00, Seabrook is shut down in a refueling outage.  

Recent Events:

No new event has been reported to the NRC since the 12/6/00 report  

Upcoming Events:

The refueling outage is expected to end on 12/30/00.  

Our Opinion:

Seabrook continues work on its emergency diesel generator.  As reported earlier, the significant factor as to whether the outage will complete by the end of this month, or if it will continue for several (3-5) more weeks is whether the crankshaft will require significant rework or replacement.  We will report to you when that determination is made.  

Page 12 of 12

_963987986

_963988101.unknown

