Enron Project – Status as of 8/2/00

Engine:


LM6000PC E-Sprint w/o VIGV’s

Climate:

Winterization to –10F, Noise to 85 dBA

Enclosures:

Water Injection Skid, Liquid Fuel Skid, and Gauge Panel

Items Not Enclosed:
Auxiliary Skid, Hydraulic Starter, Sprint Skid, and CO2 – (Winterized)

Gas/Water Units:
Duplex LP Water Injection Pumps w/Enclosures and heaters

Dual Fuel Units:


· Standard LP/HP Water Injection Pump Skids w/Enclosures and heaters

· Single Liquid Fuel Pump Skid w/Enclosure and Heat Tracing

UNIT
DWG

SERIES
UNIT SERIAL #
PROD SALES #
FUEL
GEN
PIPNG
LINE

SIDE
LUBE OIL

COOLING
EXHAUST

STACK
CONT

DELIV

DATE
ASSIGNED

PROJECT
PROJ

 DELIV 

DATE
COMMENTS
#

OF 

C/O’s
UNIT

1
559XXX
308898
601134
Gas
GE
RH
RH
Fin/Fan
45 ft
7/30/00
ESA
6/20/00
Static Test

1

2
559XXX
308951
601134
Gas
GE
LH
LH
Fin/Fan

7/30/00
Open
7/26/00
Static Test

2

3
559XXX
308972
601134
Gas
GE
RH
RH
Fin/Fan

7/30/00
Open
8/15/00
Static Test

3

4
559XXX
308999
601134
Gas
GE
LH
LH
Fin/Fan
45ft
8/30/00
ESA
7/5/00


4

5
559XXX
309020
601134
Gas
GE
RH
RH
Fin/Fan
45 ft
8/30/00
ESA
7/10/00


5

6
559XXX
309073
601134
Gas
GE
LH
LH
Fin/Fan
45 ft
8/30/00
ESA
7/21/00
Static Test

6

7
568XXX
309101
601134B
Dual
Brush
RH
RH
Fin/Fan
45 ft HVY
9/30/00
Florida
6/22/00
Static Test 
?
7

8
568XXX
309123
601134B
Dual
Brush
LH
LH
Fin/Fan
45 ft HVY
9/30/00
Florida
6/30/00
Static Test 
?
8

9
581XXX
309266
601134C
Gas
Brush
RH
RH
Shell/Tube
NA
10/30/00
Austin
8/19/00
Static Test

9

10
581XXX
309307
601134C
Gas
Brush
LH
LH
Shell/Tube
NA
10/30/00
Austin
9/1/00
Static Test

10

11
581XXX
309376
601134C
Gas
Brush
RH
RH
Shell/Tube
NA
10/30/00
Austin
9/6/00
Static Test

11

12
581XXX
309398
601134C
Gas
Brush
LH
LH
Shell/Tube
NA
11/30/00
Austin
9/14/00
Static Test

12

13
562XXX
309420
601134A
Gas
Brush
RH
RH
Fin/Fan
?
11/30/00
PSCO
9/21/00


13

14
562XXX
“
601134A
Gas
Brush
LH
LH
Fin/Fan
?
12/30/00
PSCO
9/28/00


14

15
562XXX
“
601134A
Gas
Brush
LH
LH
Fin/Fan
?
12/30/00
PSCO
10/25/00
Static Test

15

16
562XXX
“
601134A
Gas
Brush
RH
RH
Fin/Fan
?
1/30/01
PSCO
11/1/00


16

17
562XXX
“
601134A
Dual
Brush
LH
LH
Fin/Fan
45 ft HVY
1/30/01
Florida
11/13/00

1
17

18
562XXX
“
601134A
Dual
Brush
RH
RH
Fin/Fan
45 ft HVY
1/30/01
Florida
11/20/00
Static Test
1
18

19
562XXX
“
601134A
Dual
Brush
LH
LH
Fin/Fan
45 ft HVY
2/28/01
Florida
11/27/00
Static Test
1
19

20
562XXX
“
601134A
Dual
Brush
RH
RH
Fin/Fan
45 ft HVY
2/28/01
Florida
12/11/00
Static Test
1
20

21
581XXX
“
601134C
Gas
Brush
LH
LH
Shell/Tube
NA
3/30/01
Las Vegas
1/5/01
Static Test

21

22
581XXX
“
601134C
Gas
Brush
RH
RH
Shell/Tube
NA
3/30/01
Las Vegas
1/12/01


22

23
581XXX
“
601134C
Gas
Brush
LH
LH
Shell/Tube
NA
4/30/01
Las Vegas
1/20/01


23

24
581XXX
“
601134C
Gas
Brush
RH
RH
Shell/Tube
NA
4/30/01
Las Vegas
3/13/01
Static Test

24

David Davis, Enron Project Manager
5/11/00
Page 1 of 1

