
EXHIBIT F

CHANGE ORDER PRICING
[SAMPLE]

Formula for Calculation of Contract Price Change

Contract Change Orders for all Changes will be priced in accordance with the following formulas:

I.
Engineering/Project Management Costs:

Formula:

Estimated or actual man hours X direct salary costs X 2.25

Categories (includes but not limited to):

(i) 
Contractor in house engineering to design and review proposed changes;

(ii)
Contractor main office and field project management personnel involvement in preparing, and negotiating necessary changes with subcontractors and vendors; and

(iii)
Contractor engineering and project management personnel involvement in preparation of the change order estimates that are accepted by Owner.

II.
Contractor’s subcontractor/vendor costs:

Formula: Quoted estimated or actual costs by vendors and contractors X 1.10.

Categories (includes but not limited to):

(i)
Site construction subcontractors; and

(ii)
Equipment

III.
Contractor’s subcontracted engineering:

Formula: Actual invoices X 1.10

Categories (includes but not limited to):

(i)
Estimate preparation; and

(ii)
preparation of Change Order alternatives and design of accepted Change Order(s)

IV.
Out of pocket costs:

Formula: Actual costs X 1.00

Categories (includes but not limited to):

(i) 
travel;

(ii) 
subsistence;

(iii) 
unusual postage; and

(iv) 
photocopying and printing

V.
Craft Labor costs:

Formula:  Estimated or actual man hours X applicable labor rate (see attached Labor Rates)

Categories (includes but not limited to):

(i)
Erection;

(ii)
Material Handling;

(iii)
Labor; and

(iv)
Labor supervision

VI.
Permanent materials:

Formula:  Estimated costs or actual invoices X 1.05

VII.
Equipment:

Formula:  Calculated or actual costs of Equipment X 1.10

Categories (includes but not limited to):

(i)
Contractor owned equipment;

(ii)
Contractor leased equipment; and

(iii)
Outside rented equipment

VIII.
Fee

Formula: (I + II + III + IV + V + VI + VII) X 0.10

IX.
Total Change Order Costs

Formula: Sum I through VIII

(Note: Direct salary wage cost is employee’s gross salary wage subject to income tax).

PROJECT
Pastoria



CITY


STATE
CA

PROP NO.
R000332

DATE
14-Sep-00























BURDENS







ESCALATION










PREMIUM

OH/PAY TX

WORK COMP

GROUP INS

YEAR
RATE
H.O.
FLD






HOME OFC
0%

97.0%

0.35%

0.0%

2000
0.0%
35.0%
0.0%






SALARIED
0%

52.0%

0.5%

0.0%

2001
4.0%
50.0%
70.0%






HOURLY
12%

11.00%

15.0%

5.0%

2002
8.0%
15.0%
30.0%
















AVG
3.2%
5.2%








 

























CREW RATE


ESCAL

PREM PAY
TLINE BASE RATE

OVHD/PAY TAX

WORK CMP

Group Ins & Fringes


TOTAL






















ENGINEERING
HO



40.00


45.00
1.44
0.00
46.44
45.05
0.16
0.00
$91.65 



HOME OFFICE
HO



40.00


45.00
1.44
0.00
46.44
45.05
0.16
0.00
$91.65 



CONSTRUCT MGR
Sal


90,000
48.27


53.27
2.77
0.00
56.04
29.14
0.28
0.00
$85.46 



RESIDENT ENGR
Sal


68,000
37.69


42.69
2.22
0.00
44.91
23.35
0.22
0.00
$68.48 



CONSTRUCT ENGR
Sal


50,000
29.04


34.04
1.77
0.00
35.81
18.62
0.18
0.00
$54.61 



GENERAL SUPT
Sal


72,000
39.62


44.62
2.32
0.00
46.94
24.41
0.23
0.00
$71.58 



DISCIPLINE SUPTS
Sal


63,000
35.29


40.29
2.10
0.00
42.39
22.04
0.21
0.00
$64.64 



SR PROJ CTRL ENGR
Sal


70,000
38.65


43.65
2.27
0.00
45.92
23.88
0.23
0.00
$70.03 



PRJ CTRL ENGR
Sal


50,000
29.04


34.04
1.77
0.00
35.81
18.62
0.18
0.00
$54.61 



FIELD ACCOUNTANT
Sal


47,000
27.60


32.60
1.70
0.00
34.30
17.84
0.17
0.00
$52.31 



HUMAN RESOURCES
Sal


65,000
36.25


41.25
2.15
0.00
43.40
22.57
0.22
0.00
$66.19 



PURCH AGENT
Sal


52,000
30.00


35.00
1.82
0.00
36.82
19.15
0.18
0.00
$56.15 



SR QA/QC SUPV
Sal



32.04


37.04
1.93
0.00
38.97
20.26
0.19
0.00
$59.42 



QA/QC SUPV
Sal



28.52


33.52
1.74
0.00
35.26
18.34
0.18
0.00
$53.78 



SAFETY SUPT
Sal



28.51


33.51
1.74
0.00
35.25
18.33
0.18
0.00
$53.76 



MEDIC
Sal



20.00


25.00
1.30
0.00
26.30
13.68
0.13
0.00
$40.11 



FIELD ENGR
Hr



27.00


33.00
1.72
4.17
38.89
4.28
5.83
10.00
$59.00 



PARTY CHIEF
Hr



27.00


33.00
1.72
4.17
38.89
4.28
5.83
10.00
$59.00 



CHAINMAN
Hr



25.00


30.00
1.56
3.79
35.35
3.89
5.30
10.00
$54.54 



CLERKS
Hr



18.00


23.00
1.20
2.90
27.10
2.98
4.07
1.36
$35.51 



RECEPTIONIST
Hr



18.00


23.00
1.20
2.90
27.10
2.98
4.07
1.36
$35.51 



TIMEKEEPER
Hr



25.00


30.00
1.56
3.79
35.35
3.89
5.30
10.00
$54.54 



TOOLROOM
Hr



25.00


30.00
1.56
3.79
35.35
3.89
5.30
10.00
$54.54 



QA/QC TECH
Hr



21.00


26.00
1.35
3.28
30.63
3.37
4.59
1.53
$40.12 



SAFETY TECH
Hr



21.00


26.00
1.35
3.28
30.63
3.37
4.59
1.53
$40.12 





























































































































































0%
0%
75%

$1.50 
$2.50 













h3
h2
h1
jm
fm
gf











BOILERMAKERS
Crew Mix
0.0
0.0
0.5
4.6
1.0
1.0





14.69%






Base Rate
0.00
0.00
22.25
29.66
31.16
32.16
29.69
1.54
3.75
34.98
3.85
5.14
8.41
$52.38 






















CEMENT FINISHERS
Crew Mix
0.0
0.0
0.3
2.6
1.0
0.0





13.62%






Base Rate
0.00
0.00
25.36
33.81
35.31
36.31
33.57
1.75
4.24
39.56
4.35
5.39
5.57
$54.87 






















CARPENTERS
Crew Mix
0.0
0.0
0.8
7.2
1.0
0.5





13.62%






Base Rate
0.00
0.00
21.37
28.49
29.99
30.99
28.18
1.47
3.56
33.21
3.65
4.52
6.80
$48.18 






















ELECTRICIAN
Crew Mix
0.0
0.0
0.0
9.0
1.0
0.5





5.47%






Base Rate
0.00
0.00
27.28
36.37
37.87
38.87
36.63
1.90
4.62
43.15
4.75
2.36
7.34
$57.60 






















INSTR FITTER
Crew Mix
0.0
0.0
0.8
6.9
1.0
0.3





11.32%





use Pipefitter
Base Rate
0.00
0.00
25.52
34.03
35.53
36.53
33.55
1.74
4.23
39.52
4.35
4.47
10.86
$59.20 






















IRONWORKER
Crew Mix
0.0
0.0
0.9
7.9
1.0
0.5





50.92%






Base Rate
0.00
0.00
22.13
29.50
31.00
32.00
29.14
1.52
3.68
34.34
3.78
17.49
8.74
$64.35 






















LABORER
Crew Mix
0.0
0.0
1.0
9.0
1.0
0.0





13.62%






Base Rate
0.00
0.00
17.69
23.58
25.08
26.08
23.18
1.21
2.93
27.32
3.01
3.72
6.29
$40.34 






















MECHANIC
Crew Mix
0.0
0.0
0.0
1.0
0.0
0.0





11.32%






Base Rate
0.00
0.00
20.00
26.66
28.16
29.16
26.66
1.39
3.37
31.42
3.46
3.56
4.53
$42.97 






















MILLWRIGHT
Crew Mix
0.0
0.0
1.0
8.6
1.0
0.5





11.32%






Base Rate
0.00
0.00
25.01
33.35
34.85
35.85
32.88
1.71
4.15
38.74
4.26
4.39
7.70
$55.09 






















OPERATOR, HEAVY
Crew Mix
0.0
0.0
0.0
1.0
0.0
0.0





11.32%






Base Rate
0.00
0.00
21.76
29.01
30.51
31.51
29.01
1.51
3.66
34.18
3.76
3.87
4.17
$45.98 






















OPERATOR, LIGHT
Crew Mix
0.0
0.0
0.0
1.0
0.0
0.0





11.32%






Base Rate
0.00
0.00
19.13
25.50
27.00
28.00
25.50
1.33
3.22
30.05
3.31
3.40
4.69
$41.45 






















PIPEFITTER
Crew Mix
0.0
0.0
0.7
6.3
1.0
0.3





6.92%






Base Rate
0.00
0.00
27.79
37.05
38.55
39.55
36.54
1.90
4.61
43.05
4.74
2.98
10.86
$61.63 






















PAINTER
Crew Mix
0.0
0.0
0.4
3.8
1.0
0.0





16.37%






Base Rate
0.00
0.00
17.34
23.12
24.62
25.62
22.94
1.19
2.90
27.03
2.97
4.42
2.46
$36.88 






















REBAR
Crew Mix
0.0
0.0
1.1
10.0
1.0
0.1





13.62%






Base Rate
0.00
0.00
22.13
29.50
31.00
32.00
28.97
1.51
3.66
34.14
3.76
4.65
8.74
$51.29 






















RIGGER
Crew Mix
0.0
0.0
0.8
7.6
1.0
0.5





14.69%






Base Rate
0.00
0.00
22.13
29.50
31.00
32.00
29.15
1.52
3.68
34.35
3.78
5.05
8.74
$51.92 






















TRUCK DRIVER
Crew Mix
0.0
0.0
0.2
1.4
1.0
1.0





11.32%






Base Rate
0.00
0.00
15.18
20.24
21.74
22.74
21.13
1.10
2.67
24.90
2.74
2.82
3.77
$34.23 






















WELDER ALLOY
Crew Mix
0.0
0.0
0.0
1.0
0.0
0.0





6.92%





use Pipfitter
Base Rate
0.00
0.00
27.56
36.75
38.25
39.25
36.75
1.91
4.64
43.30
4.76
3.00
10.86
$61.92 






















WELDER STRUCT
Crew Mix
0.0
0.0
0.0
1.0
0.0
0.0





50.92%





use Ironworker
Base Rate
0.00
0.00
25.54
34.05
35.55
36.55
34.05
1.77
4.30
40.12
4.41
20.43
8.74
$73.70 









 












21276484.1/11111-1111

09/26/00  12:21 PM
6
21276484.1

