#
Action
Impact on Default & Termination
Benefits
Downsides
Possible Furnas Reactions 

& Defenses
Timing and Process
Impact on Financing

Note: Items in Red are Opinion of Local Council
#
Action
Impact on Default & Termination
Benefits
Downsides
Possible Furnas Reactions 

& Defenses
Timing and Process
Impact on Financing

Note: Items in Red are Opinion of Local Council


Arbitration Options







1
Arbitrate our right to terminate - we seek only the confirmation that we have the right to terminate given Furnas’ past actions.
-Suspends right to terminate during arbitration

-Default continues until cured or contract terminated


-It is preemptive

-Furthers default strategy

-Avoids appearance of weakness evident in default extensions

-Buys time to refine region’s Cuiaba strategy

-Will Save time if we terminate because Furnas will elect this option as their initial defense

- Will allow us to see Furnas’ perceived defenses 
- if we lose, may have no other remedies 

- If we lose could not pursue strategy of putting EPE to Furnas


-Furnas may sign Consent & Aditivo 4

-Furnas may proceed to arbitrate 


-Per PPA  clause 103: 

1. Send Registered Letter

2. 30 days to respond

3. 15 days - appoint 3rd
4. 90 days to arbitrate

-Final step is litigate to enforce arbitration result.
Furnas may respond to heightened threat of termination and thus sign consent.

2
Arbitrate to force specific performance by Furnas to sign current consent; and request imposition of penalty for further delay.
-In lieu of termination

-Default continues until Consent signed

-Termination would remain remedy if Furnas fails to honor positive judgement
- Avoids appearance of weakness evident in default extensions

-Buys time to refine region’s Cuiaba strategy

- Would force Furnas to address our issue without inserting theirs into discussion 

- Would clarify key legal concept for all options
-may cause consent to become uncoupled from Eletrobras Guar issue (Additivo 4) 
-Furnas may sign Consent & Aditivo 4

-Furnas may proceed to arbitrate 

-Furnas alleges our repeated revisions caused delay

-Furnas asserts other factors inhibited financing
-Per PPA  clause 103: 

1. Send Registered Letter

2. 30 days to respond

3. 15 days – appoint 3rd
4. 90 days to arbitrate

- Final step is litigate to enforce arbitration result.
Threat of penalty could result in signed consent.

3
Arbitrate to force specific performance by Furnas to sign the original consent from Assumption Agreement; and request imposition of penalty for further delay. 
-In lieu of termination

-Default continues until Consent signed

-Termination would remain remedy if Furnas fails to honor positive judgement
- Would force Furnas to address our issue without inserting theirs into discussion 

· Would clarify key legal concept for all options

· Eliminates argument that repeated revisions caused delay
-may cause consent to become uncoupled from Eletrobras Guar issue (Additivo 4)

- Lenders lose desirable provisions negotiated in interim
-Furnas may  sign 

-Furnas may proceed to arbitrate

-Furnas asserts other factors inhibited financing
-Per PPA  clause 103: 

1. Send Registered Letter

2. 30 days to respond

3. 15 days – appoint 3rd
4. 90 days to arbitrate

- Final step is litigate to enforce arbitration result.
Threat of penalty could result in signed consent.

4
Arbitrate our right to damages; and request imposition of penalty for further delay. 
-Seeks economic compensation n lieu of termination

-Default continues in interim

-Termination could occur without resolution.
- Clarifies that there is a cost associated with delay in providing Consent

- Avoids appearance of weakness evident in default extensions

- Determines Compensation  for increased legal and capital costs 


-does not address lender issues

- Eliminates strategy of putting EPE to Furnas
-Furnas may sign

-Furnas may proceed with arbitration

-Furnas asserts other factors inhibited financing
-Per PPA  clause 103: 

1. Send Registered Letter

2. 30 days to respond

3. 15 days – appoint 3rd
4. 90 days to arbitrate

- Final step is litigate to enforce arbitration result.
Threat of penalty could result in signed consent.


Litigation Option







5
Litigate to force specific performance by Furnas to sign the original consent from Assumption Agreement; and request imposition of penalty for further delay. 
-In lieu of termination

-Default continues until consent signed

-Termination would remain remedy if Furnas fails to honor positive judgement
- Would force Furnas to address our issue without inserting theirs into discussion 

-Would clarify key legal concept for all options (affirmative obligation to provide Consent)

-Could be speediest approach if injunctive


- may cause consent to become uncoupled from Eletrobras Guar issue 

- Lenders lose desirable provisions negotiated in interim
-Furnas may sign Consent & Aditivo 4

-Furnas could demand arbitration first
-We believe that we have right to litigate as 1st course of action:

1. Seek injunctive relief

2. Two weeks to see if judgment in Enron’s favor 

3. Otherwise, timing unknown under protracted litigation

4. Counter-suit possible


Threat of penalty could result in signed consent.


Economic Equilibrium







6
Submit economic equilibrium claim* to compensate for extended use of Sponsor equity capital 
-Seeks economic compensation  in lieu of termination

-Default continues in interim and Termination could occur without resolution.
-Clarifies that there is a cost associated with delay in providing Consent

- Avoids appearance of weakness evident in default extensions


-Time consuming if only option pursued

-Furnas will act only thru arbitration or litigation
-Furnas ignores us

-Furnas reviews claim and says “NO”

-Furnas alleges our repeated revisions caused delay

-Furnas asserts other factors inhibited financing

-Arbiter may rule that this is a claim for damages and throw out  (although Tozzini believes low probability)
-Under PPA EE provision:

1. Submit request w/ damage calculation;

2. Timing unknown

We would seek either:

(a) indemnification for additional expenses due to no financing; or

(b) tariff increase for past costs and for compensation for no financing
Threat of EE claim could result in signed consent.


Other Options







7
Discontinue default notice and continue negotiations with Furnas

· Contributes to amicable long term relationship

· May achieve other contractual benefits such as converting to a financial contract

· 
-EPE Foregoes right to terminate

- May introduce spot market liability as additional impediment to financing


-Furnas may negotiate in earnest

-Furnas may drag out or wait on responses from ANEEL


PPA provisions relating to EE do not specify times for response or resolution.
Furnas not under threat; however may still sign.

8
Extend default period/delay termination notice (monthly, up to 6 months)

-Buys time to refine strategy

-Does not impact our ability to terminate if < 6 mos.
-appearance of weakness 

-may lose our credibility
-Furnas may continue to ignore us
Extend monthly, up to 6 months.
Maintains threat of termination; thus may sign.

1
2

