DRAFT

3/19/01


AGREEMENT

By and Between

E-NEXT GENERATION LLC,

Acting Through Its Agent

ENRON NORTH AMERICA CORP.

AND 

GENERAL ELECTRIC COMPANY

For The Purchase Of

[____________] GAS TURBINE GENERATOR PACKAGE(S)


TABLE OF CONTENTS

1ARTICLE 1 DEFINITIONS


9ARTICLE 2 RESPONSIBILITIES OF PURCHASER


92.1
Purchaser Responsibilities


9ARTICLE 3 RESPONSIBILITIES OF SELLER


93.1
General Obligations


103.2
Delivery of Equipment and Documentation


103.2.1
Delivery to Delivery Point


103.2.2
Impact Recorders


103.2.3
Documentation Delivery


103.3
Relevant Information


103.4
Hazardous Materials Notification


103.5
Employment of Trained and Experienced Personnel


103.6
Compliance with Governmental Rules and the Requirements of this Agreement


123.7
Approved Vendors


123.8
Packing and Insurance Surveyor


123.8.1
Packing Recommendation


133.8.2
Insurability Certificate


133.8.3
Notice of Shipment


133.8.4
Compliance with Recommendation


133.8.5
Coordination


133.9
Financing and Insurance Assistance


133.10
Purchaser Permit Support


133.11
Order Definition Meeting


143.12
Spare Parts


143.12.1
Commissioning Spares


143.12.2
Operating Spares


143.13
Key Personnel


14ARTICLE 4 RESPONSIBILITY FOR INFORMATION


144.1
Purchaser Supplied Information


14ARTICLE 5 PURCHASE AMOUNT AND OTHER CHARGES


145.1
Purchase Amount


145.1.1
Purchase Amount


155.2
Taxes and Contributions


155.2.1
Seller Responsibility for Personal Taxes


155.2.2
[Seller’s Responsibility for Taxes]


155.2.3
Taxes in the Project State


155.2.4
Tax Penalties


165.3
Changes to the Purchase Amount


165.4
Cancellation by Purchaser


165.5
Suspension or Change of Delivery


17ARTICLE 6 PAYMENT TERMS


176.1
Payment of Purchase Amount


176.1.1
Payment Periods


176.1.2
Payment Milestones


186.1.3
Retention


186.2
Payment Disputes


186.3
Payments Withheld or Offset


186.3.1
Payments Withheld


196.3.2
Offset for Liquidated Damages


196.4
Payment of Liquidated Damages


196.4.1
Payment of Document Liquidated Damages


196.4.2
Payment of Delivery Liquidated Damages


196.4.3
Payment of Takeover Liquidated Damages


196.4.4
Payment of Performance Liquidated Damages


206.5
Lien Release


206.6
Invoices


206.6.1
Payee and Address for Invoices


206.6.2
Date of Receipt


206.7
Method of Payment


206.8
Payments Not Acceptance of Work


21ARTICLE 7 NOTICE TO PROCEED AND TERMINATION


217.1
Notice to Proceed


217.2
Termination


21ARTICLE 8 RESERVED


21ARTICLE 9 INSPECTION AND CORRECTION OF WORK


219.1
Inspections


229.2
Resident Facilities


229.3
Quality Plan


229.4
Notice


229.5
Correction of Equipment


229.6
Additional Factory Testing


229.7
Release for Delivery


23ARTICLE 10 DELIVERY AND PERFORMANCE


2310.1
Delivery of Documentation


2310.1.1
Delivery of Final O & M Instructions


2410.2
Delivery of Equipment


2410.2.1
Guaranteed Delivery Date


2410.2.2
Inventory Upon Delivery


2410.2.3
Delivery


2410.2.4
Extensions of the Guaranteed Delivery Dates


2510.2.5
Offloading Responsibilities


2510.3
Delay Liquidated Damages


2510.3.1
Delivery Liquidated Damages


2610.3.2
Takeover Liquidated Damages


2710.3.3
Invoicing for Delivery and Takeover Liquidated Damages


2710.4
[Specific Performance Exhaust Gas Temperature and Energy Guarantee].


2710.4.1
[Interaction of  Exhaust Gas Energy and Exhaust Gas Temperature with Turbine Net Output]


2710.5
Sound Level Guarantees


2710.5.1
Sound Level Test


2810.6
Specific Performance Emissions Guarantee


2810.7
Electrical Output Guarantees


2810.8
Heat Rate Guarantees


2810.9
Performance Liquidated Damages


2810.9.1
Output Liquidated Damages


2810.9.2
Heat Rate Liquidated Damages


2810.9.3
[Exhaust Gas Temperature and Energy Liquidated Damages


2910.9.4
Performance Test Required


2910.9.5
Setting Out of Performance Liquidated Damages


2910.9.6
Most Recent Performance Test


2910.9.7
Seller’s Improvement of Performance


2910.9.8
Reduction in Performance Liquidated Damages


3010.10
Maximum Liabilities for Liquidated Damages


3010.11
Liquidated Damages Not Penalty


3110.12
Performance Tests and Sound Level Tests


3110.12.1
Concurrence of Tests


3110.12.2
Election to Conduct a Performance Test


3110.12.3
Specific Performance Achievement


3110.12.4
Timing of Tests


3210.12.5
Seller Presence at Tests


3210.12.6
Test Results


3210.12.7
Performance Test Procedures


3210.12.8
Reconduct of Tests


3210.12.9
Fittings, Instrumentation and Test Uncertainty


3310.12.10
Consumable Spare Parts During Retests


3310.13
Remedies For Failure to Meet Specific Performance Requirements


3310.13.1
Corrective Actions


3310.13.2
Failure to Achieve Specific Performance


3310.14
Acceptance


3410.15
Readiness for Testing


3510.16
Unit Serial Numbers


35ARTICLE 11 CHANGE ORDER


3511.1
Adjustment of Purchase Amount


3511.2
Purchaser Requested Change Order


3511.3
Seller Requested Change Order


3611.4
Disputes


3611.5
Change Order Pricing


36ARTICLE 12 INTENTIONALLY OMITTED


36ARTICLE 13 ORDER OF PRECEDENCE


3613.1
Order of Precedence


36ARTICLE 14 WARRANTY


3614.1
Equipment Warranty


3614.2
Warranty Period


3714.3
Warranties During Warranty Period


3714.4
Remedies


3714.5
Additional or Extended Warranty Periods.


3714.5.1
Warranty of Repaired or Replacement Parts


3814.5.2
Extension of Warranty Due to Unavailability


3814.5.3
Limitations


3814.6
Exclusions and Limitations.


3814.6.1
Exclusions


3814.6.2
Conditions


3914.6.3
Warranties Exclusive


3914.6.4
Remedies Exclusive


39ARTICLE 15 RISK OF LOSS AND TITLE


3915.1
Risk of Loss


3915.2
Title


3915.2.1
Passage of Title


3915.2.2
Infringement Cures and Defense


4015.3
Licensing Procedure


41ARTICLE 16 TRAINING AND TECHNICAL DIRECTION OF INSTALLATION


41ARTICLE 17 DEFAULT


4117.1
Events of Default by Seller


4217.2
Purchaser’s Remedies Against Seller


4217.3
General Obligations


4217.4
Payment Obligations


4317.4.1
Determination of Obligations


4317.4.2
Damages and Expenses


4317.4.3
Cover Damages


4317.4.4
Settlement


4417.5
Events of Default by Purchaser


4517.6
Seller Remedies


45ARTICLE 18 FORCE MAJEURE


4518.1
Failure to Perform Due to an Event of Force Majeure


4518.2
Events of Force Majeure


4618.3
Certain Events Not Excused


4618.4
Notice of Event of Force Majeure


4718.5
Continued Performance


4718.6
Event of Force Majeure - Delays


4718.7
Event of Force Majeure - Cost


4718.8
Cancellation for Force Majeure


4718.9
Payment on Cancellation for Force Majeure


48ARTICLE 19 INSURANCE


4819.1
Insurance - General


4819.1.1
All Risk


4819.1.2
Workers Compensation and Employers Liability Insurance


4819.1.3
Commercial General Liability Insurance


4819.1.4
Hull and Protection and Indemnity Insurance


4919.1.5
Business Automobile Liability Insurance


4919.1.6
Aircraft Liability Insurance


4919.1.7
Excess Umbrella Liability Coverage


4919.1.8
Vendors


4919.1.9
Certificate of Insurance


4919.1.10
Other Requirements


5019.1.11
Vendor Waiver of Subrogation


5019.1.12
Compliance with Insurance


5019.1.13
Limitation


5119.2
Purchaser’s Insurance


5119.2.1
Cargo Insurance


5119.2.2
Builder’s All Risk Insurance


51ARTICLE 20 INDEMNIFICATION


5120.1
Definitions


5220.2
Seller Indemnity


5220.3
Comparative Fault


5220.4
Insurance


5320.5
Notice and Litigation


5320.6
Survival of Obligations


53ARTICLE 21 NON-DISCLOSURE OF INFORMATION


5321.1
Proprietary Information


5321.2
Press Releases


5321.3
Confidentiality


5521.4
Disclosure of Contract Details


55ARTICLE 22 ASSIGNMENT


5522.1
Assignment by Seller


5622.2
Assignment by Purchaser


57ARTICLE 23 RELATIONSHIP OF THE PARTIES


5723.1
Independent Contractor


5723.2
Responsibilities of Seller as Principal for its Employees


58ARTICLE 24 LIENS AND CLAIMS


58ARTICLE 25 NOTICES AND COMMUNICATIONS


5825.1
Notices


5925.2
Effectiveness of Notices


5925.3
Technical Communications


5925.4
Notices to be Provided by Seller.


5925.4.1
Advance Shipment Notice


5925.4.2
Notice of Witness Test Points


5925.4.3
Major Component Packing Notice


5925.5
Notices to be Provided by Purchaser.


5925.5.1
Designation of Purchaser’s Representative


5925.5.2
Individuals Authorized to Approve Change Orders


5925.5.3
Notice of Performance Tests


60ARTICLE 26 ARBITRATION


6026.1
Negotiation of Disputes and Disagreements


6026.2
Arbitration Resolution


6026.3
Continuation of Work


61ARTICLE 27 LIMITATION OF LIABILITY


6127.1
Maximum  Liability of Seller


6127.2
Maximum Liability of Purchaser


6127.3
Consequential Losses


6127.4
Releases Valid in All Events


6227.5
Separate Advice or Assistance


62ARTICLE 28 DRUG AND ALCOHOL-FREE WORKPLACE


62ARTICLE 29 PROJECT PLANNING AND CONTROLS


63ARTICLE 30 MISCELLANEOUS


6330.1
Validity and Enforceability


6330.2
Governing Law


6330.3
Entire Agreement


6330.4
Agreement Modification


6330.5
Waiver


6330.6
Headings


6330.7
Third-Party Beneficiaries


6330.8
Counterparts


6330.9
Equal Employment Opportunity


6430.10
Cooperation on Site


6430.11
Avoidance of Nuclear Use


6430.12
Miscellaneous Representations and Warranties






AGREEMENT

This Agreement is made and entered into as of this ____ day of [_______, 200__ ] and effective as of the ____ day of [_______, 200__] (the “Effective Date”), by and between E-Next Generation LLC (“Purchaser”), a Delaware Limited Liability Company, acting through its agent Enron North America Corp., a corporation incorporated under the laws of the state of Delaware,  and General Electric Company, a corporation incorporated under the laws of New York,  (“Seller”).
RECITALS

WHEREAS, Purchaser has the need to acquire [
     ] gas turbine generator package(s) (the “Units,” whether one or more) for a nominally rated [___] megawatt “MW” [simple/combined] cycle generation plant located near [
, 
] the “Facility”), scheduled to be completed by [                     , 200_], and

WHEREAS, Seller is in the business of designing, engineering, manufacturing, and supplying gas turbine generator packages;

WHEREAS, Purchaser wishes to contract with Seller for the design, engineering, manufacture, and supply of the Units for the Facility and other services related thereto;

WHEREAS, the parties desire to set forth the terms and conditions under which Seller will provide and Purchaser will pay for the Units and related services;

NOW, THEREFORE, in consideration of the mutual covenants herein contained, and intending to be legally bound, the parties hereto agree as follows:

ARTICLE 1 
DEFINITIONS

Capitalized terms used in this Agreement without other definition shall have the meanings specified in this Article 1, unless the context requires otherwise.

As used in this Agreement, the terms “herein”, “herewith” and “hereof” are references to this Agreement, taken as a whole, the term “includes” or “including” shall mean “including, without limitation,” and references to a “Section”, “subsection”, “clause”, “Article”, “Exhibit”, “Appendix” or “Schedule” shall mean a Section, subsection, clause, Article, Exhibit, Appendix or Schedule of this Agreement, as the case may be, unless in any such case the context requires otherwise.  All references to a given agreement, instrument or other document shall be a reference to that agreement, instrument or other document as modified, amended, supplemented and restated through the date as of which such reference is made, and reference to a law, regulation or ordinance includes any amendment or modification thereof.  A reference to a person includes its successors and permitted assigns.  The singular shall include the plural and the masculine shall include the feminine, and vice versa.
The terms and the definitions set forth herein apply when capitalized.

 LISTNUM \l 2 
Acceptance»

.  Shall have the meaning as set forth in Section 10.14.

 LISTNUM \l 2 
Adjusted Electrical Output»

.  Shall mean the Electrical Output adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.

 LISTNUM \l 2 
Adjusted Emissions»

.  Shall mean the emissions when operated on natural gas as measured during the Performance Tests and adjusted to Basis Conditions by the methods described in Exhibit F.

 LISTNUM \l 2 
[Adjusted Exhaust Gas Energy»

.  Shall mean the Exhaust Gas Energy of a Unit as measured during a Performance Test and adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.]  

 LISTNUM \l 2 
[Adjusted Exhaust Gas Temperature»

.  Shall mean the Exhaust Gas Temperature of a Unit as measured during a Performance Test and adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.]  

 LISTNUM \l 2 
Adjusted Heat Rate»

.  Shall mean the Heat Rate when adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.

 LISTNUM \l 2 
Affected Party»

.  Shall have the meaning set forth in Section 18.1.

 LISTNUM \l 2 
Affiliate»

.  Shall mean a person or entity who, with respect to a specified  person or entity, directly or indirectly through one or more intermediaries controls, or is controlled by, or is under common control with, the person or entity specified.

 LISTNUM \l 2 
Agreement or Contract»

.  Shall mean this Agreement, including all Exhibits attached hereto and the Specification, as amended from time to time as provided herein.

 LISTNUM \l 2 
Applicable Laws»

.  Shall mean any applicable national, municipal or local statute, ordinance or other law, regulation or by-law or any rule, code or direction or any license, consent, permit, authorization or other approval including any conditions attached thereto (whether relating to the environment or otherwise) of the government of the United States or of any public body or authority, local or national agency, department, inspector, ministry, official or public or statutory person (whether autonomous or not) which has appropriate jurisdiction.

 LISTNUM \l 2 
Base Load»

.  Shall mean the operation of a Unit at 100% Electrical Output for the prevailing ambient temperature, relative humidity, barometric pressure, fuel heating value, temperature limitation, rated frequency and voltage.

 LISTNUM \l 2 
Basis Conditions»

.  Shall mean the conditions set forth in Exhibit A which are the basis for the Guaranteed Levels and Specific Performance Levels.

 LISTNUM \l 2 
Cancellation Charge»

.  Shall have the meaning as set forth in Section 5.4.

 LISTNUM \l 2 
Change in Law»

.  Shall mean any change in, or binding change in the judicial or administrative interpretation of, or adoption of, any Applicable Law, which is implemented after the Effective Date, and which has an adverse affect on Seller’s ability to perform its obligations under this Agreement; provided, however, that a change in any federal, commonwealth, state or local income or franchise tax law, workers’ compensation, or payroll or withholding tax law shall not constitute a change in law hereunder.

 LISTNUM \l 2 
Change Order»

.  Shall have the meaning as set forth in Section 11.2.

 LISTNUM \l 2 
Claim»

.
Shall have the meaning as set forth in Section 20.1(a).

 LISTNUM \l 2 
Codes and Standards»

.
Shall have the meaning as set forth in Exhibit F, Section 1.

 LISTNUM \l 2 
Commercial Operation»

.  Shall mean the reliable operation of a Unit by Purchaser in accordance with industry standards while the Unit is connected to the utility grid and producing electrical energy for sale. This does not include power that may be sold during start up, commissioning, or a Performance Test unless the generation of such power prevents commissioning.

 LISTNUM \l 2 
Commissioning Period»

.  Shall have the meaning as set forth in Section 10.3.2(d).

 LISTNUM \l 2 
Cover Damages»

.  Shall have the meaning as set forth in Section 17.4.3.

 LISTNUM \l 2 
Day or day»

.  Shall mean a calendar day, including weekdays, weekends, and holidays.

1.2.1
Deliver or Delivery.  Shall mean the delivery of a Unit to the Delivery Point.

 LISTNUM \l 2 
Delivery Date»

.  Shall mean the date on which Seller Delivers a Unit in accordance with Section 10.2.3.

 LISTNUM \l 2 
Delivery Liquidated Damages»

.  Shall have the meaning as set forth in Section 10.3.1.

 LISTNUM \l 2 
Delivery Point»

.  Shall mean the delivery of the Units to the nearest accessible rail siding (using appropriate available rolling stock and infrastructure, etc.), or for trucked items, to the Purchaser’s designated storage facility as designated by Purchaser in Exhibit U (using conventional vehicles carrying allowable loads over existing roads with no infrastructure changes or improvements).

 LISTNUM \l 2 
Document Delivery Date»

.  Shall have the meaning as set forth in Section 10.1.

 LISTNUM \l 2 
Document Liquidated Damages»

.  Shall have the meaning as set forth in Section 10.1.

 LISTNUM \l 2 
Due Date»

.  Shall have the meaning as set forth in Section 10.1.

 LISTNUM \l 2 
Effective Date»

.  Shall have the meaning as set forth in the Preamble on Page 1.

 LISTNUM \l 2 
Electrical Output»

.  Shall mean the electric output of a Unit measured at the generator terminals during a Performance Test (after deducting for actual auxiliary loads associated with the Unit).

 LISTNUM \l 2 
Electrical Output Guarantee»

.  Shall have the meaning as set forth in Exhibit B-3, Section B.3.4.1.

 LISTNUM \l 2 
Emissions Guarantee»

.
Shall have the meaning as set forth in Exhibit B-3, Section B. 3.3.1.

 LISTNUM \l 2 
Equipment»

.  Shall mean a Unit and all other material and supplies including the control systems described in Exhibits B-1 and B-2 to be furnished by Seller pursuant to the Scope of Work.

 LISTNUM \l 2 
Event of Force Majeure»

.  Shall have the meaning as defined in Section 18.1.

 LISTNUM \l 2 
Event of Purchaser Default»

.  Shall have the meaning as defined in Section 17.5.

 LISTNUM \l 2 
Event of Seller Default»

.  Shall have the meaning as defined in Section 17.1.

 LISTNUM \l 2 
[Exhaust Gas Energy»

.  Shall mean the exhaust energy of a Unit measured or calculated at the gas turbine exhaust outlet during a Performance Test.

 LISTNUM \l 2 
[Exhaust Gas Energy Guarantee»

.  Shall have the meaning as set forth in Exhibit B-3.1.3.]

 LISTNUM \l 2 
[Exhaust Gas Energy Liquidated Damages»

.  Shall have the meaning as set forth in Exhibit B-6, Section B.6.7.]

 LISTNUM \l 2 
[Exhaust Gas Temperature»

.  Shall mean the exhaust temperature of a Unit measured at the gas turbine exhaust outlet during a Performance Test.]

 LISTNUM \l 2 
[Exhaust Gas Temperature Guarantee»

.  Shall have the meaning as set forth in Exhibit B-3.1.1.]

 LISTNUM \l 2 
[Exhaust Gas Temperature Liquidated Damages»

.  Shall have the meaning as set forth in Exhibit B-6, Section B.6.6.]
 LISTNUM \l 2 
Facility»

.  Shall have the meaning as set forth in the Recitals.

 LISTNUM \l 2 
Far Field Sound Level Guarantee»

.  Shall have the meaning as set forth in Exhibit B-3, Section B.3.2.2.

 LISTNUM \l 2 
Guaranteed Levels»

.  Shall mean the Electrical Output Guarantee, Heat Rate Guarantee, [Exhaust Gas Temperature Guarantee and Exhaust Gas Energy Guarantee].  

 LISTNUM \l 2 
Guaranteed Delivery Date(s)»

.  Shall have the meaning as set forth in Section 10.2.1.1.

 LISTNUM \l 2 
Hazardous Materials»

.  Shall mean any hazardous substance or hazardous waste as defined in the Comprehensive Environmental Response, Compensation and Liability Act of 1980, as amended, the Resource Conservation and Recovery Act, as amended, the Hazardous Waste Transportation Act, as amended, and regulations promulgated pursuant to these Acts and any similar law or regulation in the United States or  equivalent laws and regulations issued by  U.S. federal and state governmental entities defining hazardous substances or hazardous waste, and any equipment containing polychlorinated biphenyls or asbestos that may become friable.

 LISTNUM \l 2 
Heat Rate»

.  Shall mean the actual fuel energy consumed during the Performance Test determined from the actual lower heating value of the fuel multiplied by the quantity of fuel consumed and expressed in BTU, divided by the integrated Electrical Output measured in kWh at the generator terminals during the Performance Tests in accordance with the testing guidelines set forth in Exhibit F, expressed as BTU/kWh(LHV).

 LISTNUM \l 2 
Heat Rate Guarantee»

.  Shall have the meaning as set forth in Exhibit B-3, Section B.3.5.1.

 LISTNUM \l 2 
Heat Rate Liquidated Damages»

.  Shall have the meaning as set forth in Exhibit B-6.

 LISTNUM \l 2 
Import Duties»

.  Shall, subject to Section 5.2.3, mean any taxes, customs, duties, fees, imposts, assessments, value added tax, and governmental charges that are payable upon or in relation to the importation of the Units, drawings or designs into the United States.

 LISTNUM \l 2 
Installation Period»

.  Shall mean the period of thirty six (36) months from the receipt of the last Major Component of the Unit to the Delivery Point.

 LISTNUM \l 2 
Insurability Certificate»

.  Shall have the meaning as set forth in Section 3.8.2(a).

 LISTNUM \l 2 
Insurance Representative»

.  Shall have the meaning as set forth in Section 3.8.1.

 LISTNUM \l 2 
Interest Rate»

.  Shall mean the Prime Rate as published by Citibank, N.A. at its New York City office plus two percent (2%) per annum, provided however, that the rate of interest hereunder shall never exceed the highest applicable lawful rate.

 LISTNUM \l 2 
kW»

.  Shall mean kilowatt.

 LISTNUM \l 2 
kWh or kwh»

.  Shall mean kilowatt hour.

 LISTNUM \l 2 
Lender»

.  Shall mean any financial institution or financier from which Purchaser is obtaining or has obtained financing in connection with the Facility and associated facilities and services.

 LISTNUM \l 2 
Liquidated Damages»

.  Shall mean any or all Takeover Liquidated Damages, Document Liquidated Damages, Delivery Liquidated Damages and/or Performance Liquidated Damages.

 LISTNUM \l 2 
Liquidated Damages Events»

.
Shall have the meaning as set forth in Section 10.11(a)(iv).

 LISTNUM \l 2 
Major Components»

.  Shall mean and consist of the Unit components listed on Exhibit U. 

 LISTNUM \l 2 
Milestone»

.  Shall mean an event that triggers a responsibility of Purchaser to pay a Milestone Payment Amount as set forth and listed in Section 6.1.2

 LISTNUM \l 2 
Milestone Payment Amount»

.  Shall mean the percentage of the  Purchase Amount due to Seller from Purchaser as set forth in Exhibit I-1.

 LISTNUM \l 2 
Near Source Sound Level Guarantee»

.  Shall have the meaning as set forth in Exhibit B-3, Section B.3.2.1.

 LISTNUM \l 2 
Notice»

.  Shall mean any notification of one party hereto by the other party hereto with respect to any matter arising under or in connection with this Agreement, to be given as provided in Exhibit E.

 LISTNUM \l 2 
Notice to Proceed»

.  Shall have the meaning as set forth in Section 7.1.

 LISTNUM \l 2 
O&M Spares»

.  Shall have the meaning as set forth in Section 3.12.2.

 LISTNUM \l 2 
ODM»

.  Shall have the meaning set forth in Section 3.3(a).

 LISTNUM \l 2 
Output Liquidated Damages»

.  Shall have the meaning as set forth in Section 10.9.1.

 LISTNUM \l 2 
Owner»

.  Shall mean [



].

 LISTNUM \l 2 
Patent Indemnitees»

.  Shall have the meaning set forth in Section 15.2.2.

 LISTNUM \l 2 
Performance Liquidated Damages»

.  Shall mean the Output Liquidated Damages, Heat Rate Liquidated Damages, [Exhaust Energy Liquidated Damages and Exhaust Temperature Liquidated Damages].  

 LISTNUM \l 2 
Performance Test»

.  Shall mean the test(s) conducted at the Site on the Units in accordance with the Test Procedures to determine Emissions, Heat Rate, Electrical Output, and Sound Levels.

 LISTNUM \l 2 
Performance Test Certificate»

.  Shall mean the certificate prepared by Purchaser in the format attached hereto as Exhibit G-1 and provided to Seller, certifying that a Performance Test has been completed and setting forth the results thereof in such detail to reflect the performance of the Units as tested with respect to Electrical Output, Emissions, Heat Rate, and Sound Levels.

 LISTNUM \l 2 
Performance Test Completion Certificate»

.  Shall mean the certificate prepared by Purchaser in the format attached hereto as Exhibit G-2 and provided to Seller, certifying the results of the Performance Tests that have been completed and quantifying Performance Liquidated Damages, if any, due.

 LISTNUM \l 2 
Power Purchaser»

.  Shall mean the applicable utility or any power purchaser which has entered into contract with an Affiliate of Purchaser to purchase power from the Facility.

 LISTNUM \l 2 
Project Manager»

.  Shall mean the project manager designated by Seller pursuant to Section 3.3(a) hereof.

 LISTNUM \l 2 
Proper Scope Value»

.  Shall have the meaning as set forth in Section 17.4.1.

 LISTNUM \l 2 
Punchlist»

.  Shall mean the list of the incomplete or deficient work or materials associated with Seller’s Scope of Work, which is comprised of those items which are minor in nature and do not affect the performance of the Equipment, safety or personnel working on or operating the Equipment or the ability of the Equipment to be used for its intended purpose.  Such Punchlist shall be produced by Seller and approved by Purchaser.

 LISTNUM \l 2 
Purchase Amount»

.  Shall mean the amount payable to Seller set forth in Section 5.1, as adjusted pursuant to the terms of this Agreement.

 LISTNUM \l 2 
Purchaser»

.  Shall have the meaning of the entity defined as Purchaser in the Preamble and its successors and permitted assigns.

 LISTNUM \l 2 
Purchaser Indemnified Party»

.  Shall have the meaning as set forth in Section 20.1(b).

 LISTNUM \l 2 
Purchaser’s Quality Assurance Manager»

.  Shall mean the person designated by Purchaser to approve the release to ship Major Components.

 LISTNUM \l 2 
Purchaser’s Related Parties»

.  Shall have the meaning as set forth in Section 19.1.11.

 LISTNUM \l 2 
Purchaser’s Representative»

.  Shall mean the individual designated by Purchaser pursuant to Section 2.1(a)  hereof, who shall have the responsibility and authority specifically delegated to such individual by Purchaser and made known in writing to Seller.

 LISTNUM \l 2 
Refund Amount»

.  Shall have the meaning as set forth in Section 17.4.1.

 LISTNUM \l 2 
Retention Amount»

.  Shall have the meaning as set forth in Section 6.1.3.

 LISTNUM \l 2 
Retention Letter of Credit»

.  Shall have the meaning as set forth in Section 6.1.3.

 LISTNUM \l 2 
Scope of Supply»

.  Shall have the meaning as set forth in Exhibit B-1.

 LISTNUM \l 2 
Scope of Work»

.  Shall mean all design, engineering, manufacture, delivery, transportation, technical direction of installation, training, other services, Equipment, drawings, documentation, supplies and materials to be performed and/or furnished by Seller (including that provided by its Vendors) pursuant to this Agreement or would have been reasonably expected to be supplied by a prudent supplier to ensure the successful operation of the Units.

 LISTNUM \l 2 
Scope Value Due»

.  Shall have the meaning as set forth in Section 17.4.1.

 LISTNUM \l 2 
Seller»

.  Shall mean have the meaning of Seller as defined in the Preamble and its successors and permitted assigns.

 LISTNUM \l 2 
Seller Indemnifying Party»

.  Shall have the meaning as set forth in Section 20.1(c).

 LISTNUM \l 2 
Shortfall»

.  Shall mean the amount by which a Unit fails to meet a Guaranteed Level or a Specific Performance Level as applicable.  Such shortfall shall be measured in the same units as the respective guarantee.

 LISTNUM \l 2 
Site»

.  Shall mean any part of the land where the Facility is to be constructed.

 LISTNUM \l 2 
Sound Level Guarantees»

.  Shall mean the Specific Performance guarantees of the Far Field Sound Level Guarantee and the Near Source Sound Level Guarantee.

 LISTNUM \l 2 
Sound Level Test»

.  Shall have the meaning as set forth in Exhibit B-3.

 LISTNUM \l 2 
Sound Level Test Procedures»

.  Shall mean the test procedures used to measure Sound Levels as set forth in Exhibit F-1.

 LISTNUM \l 2 
Sound Levels»

.  Shall mean the near source sound levels and the far field sound levels of the Units as measured during a Performance Test or Sound Level Test.

 LISTNUM \l 2 
Spare Parts Amount»

.  Shall have the meaning as set forth in Section 3.12.2.

 LISTNUM \l 2 
Specific Performance»

.  Shall mean, whether used by itself or as part of another defined term, an obligation that Seller must fulfill or achieve, or otherwise be in breach of its obligations hereunder.  Seller shall not be able to pay Liquidated Damages in lieu of meeting such specific performance requirements.

 LISTNUM \l 2 
Specific Performance Electrical Output Guarantee»

.  Shall mean Specific Performance Electrical Output Guarantee as set forth in Exhibit B-3, Section B.3.4.2.

 LISTNUM \l 2 
[Specific Performance Exhaust Gas Energy Guarantee»

.  Shall have the meaning  as set forth in Exhibit B-3, Section B.3.1.4.]  

 LISTNUM \l 2 
[Specific Performance Exhaust Gas Temperature Guarantee»

.  Shall have the meaning as set forth in Exhibit B-3, Section B.3.1.2.]  

 LISTNUM \l 2 
Specific Performance Heat Rate Guarantee»

.  Shall have the meaning  as set forth in Exhibit B-3, Section B.3.5.2.

 LISTNUM \l 2 
Specific Performance Levels»

.  Shall mean the Specific Performance Electrical Output Guarantee, Specific Performance  Heat Rate Guarantee, [Exhaust Gas Energy Guarantee, Exhaust Gas Temperature Guarantee,] Emissions Guarantee and Sound Level Guarantees.  
 LISTNUM \l 2 
Specification»

.  Shall mean the specification as issued by Purchaser for the design, manufacture, assembly set forth in Exhibit B, and the specification by Seller for the supply of the Units as set forth in Exhibit B-1.

 LISTNUM \l 2 
Takeover»

.  Shall mean the Facility has achieved Substantial Completion as set forth in the [Owner Agreement] [Note:  Not defined herein.]  (Substantial Completion meaning, accepted for Commercial Operation).

 LISTNUM \l 2 
Takeover Liquidated Damages»

.  Shall have the meaning as set forth in Section 10.3.2.

 LISTNUM \l 2 
TD of I»

.  Shall have the meaning and scope as set forth in Exhibit H-1.

 LISTNUM \l 2 
Termination Costs»

.  Shall have the meaning as set forth in Section 17.4.2.

 LISTNUM \l 2 
Termination Settlement»

.  Shall have the meaning as set forth in Section 17.4.4.

 LISTNUM \l 2 
Test Procedures»

.  Shall have the meaning as set forth in Section 10.12.7.

 LISTNUM \l 2 
Test Run»

.  Shall have the meaning as set forth in Exhibit F, Section 2. 

 LISTNUM \l 2 
Third Party»

.
Shall have the meaning as set forth in Section 20.1(d).

 LISTNUM \l 2 
Time for Completion»

.  Shall mean the date set forth in Exhibit U as the date the Facility is scheduled to be completed.

 LISTNUM \l 2 
Training»

.  Shall have the meaning and scope as set forth in Exhibit H-2.

 LISTNUM \l 2 
Unit»

.  Shall mean the gas turbine generator package already defined in the recitals of this Agreement.

 LISTNUM \l 2 
Vendor»

.  Shall mean any vendor, supplier or subcontractor utilized by Seller in the performance of the Scope of Work hereunder.

 LISTNUM \l 2 
Warranty Period»

.  Shall have the meaning as set forth in Section 14.2(b).

ARTICLE 2 
RESPONSIBILITIES OF PURCHASER

2.1 Purchaser Responsibilities»

.  Purchaser recognizes and acknowledges the duty to reasonably cooperate with Seller, and agrees not to wrongfully interfere with Seller’s agents, employees or Vendors during the performance of this Agreement.  Without limiting the generality of the foregoing, Purchaser shall be responsible for the following matters and actions to be performed on a timely basis:

(a) Purchaser shall notify the Seller in accordance with Section 25.5.1 of the individual it has designated as Purchaser’s Representative who shall act as the primary point of contact for Seller with respect to the prosecution of the Scope of Work;

(b) Purchaser shall notify the Seller in accordance with Section 25.5.2 of the persons within Purchaser’s organization that have authority to approve Change Orders;

(c) Purchaser shall pay to Seller the sums required to be paid by Purchaser pursuant to the terms of this Agreement; and

(d) the Units shall be installed, operated and maintained by Purchaser as identified in Exhibit B-1, and as otherwise stated in the Agreement.  
ARTICLE 3 
RESPONSIBILITIES OF SELLER

3.1 General Obligations»

.  Except as expressly set forth in this Agreement, Seller shall provide the new materials and supplies, technical and professional personnel, supervision at Seller’s facilities and as required for Seller to fulfill its transportation responsibilities, tools and equipment, and the services required for performance and timely completion of the Scope of Work.  Seller shall be responsible for timely completing the Scope of Work in accordance with the terms of this Agreement, including all Exhibits.
References in the Specification to equipment, material, articles or patented processes by trade name, make, or catalog number, shall be regarded as the standard of quality to be met by Seller.  Seller may, subject to written notification to Purchaser, use any equipment, material, article, or process that is operationally, technically and functionally equivalent to that named in the Specification.  

3.2 Delivery of Equipment and Documentation»

.

3.2.1 Delivery to Delivery Point»

. Seller shall Deliver the Equipment (except as otherwise specifically set forth in the Agreement) in accordance with Section 10.2.

3.2.2 Impact Recorders»

.  Seller shall provide Purchaser with details of procedures pertaining to securing the Unit’s rotors during transportation.  If, as a result of such review, Purchaser reasonably determines that impact recorders are required, Seller shall provide such impact recorders within the Purchase Amount.

3.2.3 Documentation Delivery»

.  Seller shall deliver documentation as set forth in Section 10.1 by the dates set forth therein.

3.3 Relevant Information»

.  Seller shall provide on a timely basis to Purchaser information reasonably necessary to fulfill Seller’s obligations pursuant to this Agreement, including, without limitation:

(a) at the order definition meeting (the “ODM”) pursuant to Section 3.13, the identity of a project manager (the “Project Manager”) who shall have full supervision over the completion of  the Scope of Work and who shall act as the primary point of contact with Purchaser regarding all matters relating to the Scope of Work; and

(b) such information as is requested by Purchaser in dealing with the Power Purchaser and/or any governmental authority in matters relating to the Scope of Work.  Such obligation shall not include information such as grid or power generation studies for the total power system.

3.4 Hazardous Materials Notification»

.  Seller warrants to Purchaser that in relation to the Scope of Work, it will use reasonable skill and care to ensure that there will not be Hazardous Materials specified or incorporated into the Equipment. In the event Seller incorporates any Hazardous Materials into the Equipment, Seller shall provide Purchaser with notification as set forth in Exhibit O.

3.5 Employment of Trained and Experienced Personnel»

.  Seller shall be responsible for employing and utilizing personnel, and for ensuring that its Vendors employ and utilize personnel, who possess the proper training and experience and are capable of performing the tasks for which they are employed or utilized.

3.6 Compliance with Governmental Rules and the Requirements of this Agreement»

.  Seller shall comply with all Applicable Laws including but not limited to those described in the categories enumerated below.

(a) Seller Conduct.  Seller shall comply with applicable regulatory requirements including, without limitation, all Applicable Laws issued or promulgated by units of government and regulatory bodies with jurisdiction over any aspect of the performance of this Agreement by Seller. Seller shall not act in violation of the U.S. Foreign Corrupt Practices Act or similar law of the United States, and in connection therewith shall not make any payments, loans, or gifts directly or indirectly, to or for the use or benefit of any official employee, agency or instrumentality of any government, political party or candidate thereof, or any other person or entity, the payment of which would violate the laws or policies of the United States, or the country or countries in which the Scope of Work is performed, in whole or in part.  Seller shall possess or procure all permits, certificates, and licenses necessary to allow Seller to perform this Agreement at all Seller or Vendor locations of performance and shall ensure that Vendors have all permits, certificates, and licenses necessary for such Vendors to perform under this Agreement. Seller shall answer promptly and in reasonable detail any questionnaire or other written or oral communications, to the extent the same pertain to compliance with this Section 3.6 (a) or (b) whether such questionnaires or communications are from Purchaser, their outside auditors, or other representatives.  

(b) Employment Practices.  Seller agrees that at all times during the term of this Agreement it shall be in full compliance with all Applicable Laws relative to Seller’s employment of employees and agents of Seller.

(c) Scope of Work to Comply with Applicable Laws and Specifications.  Subject to the provisions of Section  3.6(c)(iv):

(i) Seller shall cause the Scope of Work to comply with Applicable Laws that were:

(A) in effect on the Effective Date; or

(B) were not yet in effect on the Effective Date, but at such time a change to such valid Applicable Laws, issued or promulgated by units of government and regulatory bodies had passed but was not yet effective;


Seller shall also comply with the Specification attached hereto as Exhibit B-1.  In the event Seller fails to cause the Scope of Work to so comply with the Specification and Applicable Laws, Seller shall correct such noncomplying Scope of Work or portion thereof as necessary to comply with the above.  Seller shall bear the costs of correction of such noncomplying Scope of Work.  In the event that Purchaser reasonably determines that Seller is either not capable of performing the corrections or not capable of performing such corrections in time to meet Purchaser’s requirements, Purchaser may, at Seller’s expense, have the corrections made by a third party or make them itself; provided, however,  prior to Purchaser having the corrections performed by a third party or itself Purchaser shall have provided Seller notice of its determination that it believes Seller is not capable of such performance of work or performing such corrections in a timely manner.

(ii) In the event that Seller does not comply with the Specification or Applicable Laws, and Purchaser at its sole determination agrees Seller cannot reasonably incorporate the changes necessary for Seller to comply, Purchaser, in its sole discretion, may either terminate the Agreement in accordance with Article 17, or direct Seller to complete the Equipment without such changes, in which case Purchaser shall assume full responsibility for obtaining any necessary waivers from the appropriate federal, state or local authorities.

(iii) Seller shall, on a reasonable efforts basis, advise Purchaser of pending Applicable Laws so that Purchaser may make an informed decision as to whether to have the Equipment designed in anticipation of such pending change as it affects the Scope of Work.

(iv) In the event a Change in Law occurs subsequent to the times set forth in Section 3.6(i), Seller shall prepare a request for a Change Order to Purchaser identifying the nature of the change, including any resultant extensions of time to the performance of the Scope of Work and the Purchase Amount.  In the event that Purchaser elects to not have Seller comply with such change, Purchaser shall indemnify Seller for such failure of the Scope of Work to comply with such new law requirement.

3.7 Approved Vendors»

. Purchaser agrees that Seller may utilize the Vendors listed in Exhibit B-4 for procurement of the components under which they are listed.  

3.8 Packing and Insurance Surveyor»

.

3.8.1 Packing Recommendation»

.  Seller shall perform all packaging of the Equipment to the highest commercial standard practices of the industry to prevent damage during its handling and transportation to the Delivery Point.  Seller shall respond to and comply with Purchaser’s insurance representative’s (salvage association or similar insurance surveyor as appointed by Purchaser) (the “Insurance Representative”) recommendations concerning:

(a) packaging of the Equipment;

(b) Seller’s execution of the load plan on its transport to preclude damage during transit;

(c) transshipment;

(d) movement to the Delivery Point, including route surveys; and

(e) prohibition of the use of tandem barges.

Seller shall immediately notify Purchaser of any unreasonable recommendations.

3.8.2 Insurability Certificate»

.  Seller expressly acknowledges and agrees that it will not commence transport of the items of Equipment unless;

(a) the Insurance Representative conducts a load plan and load survey and issues an insurance certificate, (the “Insurability Certificate”) attesting that its recommendations were carried out for such shipment with respect to the Equipment listed in Exhibit L; or

(b) Purchaser’s Representative expressly waives such requirement for that shipment.

3.8.3 Notice of Shipment»

.  Seller recognizes that failing to comply with this Section 3.8 may jeopardize Purchaser’s insurance program.  Seller shall provide Purchaser’s Representative with the notice required pursuant to Section 25.4.1. Purchaser may designate its Insurance Representatives as recipient of such notice.  Provided Seller has provided Purchaser with such notice in accordance with Section 25.4.1, if the Insurance Representative is not available to perform the necessary inspections on the dates of loading indicated in Seller’s final notice or the recommendations of the Insurance Representative are mutually agreed by Seller and Purchaser to have been unreasonable, Purchaser shall extend the Guaranteed Delivery Dates to the extent Seller is delayed by such unavailability or unreasonable recommendations and shall compensate Seller for any applicable costs including demurrage attributable thereto.  Seller acknowledges that all efforts and delays (other than as set forth in this Section 3.10) associated with receiving the Insurability Certificate shall not be grounds for extension to the Guaranteed Delivery Date(s).

3.8.4 Compliance with Recommendation»

.  Seller’s compliance with the Insurance Representative’s recommendations shall not relieve Seller of its responsibility for risk of loss and damage of the Equipment in accordance with this Agreement through Delivery.

3.8.5 Coordination»

.  Seller agrees to host a transportation coordination meeting on a mutually agreed date at its facility no later than forty five (45) days prior to shipment of the first Major Component.  Purchaser shall coordinate attendance by its Insurance Representative.

3.9 Financing and Insurance Assistance»

.  Seller shall provide such information as Purchaser may reasonably request in connection with obtaining financing and insurance for the Facility including, without limitation, providing information related to design, engineering and status of the completion of the Scope of Work and Seller’s credentials and experience, and as required perform reasonable travel.  Purchaser shall reimburse Seller at commercially reasonable rates for its time in providing information not related to the Scope of Work.  Lender and the Lender’s engineers and consultants shall have the right to participate in all inspections conducted by Purchaser under this Agreement and to attend all tests of the Equipment.  At Purchaser’s request, Seller shall furnish to Lender copies of notices given to Purchaser hereunder.

3.10 Purchaser Permit Support»

.  Seller shall provide in a timely fashion all information, data and documents that Purchaser may reasonably require for Purchaser to obtain Facility permits.

3.11 Order Definition Meeting»

.  Seller agrees to host an ODM at its facility to finalize project scope issues for the purpose of Seller’s issuance of its ancillary equipment order and commencement of detailed engineering.  The parties agree that such equipment order releases and detailed engineering shall not proceed prior to the completion of the ODM except as may be mutually agreed or otherwise required in the Agreement.
3.12 Spare Parts»

.

3.12.1 Commissioning Spares»

.  Seller’s representative priced list of start-up and commissioning spares and a representative list of special tools needed during start-up and commissioning are set forth in Exhibit M-2.  Seller shall provide to Purchaser at no additional charge: (a) all spare parts necessary to achieve start up, commissioning, performance testing, and (b) all installation and maintenance tools that are not normally found available in the market place.

3.12.2 Operating Spares»

.  Set forth in Exhibit M-1 is a priced listing of operating and maintenance spare parts (the “O&M Spares”) for the Units.  In addition to the Purchase Amount, Purchaser may elect to purchase any quantity or type of spare parts listed in Exhibit M-1 through the validity period stated in the footer of Exhibit M-1.  Spare parts that are covered by this Section 3.12.2 that are ordered by Purchaser shall be delivered FOB factory in accordance with Exhibit M-1.  The purchase value of any ordered spare parts covered by this Section 3.12.2  shall not be included in the Purchase Amount, and will be referred to as the “Spare Parts Amount”.  Purchaser’s purchase or lack of purchase of O&M Spares  under this Agreement shall not preclude Purchaser, or Purchaser’s operator, from purchasing such spare parts under separate agreement with Seller.

3.13 Key Personnel»

.  If, in its reasonable opinion, Purchaser determines Seller’s Project Manager or lead technical advisor is not adequately performing, Purchaser may require Seller to remove such person from work on the Scope of Work under this Agreement and replace such person with a satisfactory replacement.

ARTICLE 4 
RESPONSIBILITY FOR INFORMATION

4.1 Purchaser Supplied Information»

.  Except to the extent that the information provided by Purchaser to Seller is in the form of a specification or performance requirement specifically called out in this Agreement or performance requirements which Purchaser is obligated to provide under the Agreement, it is Seller’s responsibility to ensure that the information provided to Seller by Purchaser is accurate, correct, complete and fit for the particular purpose(s) for which Seller utilizes it.

ARTICLE 5 
PURCHASE AMOUNT AND OTHER CHARGES

5.1 Purchase Amount»

.

5.1.1 Purchase Amount»

.  The purchase amount as set forth in Exhibit N-1 (the “Purchase Amount”) shall be Seller’s full compensation for Seller’s performance of the Scope of Work, including but not limited to Seller’s Delivery of the Equipment, as provided hereunder, which shall be paid in accordance with Article 6.  The Purchase Amount is subject to increases or decreases only as provided in Section 5.3 or Change Orders with respect to the Scope of Work approved in accordance with Article 11.  The Purchase Amount shall be complete compensation for Seller to perform its obligations under this Agreement.

Exhibit N-1 sets forth a full reconciliation of the Purchase Amount.  Exhibit N-2 lists options of the Purchaser, prices and times by which the options must be exercised by Purchaser.  If an option is exercised by Purchaser, the applicable option amount shall be used to adjust the Purchase Amount.

5.2 Taxes and Contributions»

.

5.2.1 Seller Responsibility for Personal Taxes»

.  Seller assumes full responsibility for and agrees to pay all contributions and taxes payable under all Applicable Laws pertaining to social security laws, unemployment compensation laws and income tax laws as they apply to Seller’s and Vendor’s employees engaged in the performance of the Scope of Work.  Seller acknowledges that Purchaser has no responsibility for such taxes as they apply to Seller, Seller’s employees or the employees of Vendors.

5.2.2 [Seller’s Responsibility for Taxes]»

.  Except as provided for in Section 5.2.3 Seller agrees to pay, and shall be responsible for, within the Purchase Amount, corporate income tax, export duties, Import Duties, customs clearance, sales taxes, or other similar taxes associated with the design, manufacture and Delivery of the Equipment and the performance of the Scope of Work assessed by any federal, state country, local or other legal taxing authority and any of its subdivisions, and to pay any and all valid sales or use taxes levied on general office, engineering and drafting supplies, materials, equipment, and services performed by Seller hereunder.] [Note: Parties’ tax counsel to discuss this]

5.2.3 Taxes in the Project State»

.  The Purchase Amount excludes any US state or local jurisdiction imposed property, license privilege, sales, use, excise, gross receipts, valued added, or similar tax which may now or hereafter be applicable to, measured by, or imposed upon with respect to the transaction, Seller’s Scope of Work, its sale, its value, its presence in the project state’s taxing jurisdiction or its use, or any services performed in connection therewith.  Such taxes are for the account of Purchaser and Purchaser agrees to pay any such tax when due or reimburse Seller within twenty five (25) days after the date of Seller’s invoice Purchaser for any such tax which it is required to pay.  Should Purchaser be exempted from any such tax it shall provide Seller with certification prior to transfer of title of such Work, or at the time the certification is obtained, whichever first occurs.

5.2.4 Tax Penalties»

.  Seller further agrees to pay any tax, interest, penalty, fines, costs, losses and expenses (including, without limitation, court costs and attorney’s fees) of whatever kind, which Purchaser may incur, be required by law to pay, or be liable for as a result of, arising from, in connection with, related to or based on any failure to withhold any amounts from any payments made or any amounts which Seller fails to pay in connection with, as a result of, arising from or based on the Scope of Work  or otherwise comply with this Section, except and to the extent such failure is attributable to Purchaser’s negligent act or failure to act, in which case Purchaser shall be responsible for and agrees to pay the portion of such tax related amounts as referred to above as are attributable to Purchaser’s negligent act or failure to act.

5.3 Changes to the Purchase Amount»

.  The Purchase Amount may only be adjusted in the following circumstances:

(a) Change in Law requiring changes as provided in Section 3.6(c)(iv);

(b) suspension pursuant to Section 5.5;

(c) breach or default of this Agreement by Purchaser or Seller;

(d) an Event of Force Majeure in which Purchaser is the Affected Party; exceeding a duration in the aggregate of thirty (30) Days in accordance with Section 18.9;

(e) Change Orders issued pursuant to Article 11; 

(f) Purchaser exercising options such as cancellation pursuant to Section 5.4. of this Agreement.

Seller’s entitlement to an increase in the Purchase Amount shall be conditional upon:

(g) a demonstrable increase in the Purchase Amount or an adverse impact on Seller’s ability to deliver the Units by the Delivery Date;

except with respect to clauses (e) and (f) of this Section 5.3:

(h) Seller having used reasonable endeavors to mitigate the cost increase (except for Purchaser’s exercise of options or Purchaser instructing Seller in its performance of any option, then compliance would not be considered a breach of this provision);

(i) Seller having given notice in accordance with the terms of this Agreement; and

(j) the cost increase not being attributable to Seller’s default.

5.4 Cancellation by Purchaser»

.  Purchaser may cancel this Agreement at any time in whole or in part, without cause and for its own convenience, upon written notice to Seller.  If Purchaser cancels this Agreement under this Section 5.4, then Purchaser shall pay Seller the Cancellation Charge applicable to the canceled Units in accordance with Exhibit I within thirty (30) days after the effective date of such cancellation.  If Purchaser cancels this Agreement pursuant to this Section 5.4, Seller shall retain title to the Equipment unless title has passed or will pass to Purchaser pursuant to Article 15.  For the avoidance of doubt, Seller will not cease manufacture of the Units for reasons of Purchaser cancellation or suspension.

5.5 Suspension or Change of Delivery»

.

5.5.1
Purchaser shall be entitled to suspend Delivery in accordance with Section 5.5.2. 
5.5.2
If Purchaser instructs Seller to suspend Delivery by written notice, such notice to be provided no later than ninety (90) days prior to the shipment of a Unit and the Major Components thereof, and the Equipment or any part of the Equipment cannot be shipped to the Delivery Point in accordance with the Agreement when ready due to any cause not attributable to Seller, Seller shall ship such Equipment to such other locations in the United States as Purchaser shall designate.  Cost increases or decreases which are directly associated with delivering a Unit to a changed Delivery Point such as offloading, transshipments or change of mode of transport, shall be grounds for a Change Order.  If such Equipment is directed by Purchaser to be placed in storage, including storage at the facility where manufactured, the following conditions shall apply: (a) for the purpose of assessing Liquidated Damages and final payment, Seller’s delivery obligation shall be deemed fulfilled upon delivery to storage and title shall thereupon pass to Purchaser if it had not already passed; (b) any amounts otherwise payable to Seller upon delivery shall be payable upon presentation of Seller’s invoices pursuant to Section 6.1.1; (c) all expenses incurred by Seller, such as preparation for and placement into storage, handling, inspection, preservation, insurance, storage, removal charges and any taxes (anything to the contrary in the Agreement notwithstanding), shall be added by Change Order and payable by Purchaser upon submission of Seller’s invoices pursuant to Section 6.1.1; and (d) if the a Unit is placed in storage other than at its final use point, when conditions permit, Seller shall arrange on behalf of Purchaser and at Purchaser’s expense for any additional or incremental costs of shipment of the Equipment not then included in Seller’s Scope of Work.  In the event Purchaser directs Seller to store the Equipment in lieu of shipping to the Delivery Point and to retain care and custody, Seller will retain risk of damage and loss.
ARTICLE 6 
PAYMENT TERMS

6.1 Payment of Purchase Amount»

.

6.1.1 Payment Periods»

.  Payment of each Milestone Payment Amount, unless otherwise noted in Exhibit I-1, shall be due and payable by Purchaser to Seller within thirty (30) days of:

(a) Seller achieving the applicable Milestone; and

(b) Purchaser’s receipt of a properly prepared invoice for such Milestone Payment Amount.

Payment of the Spare Parts Amount, to the extent Purchaser orders O&M Spares, shall be due and payable by Purchaser to Seller within thirty (30) days of:

(x)
Seller’s proper delivery of all of the O&M Spares to Purchaser’s carrier at the factory; and

(y)
Purchaser’s receipt of a properly prepared invoice for such Spare Parts Amount.

6.1.2 Payment Milestones»

.  The detailed payment milestone schedule is set forth in Exhibit I-1.

Payment of the final five percent (5%) of the Purchase Amount is subject to Section 6.1.3.

For foreign sourced Major Components, with respect to actions triggered by shipment, shipment shall be understood to occur upon clearance from customs at the U.S. port of import and departure to the Site.

6.1.3 Retention»

.  As set forth in Section 6.1.2, Purchaser shall retain the last five percent (5%) of the Purchase Amount, unless a greater amount is required to be retained by state law, in which case the amount specified pursuant to state law shall apply (the “Retention Amount”), until the expiry of the Warranty Period; provided, however, Purchaser shall pay Seller the Retention Amount as earned when:

(a) Seller satisfies the requirements set forth in Section 6.5; and

(b) Seller provides the Retention Letter of Credit in the amount of five (5%) percent of the Purchase Amount.  [Note:  If Agreement is for more than one Unit, the Retention Amount will be 5% of the Purchase Amount for each Unit multiplied by the number of Units acquired.]
Seller shall present as the “Retention Letter of Credit” an irrevocable on demand retention letter of credit for the full amount of the Retention Amount in a form generally in accordance with the sample set forth in Exhibit D from a United States bank located in the United States acceptable to Purchaser.  [Note:  If more than one Unit is purchased, the Letter of Credit shall be reduced incrementally as the Warranty Period for each Unit expires.]

6.2 Payment Disputes»

.  Payment of any invoices or portions of invoices shall not prejudice the right of Purchaser to protest or question the correctness thereof or Seller’s compliance with the terms of this Agreement and the Scope of Work or any portion thereof or prejudice or constitute a waiver of any right of Purchaser hereunder.  Any amount questioned by either party and found to be in such party’s favor shall be refunded or paid, as appropriate.  In the event an amount is withheld because of a dispute, and it is subsequently determined that the disputed amount or a portion of the disputed amount was due and payable, interest shall accrue at the Interest Rate commencing on the date the payment would have been payable if the dispute had not occurred.  Seller’s acceptance of partial payment of the Purchase Amount shall not be deemed to constitute a waiver of the right to receive amounts which are then in dispute, and Seller and Purchaser shall use their best efforts to resolve all disputed amounts as soon as practicable.  Any undisputed amounts not paid when due shall bear interest at the Interest Rate.

6.3 Payments Withheld or Offset»

.

6.3.1 Payments Withheld»

.  Purchaser may, following notice to Seller of its intent to withhold, and Seller not having eliminated the basis for the withholding within thirty (30) days of Purchaser’s notice, withhold payment on an invoice or a portion thereof, in an amount and to such extent as may be reasonably necessary, subject to the dispute resolution provisions of Article 26, to protect Purchaser from loss because of:

(a) defective work or Equipment not remedied pursuant to Section 9.5 or the warranty provisions of Article 14;

(b) third party suits, stop notices or liens for which Seller is liable under this Agreement, whether directly or pursuant to any indemnification obligation hereunder, (other than those provided for by insurance, bonds or other security) made on or filed with Purchaser or with respect to the Site or the project and not cleared by Seller by payment, deposit or otherwise to the reasonable satisfaction of Purchaser within ten (10) days after receipt by Seller of written notice from Purchaser requesting such action; and

(c) uninsured damage to Purchaser or Vendor any which results solely from Seller’s failure to obtain or maintain the insurance required by the provisions of Article 19 or from any action or inaction by Seller or any Vendor which excuses any insurer from liability for any loss or claim otherwise covered by insurance.

In the event a payment is improperly withheld or not paid when due and payable, such payment amounts due and payable shall accrue interest at the Interest Rate commencing on the date that payment would have been payable, had the withholding not occurred.

6.3.2 Offset for Liquidated Damages»

.  Purchaser shall have the right to offset from  any payments due to Seller  (or draw against the Retention Amount or Retention Letter of Credit in cases where no amounts remain to be invoiced), any amounts due to Purchaser from Seller, including, but not limited to, the amount of any Liquidated Damages due from Seller.  In the event the Liquidated Damages exceed the payment amount, Retention Amount or remaining value of the Retention Letter of Credit, Purchaser shall retain the payment amount and invoice the excess amount of Liquidated Damages in accordance with Section 6.4.  In the event Purchaser offsets a Liquidated Damage which Seller disputes and it is subsequently determined that amount or a portion of the disputed amount should not have been offset, interest on the portion of the offset that should not have been offset shall accrue at the Interest Rate commencing on the date the payment that was offset would have been payable if the amount had not been offset.

6.4 Payment of Liquidated Damages»

.

6.4.1 Payment of Document Liquidated Damages»

.  Purchaser may upon the fifth (5th) day of each month, invoice Seller for any Document Liquidated Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such Document Delivery Liquidated Damages, Seller shall pay such invoiced amount within thirty (30) days of receipt of Purchaser’s invoice.

6.4.2 Payment of Delivery Liquidated Damages»

.  Purchaser may upon the fifth (5th) day of each month, invoice Seller for any Delivery Liquidated Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such Delivery Liquidated Damages, Seller shall pay such invoiced amount within thirty (30) days of receipt of Purchaser’s invoice.

6.4.3 Payment of Takeover Liquidated Damages»

.  Purchaser may upon the fifth (5th) day of each month invoice Seller for any Takeover Liquidated Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such Takeover Liquidated Damages, Seller shall pay such invoiced amount within thirty (30) days of receipt of Purchaser’s invoice.

6.4.4 Payment of Performance Liquidated Damages»

.  Performance Liquidated Damages, if any, shall be calculated in accordance with Section 10.9 and set out in the Unit’s Performance Test Completion Certificate as prepared by Purchaser after completion of the Performance Test demonstrating that the Unit has not met the Guaranteed Levels.  Purchaser may invoice Seller for Performance Liquidated Damages upon completion of the Performance Test on the Units.  Purchaser may invoice for Performance Liquidated Damages regardless of whether or not Seller has achieved the Specific Performance Levels that correspond with the Guaranteed Levels.  In the event that the Performance Test which is the basis for the Performance Liquidated Damages occurred after Takeover, the effective date of delivery of the invoice shall be the date of delivery of the invoice to Seller.  Payment of the Performance Liquidated Damages shall be due within thirty (30) days of the effective date of delivery of the invoice.

6.5 Lien Release»

.  Seller agrees and represents that in submitting its final invoice under this Agreement, Seller waives and releases all liens, claims, security interests and other encumbrances arising in favor of Seller by reason of having provided labor, materials or equipment relating to performance of this Agreement.  Seller shall not be entitled to final payment of its final Retention Amount unless and until Seller submits to Purchaser:

(a) an affidavit in the form set forth in Exhibit S; and

(b) a release and waiver of liens, claims, security interests and encumbrances for payment for labor, material and services arising out of the Scope of Work for Seller.

6.6 Invoices»

.

6.6.1 Payee and Address for Invoices»

.  Invoices will be made out as payable by and mailed or hand carried to the address set forth in Exhibit E-1 following the Milestone Payment Schedule provided in Exhibit I-1.

Purchaser anticipates that the mailing address of the invoice may change, and agrees to notify Seller of such change prior to the change.

6.6.2 Date of Receipt»

.  Date of receipt of invoice by Purchaser will be evidenced by date stamp, or other generally accepted date receipting system.

6.7 Method of Payment»

.  Payment will be made by electronic wire transfer, unless otherwise requested by Seller, to a United States bank within the United States.  Seller’s invoices must provide all necessary information (including Tax I.D. and account number) to enable Purchaser to effect such payment.

6.8 Payments Not Acceptance of Work»

.  No payment made by Purchaser hereunder shall be considered or deemed to represent that Purchaser has inspected the work or Equipment or checked the quality or quantity thereof or that Purchaser knows or has ascertained how or for what purpose Seller has used sums previously paid, and shall not be deemed or construed as an approval or acceptance of any work or Equipment or Seller’s compliance with any other of its obligations under this Agreement or as a waiver of any claim or right Purchaser may have hereunder.

ARTICLE 7 
NOTICE TO PROCEED AND TERMINATION

7.1 Notice to Proceed»

.  [Note: Insert “Robust Scope” language once agreed to by parties.].

7.2 Termination»

.  This Agreement shall terminate upon the earlier of:

(a) the cancellation by Purchaser of all the Scope of Work under Section 5.4; or

(b) termination due to an event of default by Seller or Purchaser under Article 17; or

(c) when all obligations of the Parties under this Agreement are complete; or

(d) cancellation for an Event of Force Majeure under Section 18.8

after payments by both parties of amounts due by each party under this Agreement; provided, however, that the rights and obligations of the parties under Articles 7 (Default), 20 (Indemnification), 21 (Non-Disclosure of Information), 25 (Notices and Communication), 26 (Arbitration), 27 (Limitation of Liability) and Sections 5.2 (Taxes and Contributions) and 30.2 (Governing Law) shall survive termination of the Agreement; except that, if termination occurs under (a) or (b) above, obligations under Article 14 (Warranties) shall also survive.

ARTICLE 8 
RESERVED

ARTICLE 9 
INSPECTION AND CORRECTION OF WORK

9.1 Inspections»

.  Seller shall provide Purchaser and Lender, or their designated representatives, access to the Scope of Work at all reasonable times wherever in preparation or progress and shall work closely with Purchaser in performing this Agreement.  Purchaser, or its designated representatives, shall have the right  from time to time during this Agreement to observe, inspect, examine and review, Seller’s performance of this Agreement.  Purchaser’s or its designated representative’s (provided such representative is not employed, affiliated or in competitive activities with Seller) rights to inspect under this Section 9.1 shall include but not be limited to manufacturing schedules, compliance with Specification, workmanship, dimensional tolerances, production tests, production inspections, assembly of components, panel inspection and testing, or witnessing testing of Equipment at any stage of design, procurement, production, or manufacture at  Seller’s works or those of its Vendors to verify that the Equipment conforms to the specified requirements of this Agreement. However, any observance, inspection or review of performance of this Agreement shall not constitute or be deemed to be actual control or a right to control Seller, its employees, agents, personnel, Affiliates, or Vendors.  Purchaser’s or its designated representative’s inspection of any part of the Equipment shall in no way affect Seller’s obligation to perform the Scope of Work in accordance with the Specification and all other terms of this Agreement, and any audit, examination, inspection, review, or testing by Purchaser shall not constitute acceptance or prejudice, be a waiver, or be deemed to be a waiver of any of Purchaser’s rights hereunder or of its rights to reject defective performance of this Agreement or release Seller from any obligation under this Agreement.  Seller shall not be required to provide Purchaser or Purchaser’s representative access to area’s where Seller is performing proprietary work. [Note: Purchaser oversight to be addressed in Witness Test Points]

9.2 Resident Facilities»

.  If reasonably requested by Purchaser,  Seller will provide facilities as reasonably available for a resident quality representative in Seller’s works and those of its Vendors who are manufacturing Major Components.

9.3 Quality Plan»

.  Seller shall maintain a quality plan compliant with ISO 9001, 1994 and with the quality assurance plan set forth in Exhibit J, detailing:

(a) specific authorities and responsibilities;

(b) procedures, methods and work instructions; and

(c) inspection and test plans.

In the event of a conflict between Exhibit J, ISO 9001, 1994 and Seller’s quality system, the order of precedence shall be, ISO 9001, 1994, Seller’s quality system and Exhibit J.  [Note: To be revised pending revision of Exhibit J].

9.4 Notice»

.  Seller shall prepare and provide to Purchaser in accordance with Section 25.4.2 its proposed schedule of witness test points for Purchaser’s review and approval, which approval shall not be unreasonably withheld.  

9.5 Correction of Equipment»

.  Prior to commencement of the Warranty Period, Seller shall, at its sole cost and expense and with exception of defects included in the Punchlist, promptly correct any part of the Equipment which is defective or not in accordance with this Agreement, regardless of the stage of its completion or the time or place of discovery of such defects  and regardless of whether Purchaser has previously paid for or accepted such part of the Equipment through oversight or otherwise. Seller shall replace or correct such defective work or condition such that the Equipment is in accordance with this Agreement, including the Specification.    

9.6 Additional Factory Testing»

.  Purchaser may request Seller to repeat a test, perform the test using more precise instrumentation than planned, or conduct a test not in Seller’s standard factory test program.  In the event as a result of such Purchaser requested test requirement the Equipment is found to not be compliant with the requirements of this Agreement, Seller shall correct such noncompliance and the cost and time associated with such Purchaser test requirement shall be to Seller’s account.  If the Equipment is found to be compliant with this Agreement, Seller shall be eligible for a Change Order arising out of such Purchaser test requirement.

9.7 Release for Delivery»

.  In addition to other conditions set forth in this Agreement, pursuant to Section 25.4.3 Seller shall provide to Purchaser (a) notice of packing and (b) a request in writing to Purchaser’s Quality Assurance Manager for release to ship such Major Components.  Purchaser’s approval shall not be unreasonably withheld provided Seller has met the requirements of this Agreement.  In the event Purchaser fails to respond to Seller’s notice of intent to pack and ship the Major Component, Seller will proceed to perform packing and will complete staging at Seller’s facility pursuant to the notice.

ARTICLE 10 
DELIVERY AND PERFORMANCE

10.1 Delivery of Documentation»

.  In addition to the documentation specifically described within the Articles of this Agreement, Seller shall supply the documentation deliverables as set forth in Exhibit T by the due dates therein.  In the event Seller fails to deliver any item of documentation annotated in Exhibit T with an asterisk (*) by its respective due date (the “Due Date”) Liquidated Damages (“Document Liquidated Damages”) shall be assessed by Purchaser, and Seller agrees to pay Purchaser, at the rates per day per such document from the respective Due Date until the actual date of delivery of such item of documentation (the “Document Delivery Date”) as set forth in Exhibit B-6, Section B.6.1.

For the purpose of accessing Document Liquidated Damages, the Document Delivery Date shall be the date Seller delivers such document to Purchaser, provided that upon Purchaser’s review of such document Purchaser reasonably determines and assigns a “Status 1”, “Status 2” or “Status 4”.  In the event that Purchaser reasonably determines and assigns a “Status 3” to a document the Document Delivery Date shall not occur until the date of resubmission which results in Purchaser assigning a “Status 1”, “Status 2”, or “Status 4”.  As soon as Purchaser determines that a document will receive a “Status 3” it will notify Seller of such determination.  The criteria for Status 1,2,3, and 4 are set out in Exhibit T including the following:

(a) Upon delivery of each item of documentation Purchaser shall use its best efforts to  review the document and provide Seller the applicable status code and comments within ten (10) business days of receipt;

(b) Upon receipt of any comments from Purchaser, Seller shall use its best efforts to correct and resubmit such returned documentation within ten (10) business days; and

(c) If Purchaser does not provide comments within the ten (10) business day period after receipt, the document shall be deemed to be assigned a Status 1.

Purchaser’s review of any drawing or document hereunder shall not be construed as constituting approval of Seller’s work, nor shall Purchaser’s failure to review or failure to comment be construed as approval or disapproval.  Seller at all times shall retain responsibility for a Scope of Work that meets the requirements of this Agreement, regardless of whether or not Purchaser has reviewed Seller’s drawings or documents.  Changes to the documentation for the convenience of Purchaser, which can be accommodated by Seller shall be adopted pursuant to Article 11 of the Agreement.

10.1.2 Delivery of Final O & M Instructions»

.  Seller shall provide the final operations and maintenance instruction books within forty five (45) to eighty five (85) days after the delivery of the first Unit.  Purchaser may offset Liquidated Damages due to late delivery of the O & M instruction manuals in accordance with Section 6.3.2 upon the completion of delivery.

10.2 Delivery of Equipment»

.

10.2.1 Guaranteed Delivery Date»

.

10.2.1.1 Delivery to the Delivery Point»

.  Purchaser shall have the right to inspect the Equipment for completeness, condition and packing prior to loading on Seller’s transport.  Seller shall cause the Equipment to be Delivered in an undamaged condition in accordance with the Specification no later than the date set forth in Exhibit B-2 (the “Guaranteed Delivery Date”).

10.2.1.2 Delivery Restrictions»

.  Seller shall use appropriately licensed and insurable carriers who shall not be permitted to transport Equipment utilizing tandem tows.

10.2.2 Inventory Upon Delivery»

.  Seller shall be required to inspect the Equipment for completeness, condition and packing upon Delivery, and Seller shall immediately inform Purchaser of any damage discovered.

10.2.3 Delivery»

.  Delivery of a Unit shall be considered complete for the purposes of Delivery Liquidated Damages when the last Major Component of that Unit is Delivered (and other such items of Equipment as reasonably necessary so as to not impede the continuous progress of installation and erection of the Unit), in a complete and undamaged condition.  Purchaser shall have the right to inspect the Equipment for completeness and condition upon Delivery for the purposes of determining actual delivery.  Purchaser reserves the right to reject damaged Equipment at any location.  In the event a portion of the Equipment is damaged or defective upon Delivery, Purchaser after making an initial assessment of the damage and consulting with Seller as to how such damage or defect will affect the installation, operation, performance, reliability, efficiency, and warranty of the damaged Equipment may either (a) reasonably determine that such damage or defect is such that the preceding criteria is so adversely affected that Purchaser cannot accept delivery of the damaged Equipment and declare that delivery has not occurred, or (b) after taking into account such criteria and Seller’s proposed plan for correcting such damage or defect in accordance with Section 9.5, declare that delivery has occurred.  In the event Purchaser discovers such a damage or defect it shall notify Seller of such as soon as practical.

10.2.4 Extensions of the Guaranteed Delivery Dates»

.

10.2.4.1
A Guaranteed Delivery Date may only be extended if there has been a delay due to:

(a) a Change Order requested by Purchaser;

(b) a Charge Order requested by Seller, which is approved in writing by Purchaser in accordance with Section11.3;

(c) an Event of Force Majeure;

(d) a material breach of the Agreement or default (as defined in Section 17.5) thereunder by Purchaser; 

(e) a Change in Law requiring changes as provided in Section 3.6(c)(iv); or

(f) a delay by Purchaser in the performance of its obligations under this Agreement, which has an adverse impact on Seller’s ability to Deliver the Units by the Delivery date.

10.2.4.2
Seller’s entitlement to an extension of time shall be conditional upon:

(g) its having used reasonable endeavors to mitigate the delay;

(h) its having given notice in accordance with the terms of this Agreement; and

(i) the delay not being attributable to its default.

10.2.5 Offloading Responsibilities»

.  Purchaser shall be responsible for promptly offloading the Equipment from Seller’s mode of transportation (a) within forty eight (48) hours after arrival at the Delivery Point if by railcar, and (b) with sixty (60) hours after arrival at the Delivery Point if by loaded trailers.  Subject to thirty (30) days advance written notice from Seller to Purchaser of the Delivery of the Equipment, Purchaser shall reimburse Seller any demurrage charges caused by its failure of this obligation except to the extent that such failure is attributable to Seller’s acts or omissions.
10.3 Delay Liquidated Damages»

.

10.3.1 Delivery Liquidated Damages»

.  For each day that Seller Delivers a Unit (the “Delivery Date”) after its respective Guaranteed Delivery Date, Purchaser may assess and Seller shall pay to Purchaser delivery liquidated damages at the rates per day (the “Delivery Liquidated Damages”) for such lateness as set forth in Exhibit B-6, Section B.6.2.

For the avoidance of doubt, no Delivery Liquidated Damages shall be assessable as a result of Seller delivering an item of Equipment which is not a Major Component of the applicable Unit after its Guaranteed Delivery Date, unless such non-Major Component is shown by Purchaser to impede the continuous progress of installation or erection of the Unit.  The Delivery Liquidated Damages rate assessable on the late non-Major Component that impedes installation or erection after the Guaranteed Delivery Date shall be the rate assessable per Exhibit B-6, Section B.6.2, for each such day of impedance until the completion of delivery.  All Delivery Liquidated Damages shall begin to accrue at 12:01 a.m. on the day following the applicable Guaranteed Delivery Date.
Example: The Delivery Date of one non-Major Component to the Delivery Point is sixty (60) days after the  Guaranteed Delivery Date.  The Delivery Date of a second non-Major Component is seventy (70) days after the Guaranteed Delivery Date.  The Delivery Date of the last Major Component to the Delivery Point is thirty six (36) days after the Guaranteed Delivery Date.  The first late delivered non-Major Component did not impede installation until the thirtieth (30th) day after the Guaranteed Delivery Date.  The second late delivered non-Major Component did not impede erection until the fiftieth (50th) day after the Guaranteed Delivery Date.  Seller will be assessed Delivery Liquidated Damages as calculated below:

Major Component:


35 x $22,500.00 = $787,500.00

First non-Major Component:

29 x $0.00  =  $0.00






31 x $22,500 =  $697,500.00

Second non-Major Component:
49 x $0.00  =  $0.00






21 x $22,500.00 =$472,500.00

Total Delivery Liquidated Damages due = $1,957,500.00

10.3.2 Takeover Liquidated Damages»

.  Purchaser may assess and Seller agrees to pay liquidated damages (the “Takeover Liquidated Damages”) as set forth in Exhibit B-6, Section B.6.3, for each day that the Facility fails to achieve Takeover by the Time for Completion as a result of any or all of the following:

(a) a Unit is unable to be commissioned and/or operated reliably (such inability being within Seller’s sole responsibility as defined herein), but only after the expiration of the Commissioning Period; or

(b) a Unit demonstrating performance below the Specific Performance Levels,

Assessment of such Takeover Liquidated Damages is subject to the following:

(c) Purchaser elects at its sole discretion not to place a Unit in Commercial Operation;

(d) Purchaser allows [thirty (30) days] from first fired roll of the Units to complete Unit commissioning check outs, any needed replacement, adjustments or corrections to make the Units ready for testing (the “Commissioning Period”);

(e) [Purchaser makes reasonable efforts to provide the necessary time and operating loads for Seller and Purchaser to commission and check out the Units.  Seller’s time and load requirement shall not be to the exclusion of the needs of other Facility equipment being commissioned.  Purchaser shall coordinate the most advantageous utilization of time and assets whenever conflicting requirements exist and such situations shall not be deemed delay by Purchaser];

(f) Subject to (g) below, Purchaser may not assess Takeover Liquidated Damages prior to the expiry of the Commissioning Period;

(g) [In the event Seller fails to use its best efforts to minimize time to make corrections, adjustments or repairs to the deficiently performing Unit during the Commissioning Period, Purchaser shall have the right to void the Commissioning Period and assess Takeover Liquidated Damages without regard for the period afforded by the Commissioning Period];

(h) Purchaser provides prompt oral notice of delays affecting commissioning;

(i) Purchaser provides Seller its commissioning schedule no less than forty five (45) days prior to commencement of commissioning on the first Unit and provides periodic updates thereto;

(j) In the event Purchaser is not subject to similar delay liquidated damages with Owner, then Seller will not be subject to Takeover Liquidated Damages; and

(k) In the event that Purchaser is subject to similar delay liquidated damages with Owner, then Seller shall pay Takeover Liquidated Damages in accordance with this Section 10.3.2.

10.3.2.1
Seller shall use reasonable efforts to obtain, or assist Purchaser (if Purchaser so elects) in obtaining, a permit variance or modification which will enable the Facility to operate in the event a Unit does not meet the Sound Level Guarantees or Emissions Guarantee.

In the event that a Unit fails to meet the Emissions Guarantee or a Sound Level Guarantee, in parallel with Seller’s efforts to remedy Guaranteed Levels, Purchaser and Seller agree to pursue alternate remedies including, at the Seller’s expense, improving or modifying other Facility components in order to mitigate the effects of the Unit on the Facility’s performance.  Such alternate remedies must be mutually agreed to by Seller and Purchaser.

10.3.3 Invoicing for Delivery and Takeover Liquidated Damages»

.  Except to the extent of an offset in accordance with Section 6.3, invoicing for and payment of Document, Delivery and Takeover Liquidated Damages shall be in accordance with Section 6.4.

10.4 [Specific Performance Exhaust Gas Temperature and Energy Guarantee].»

  Seller shall provide the Specific Performance Gas Temperature and Energy Guarantees as set forth in Exhibit B-3, Section B.3.1.

10.4.1 [Interaction of  Exhaust Gas Energy and Exhaust Gas Temperature with Turbine Net Output]»

.  Exhaust heat measurement will be performed per the guidelines of ASME PTC 4.4.  The Exhaust Gas Energy Guarantee will be corrected to account for Adjusted Electrical Output in excess of the Electrical Output Guarantee].  

10.5 Sound Level Guarantees»

.  Seller shall provide the Sound Level Guarantees as set forth in Exhibit B-3, Section B.3.2.

10.5.1 Sound Level Test»

.  Purchaser shall conduct tests at the Site to measure the Sound Levels generated by the Equipment in accordance with the procedures set out in Exhibit F-1 (the “Sound Level Test”).

(a) The Test Procedures pertaining to Sound Level Guarantees shall take into account corrections for environmental conditions and sound produced by other Facility equipment in determining the sound levels produced by the Units.

(b) Purchaser will, (i) provide all instrumentation (including special test instrumentation), operations, labor, consumables and fuel required for the Sound Level Test, (ii) provide sufficient load during the Sound Level Test, (iii) read and record the Sound Level Test data, and (iv) calculate the Sound Level Test results, all at no cost to Seller.

(c) Seller (i) have the right of representation at the Sound Level Test, (ii) have the right to take its own data, (iii) will have access to all data resulting from the Sound Level Test, and (iv) verify the calculated Sound Level Test results.

10.6 Specific Performance Emissions Guarantee»

. Seller shall provide the Emissions Guarantee as set forth in Exhibit B-3, Section B.3.3.1.

10.7 Electrical Output Guarantees»

.  Seller shall provide the Electrical Output Guarantees as set forth in Exhibit B-3, Section B-3.4.
10.8 Heat Rate Guarantees»

.  Seller shall provide the Heat Rate Guarantees as set forth in Exhibit B-3, Section B-3.5.
10.9 Performance Liquidated Damages»

.

10.9.1 Output Liquidated Damages»

.  Provided Seller’s Equipment has demonstrated that it meets  the Specific Performance Electrical Output Guarantee, liquidated damages shall be assessed by Purchaser, and Seller agrees to pay, at a rate set forth in Exhibit B-6, Section B.6.4 for each kW that the Adjusted Electrical Output of a Unit (as measured during the most recent Performance Test) is less than the Electrical Output Guarantee (the “Output Liquidated Damages”).

10.9.2 Heat Rate Liquidated Damages»

.  Provided Seller’s Equipment has demonstrated that it meets the Specific Performance Heat Rate Guarantee, liquidated damages shall be assessed by Purchaser, and Seller agrees to pay, at a rate set forth in Exhibit B-6, Section B.6.5 for each Btu/kWh (LHV) that the Adjusted Heat Rate for a Unit (as measured during the most recent Performance Test) exceeds the Heat Rate Guarantee (the “Heat Rate Liquidated Damages”).

10.9.3 [Exhaust Gas Temperature and Energy Liquidated Damages»

.

10.9.3.1 Exhaust Gas Temperature Liquidated Damages»

.  Provided Seller’s Equipment has demonstrated that it meets the Specific Performance Exhaust Gas Temperature Guarantee, liquidated damages shall be assessed by Purchaser, and Seller agrees to pay, at the rate set forth in Exhibit B-6, Section B.6.6 for each 0F that the Adjusted Exhaust Gas Temperature of a Unit (as measured during the most recent Performance Test) is less than the Exhaust Gas Temperature Guarantee (the “Exhaust Gas Temperature Liquidated Damages”).

10.9.3.2 Exhaust Gas Energy Liquidated Damages»

.  Provided Seller’s Equipment has demonstrated that it meets the Specific Performance Exhaust Gas Energy Guarantee, liquidated damages shall be assessed by Purchaser, and Seller agrees to pay, at the rate set forth in Exhibit B-6, Section B.6.7 for each MMBTU/hr that the Adjusted Gas Energy of a Unit (as measured during the most recent Performance Test) is less than the Exhaust Energy Guarantee (the “Exhaust Gas Energy Liquidated Damages”).]  
10.9.4 Performance Test Required»

.  No Performance Liquidated Damages shall be payable if no Performance Test has been conducted.

10.9.5 Setting Out of Performance Liquidated Damages»

.  Performance Liquidated Damages, if any, shall be due and payable by Seller pursuant to Section 6.4 in accordance with the rates set forth in this Section 10.9 and the calculations set forth in the Performance Test Completion Certificate prepared by Purchaser.  Performance Liquidated Damages shall be paid upon completion of the Performance Test.

10.9.6 Most Recent Performance Test»

.  Performance Liquidated Damages shall be assessed by Purchaser, and Seller agrees to pay on the results of the most recent Performance Test, including any reperformance of the Performance Tests in accordance with Section 10.12.8, regardless of whether the performance improves or worsens upon the later Performance Test.

10.9.7 Seller’s Improvement of Performance»

.  In the event a Unit fails to meet a Guaranteed Level but does meet the Specific Performance Levels, Seller shall use its best reasonable efforts, for a period of one hundred and eighty (180) days after the Unit is placed into Commercial Operation, to cause the Unit to meet the Guaranteed Levels.  Prior to Commercial Operation of the Facility, Purchaser shall provide Seller a reasonable opportunity to implement such changes or improvements; however, it is understood by both parties that Purchaser will not be required to delay commencement of Commercial Operation of the Facility for the purpose of Seller making such changes or improvements.  After Purchaser places the Unit into Commercial Operations, Purchaser shall provide Seller reasonable opportunity to make such corrections or improvements during scheduled and unscheduled outages.

10.9.8 Reduction in Performance Liquidated Damages»

.  In the event Seller improves the Unit’s guaranteed performance for which Performance Liquidated Damages are payable after Purchaser has:

(a) made an offset in accordance with Section 6.3 against payments due Seller to cover Performance Liquidated Damages; and/or

(b) been paid Performance Liquidated Damages by Seller,

Purchaser shall be entitled to a reduction/refund of the Performance Liquidated Damages subject to the following:

(i) If:

(A) the Shortfall has not prevented Purchaser from placing the Unit into Commercial Operations;

(B) such corrections are made and are complete prior to Commercial Operation of the Unit; and

(C) such corrections cause a reduction in the performance Shortfall,




then Purchaser shall:

(D) refund to Seller an amount equal to the Performance Liquidated Damages associated with such reduction in the Shortfall; and/or

(E) reduce the offset associated with such reduced Shortfall;

however, such reduction in offset or amount of refund shall not exceed the amount actually offset in accordance with Section 6.3 or paid in accordance with Section 6.4 for such Shortfall, or

(ii) If:

(A) such Shortfall has prevented Purchaser from placing the Unit or Facility into Commercial Operation; or

(B) the corrections to reduce a Shortfall are completed after the Unit or Facility goes into Commercial Operations, and such corrections are completed within one hundred eighty (180) days after the Facility went into Commercial Operations, and such corrections cause a reduction in the Shortfall;

then Purchaser shall:

(C) refund to Seller an amount equal to the Performance Liquidated Damages associated with such reduction in the Shortfall; and/or

(D) reduce the offset associated with such reduced Shortfall. [Note: J. Rigby to provide revised language].
10.10 Maximum Liabilities for Liquidated Damages»

.  Seller’s maximum liability for Liquidated Damages is set forth in Exhibit U.

10.11 Liquidated Damages Not Penalty»

.  The parties acknowledge and agree that because of the unique nature of the Equipment and the time requirements for performance:

(a) Purchaser shall be damaged by:

(i) Seller failing to accomplish delivery of documents in accordance with Section 10.1;

(ii) Seller failing to deliver the Units by the Guaranteed Delivery Date;

(iii) The Unit’s performance causing Purchaser a delay in Takeover of the Unit; and/or

(iv) Seller failing to cause the Units to achieve Guaranteed Levels, (the “Liquidated Damages Events”);

(b) it would be impracticable or extremely difficult to fix the actual damages resulting from late delivery or failure to meet the Guaranteed Levels;

(c) any sums which would be payable under this Article 10 are in the nature of liquidated damages, and not a penalty, and are fair and reasonable; and

(d) [such payment represents a reasonable estimate of fair compensation for the losses that may reasonably be anticipated from such Liquidated Damages Events.  Such payments are compensation solely for Liquidated Damages Events and shall not prejudice any other rights of Purchaser hereunder and shall not relieve Seller of its obligations hereunder].

10.12 Performance Tests and Sound Level Tests»

.

10.12.1 Concurrence of Tests»

.  To the extent practical, Purchaser shall conduct the Performance Tests for a Unit concurrently so as to assure itself that the Unit is capable of meeting all of the Guaranteed Levels and Specific Performance Levels concurrently. 

10.12.2 Election to Conduct a Performance Test»

.  At Purchaser’s sole discretion, Purchaser may elect to waive the conduct of the Performance Test.  Regardless whether Purchaser waives the Performance Test, Purchaser may at its sole discretion choose to conduct the Performance Test for the purpose of evaluating Seller’s attainment of the Guaranteed Levels or Specific Performance Levels prior to the expiry of the Installation Period.

10.12.3 Specific Performance Achievement»

.  In the event that as a result of the Performance Test it is reasonably evident that the Equipment is performing significantly out of compliance with a Specific Performance Level, Purchaser may require Seller to take corrective actions in accordance with Section 10.13 without the benefit of Performance Test or Sound Level Test results; otherwise, Performance Test or Sound Level Test results will be required to be the basis of such action.

10.12.4 Timing of Tests»

.

10.12.4.1
Purchaser may conduct or cause a Performance Test or Sound Level Test to be conducted on the Units after Seller’s representative certifies that the Units to the best of his knowledge:

(a) are properly installed;

(b) can be safely tested; and

(c) have been and may be run up to full load.

10.12.4.2
In the event that a Performance Test or Sound Level Test has been conducted on the Units within the Installation Period and corrective measures or modifications have been performed, if Purchaser elects to conduct a retest in accordance with Section 10.12.8, it shall conduct such retest within thirty (30) days of the completion of such corrective measures or modifications.

Unit performance shall not be adjusted for degradation unless such Unit has been operated for more than two hundred (200) operating hours at the time of conduct of the initial Performance Test.  Operating hours necessary to diagnose the Unit’s failure to operate in accordance with the requirements of this Agreement shall not be added to the hour count.  Operating hours associated with the conduct of Performance Tests, shall be added to the hour count.  Methods of correcting for degradation shall be set out in the Performance Test Procedures.

10.12.5 Seller Presence at Tests»

.  Seller shall have the right to be present or to have a representative present at each Performance Test and Sound Level Test.  Purchaser shall provide Seller with advance notice of the Performance Tests in accordance with Section 25.5.3.

10.12.6 Test Results»

.  Upon the completion of each Performance Test or Sound Level Test, Purchaser will issue a Performance Test Certificate setting forth the results achieved during such test.

10.12.7 Performance Test Procedures»

.  Guidelines for the conduct of the Performance Tests are set forth in Exhibit F hereto.  

10.12.8 Reconduct of Tests»

.  In the event that Seller has made repairs or has taken other corrective action to correct a Shortfall subsequent to the conduct of the Performance Test or Sound Level Test, Purchaser at its sole reasonable discretion may require the conduct of another Performance Test(s) or Sound Level Test to:

(a) demonstrate that such repairs or corrective actions have caused the Equipment to now meet the previously failed Specific Performance Level or Guaranteed Level which such repairs or corrective actions were intended to correct; and/or

(b) demonstrate that such repairs or corrective actions have not caused the performance of the Equipment as it pertains to the Specific Performance Levels to degrade so that the Equipment no longer meets the Specific Performance Levels; and/or

(c) demonstrate that such repairs or corrective actions have not caused the performance of the Equipment as it pertains to the Guaranteed Levels to degrade since the last Performance Test or Sound Level Test.

10.12.9 Fittings, Instrumentation and Test Uncertainty»

.

(a) Seller shall be responsible for ensuring that the Units are designed and manufactured with the proper fittings, orifices, and connections necessary to permit the conduct of the Performance Tests in accordance with the Test Procedures.  Seller shall also be responsible for identifying to Purchaser the necessary fittings, orifices, and connections that should be installed in the remainder of the Facility to allow a proper Performance Test to be conducted.

(b) The parties anticipate using station instrumentation for performance testing.  The Performance Test shall be conducted using a combination of special test instruments and appropriate station instruments meeting the intent of the applicable test codes, but all instruments used to calculate the test results shall meet the calibration and accuracy requirements of the test code.  Calibration of all of these instruments shall be traceable to NIST, or equivalent international standards, with calibration documentation supplied according to NIST standards and procedures.  In the event that Purchaser elects to conduct the first Performance Test on a Unit, the cost of the necessary instrumentation that is not Facility instrumentation shall be borne by Purchaser, and in the case of subsequent Performance Tests caused by Seller’s Equipment not meeting a Guaranteed Level or Specific Performance Level the cost of instrumentation shall be to Seller’s account.

(c) Test uncertainties shall be accounted for in Exhibit F.

10.12.10 Consumable Spare Parts During Retests»

.  The cost of consumable spare parts during retests caused by Seller’s failure to achieve Guaranteed Levels or Specific Performance Levels shall be to Seller’s account.

10.13 Remedies For Failure to Meet Specific Performance Requirements»

.

10.13.1 Corrective Actions»

.  If a Unit fails to satisfy one or more of the Specific Performance Levels or a Guaranteed Level, Purchaser will, if Seller so requests and if Takeover has not occurred, operate the Facility or cause the Facility to be operated at the loads and conditions necessary to allow Seller to determine the causes of the nonconformity, if any, and the expedient remedial action.

Following the Performance Test as applicable, or additional running of the Facility for such diagnostic purposes, Seller shall at its own expense:

(a) repair at the Site such parts of the Unit; or

(b) remove the defective parts and provide and install the new parts, to cause the Unit to meet Specific Performance Levels.

If the Unit still fails to satisfy Specific Performance Levels, Seller shall at its own expense make such further repair or replacement until the Unit meets Specific Performance Levels.  In no event shall Purchaser be required to operate Equipment in violation of Applicable Laws.

10.13.2 Failure to Achieve Specific Performance»

.  In the event of any failure to achieve the Specific Performance Levels within one hundred eighty (180) days of the completion of the applicable Unit’s Performance Test, Purchaser shall have the right to terminate the Agreement in accordance with Sections 7.2, 17.2, 17.3 and 17.4.

10.14 Acceptance»

. 

10.14.1.1 Completion of Punchlist Items.  Seller agrees to complete the Punchlist to the satisfaction of Purchaser.  In the event Seller does not complete such Punchlist either (a) to the standards of the Agreement, or (b) within a reasonable period of time, but not later than the end of the Warranty Period, Purchaser may, after prior written notice to Seller, draw down against the Retention Letter of Credit the estimated value of the uncompleted work in order to have such work completed by others.

10.14.1.2 Acceptance of a Unit»

. Acceptance of each Unit shall occur upon:

(a) the earliest of:

(i) if, through no fault of Seller, a Performance Test or Sound Level Test on the Unit has not been conducted, by the end of the Installation Period (except as provided in Section 10.12.4.2); or

(ii) upon the issuance of a Performance Test Completion Certificate by Purchaser evidencing that the Specific Performance Levels and the Guaranteed Levels have been achieved (such Performance Test Completion Certificate to be issued within thirty (30) days after successful completion of testing); or

(iii) in the event that the Unit has passed the Specific Performance Levels, but not the Guaranteed Levels and (A) Seller has for a period of one hundred eighty (180) days after provisional acceptance of the Unit made reasonable best efforts to improve the Unit’s performance and still have met the Specific Performance Levels, but not the Guaranteed Levels, and, (B) Seller has paid Liquidated Damages in accordance with Section 6.4 hereof with respect to any Guaranteed Levels not achieved;

(b) all special tools provided hereunder shall have been delivered to Purchaser; and

(c) Seller has delivered to Purchaser a waiver of liens in form as shown in Exhibit-S that have been or could have been placed upon the Equipment and that there are no outstanding claims of Seller or any Vendor with respect to the Equipment;

(d) Seller has paid any Takeover Liquidated Damages due [Note: Small Group to discuss]; and

(e) Seller has paid any Delivery Liquidated Damages due.

Upon the occurrence of these events, Seller may submit a certificate to Purchaser indicating it has achieved Acceptance.  Purchaser shall within ten (10) days of receipt of such certificate, either sign such certificate acknowledging concurrence or reject such certificate specifically stating the reasons for such rejection.

10.15 Readiness for Testing»

.  Upon Seller’s certification that the Units are substantially complete, installed in accordance with Seller’s installation instructions and that the Units are safe to operate, the Units, at Purchaser’s sole option, shall be tested by Purchaser in accordance with the Test Procedures.  Seller’s TD of I manager and Purchaser’s Site manager shall conduct a pre-commissioning meeting at the Site, as soon as practical prior to start of commissioning.  The parties shall agree upon the pre-commissioning test criteria to demonstrate the Units’ readiness for Performance Tests and Facility tests.

10.16 Unit Serial Numbers»

.  Seller has identified the Unit serial numbers which are listed in Exhibit P.  Seller may not change such serial numbers without Purchaser’s prior written agreement. Purchaser shall only withhold such written agreement if, based upon the reasons given by Seller and verified by Purchaser, Purchaser reasonably believes that such change would result in a delay of the Units.

ARTICLE 11 
CHANGE ORDER

11.1 Adjustment of Purchase Amount»

.  The Purchase Amount shall be subject to adjustment solely for (a) Purchaser-requested changes in the Scope of Work, and (b) Seller requested changes in the Scope of Work which are approved by Purchaser.

11.2 Purchaser Requested Change Order»

.  If Purchaser desires to make any change in the Scope of Work (a “Change Order”), Purchaser shall advise Seller, and Purchaser and Seller shall consult concerning the estimated cost and impact on the Guaranteed Delivery Date(s) set forth in Exhibit B-2 and the Purchase Amount. Thereafter, Purchaser may request and Seller shall, upon receipt of such reasonable request, prepare a detailed estimate of the cost of such change, taking into account the effect of such change on the Scope of Work and other agreed upon and contemplated Change Orders.  Purchaser shall review Seller’s estimate, and if Purchaser accepts or the parties otherwise agree as to the Change Order, it shall be endorsed by Purchaser.  Thereafter, the parties shall promptly adjust the Guaranteed Delivery Date(s) set forth in Exhibit B-2 and the Purchase Amount and any other Exhibits requiring adjustment to reflect the Change Order.  In the event Seller proceeds with any proposed changes in the Scope of Work prior to execution of a Change Order, Seller shall do so at its own risk.  Purchaser has no obligation to pay Seller for any additional cost and Seller is not entitled to any extension of time for performance as a result of any change implemented by Seller without an executed Change Order.  Modifications or changes in the Specification which are within the general scope of the Agreement documents may be made at any time by Purchaser’s Representative written order to Seller.

11.3 Seller Requested Change Order»

.  If Seller determines that a condition or the occurrence of an event requires a change in the Scope of Work, Seller shall within fifteen (15) days of being aware of the occurrence or condition of the event prepare and deliver to Purchaser a request for a Change Order which shall describe such condition or event in detail.  Within fifteen (15) days following delivery of such request, or such other period as may be agreed upon by the parties, Seller shall submit the proposed adjustment to the Scope of Work, the Guaranteed Delivery Date(s) as set forth in Exhibit B-2 and/or the Purchase Amount requested by it.  Following receipt of such request, Purchaser shall determine, in its sole and exclusive discretion, whether any changes to the Scope of Work, the Guaranteed Delivery Date(s) set forth in Exhibit B-2 and/or the Purchase Amount shall be effected, but failure by Purchaser to approve any such changes  shall not affect or modify any of Seller’s obligations hereunder or cause an increase in the Purchase Amount and/or extension of the Guaranteed Delivery Date(s).  If Seller proposes changes in the Scope of Work to Purchaser, Seller shall not make such changes without receiving the prior written consent of Purchaser which shall be reflected on a Change Order, in accordance with the procedures as described in Section 11.2.

11.4 Disputes»

.  In the event of an unresolved dispute regarding a Change Order, the parties agree that the matter shall be submitted to dispute resolution in accordance with Article 26.

11.5 Change Order Pricing»

.  All changes to this Agreement shall be either lump sum, or unit price.

ARTICLE 12 
INTENTIONALLY OMITTED


ARTICLE 13 
ORDER OF PRECEDENCE

13.1 Order of Precedence»

.  This Agreement shall be read as a whole and in the event of a conflict between documents, the following order of precedence shall govern:

a:
Articles 1 through 30

b:
Exhibits, other than Exhibits B and B-1

c:
Exhibits B and B-1

d:
Seller’s and its Vendor’s operation and maintenance manuals made part of this Agreement by reference.

ARTICLE 14 
WARRANTY

14.1 Equipment Warranty»

.  All equipment, material and components, whether or not specifically referenced in the Specification or elsewhere in the Agreement, which are incorporated by Seller or its Vendors into the Scope of Work, shall be new, unrepaired and suitable for the purpose for which it is intended except as otherwise allowed pursuant to this Agreement.

14.2 Warranty Period»

.  The warranties set forth in Section 14.3 in respect of:

(a) any Scope of Work that is part of or relating to a Unit (except warranties as to title) shall apply to defects which appear during a period of one (1) year commencing upon the earlier of (i) Acceptance of the Unit, (ii) first Commercial Operation of the Unit; provided, however, such period shall not commence later than the end of the Installation Period; and 

(b) any Scope of Work that is not part of or relating to a Unit (except warranties as to title) shall apply to defects which appear during a period of one (1) year commencing upon Acceptance of the last Unit (the warranty periods in Section 14.2(a) and (b) hereinafter referred to as the “Warranty Period”).

14.3 Warranties During Warranty Period»

.  Seller warrants to Purchaser that during the Warranty Period: (a) the Equipment to be delivered hereunder shall be new and unrepaired (except as permitted by Purchaser); suitable for the purpose for which it is intended; designed, of suitable grade, and fit for the purpose of generating electric power when operated in accordance with Seller’s written operating instructions and, in the absence thereof, in accordance with generally accepted operating practices of the electric power producing industry; conforms to the Specification, Applicable Laws and other requirements of this Agreement; and shall be free from defects in material, workmanship and title; and (b) the balance of the Scope of Work shall be performed in a competent, diligent manner and shall conform with the Specification, Applicable Laws and other requirements of this Agreement.

14.4 Remedies»

.  If the Equipment delivered or Scope of Work performed hereunder do not meet the above warranties during the Warranty Period, Seller shall immediately or on an expedited basis such that it meets the requirements of this Agreement, and at no cost to Purchaser,  correct any defect by (a) reperforming the defective Scope of Work, (b) repairing the defective part of the Equipment or (c) making the necessary replacement of the defective part of the Equipment.  Seller shall provide a service engineer at the Site and all other technical advisory services reasonably necessary for any such repair of the Equipment as soon as reasonably possible after receipt of notice by Purchaser of said defect (but in any case not later than five (5) days after receipt of notice).  Seller shall at its sole expense disassemble, remove, replace and reinstall the Equipment to the extent necessary while minimizing the downtime required for Seller to perform its warranty obligations.  Seller shall not be responsible for removal or replacement of structures or other parts of the Facility which have not been furnished by Seller or its Vendors.  Any change to the Equipment that would alter conformance with the Specification may be made only with prior written approval of Purchaser.  If after notice of such defect Seller unreasonably delays the commencement and/or completion of rectifying the defect, Purchaser may then, following written notice to Seller, correct such defect and Seller shall be responsible and pay Purchaser for all reasonable costs and expenses incurred by Purchaser upon receipt of Purchaser’s certified invoice.  In an emergency where delay would cause serious risk of loss or damage, and notice to and corrective action of a warranty defect by Seller is not possible in a timely manner, Purchaser may, for the account of Seller, take such actions as necessary to mitigate such risk and correct the defect upon oral notice to Seller followed immediately with written confirmation of such notice. The condition of any tests shall be mutually agreed upon and Seller shall be notified of and may be represented at, all tests that may be made.  

14.5 Additional or Extended Warranty Periods.  

14.5.1 Warranty of Repaired or Replacement Parts»

.  The Warranty Period applicable to any reperformed work or repaired or replacement part furnished pursuant to Section 14.3 shall commence upon completion of such reperformed work or the installation of such repaired or replacement part and shall end twelve (12) months next following such reperformance, repair or replacement.

14.5.2 Extension of Warranty Due to Unavailability»

.  The Warranty Period with respect to any Equipment or Scope of Work shall be extended by a period equal to the period during which the Equipment or Scope of Work (or that part in which the defect has appeared) cannot be used in Commercial Operation pursuant to the terms of this Agreement by reason of that defect.

14.5.3 Limitations»

.  In any event all Warranty Periods with respect to (a) any Scope of Work that is part of or related to a Unit and Seller’s responsibilities set forth herein for repaired or replacement parts contained therein shall end upon thirty-six (36) months next following (i) Acceptance of the Unit or (ii) first Commercial Operation of the Unit and (b) any Scope of Work that is not part of or related to a Unit and Seller’s responsibilities set forth herein for repaired or replacement parts contained therein shall end upon thirty-six (36) months next following Acceptance of the last Unit.

14.6 Exclusions and Limitations.  

14.6.1 Exclusions»

.  Seller does not warrant the Equipment or any repaired or replacement parts against:

(a) normal wear and tear; 

(b) normal degradation in the performance of the Equipment; 

(c) Purchaser’s misuse or negligence; or

(d) Failure by the Purchaser to (i) promptly notify the Seller that a defect has become apparent (such notice not to be later than thirty (30) days from the date supervisory level personnel of Purchaser or Owner responsible for the Facility become aware of such defect); (ii) immediately take reasonable action to mitigate the damage consequent to the occurrence of the defect once it becomes apparent to the supervisory personnel of Purchaser or Owner responsible for the Facility, and (iii) provide access to the Seller to remedy such defect (provided such access does not unreasonably interfere with the operation of the Facility).

14.6.2 Conditions»

. The warranties and remedies set forth herein are further conditioned upon:

(a) the proper storage, installation, operation, maintenance of the Equipment pursuant to the operation and maintenance manuals (including revisions thereto) and other written instructions provided by Seller and/or its Vendors, as applicable, except as otherwise specifically set forth in this Agreement; and

(b) the repair or modification of the Equipment being performed pursuant to the operation and maintenance manuals (including revisions thereto) and other written instructions or approval provided or given by Seller and/or its Vendors, as applicable, except as otherwise specifically set forth in this Agreement; and provided that Seller has not defaulted on any obligation under this Agreement to make such repairs or modification.

14.6.3 Warranties Exclusive»

. The foregoing warranties are exclusive and are in lieu of all other warranties whether written, oral, implied or statutory.  NO IMPLIED STATUTORY WARRANTY OF MERCHANTABILITY OR FITNESS FOR A PARTICULAR PURPOSE SHALL APPLY.

14.6.4 Remedies Exclusive»

. The preceding Sections of this Article set forth the exclusive remedies for all claims based on a breach of any of the foregoing warranties whether a claim, however instituted, is based on contract, indemnity, warranty, tort (including negligence), strict liability or otherwise.

ARTICLE 15 
RISK OF LOSS AND TITLE

15.1 Risk of Loss»

.  Seller shall bear the risk of loss and damage with respect to an item of Equipment until Delivery of such of Equipment, in accordance with Section 10.2 hereof.  Risk of loss for a particular item of Equipment shall transfer from Seller to Purchaser upon Purchaser commencing first lift of such item of Equipment from Seller’s mode of transport after Delivery.

15.2 Title»

.

15.2.1 Passage of Title»

.  Title to Equipment, spare parts, drawings, specifications, operation and maintenance manuals and like materials prepared specifically for the Scope of Work under this Agreement will pass from Seller to Purchaser when the Equipment manufactured in the United States is ready for shipment.  In the case where Major Components are not manufactured in the United States, title to such Major Components will pass to Purchaser at the foreign port of export immediately after clearance of the foreign customs.  Seller shall be the importer of record for all such non-United States manufactured Major Components, and will be responsible for all Import Duties and costs associated with clearing United States customs.  Seller warrants that legal title to and ownership of the Equipment shall be free and clear of any and all liens, claims, security interests or other encumbrances when title thereto passes to Purchaser.  Title to Seller’s standard drawings and documents which are provided to Purchaser shall remain with Seller, provided however Seller grants permission without charge to Purchaser, Lender, Purchaser’s Facility operator and subsequent owners and operators to use such documents as set out in Section 15.3.

15.2.2 Infringement Cures and Defense»

.  In the event a suit or proceeding is brought against Purchaser, Lender, Purchaser’s Facility operator or their affiliates, (the “Patent Indemnitees”) for infringement of any patent, copyright, trademark, trade secret or other intellectual property right, Seller shall indemnify and hold harmless Patent Indemnitees, their authorized agent, and anyone directly or indirectly employed by either of them from and against all claims, damages, losses and expenses (including attorneys’ fees) arising out of any infringement of patent rights or copyrights incident to the use or production of the Equipment or incorporation therein of any invention, design process, product or device not specified in the Agreement, and shall defend all such claims in connection with any alleged infringement of such rights.  Seller shall pay all costs and expenses of any such action or suit or threat thereof, including compensation and expenses of experts and counsel of its choice and selection and Seller shall also pay and hold Patent Indemnities free and harmless from expenses incurred or any damages or other sums awarded or assessed in any such action or suit including costs resulting from imposition of any injunction against Patent Indemnitees.  Patent Indemnitees may be represented by counsel of their own selection and expense, but agree to cooperate fully in the defense of any such action or suit and to furnish all the evidence in their control.

Nothing herein shall authorize Seller to settle any such suit or action as referred to in this Section 15.2.2 without prior authorization from the affected Patent Indemnitee if, by such settlement, the affected Patent Indemnitee shall be obliged to make any monetary payment, part with any property or any interest therein, to assume any obligation or restriction upon operation of the Equipment or Facility or production of electricity, to be subject to any injunction or to grant licenses or other rights under its patent or other industrial or intellectual property rights, or surrender or release any other rights, remedies, interests or claims.

In the event a Patent Indemnitee is, as a result of such suit or proceeding, prevented from using such alleged infringing Equipment or other deliverables, Seller shall undertake and conclude as quickly as reasonably possible at its option and expense one of the following courses of action:

(a) obtain the right to continued use of the Equipment or other deliverables under this agreement;

(b) correct or modify the infringing aspect of the Equipment or other deliverables under this Agreement so that it becomes non-infringing; or

(c) replace the infringing Equipment or other deliverables under this Agreement with equivalent non-infringing Equipment or other deliverables.

THIS SECTION IS AN EXCLUSIVE STATEMENT OF ALL THE DUTIES OF THE PARTIES RELATING TO PATENTS AND DIRECT OR CONTRIBUTORY PATENT INFRINGEMENT AND OF ALL THE REMEDIES OF PURCHASER RELATING TO ANY CLAIM, SUIT, OR PROCEEDING INVOLVING PATENTS.  Compliance with this Section as provided herein shall constitute fulfillment of all liabilities of the parties under the Agreement with respect to patents, copyright, trademark, trade secret or other intellectual property rights.

15.3 Licensing Procedure»

.  Seller grants Purchaser a non-exclusive license to use the Equipment (including all calculations, as-built drawings, arrangements drawings, detailed engineering drawings and other drawings and documentation) supplied under this Agreement for operating, maintaining and repairing the Facility.  Purchaser shall have no right to the source code; provided, however, in the event Seller or Seller’s vendor discontinue maintenance of such Equipment, Seller shall, on a best efforts basis, attempt to obtain such source code for Purchaser.  The non-exclusive license granted herein to Purchaser may be transferred by Purchaser to Purchaser’s Facility operator, Lender(s), or successor owners of the Facility (for the sole purpose of operating the Facility). Nothing herein shall constitute a grant of a license to the Purchaser, Purchaser’s Facility operator or a subsequent owner of the right to make or have made spare or renewal parts using the drawings and data described in this Section 15.3.

Seller and/or its licensors shall at all times remain owners of the software/firmware licensed.

ARTICLE 16 
TRAINING AND TECHNICAL DIRECTION OF INSTALLATION

Seller shall provide technical direction of installation of the Equipment in accordance with Exhibit H-1.  Seller shall provide on Site operation and maintenance training for Purchaser’s operations and maintenance personnel in accordance with Exhibit H-2.  Purchaser shall be responsible for the travel and per diem costs of its personnel and for providing or procuring all training facilities on or in the immediate vicinity of the Site.

ARTICLE 17 
DEFAULT

17.1 Events of Default by Seller»

.  Seller shall be in default hereunder upon the occurrence of any one of the following events, which shall be events of default (each an “Event of Seller Default”) if not cured within thirty (30) days following delivery to Seller of a notice of such event from Purchaser, or, if not curable in such thirty (30) Day period, if Seller has not commenced the cure within such period and does not thereafter diligently pursue such cure; provided that in no event shall such extended cure period exceed one hundred eighty (180) days unless otherwise mutually agreed; provided further that the event described in paragraph (d) below shall be an Event of Seller Default upon its occurrence:

(a) Seller shall have assigned or transferred this Agreement or any right or interest herein except as expressly permitted by this Agreement; or

(b) representations made by Seller in this Agreement are found to be materially false or misleading, or;

(c) Seller shall have defaulted in its performance under any material provision of this Agreement.  The parties agree that Purchaser may not terminate for default based upon a Unit’s failure to meet Guaranteed Levels if Seller has caused the Unit to meet Specific Performance Levels.  Purchaser may terminate this Agreement for default in the event:

(i) Seller’s liability for Delivery Liquidated Damages exceeds the amount specified in Exhibit U; or

(ii) Seller’s liability for Takeover Liquidated Damages exceeds the amount specified in Exhibit U; or

(iii) Seller fails to cause a Unit to achieve a Specific Performance Level within one hundred eighty (180) days after Purchaser conducts a Performance Test or Sound Level Test; or

(d) any proceeding is instituted against Seller seeking to adjudicate Seller as a  bankrupt or insolvent, or Seller makes a general assignment for the benefit of its creditors, or a receiver is appointed on account of the insolvency of Seller, or Seller files a petition seeking to take advantage of any other law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts and, in the case of any such proceeding instituted against Seller (but not by Seller), such proceeding is not dismissed within sixty (60) days of such filing.

17.2 Purchaser’s Remedies Against Seller»

.  The provisions of Article 26 hereof notwithstanding, and without limitation of Purchaser’s rights under Article 10 for those Liquidated Damages paid or due prior to an Event of Seller Default, if an Event of Seller Default shall have occurred and be continuing, Purchaser or its assignee shall have the right to terminate this Agreement in whole or in part by delivery of a notice of termination to Seller.  In the case of Event of Seller Default as set forth in Section 17.1 (c) (i) or (ii), Purchaser shall be entitled to such Liquidated Damages plus other amounts as associated with the termination.  For the avoidance of doubt, this Agreement may be partially terminated on a Unit basis as to result of an Event of Seller Default in accordance with the provisions of the Agreement.

17.3 General Obligations»

.  If Purchaser elects to terminate this Agreement pursuant to Section 17.2 hereof, Seller shall, at Purchaser’s request and at Seller’s expense, subject to Section 27.1 hereof, either:

(a) promptly refund all amounts paid to date and pay Cover Damages plus Termination Costs described in Sections 17.4.2(a) and 17.4.2(d) described below, provided, however, that if and to the extent title to Equipment has passed to Purchaser, Seller shall have the right to retrieve such Equipment at its cost; or

(b) perform the following services relative to the Scope of Work so affected;

(i) assist Purchaser in preparing an inventory of all Equipment and documentation to which Purchaser has not already taken title;

(ii) assign to Purchaser, or to any person designated by Purchaser without any right to compensation not otherwise provided for herein, title to all portions of the Equipment and documentation not already owned by Purchaser, together with all subcontracts and other contractual agreements (including warranties) as may be designated by Purchaser, all of which subcontracts and contractual agreements shall be so assignable, and to Purchaser to the extent assignable all issued licenses, authorizations, approvals and rights to complete and to use the Equipment under patents and other proprietary or intellectual property rights then held by Seller or its Vendors pertaining to the Equipment;

(iii) afford to Purchaser all design, expertise and other information as may be  necessary for the operation of the Equipment for which title has passed to Purchaser (subject to the requirements of Section 21.1 hereof); and

(iv) supply any proprietary components or procure and supply substituted nonproprietary components need for the completion and operation of the Equipment.

17.4 Payment Obligations»

.

17.4.1 Determination of Obligations»

.  If Purchaser terminates this Agreement pursuant to Section 17.2 hereof, and requests delivery of the Equipment and the materials and services described in Section 17.3.(b) above, Purchaser shall determine the value of that portion of the Scope of Work, which has been properly completed, if any (the “Proper Scope Value”).  If Purchaser has paid Seller an amount greater than the Proper Scope Value, the difference between the amount paid to Seller and the  Proper Scope Value (the “Refund Amount”) shall be settled between the parties in accordance with Section 17.4.4 below.  If the amount paid by Purchaser to Seller is less than the Proper Scope Value, the difference between the amount paid and the Proper Scope Value (the “Scope Value Due”) shall be settled between the parties in accordance with Section 17.4.4 below.  If Seller disagrees with Purchaser’s determination of the Proper Scope Value, such dispute shall be resolved in accordance with Article 16.

17.4.2 Damages and Expenses»

.  Purchaser shall determine the total damages and reasonable and necessary expenses incurred in connection with:

(a) the termination of this Agreement (including all legal fees and expenses for,  inter alia, the negotiation of an agreement with an alternate supplier);

(b) if Section 17.3(b) hereof is applicable, any rework, modifications or replacement of the Equipment to cause it to comply with the requirements of this Agreement;

(c) if Section 17.3(b) hereof is applicable, the completion of the Scope of Work and all associated incidental costs, and

(d) amounts otherwise due Purchaser from Seller pursuant to this Agreement (including but not limited to Liquidated Damages and Takeover Liquidated Damages).

The total of items (a) through (d) above shall be referred to as the “Termination Costs”.

17.4.3 Cover Damages»

.  If Section 17.3(a) hereof is applicable, the amount of “Cover Damages” shall be the difference between the Purchase Amount under this Agreement and the purchase price payable by Purchaser for a replacement contract for a substantially similar gas turbine generator and the other equipment and materials included in the Scope of Work under this Agreement, suitable for the Facility and substantially meeting the specifications set forth in this Agreement, plus incremental transportation costs incurred.  Purchaser agrees that it has a duty to mitigate any damages and that it shall use commercially reasonable efforts to minimize Cover Damages it may incur as a result of procuring a replacement contract in the event of termination hereunder.

17.4.4 Settlement»

.  Upon determining the Proper Scope Value and the Termination Costs, if any, the termination settlement (the “Termination Settlement”) shall be determined and invoiced as follows:

(a) if Section 17.3(a) is applicable, the Termination Settlement shall be the amounts described in Section 17.3(a).

(b) if Section 17.3(b) hereof is applicable, the Termination Settlement shall be as follows:

(i) if the Scope Value Due is greater than zero (0), and if

(A) the Termination Costs are greater than the Scope Value Due, Seller shall pay Purchaser the difference of the Termination Costs less the Scope Value Due, or

(B) the Scope Value Due is greater than the Termination Cost, Purchaser shall pay Seller the difference of the Scope Value Due less the Termination Costs.

(ii) if the Refund Amount is greater than zero (0), then Seller shall pay Purchaser the sum of the Refund Amount plus the Termination Costs.

(iii) if the Refund Amount and the Scope Value Due are each zero (0), Seller shall pay Purchaser the Termination Costs.

Seller or Purchaser, as applicable, shall make payment of an invoice received for Termination Settlement within thirty (30) Days of receipt of such invoice.  Any such Termination Settlement not paid when due shall accrue interest at the Interest Rate.

17.5 Events of Default by Purchaser»

.  Purchaser shall be in default hereunder upon the occurrence of any one of the following events, which shall be events of default (each an “Event of Purchaser Default”) if not cured within thirty (30) days following delivery to Purchaser of a notice of such event from Seller or, if not curable in such thirty (30) day period, if Purchaser has not commenced the cure within such period and does not thereafter diligently pursue such cure; provided that the event described in paragraph (d) below shall be an Event of Purchaser Default upon its occurrence:

(a) Purchaser shall have assigned or transferred this Agreement or any right or interest herein except as expressly permitted by this Agreement;

(b) any representation made by Purchaser in this Agreement shall have been materially false or misleading when made;

(c) Purchaser shall have defaulted in its performance under any material provision of this Agreement; or

(d) any proceeding is instituted against Purchaser seeking to adjudicate Purchaser as a bankrupt or insolvent, or Purchaser makes a general assignment for the benefit of its creditors, or a receiver is appointed on account of the insolvency of Purchaser, or Purchaser files a petition seeking to take advantage of any other law relating to bankruptcy, insolvency, winding up or composition or readjustment of debts and in the case of any such proceeding instituted against Purchaser (but not by Purchaser) such proceeding is not dismissed within sixty (60) days of such filing.

17.6 Seller Remedies»

.  The provisions of Article 26 hereof notwithstanding, if an Event of Purchaser Default shall have occurred and be continuing, Seller shall have the right to terminate this Agreement by delivery of a notice of termination to Purchaser, in addition to any rights and remedies that may be available at law or in equity.

ARTICLE 18 
FORCE MAJEURE

18.1 Failure to Perform Due to an Event of Force Majeure»

.  Subject to the terms of this Article 18, either party shall be excused from performance and shall not be considered to be in default with respect to any obligation hereunder, to the extent such party’s (the “Affected Party”) failure of performance is due to an event of force majeure as defined in this Article (the “Event of Force Majeure”).»

18.2 Events of Force Majeure»

., the following occurrences constitute Events of Force Majeure, unless excepted  in Section 18.3 below:

(a) explosions, fires, nuclear radiation contamination, hurricanes, earthquakes, floods, natural disasters, epidemics, other acts of God, and any other similar circumstances;

(b) war and other hostilities (whether declared or not), revolution, public disorders, insurrection, rebellion, sabotage, acts of public officials or terrorist action;

(c) any action or relative material inaction taken by any national or local government or judicial authority after the date of this Agreement, including without limitation any order, legislation, enactment, judgment, ruling or decision; or

(d) national or regional strikes (to the extent affecting the Seller’s performance of Scope of Work) and strikes specific to the Site or to Seller’s and its approved Vendor’s (as listed in Exhibit B-4) manufacturing facilities.


Notwithstanding the foregoing, the occurrences set forth in (a) through (d) above shall not be considered Events of Force Majeure if:


(e)
such circumstance is within the reasonable control of the party affected;


(f)
such circumstance, with the exercise of reasonable diligence, can be prevented, avoided or removed by such party;


(g)
such circumstance does not prevent the Affected Party from fulfilling its obligations under the Agreement;


(h)
the Affected Party has not taken all reasonable precautions, due care and reasonable alternative measures in order to avoid the effect of such event on the affected party’s ability to fulfill its obligations under the Agreement and to mitigate the consequences thereof; and


(i)
such event is the result of any failure of such party to perform any of its obligations under the Agreement.

18.3 Certain Events Not Excused»

.  Notwithstanding that an Event of Force Majeure may otherwise exist, the provisions of this Article 18 shall not excuse:

(a) late delivery of equipment or materials caused by Seller, or caused by any of the subcontractors of Seller, if Seller could have avoided such late delivery by exercising all reasonable endeavors as a prudent equipment supplier;

(b) late performance by Seller caused by (i) Seller’s failure to engage qualified subcontractors and suppliers, (ii) Seller’s failure to hire an adequate number of personnel or labor or (iii) by inefficiencies on the part of Seller; or

(c) delays resulting from reasonably foreseeable unfavorable weather or reasonably foreseeable unsuitable ground conditions.

18.4 Notice of Event of Force Majeure»

.  


(a)
Promptly following the occurrence of any Event of Force Majeure, but in no event more than three (3) days after learning of such Event of Force Majeure, the party declaring that an Event of Force Majeure (i) excuses or delays the performance of any obligation hereunder or (ii) requires a potential adjustment of the Purchase Amount, shall promptly provide written notice to the other party in accordance with Section 25.1 hereof.  The Affected Party has the burden of proof to establish that an Event of Force Majeure has occurred and adversely affects its ability to perform. The Affected Party shall provide the other party, its employees or its agents or contractors, with access to its premises and equipment as soon as practicable after the occurrence of an Event of Force Majeure.


(b)
Within seven (7) days of providing notice regarding the occurrence of an Event of Force Majeure, the Affected Party shall provide a written description of (i) the Event of Force Majeure (including the nature and expected duration of such Event of Force Majeure) and (ii) measures the Affected Party has taken to avoid the effect of such Event of Force Majeure on such party’s ability to fulfill its obligations under the Agreement and to mitigate the consequences thereof.  The Affected Party shall provide any additional information concerning the Event of Force Majeure reasonably requested by the other party (including, without limitation, updating of any information already provided under this Section 18.4).


(c)
As soon as practicable following the termination of an Event of Force Majeure, the Affected Party shall submit to the other party sufficient evidence regarding the nature and extent of the delay and its effect upon (i) the Guaranteed Delivery Date or (ii) the Purchase Amount, as appropriate.


(d)
Within ten (10) days after the termination of an Event of Force Majeure the parties hereto shall meet to discuss appropriate measures necessary that should be taken, including whether extension of the Guaranteed Delivery Date(s) described in Section 10.2.1 or the Installation Period(s), or, if applicable, an adjustment in the Purchase Amount described in Section 5.1.1, by the parties to take into account the effect of such Event of Force Majeure on the ability of Purchaser and Seller to reschedule project activities to avoid or minimize overall delays or additional costs resulting from the Event of Force Majeure. 


(g)
The parties  shall (i) make all reasonable efforts to prevent, reduce to a minimum and mitigate the effect of any delay or potential adjustment of the Purchase Amount occasioned by any Event of Force Majeure, including recourse to alternate acceptable source of services, equipment and materials and construction equipment; and (ii) shall use their best efforts to ensure resumption of normal performance of this Agreement after the occurrence of any Event of Force Majeure and shall perform their obligations as agreed between the parties to the maximum extent practicable.

18.5 Continued Performance»

.  Upon the occurrence of any Event of Force Majeure, the parties shall endeavor to continue to perform their obligations under the Agreement so far as reasonably practicable and Seller shall during the period of such circumstances protect and secure the works in such manner as Purchaser shall require.  Seller shall notify Purchaser of the steps he proposes to take including any reasonable alternative means for performance of the works not prevented by the Event of Force Majeure.

18.6 Event of Force Majeure - Delays»

.  If either party becomes unable to perform all or part of its obligations under this Agreement because of an Event of Force Majeure, and the Affected Party has properly invoked and observed the provisions of Section 18.4 in respect thereof, the Affected Party shall be permitted a delay in the performance of its obligations affected by the Event of Force Majeure and an extension of the Guaranteed Delivery Date or the Installation Period as applicable.

18.7 Event of Force Majeure - Cost»

.  Seller shall bear its own delay costs occasioned by any Event of Force Majeure for the first thirty (30) Day period during the occurrence or continuance of each such Event of Force Majeure.  If an Event of Force Majeure continues beyond such thirty (30) Day period in which Purchaser is the Affected Party, Seller shall be entitled, subject to the provisions of Section 11.3, to recover costs occasioned by each such Event of Force Majeure which accrue after each such thirty (30) Day period pursuant to a Purchase Amount adjustment in accordance with Section 5.3 and Article 11 hereof.

18.8 Cancellation for Force Majeure»

.  Notwithstanding that Seller may have been granted under Section 10.2.4 an extension of a Guaranteed Delivery Date(s), if by virtue of Section 18.1 either party shall be excused the performance of any obligation for a continuous period of one hundred eighty (180) days, then Purchaser may at any time thereafter, and provided such performance is still excused, terminate this Agreement by notice to Seller.

18.9 Payment on Cancellation for Force Majeure»

.  If the Agreement is canceled under Section 18.8, Seller shall be entitled to be paid pursuant to Sections 5.4.1 and 5.4.2, plus the amount of any other expenditure which in the circumstances was reasonably incurred by Seller in the expectation of completing the whole of the Scope of Work; but Seller shall not be entitled to any other payment, including, without limitation, any payment in respect of anticipated profit on this Agreement.

ARTICLE 19 
INSURANCE

19.1 Insurance - General»

.  Seller shall procure insurance at its own expense and maintain in full force and effect at all times throughout Seller’s performance under this Agreement (to include Seller’s performance of its warranty obligations) with responsible insurance carriers insurance as set forth in this Agreement.  Seller may establish programs of self insurance to the same minimum levels as set forth below, as allowed by law.

19.1.1 All Risk»

.  Seller shall purchase and maintain insurance for the full replacement cost of the Equipment during the process of fabrication and in the factory, and until transportation from Seller’s final assembly factory commences, for physical loss and damage, including, but not limited to, theft, vandalism, and malicious mischief, collapse, water damage and such other perils as Seller deems appropriate.  Seller may self insure work during the fabrication process.

19.1.2 Workers Compensation and Employers Liability Insurance»

.  Seller agrees to comply with workers compensation laws of each jurisdiction where the Scope of Work is performed, and to maintain a Workers Compensation and Employers Liability policy.  This policy shall be endorsed, if applicable, to provide all state coverage, alternate employer, voluntary compensation coverage and occupational disease with the limits set forth below. If the work is to be performed  on or near navigable U.S. waters, the policy shall include coverage for United State Longshoreman’s and Harbor Worker’s Act, Death on the High Seas Act, Jones Act, or their equivalent as required by the applicable laws in the jurisdiction where such work is performed.


Workers Compensation
Statutory


Employers Liability

$1,000,000 Each Accident






$1,000,000 Disease






Each Employee (Minimum)

19.1.3 Commercial General Liability Insurance»

.  Seller shall maintain Commercial General Liability Insurance, endorsed to provide coverage for: Explosion, Collapse and Underground hazards; Contractual Liability (particularly applicable to the provisions of the “General Indemnity” section of this Agreement);  and Products and Completed Operations (for a minimum of one year after completion of the Scope of Work) with the following limits:


Bodily Injury and

$1,000,000 Combined Single Limit


Property Damage

Each Occurrence, (Minimum).

19.1.4 Hull and Protection and Indemnity Insurance»

.  Seller shall ensure that if any owned or non-owned watercraft of any kind is used for performance of the Scope of Work, Hull and Protection and Indemnity Insurance shall be provided for the vessels in the amounts as follows:


Hull



Full replacement value of the watercraft.


P&I



$1,000,000 Each Occurrence or the full value of the vessel,

whichever is greater.

Such insurance may be provided by the vessel operator, by the vessel charter agreement, or by Seller as Seller deems appropriate.

19.1.5 Business Automobile Liability Insurance»

.  Seller shall provide Business Automobile Liability Insurance which shall include the following coverage for all owned, non-owned and hired vehicles:


Bodily Injury  

$1,000,000 Each Person  (Minimum)






$1,000,000 Each Occurrence (Minimum)


Property Damage 

$1,000,000 Each Occurrence (Minimum)

or


Bodily Injury and 

$1,000,000 Combined Single Limit


Property Damage 

Each Occurrence (Minimum)

19.1.6 Aircraft Liability Insurance»

.  If the Scope of Work necessitates the use of Seller’s or Seller’s Affiliate’s owned or leased aircraft, Seller shall provide Aircraft Liability Insurance which shall be endorsed to provide coverage for non-owned as well as Guest Voluntary Settlement, with limits of:


Bodily Injury and

$10,000,000 Combined Single Limit


Property Damage

Each Occurrence.

Such insurance may be provided by the aircraft operator, by the aircraft charter agreement, or by Seller as Seller deems appropriate.

19.1.7 Excess Umbrella Liability Coverage»

.  Seller shall provide Excess Umbrella Liability coverage with minimum limits of:


Bodily Injury and

$5,000,000 Combined Single Limit


Property Damage 

Each Occurrence.

19.1.8 Vendors»

.  Seller shall require its Vendors and others connected with the Scope of Work  to provide and maintain insurance at all times during the period that their agreement related to the Scope of Work under this Agreement is in force and effect at the Vendor’s, or other’s own cost, with insurance limits which at minimum meet levels as required for similar contracts and is customary for the applicable industry.

19.1.9 Certificate of Insurance»

.  Within twenty (20) days of execution of this Agreement, Seller shall submit to Purchaser a Certificate of Insurance, in form satisfactory to Purchaser, evidencing that satisfactory coverage of the type and limits set forth herein above are in effect.  Policies providing such coverage shall contain provisions that no cancellation or material changes in the policies shall become effective except on sixty (60) days advance written notice thereof to Purchaser.  Irrespective of the requirements as to insurance to be carried as provided for herein, the insolvency, bankruptcy or failure of any insurance company carrying insurance of Seller, or the failure  of any insurance company to pay claims accruing, shall not affect, negate or waive any of the provisions of this Agreement including, without exception, the indemnity obligations of Seller.

19.1.10 Other Requirements»

.  Seller shall be responsible for the payment of all deductible and self insurance retention amounts with respect to the insurance required to be maintained by it pursuant to this Agreement, and all Seller policies shall apply as primary insurance without right of contribution of similar policies which may be maintained by Purchaser.  All Seller insurance shall:

(a) specify Purchaser and Lender, and such other parties as Purchaser may require as additional insured for all insurance coverage other than Worker’s Compensation Insurance, or its equivalent as required in jurisdictions other than the United States;

(b) provide that Purchaser shall have the right, but not any obligation, to pay any premiums if Seller shall fail to do so, and such payment of premiums by Purchaser shall be at Seller’s expense, either by direct charge or setoff;

(c) for all insurance coverage related to Scope of Work, waive any right of subrogation against Purchaser and Lender, their parent and affiliated companies and their directors, officers, employees and agents, and all other named and additional insured and any other right of the insurer to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of any liability of Purchaser or Lender, or any other named or additional insured; and

(d) for all other insurance other than as stated in (c) immediately above, waive any right of subrogation against Purchaser, Lender and all other named and additional insured and any other right of the insurer to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of Purchaser, or any other named or additional insured.

19.1.11 Vendor Waiver of Subrogation»

.  Seller agrees to require all policies of insurance which are in any way related to the Scope of Work and that are secured and maintained by Seller’s first tier Vendors to include clauses providing that each underwriter shall waive its rights of recovery, under subrogation or otherwise, against Purchaser and Lender, their parent and affiliated companies and their directors, officers, employees and agents (the “Purchaser Related Parties”) or alternatively shall indemnify and defend Purchaser Related Parties against such action if such action arises out of or is in any way related to this Agreement.

19.1.12 Compliance with Insurance»

.  Seller and its directors, officer, representatives, agents and employees shall comply with all the terms of the policies of insurance referred to in Section 19.1 and to the extent Seller is made aware of such terms, in any Delay in Start-Up and Business Interruption Insurance obtained by Purchaser.  Seller and its directors, officers, representatives, agents and employees shall comply with the procedures for claims, notification and administration under the aforesaid insurance policies and shall not do or omit to do anything which might render voidable policies of insurance or entitle insurers to avoid liabilities thereunder.  Seller shall ensure that all Vendors and major subcontractors shall be subject to provisions identical to this Section 19.1.12.

19.1.13 Limitation»

.

19.1.13.1
In the event that Seller breaches its obligations under the first two sentences of Section 19.1.12 of the Agreement and such breach results in an insurer avoiding, in relation to Seller, any policy of insurance obtained by Purchaser pursuant to Section 19.2 of the Agreement, Seller shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of Seller included in that policy pursuant to Section 19.2 shall not apply.

19.1.13.2
In the event that any Vendor fails to comply with the procedures for claims notification and administration under any policy of insurance obtained by Purchaser pursuant to Section 19.2 of the Agreement or does anything which might render any such policy of insurance voidable or entitle insurers to avoid liability thereunder and as a result thereof an insurer avoids in relation to that Vendor any such policy of insurance, that Vendor shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of that Vendor included in that policy pursuant to Section 19.2 of the Agreement shall not apply.

19.2 Purchaser’s Insurance»

.

19.2.1 Cargo Insurance»

.  Purchaser shall provide or cause to be provided and maintained All Risk Marine Cargo Insurance for the period of transportation commencing upon transportation from factory where final assembly occurs prior to commencing delivery to Purchaser and ending upon Delivery.  The maximum per occurrence deductible, shall be no more than $25,000.  Purchaser shall cause Seller to be an additional insured and provided a waiver of subrogation under such policy.

19.2.2 Builder’s All Risk Insurance»

.  Purchaser shall provide, or cause to be provided and maintained, a Builder’s All Risk policy covering activities at the Site for the period of time that Seller performs TD of I services at the Site.  Seller, to the extent of its TD of I services on the Site, shall be named as an additional insured and provided a waiver of subrogation under such policy.

Seller shall have an opportunity to review and make reasonable comments to the Purchaser’s proposed insurance policies in respect to the Cargo insurance and Builder’s All Risk insurance.  Upon request, Purchaser shall provide Seller one copy of the relevant portions of such final insurance policies as such policies become available.  [Note: Parties to discuss new language for this Article]

ARTICLE 20 
INDEMNIFICATION

20.1 Definitions»

.
The following defined terms shall apply with respect to the Parties obligations under this Article 20:

(a) “Claim” shall mean any and all demands, claims, suits and causes of action and any liability, costs, expenses and judgments incurred in connection therewith (including court costs and reasonable attorney’s fees) whether arising in equity, at common law, by statute or under the laws of contract, tort (including negligence or strict liability without regard to fault) or any other cause of action.

(b) “Purchaser Indemnified Party” shall mean Purchaser, Purchaser’s Affiliates, the Lender, and their respective employees, officers, directors, agents, subcontractors and representatives.

(c) “Seller Indemnifying Party” shall mean Seller, Seller’s Affiliates, and their respective employees, officers, directors, agents, subcontractors and representatives.

(d) “Third Party” shall mean any natural person, corporation, company, partnership (general or limited), limited liability company, business trust, or other entity or association other than a Purchaser Indemnified Party.

20.2 Seller Indemnity»

.
Seller agrees to indemnify, protect, defend and hold harmless each Purchaser Indemnified Party from and against the following:

(a) each and every Claim for personal injury (including death) or damage to tangible physical property of a Third Party to the extent based upon, in connection with, relating to or arising out of or alleged to arise out of the negligent or culpable wrongful acts or omissions of a Seller Indemnifying Party or out of Seller’s strict liability;

(b) each and every Claim for fines or similar penalties imposed by a cognizant government, and associated damages, costs, losses and expense, resulting from Seller’s failure to comply with the provisions of Section 3.6 (Compliance with Governmental Rules and the Requirements of this Agreement);

(c) each and every Claim resulting from Seller’s failure to comply with the provisions of Section 15.2.2 (Infringement Cures and Defense);

(d) each and every Claim resulting from Seller’s failure to comply with the provisions of Section 3.4 (Hazardous Materials Notification); and

(e) each and every Claim resulting from Seller’s failure to comply with the provisions of Section 6.5 (Lien Release) and Article 24 (Liens and Claims).

20.3 Comparative Fault»

.  Seller’s contractual obligations of indemnification under this Article 20 shall apply even if due in whole or in part to Purchaser’s concurrent negligence, fault, breach of contract or warranty, or strict liability without regard to fault; provided, however, that such contractual obligation of indemnification shall not extend to the percentage of the damages or injuries attributable to Purchaser’s negligence, fault, breach of contract or warranty, or to strict liability without regard to fault imposed as a matter of law. In the event that both Seller and Purchaser are negligent, at fault or strictly liable without fault with respect to damage or injuries for which the provisions of this Article 20 apply, then the Seller’s contractual obligations of indemnification shall still continue but Seller shall indemnify Purchaser only for the percentage of responsibility of the damage or injuries adjudicated to be attributed to Seller.

20.4 Insurance»

.  Seller’s indemnification obligations under this Article 20 shall apply regardless of the amount of insurance coverage held by Seller, including that under any worker’s compensation act, disability act, or other act or law which would limit the amount or type of damages, compensation, or benefits payable by or for Seller, and shall not be limited by any insurance carried or provided by the Seller in accordance with this Agreement or otherwise.

20.5 Notice and Litigation»

.  It is a condition precedent to the Seller’s contractual obligations of indemnification under this Article 20 that Purchaser shall provide written notice of a Claim promptly after such Claim is received by Purchaser. It is further a condition precedent to the Seller’s contractual obligations of indemnification under this Article 20 that Seller shall thereafter have the right to participate in the investigation, defense and resolution of such Claim so long as the same does not impair Purchaser’s rights and interests.

20.6 Survival of Obligations»

.  The obligations to indemnify under this Article 20 will continue in full force and effect notwithstanding the expiration or termination of this Agreement.

ARTICLE 21 
NON-DISCLOSURE OF INFORMATION

21.1 Proprietary Information»

.  Without prejudice to Sections 21.3 and 21.4, any information concerning the parties which is designated in writing as proprietary and/or confidential and disclosed to the other party incident to the performance of the Scope of Work pursuant to this Agreement in confidence shall not be published or otherwise disclosed it to others without the written approval of the disclosing party, provided, however, that nothing herein shall limit either party’s rights to disclose data which:

(a) was developed on its own or furnished to it prior to this Agreement without restriction;

(b) becomes generally available to the public through no fault of either party; or

(c) is received by either party from a third party without restriction and not in breach of this Agreement.

Proprietary and/or confidential information disclosed hereunder shall only be used by the transferee in the performance of its obligations hereunder or as expressly permitted under this Agreement.  Each party shall take such actions to protect proprietary and/or confidential information disclosed by the other party as are consistent with its practices to protect its own proprietary and/or confidential information.

Furthermore, Purchaser or Seller may provide any such information to any governmental authority having jurisdiction and asserting a right to obtain such information, but only to the extent required to do so by law. This clause shall survive the termination of this Agreement.

21.2 Press Releases»

.  Seller agrees that it is in Purchaser’s interest to limit information of strategic value disseminated to the independent power industry regarding this Facility.  To the extent that Seller desires to issue press releases, advertisements in the trade press, tombstones in the financial or trade press, then Seller must obtain Purchaser’s written release to do so.

21.3 Confidentiality»

.  Seller acknowledges that Purchaser’s business is highly competitive and that Purchaser’s books, records, documents and technical information concerning its products, equipment, services, processes, procurement procedures, pricing techniques, the names of and other information (such as credit and financial data) concerning Purchaser’s customers and business affiliates, all comprise confidential business information and trade secrets of Purchaser which are valuable, special and unique proprietary assets.  Seller further acknowledges that protection of Purchaser’s confidential business information and trade secrets against unauthorized disclosure and use is of critical importance to Purchaser in maintaining its competitive position.  Accordingly, Seller hereby agrees that it will not, at any time during or after the term of this Agreement, make any unauthorized disclosure of any confidential business information or trade secrets of Purchaser or make any use thereof, except for the benefit of, and on behalf of, Purchaser.  However, Seller’s obligation under this Section 21.3 shall not extend to information which is or becomes part of the public domain or is available to the public by publication or otherwise through no wrongful act or omission or noncompliance with this Section by Seller or its agents.  The provisions of this Section 21.3 shall survive the termination of this Agreement.  Seller agrees and acknowledges that money damages would not be sufficient to remedy  for any breach of this Section 21.3 by Seller, and Purchaser shall be entitled to specific performance and injunctive relief as remedies for such breach or any threatened breach.  Such remedies shall not be deemed the exclusive remedies for a breach of this Section 21.3 by Seller, but shall be in addition to all remedies available at law or in equity to Purchaser including recovery of damages from Seller.  For the purposes of this paragraph, the term “Purchaser” shall also include Affiliates of Purchaser.

Seller shall deliver to Purchaser all Purchaser confidential information provided or disclosed to or used or acquired by Seller, including all information developed, derived, or created therefrom, or portions thereof, upon the earlier of:

(a) the ending of the need for the information for performance of the Scope of Work;

(b) Purchaser’s request;

(c) the completion of the Scope of Work for which it was provided, disclosed used or acquired; or

(d) cancellation, termination or suspension of this Agreement.

Seller may retain a single copy of all information upon which its Scope of Work is based for record purposes only.  In the event Seller, with Purchaser’s consent, releases Purchaser’s confidential information to a third party, Seller shall require such third party to enter into a confidentiality agreement similar to this Section 21.3 with Seller, and Seller shall retrieve all such released confidential information, including any and all copies of the confidential information and all information developed, derived, or created therefrom, upon the earlier of the events set forth above in this Section.

No documents, data, materials or information available to Seller as set forth in this Section 21.3 or produced in whole or in part under this Agreement shall be the subject of an application for copyright by or on behalf of Seller without the prior written consent of Purchaser.

Either party shall be entitled to disclose the terms and conditions of this Agreement and any data or information acquired by it under or pursuant to this Agreement without the prior consent of the other party:

(e) to any Affiliate of such party;

(f) to any outside consultants or advisers engaged by or on behalf of such party in connection with the Scope of Work or the financing or operation of the Facility and acting in that capacity;

(g) to any operator of the Facility, Lenders or permitted assignees;

(h) to the extent required by the rules of a relevant and recognized stock exchange;

(i) to the extent required by law or pursuant to an order of any court of competent jurisdiction, provided that the original disclosing party is given notice and adequate time to seek a protective order applicable to the information before it is disclosed;

(j) to any insurer under a policy of insurance required to be taken out by either party under the Agreement; or

(k) to directors, employees and officers of such party;

provided that:

(l) the disclosing party determines in good faith that the recipient has a legitimate need to see such data or information; and

(m) the recipient has been made aware of and has agreed to be bound by the requirements of this Article 21.

21.4 Disclosure of Contract Details»

.  The documents which constitute this Agreement and the contents thereof shall be deemed to be confidential and proprietary to both Parties for the purposes of this Article 21, and the information contained herein may be disclosed to third parties only in accordance with the provisions hereof.  Without limiting the generality of the foregoing provisions of this Article 21, this contract document may be disclosed in its entirety by Purchaser, with or without its Exhibits, only:  (a) in redacted form, (i) to potential assignees pursuant to Article 22 hereof, provided that Seller shall have been notified in advance of such disclosure. or (ii) to other contractors of Purchaser, on the conditions set forth in section 21.1 above; or (b) in unredacted form, to a potential assignee whom Purchaser has reasonably determined to be capable of accepting such assignment and to be acting in good faith in connection therewith, and, if such approval is required pursuant to Article 22, whom Seller has so approved as an assignee.

ARTICLE 22 
ASSIGNMENT

22.1 Assignment by Seller»

.  This Agreement may be assigned by Seller without Purchaser’s consent to a wholly owned subsidiary of Seller’s ultimate parent company subject to Section 3.7.  This Agreement may not be assigned by Seller to any other entity without the prior written consent of Purchaser, which consent shall not be unreasonably withheld. As a condition precedent to the effectiveness of any such assignment. Seller shall deliver to Purchaser an unconditional guarantee in the form set forth in  Exhibit C-1 hereto, which shall guarantee full payment and performance of all Seller obligations under this Agreement as due in accordance with the terms of this Agreement.

22.2 Assignment by Purchaser»

.  [Note: Enron to provide new assignment language]  This Agreement or any right or obligation contained herein may be assigned by Purchaser without Seller’s consent to:

(a) an Affiliate of Purchaser;

(b) a joint venture, partnership, or other similar entity in which Purchaser or any of its  Affiliates is a venturer, partner or participant with no less than a nineteen and one-half percent (19.5%) equity interest;

(c) any Lender or financial institution providing financing to Purchaser or its Affiliates or any permitted assignee in connection with the Equipment or the Facility;

(d) any party which is obligated or may be obligated to indemnify Seller from any claims or liabilities arising in connection with this Agreement;

(e) any party (i) for which Purchaser or any of its Affiliates has agreed to construct or develop a facility using the Equipment or (ii) to which Purchaser or any of its Affiliates has agreed to convey a power plant project which it has under development; or

(f) any contractor or developer which is retained by Purchaser or any of its Affiliates to construct or develop a power plant using the Equipment.

Except for (a) through (f) above, this Agreement may be assigned by Purchaser to other parties only upon the prior written consent of Seller which consent shall not be unreasonably withheld, conditioned or delayed.  Seller agrees to respond to any request for consent within thirty (30) days following its receipt of such request.  Any failure to respond within the foregoing time period shall be deemed to be a grant by Seller of its consent to the proposed assignment.  In determining whether Purchaser shall be permitted to assign this Agreement, Seller shall only be deemed to be reasonable in withholding its consent if the proposed assignee: (i) does not have substantially the same or better credit quality than Purchaser unless (A) the proposed assignee provides appropriate guaranties, letters of credit or other assurances of payment issued by an entity or person with substantially the same or better credit quality than Purchaser or (B) the assignor agrees to remain liable for all future liability under this Agreement, (ii) is a direct competitor of Seller in the turbine manufacturing business, (iii) is an adverse party to Seller in any material litigation or (iv) if purchasing any Equipment (or its rights thereto), is not purchasing such Equipment (or rights thereto) as part of a transaction in which (x) Purchaser or any of its Affiliates is providing related goods and/or services to such assignee, and (y) Purchaser is not merely acting as a broker or market maker with respect to such Equipment (or rights thereto). As a condition precedent to the effectiveness of an assignment which requires Seller’s approval and if Seller has expressed a concern about the credit worthiness of assignee requiring the approval of Seller, an unconditional guarantee generally in the form set forth in Exhibit C-2 hereto, which shall guarantee full payment and performance of all Purchaser obligations under this Agreement as due in accordance with the terms of this Agreement, shall be provided to Seller by the assignee.  Purchaser shall have the right to assign or pledge the Agreement as collateral for financing of the Facility without Seller’s consent.  When duly assigned in accordance with the foregoing, this Agreement shall be binding upon and shall inure to the benefit of the assignee (and all rights hereunder, including, without limitation, any and all warranty rights, shall be assigned to the assignee as if such assignee were an original party hereto) and the assignor shall be relieved of all liability under this Agreement so long as the assignee executes an assumption of such liabilities.  Any assignment by Purchaser other than as permitted herein shall be void and without force or effect.

The parties hereto further agree and acknowledge that the foregoing provisions relating to this assignment will only control the assignment of Purchaser’s rights under this Agreement prior to the date upon which the Equipment achieves Commercial Operations.  Following such date, Purchaser shall be permitted, without Seller’s consent, to: (i) assign its rights under this Agreement, (ii) convey any ownership interest that it may have in the Facility and/or (iii) convey any equity interest that it may have in the entity which owns the Facility.

In the event of assignment to other than Lender, the guarantee by [Enron Power Corp.,] if required, shall be amended, or a similar guarantee from a guarantor acceptable to Seller substituted therefor (such acceptance not to be unreasonably withheld) shall be amended, to guarantee the obligations of the assignee.  [Note:  Isn’t this paragraph somewhat duplicative of the guarantee language in the first large paragraph above?  Can this paragraph be deleted?]

ARTICLE 23 
RELATIONSHIP OF THE PARTIES

23.1 Independent Contractor»

.  Seller undertakes performance of this Agreement as an independent contractor.  Nothing herein shall create a relationship of employer and employee, joint venture, or partnership between Purchaser and Seller, its agents, representatives, employees, Affiliates, Vendors or subcontractors, for any purpose whatsoever.  Nothing herein shall create a relationship of principal and agent between Purchaser and Seller, its agents, employees, representatives or subcontractors.  Neither party shall have the authority to bind or obligate the other in any manner as a result of the relationship created hereby.  Purchaser shall not have the right to control the manner(s) or prescribe the method(s) by which Seller performs this Agreement.  Seller shall be wholly responsible for supervision and the methods of performance.  Seller is entirely and solely responsible for its acts and the acts of its agents, employees, representatives, Affiliates, and Vendors engaged in the performance of this Agreement.  Seller shall provide qualified personnel who shall be and remain solely the employees of Seller, and at no time or in any manner shall said personnel be considered as, or deemed to be, employees of Purchaser.  Purchaser’s general coordinative efforts, suggestions and procedures with respect to the Scope of Work, and Purchaser’s right of inspection, review and observation of the performance of this Agreement, shall not make Seller or its employees, employees of Purchaser.

23.2 Responsibilities of Seller as Principal for its Employees»

.  Seller has complete and sole responsibility as a principal for its agents, Vendors and all other hires to perform or assist in performing the Scope of Work.

ARTICLE 24 
LIENS AND CLAIMS

Seller shall not directly or indirectly create, incur, assume or suffer to be created by it or any Vendors, employees, laborers, materialmen or other suppliers of goods or services any claim, lien, security interest, charge or other encumbrance on the Equipment or any part thereof or interest therein and Seller shall immediately notify Purchaser of the assertion of any lien, claim, security interest or other encumbrance against the Equipment or any part thereof.  Seller shall remove immediately any lien, claim, security interest or other encumbrances against Purchaser, Purchaser’s property, Purchaser’s Affiliates’ property, or the Equipment arising in favor of Seller or its Vendors or other persons or entities by reason of having provided labor, materials or equipment related to performance of this Agreement and to pay any damages, costs, losses and expenses (including, without limitation, court costs and attorneys’ fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, in connection with, arising out of, or related to any such lien, claim, security interest or other encumbrance.  In the event of a lien from a Vendor, supplier or service provider is levied, Seller shall immediately post a letter of credit acceptable to Purchaser against such lien.  Upon the failure of Seller promptly to pay or discharge any lien claim, security interest or other encumbrance as required hereby within twenty (20) days of notice of the existence thereof from any source, Purchaser may, but shall not be obligated to, pay or discharge such lien claim, security interest or other encumbrance and, upon the payment or discharge thereof, shall be entitled to recover from Seller the amount thereof together with all expenses incurred by Purchaser in connection with such payment or discharge.

ARTICLE 25 
NOTICES AND COMMUNICATIONS

25.1 Notices»

.  Any notice pursuant to the terms and conditions of this Agreement shall be in writing and either:

(a) delivered personally;

(b) sent by certified mail, (return receipt requested);

(c) sent by a recognized overnight mail or courier service with delivery receipt required; or

(d) sent by confirmed facsimile transfer:

Commercial - Legal:

If to Seller:

See Exhibit E.1

If to Purchaser:
See Exhibit E.1  [Note:  Would it be easier for the reader to move the





information in Exhibit E into the Agreement itself?]

Either party may change its address or the person to be notified by a notice delivered in accordance with this section.

25.2 Effectiveness of Notices»

.  Notices shall be effective when received  at the address or facsimile number specified.

25.3 Technical Communications»

.  Notwithstanding communications and notices addresses as set forth in Exhibit E.1, the parties will route routine and technical communications as set forth in Exhibit E.2:

If to Seller:

See Exhibit E.2

If to Purchaser:
See Exhibit E.2  [Note:  Would it be easier for the reader to move the





information in Exhibit E into the Agreement itself?]

25.4 Notices to be Provided by Seller.
25.4.1 Advance Shipment Notice»

.  Seller shall provide Purchaser’s Representative with reasonable advance notice of the expected packing date and the expected loading date of any shipment of Equipment, and shall provide five (5) business days advance notice of the actual packing date and the actual loading date of such shipment, in accordance with Section 3.8.3.  Seller shall provide Purchaser’s Insurance Representative with a load and transportation plan forty five (45) days prior to loading of the Equipment.

25.4.2 Notice of Witness Test Points»

.  Not later than ninety (90) days after the latest date of signing of the Agreement, Seller shall provide Purchaser its proposed schedule of witness test points set forth in Exhibit R, excluding those that have transpired on the Units being manufactured (in such case test and inspection results shall be provided).  Seller shall provide Purchaser with a notice of the date of a witness test point not less than fourteen (14) days prior to such date.
25.4.3 Major Component Packing Notice»

.  Seven (7) days prior to Seller performing any Major Component packing, Seller shall provide to Purchaser the notice and request for release described in Section 9.7.

25.5 Notices to be Provided by Purchaser.  

25.5.1 Designation of Purchaser’s Representative»

.  Within thirty (30) days of the latest date of signature of this Agreement, Purchaser shall notify the Seller of the individual it has designated as Purchaser’s Representative who shall act as the primary point of contact for Seller with respect to the prosecution of the Scope of Work.
25.5.2 Individuals Authorized to Approve Change Orders»

.  Within thirty (30) days of the latest date of signature of this Agreement, Purchaser shall deliver a notice to Seller identifying such persons within Purchaser’s organization that have authority to approve Change Orders.

25.5.3 Notice of Performance Tests»

.  Pursuant to Section 10.2.5, Purchaser shall provide Seller with a thirty (30) days initial notice and a five (5) days confirmation notice in advance of each Performance Test.
ARTICLE 26 
ARBITRATION

26.1 Negotiation of Disputes and Disagreements»

.  In the event of any dispute or disagreement arising out of or relating to the implementation or performance of this Agreement, which the parties hereto have been unable to settle or agree upon within a period of thirty (30) days after the dispute or disagreement arises, each party shall nominate a senior officer of its management to meet at a mutually agreed time and place not later than forty five (45) days after the dispute or disagreement has arisen to attempt to resolve such dispute or disagreement.  Should a resolution of such dispute or disagreement not be obtained within fifteen (15) days after the meeting of senior officers for such purpose, or if such meeting does not take place within sixty (60) days after the dispute or disagreement has arisen, either party may then by notice to the other submit the dispute to arbitration in accordance with the provisions of Section 26.2.

26.2 Arbitration Resolution»

.  With respect to arbitration resolution, the parties agree that:

(a) In the event of dispute between Purchaser and Seller concerning the interpretation of any provision of this Agreement or the performance of any of the terms of this Agreement, such matter or matters in dispute shall be finally settled under the arbitration rules of the American Arbitration Association by three arbitrators, one appointed by each party, and the third, who shall be the chairman, will be selected by the two appointed arbitrators, and, failing agreement, by the chairman of the American Arbitration Association.  The language of the arbitration shall be English.  The place of arbitration shall be mutually agreed upon by the parties.

(b) The decision of the arbitrators shall be final and binding upon the parties;

(c) If any dispute to be referred to arbitration under this agreement raises issues which are, as mutually agreed, substantially the same as or connected with issues raised in any other dispute between the parties (and their successor in title and assigns), then such latter dispute shall constitute a “related dispute”;

(d) If a related dispute has already been referred to arbitration in accordance with arbitration provisions identical (mutatis mutandis) to this clause:

or, if the dispute under this Agreement has already been referred to arbitration under this clause, then:

(i) the dispute under this Agreement shall be referred to the arbitrators appointed to determine the related dispute; and

(ii) the arbitrators shall have power to join one or more defendants or third parties or consolidate actions as provided by applicable law.

26.3 Continuation of Work»

.  Pending final resolution of any dispute, Purchaser and Seller shall continue to fulfill their respective obligations hereunder.

ARTICLE 27 
LIMITATION OF LIABILITY

27.1 Maximum  Liability of Seller»

.  Seller’s maximum aggregate liability for claims by Purchaser arising out of Seller’s performance of this Agreement, including Liquidated Damages, whether arising from tort (including negligence or strict liability without regard to fault), breach of contract or any other cause of action, shall be the greater of [$25,000,000  SSEP to Comment] or one hundred percent (100%) of the Purchase Amount. Notwithstanding the foregoing, the limitation of liability under this Section shall not apply to any of the following categories of liability of Seller:

(a) under paragraphs (a) and (b) of Section 20.2 (Seller Indemnity); and

(b) under Section 15.2 (Title).

All liability of Seller under this Agreement with respect to any Unit shall terminate six (6) years after Delivery of the Unit, as determined in accordance with Section 10.2. [Note from Enron: need to discuss termination provisions of Article 17 and limitation of liability.]
27.2 Maximum Liability of Purchaser»

.  Purchaser’s maximum aggregate liability for claims by Seller arising out of Purchaser’s performance of this Agreement, including the Cancellation Fee, whether arising from tort (including negligence or strict liability without regard to fault), breach of contract, indemnity or any other cause of action, shall be one hundred percent (100%) of the Purchase Amount

All liability of Purchaser under this Agreement with respect to any Unit shall terminate six (6) years after Delivery of the Unit, as determined in accordance with Section 10.2.

27.3 Consequential Losses»

.  The Parties have agreed to liquidate certain direct damages and have provided for these damages as Liquidated Damages and Cancellation Fees.  For purposes of this Section, Liquidated Damages and Cancellation Fees shall not be deemed consequential losses.  In no event, whether as a result of breach of contract, breach of warranty, tort liability (including negligence or strict liability without regard to fault) or otherwise, and whether arising before or after completion of the Scope of Work, shall either Party be liable to the other Party for special, indirect, exemplary or consequential losses of any nature whatsoever, including losses or damages caused by reason of unavailability of the Equipment, shutdowns or service interruptions, loss of use, loss of profits or revenue, inventory or use charges, cost of purchased or replacement power, interest charges or cost of capital or claims of a Party’s customers.  For the avoidance of doubt, the foregoing limitation of liability in this Section shall not limit Seller’s obligation to indemnify, defend and hold harmless Purchaser in respect of the consequential portion of any damages for which Seller would otherwise properly be liable in accordance with Sections 20.2(a) and (c).

27.4 Releases Valid in All Events»

. Except as otherwise specifically set forth herein, releases, disclaimers and limitations on liability expressed herein shall apply even in the event of the negligence, strict liability without regard to fault or breach of contract (including other legal bases of responsibility such as fundamental breach) of the Party whose liability is released, disclaimed or limited.

27.5 Separate Advice or Assistance»

.  If, at the request of Purchaser, Seller furnishes Purchaser with advice or assistance which is not clearly required by this Agreement, Seller shall not be subject to any liability whether in contract, warranty, tort (including negligence or strict liability without regard to fault), indemnity or otherwise in connection with Seller’s provision of such out of scope of service advice or assistance, so long as such advise or assistance (a) is given in good faith and in accordance with industry practices and standards and (b) does not otherwise conflict with Seller’s obligations under this Agreement or cause Seller to be in breach of the terms of this Agreement.

ARTICLE 28 
DRUG AND ALCOHOL-FREE WORKPLACE

The parties desire to provide a safe and productive work environment.  The parties believe that the use, possession and/or distribution of illegal/unauthorized drugs and alcohol presents a serious threat to the safety of employees, visitors and others at the job site, or other premises owned, leased, or occupied by Purchaser.  All Seller’s and Seller’s Vendors’ employees associated with the Scope of Work under this Agreement must agree to compliance with Purchaser’s drug and alcohol policy Number [1200-2, dated September 11, 1995] including:  [Note:  Do we want a specific reference or just a statement that Purchaser will provide Seller with its policy and Seller will agree to compliance therewith?]

(a) while on or entering the Site or other premises owned, leased, or occupied by Purchaser, search of personal and professional possessions, including but not limited to automobiles, trucks, briefcases, lunch boxes, and person for illegal drugs.  Failure to consent to such search shall be grounds for immediate removal from the Site or other premises owned, leased, or occupied by Purchaser;

(b) drug testing at any time while on the Site or other premises owned, leased or occupied by Purchaser.  Failure to do so or failing any such test shall be grounds for immediate removal from the Site or other premises owned, leased, or occupied by Purchaser; and

(c) failure of a Seller’s or Vendor’s employee to agree and abide by these requirements will be grounds for immediate removal from the job site or other premises owned, leased, or occupied by Purchaser from any work site or location under the control of Purchaser that is associated with the Scope of Work under this Agreement.

ARTICLE 29 
PROJECT PLANNING AND CONTROLS

Exhibit K sets forth the Project Planning and Control system for tracking the progress of the Scope of Work.  Seller shall establish a program and submit reports and data as set forth therein.

ARTICLE 30 
MISCELLANEOUS

30.1 Validity and Enforceability»

.  The invalidity or unenforceability of any portion or provision of this Agreement shall not affect the validity or enforceability of any other portion or provision.  Any invalid or unenforceable portion or provision shall be deemed severed from this Agreement, and the balance of the Agreement shall be construed and enforced as if the Agreement did not contain such invalid or unenforceable portion or provision.  Notwithstanding the provisions of the preceding sentence, should any term or provision of this Agreement be found invalid by any governmental authority having jurisdiction thereof, the parties shall immediately renegotiate in good faith such term or provision of the Agreement to eliminate such invalidity.

30.2 Governing Law»

.  This Agreement, its interpretation and any disputes relating to, arising out of or connected with this Agreement, shall be governed by the laws of the State of [_________], without regard to its conflicts of law provisions.

30.3 Entire Agreement»

.  This Agreement, and the Exhibits attached hereto constitute the entire agreement between the parties with respect to the subject matter hereof, and there are no oral or written understandings, representations or commitments of any kind, express or implied, not set forth herein.  This Agreement supersedes all prior agreements between the parties with respect to the subject matter hereof.

30.4 Agreement Modification»

.  No oral or written modification of this Agreement either before or after its execution shall be of any force or effect unless such modification is in writing and signed by the party to be bound thereby.

30.5 Waiver»

.  The waiver by any party of any breach or failure to enforce any of the terms, covenants or conditions of this Agreement shall not in any way affect, limit, modify or waive the future enforcement of such terms, covenants or conditions.

30.6 Headings»

.  The headings contained herein are included solely for the convenience of the parties and are not to be used as a basis for interpreting the various sections of this Agreement.

30.7 Third-Party Beneficiaries»

.  The provisions of this Agreement are intended for the sole benefit of Purchaser and Seller, and there are no third-party beneficiaries other than assignees contemplated by the terms herein.

30.8 Counterparts»

.  This Agreement may be executed in counterparts, each of which when so executed and delivered shall be an original, and all of which, when taken together, shall constitute one and the same instrument.

30.9 Equal Employment Opportunity»

.  To the extent performance if any Scope of Work is performed in the United States, the parties hereto agree that the provisions of Executive Order 11246, as amended, and the Rehabilitation Act of 1973 (Section 503, Public Law 93-112, as amended), the Vietnam Era Veteran’s Readjustment Assistance Act of 1974, as amended (including the provisions of the “Equal Opportunity” clauses), and the regulations promulgated pursuant to the above, are hereby incorporated into this Agreement by reference as if fully set out.

30.10 Cooperation on Site»

. To the extent Seller is required to perform services on Site it shall cooperate with other contractors on Site so as to coordinate work and schedules.

30.11 Avoidance of Nuclear Use»

.  The Equipment sold hereunder is not intended for application (and shall not be used) in connection with the use or handling of nuclear material or the construction or operation of a nuclear installation.  Purchaser warrants that it shall not use such Equipment for such purposes, or permit others to use such Equipment while such Equipment is owned by Purchaser for such purposes unless such use is agreed to in writing by the Seller.  If, in breach of the foregoing, any such use occurs, Seller disclaims all liability for any nuclear or other damage, injury or contamination, and Purchaser shall indemnify Seller against any such liability, whether arising as a result of breach of contract, warranty, tort (including negligence), strict liability, indemnity or otherwise.

30.12 Miscellaneous Representations and Warranties»

.  The parties represent and warrant to each other that as of the date of this Agreement:

(a) the party is duly incorporated, organized, existing and in good standing under the laws of New York; (in the case of Seller) or [__________] (in the case of Purchaser); the party  possesses all requisite power and authority to enter into and perform this Agreement, to carry out the transactions contemplated herein, and to conduct business in each of the locations where any portion of the Scope of Work is to be performed; and has all legal power and authority to own and use its properties and to transact the business in which it is engaged and holds or expects to obtain all franchises, licenses, and permits required therefor;

(b) the party’s execution, delivery, and performance of this Agreement have been duly authorized by, and are in accordance with, its articles of incorporation and by-laws; this Agreement has been duly executed and delivered for it by the signatories so authorized; and this Agreement constitutes the party’s legal, valid, and binding obligation;

(c) no suit, claim, action, arbitration, or legal, administrative or other proceeding is pending or threatened against the party that would affect the validity or enforceability of this Agreement, the ability of the party to fulfill its commitments hereunder in any material respect, or that could result in any material adverse change in the business or financial condition of the party;

(d) Equipment of the same type and model number which is sold by Seller or its Affiliates to other clients is of the same manufacturing technology, includes the same principal components and has not demonstrated trends of failure; and

(e) the party is not in breach of, in default under, or in violation of, any applicable statute, law, ordinance, decree, rule, or regulation of any governmental authority, or the provisions of  its articles of incorporation or by-laws or any franchise or license, or in breach of, in default under, or in violation of, any provision of any indenture or any evidence of indebtedness or security therefor, lease, contract, license or other agreement by which it is bound if such breach, default or violation may result in a material adverse effect on the business or financial condition of the party; and the execution and delivery of this Agreement and the performance of its obligations hereunder will not constitute or result in any such breach, default or violation.

[THE REMAINDER OF THIS PAGE IS INTENTIONALLY LEFT BLANK]

IN WITNESS WHEREOF, the parties have caused this Agreement to be executed as of the date and the year first above written.

	AGENT:

ENRON NORTH AMERICA CORP.

By:  

Name:  

Its:  

ACKNOWLEDGED AND AGREED

PURCHASER:

E-NEXT GENERATION LLC



	By: Wilmington Trust Company, not in its

individual capacity, but solely as Manager  

By:  

Name:  

Its:  



	ACKNOWLEDGED AND AGREED

SELLER:

GE PACKAGED POWER, INC.

By:  


Name:  


Its:  





�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�page \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.


�PAGE \# "'Page: '#'�'"  ��Please do not type any text in this area.





WAS:84655.4 

