[image: image1.png]E CALIFORNIA ISO












UPDATE - OASIS/BEEP SPLIT/SC SPECIFIC PMI

INFORMATION& TIME-LINE OF EVENTS
REVISED INSTALLATION DATE: 05/23/01
 TIME:  19:00PST to 22:00PST
Conference Bridge Number**:
1-888-837-2407
Passcode: 362256

**The conference bridge will be activated for all SCs to utilize during the Installation 

UNSTRUCTURED TESTING (round 2)  DATE: 05/22/01  TIME: 10:00PST to 15:00PST

Please be advised that we will hold unstructured testing on the following system:  https://alhidev33/iso in response to requests made by several SCs.  We will use the same passwords as round 1 of unstructured testing.  Please contact Jim Blatchford at (916) 608-7051 if you did not participate in round 1 for passwords to the test system.   You will use the same Logon Ids as production SI.  

TIMELINE OF EVENTS PRIOR TO AND DURING IMPLEMENTATION

DATE
Time
Task

5/17/01

DONE
By the End of the Day
Issue notice to SCs about implementation.



5/18/01

DONE
10:00
Conference call 

· Review Implementation Plan

· Address questions/concerns regarding the Plan

· Review Contact information

· Review Information regarding unstructured testing

· Review Screen Prints

5/22/01
11:00-14:00
Unstructured Testing held on https://alhidev33/iso

Submit Day Ahead and Hour Ahead schedules in Unstructured environment – will not be running markets and producing final information and PMI unless otherwise agreed to.



5/23/01
09:00
HA Operator - Issue Reminder notice to Market Status e-mail list and through SI Messaging system  about early submission of Hour Ahead and Supplemental Energy Schedules to account for system down time .


14:00
Publish DA Finals in current format.  Implementation team to convert DA Default Hour Ahead schedules to beep-split format for use beginning Operating Hour Ending (HE) 1:00 Trade day  5/24/01.


Prior to 19:00
· SCs to submit their Hour Ahead schedules for HE 23&24 for trade date 05/23/01 before 19:00PST

· SCs to submit their Supplemental Energy schedules for hours 21-24 trade date 05/23/01 before 19:00PST
· Download All SC Specific History (Workspace, Schedules, and Usages) as all history will be removed as a result of the new implementation.



5/23/01


19:00-

19:45
· Run HE 22 Normal and Pre-run HA markets for HE hours 23&24 (05/21/01) transfer data to SI database and Publish.

· Notify SCs on the conference bridge as each hour’s hour-ahead finals and PMI are available to download (HE22-HE24). 


19:45-20:00
Allow for all SCs on bridge to verify downloads complete (with a maximum wait time of 15 minutes)  Remember Public PMI is still accessible from www.caiso.com OASIS site 


20:00
SI Down - All DA and HA Ancillary Spin and Non-Spin schedules for trade date 5/24/01 will be converted by ISO to the new format with the Contingency Flag set to default status, "No".  New Software Installed to systems and configured  (excluding contingency only units).


22:15-22:30
SI Up- SCs to submit any changes for HE 1 within 15mins.  Close HE1 with new software and publish as normal.

Last Revision: 05/18/2001

Page 1
BEEP Split 

INSTALLATION PLAN

