MARKETING AND COMMUNICATIONS PLAN FOR OLER

GOAL:
To make employees aware of services and to be seen as a neutral third party resource available to resolve

employee conflicts and or disputes.

Suggested Course of Action:

1. Decide upon and develop key messaging points for audience

2. Decide on name of group

3. Decide what employee services you want to highlight, and catalog those services

4. Develop look and feel that is unique to OLER, yet still falls within the Enron  branding guidelines

5. Establish presence on Enron Intranet

6. Review current literature and make certain that it is appropriate for audience, if not develop literature for target audience

7. Push service through internal marketing channels

8. Because Enron is such a large company and things change so quickly, some type of re-marketing needs to be done every three months.
ACTION ITEM
PERSON RESPONISBLE
DUE DATE
STATUS

Decide on messaging points
Michelle Cash, Valeria Hope—I will work with you on this.  We need 3 key thoughts that will create one overall message.  From this we can come up with a tag line.
By end of July 2001


Decide on Name of Group
Valeria to meet with Karen Denne to discuss and should be determined by next week
August 2, 2001


With messaging and name decided upon, work with Mark Wilson to develop several looks and feels that will be a unique identifier for the OLER group
Karen Moore, Mark Wilson
August 9, 2001


Present four possible looks to Michelle and Valeria for their final decision and approval  
Moore and Wilson
August 9, 2001


Create content for Intranet; work with web designers to create site; decide where it should be housed
Valeria Hope, Karen Moore and Johnny Hoang
August 16, 2001


Create new written materials (if needed)
Content to be provided by OLER; Moore and Wilson on layout and look and feel
August 16, 2001


Work with Courtney Votaw to create a series of 3 ETV ads to run during the week of August 19, 2001 
Moore, Votaw, and Bowne
August 16, 2001


Schedule an eSpeak with Michelle Cash
Moore to schedule with Palmer
TBD


Have banner created for infozone kiosk (with new look and feel).  Also have a monitor with new website up so that you can show it off to employees and demonstrate navigation if employees are interested
OLER to staff Infozone one day during week of August 19, 2001
Date TBD will check with Sally Alvarez


Decide on giveaway that can be handed out at the kiosk that feeds into the overall marketing theme
Moore to work with Valeria
ASAP


Once theme is decided upon and messaging is clear, speak to Karen Denne about having a short write up in Enron Business
Moore to work with Mary Clark and Karen Denne
TBD


Make certain that New Hire information is updated if employee literature changes
Valeria
TBD


Possible phone message from Jeff Skilling encouraging employees to stop by the kiosk
Moore to write script (Cash and Hope approve) and schedule recording date with Joannie 
TBD


Sending out a well-crafted email to employees telling them about the services and encouraging them to visit the kiosk
Moore to write and coordinate (Cash and Hope give final approval)
TBD


Possible ideas for future marketing would include:

--having a booth at a Big E Café.

--every three months running eTV ads.

--possible brown bag lunches where you can explore a specific topic

--possibly working with the Culture Committee on a joint venture

PAGE  
4

