DRAFT - Confidential
Page 1
08/03/00

ACTION
RESPONSIBILITY
DUE DATE
STATUS
ISSUES







Press Release


Palmer, Denne*
Miceli (buy side edits)


Aug. 8
Draft
Buy side review underway



Q & A Documents

· Deal/external

· Employee/internal

· Customer/partner


Denne/Ambler

Ambler/Vegas/Bonnard

Buyer Commercial/Miceli
Aug. 8

Aug. 8

Aug. 8
Not drafted

Draft

Not drafted
8-K, Board presentation will help; P & S Agreement needs more answers; ID more questions

Contact Lists/Protocol/Timing

· Media

· Gov’t Officials/Partners

· U.S./Europe

· CALME

· ESA

· EI

· APACHI

· In-country media conference call
Corp./In-country

Shapiro

Shapiro/Schroeder

McClelland/Haug

Bestard/Bannatine

Wilson/Cline

Dahlke&Merrill/McDonald

Zaayman/Regional PR
Announce date

Aug. 4

Aug. 4

Aug. 4

Aug. 4

Aug. 4

Aug. 7
Done

Open

Open

Open

Open

Open

Open

Open


Need to coordinate timing

Separate Government Regulator from Commercial

Key Messages


Denne/Kean/Palmer

(Vegas draft)


Aug. 4
Draft


ACTION
RESPONSIBILITY
DUE DATE
STATUS
ISSUES







Employee Communication

· Email

· Voice mail

· Video script/production

· Lay – Employee Meeting

· Sutton EI Meeting

· Enron TV

· e-Speak

· Corp. Intranet Updates

· E Biz & Enron Business

· EI bi-weekly e-mail newsletter

· EI employee hotline


Bonnard/Clark/Vegas/Ambler

Clark/Ambler
Clark/Vegas
Clark/Vegas
Clark/Denne
Ambler/Haux

Clark/Vegas
Sarah/Erin Rice/Ambler

Clark/Rigney/Vegas/Haux

Clark/Vegas
Ambler/Vegas/Feener

Bonnard/Vegas
Day prior

Day prior

Day prior

Announce date

Day after

Day after +

Two days after

Ongoing

Ongoing

Ongoing

Day after
Open

Open

Open

Open

Open

Open

Open

Open

Open

Open

Open
Ambler to supply 1st draft by 8/8

Vegas to supply 1st draft by 8/8

Vegas to supply 1st draft by 8/8







Asset Information/MAPS
Means/Haux
Aug. 4
Done
Re-format









Online Newsroom
Brandon Rigney/Means
Announce date
Open








Analyst’s Materials
IR
Announce date
Open










Message Conference Call
Dick Leibert
Day prior to ann.











Buyer Identity
Dick Leibert
ASAP
Unknown
Could be major part of story, spokesperson?









ACTION
RESPONSIBILITY
DUE DATE
STATUS
ISSUES







Ratings Agencies
Fastow
Immed. prior
Open










Translation
Ambler/Vegas
Day prior
Open


Spanish, Portuguese, Japanese, Korean and German







NGO Notification
Kimberly/Goldblatt/Miceli
Announce date
Open


Need to prepare contact list of NGOs







Stakeholder Letter


Miceli
August 4
Draft
Needed for country manager packet







Business Unit Communication Plans
Ambler/Vegas/Miceli/

Zaayman/Means
August 4
Draft
APACHI, CALME, EGE&P, ESA, India and Wind needed







Media/Stakeholder Tracking
Means/Zaayman
Announce Date
Open








Broadcast Addresses (How does it work)
Zaayman/Means
August 8
Open
Secure contact info. and input lists







Develop V & V Draft for EI
Miceli/Ambler
Week after
Open








Buyer Info. Q&As
Leibert/Ambler/Vegas
August 8
Open
Anticipate/position concerns







Multilateral Contacts
John Hardy/Miceli
August 4
Open
Lists and draft letter

* Lead contact for communication team in bold





