DRAFT OREGON TIMELINE—Not reviewed NNG

	
	Action
	Responsible 
	participants

	10.19
	Meeting in Salem with OPUC Staff and customer groups
	Susan Ackerman, Carla Kelley
	Ackerman, Kelley, Pamela Lesh, Paul Kaufman, Mike Morgan, NNG Counsel, Jay Dudley

	10.19
	Draft portions of OPUC testimony and application due
	Ackerman, Kelley, Morgan, NNG Counsel.  

Witnesses:  Dick Reiten, Mark Dodson, Bruce DeBolt, Peggy Fowler.
	State Team:  Ackerman, Kelley, Lesh, Kaufman, Morgan, NNG Counsel, Dudley

	10.29
	Draft Remaining Portions of testimony due 
	NNG Counsel and Morgan
	‘’

	11.07
	File OPUC testimony and applications
	‘’
	‘’

	11.07
	Open Data Room
	‘’
	‘’

	11.23
	OPUC Pre-Hearing Conference
	‘’
	‘’

	11.30
	OPUC Public Meeting 
	‘’
	‘’

	12.19--DEADLINE FOR OPUC, WUTC, SEC, FERC FILINGS

	02.01.02
	OPUC Staff and Intervenors Reply Testimony Due 
	‘’
	‘’

	02.22.
	OPUC—NNG/PGE file Rebuttal
	
	‘’

	02.25 – 

03.01.
	Settlement Conferences
	‘’
	‘’

	03.04 –

03.08.
	Hearings
	‘’
	‘’

	03.22


	Concurrent Opening Briefs
	‘’
	‘’

	04.05
	Concurrent Reply Briefs
	‘’
	‘’

	04.30
	OPUC Decision 
	‘’ 
	‘’


