Draft Confidential
Page 6
08/01/00

   Strictly Confidential

INDIA BUSINESS UNIT

Day 1-2: The Announcement (external)

India is 10.5 hrs ahead of CST (3:30 p.m. in Houston is 2:00 a.m. in Mumbai)

CORPORATE FOCUS 

(SELLER)



Action
Description
Responsibility
Timing

Issuing of Press Release
Distribution to identified list of media contacts in Houston and Business Unit offices 
Corp. PR / BU PR team
Day of Announcement, between 3:00 and 4:00 p.m. (CST)






Analyst & Media Call in Houston


Key players would discuss details of the transaction to the media 

(option: KL alone or KL, JS/JS)
Corp. PR
Day of Announcement

Between 3:00 and 4:00 p.m. (CST)






Newsroom 
On-line distribution of press release and a few standard FAQs: Business Unit and Corp. website
Corp. PR / BU PR team
Day of Announcement, one hour after release

INDIA BUSINESS UNIT FOCUS (BUYER)




                   Action
                   Description 
              Responsibility
          Timing

Spokesperson
These individuals need:

· Message

· Q&As

· Mumbai spokespersons handle local media inquiries re specific India issues

· Houston spokespersons international media inquires re specific India issues

· Media inquiries re all other issues referred to Corp. spokespersons 
Mumbai (local)

· Sanjay Bhatnagar

· Jimmy Mogal

Houston (international)

· John Ambler

· Johan Zaayman

Enron Corp.

· Mark Palmer

· Karen Denne
On-going



              
          

Stakeholders (in priority)

1. Chief Minister and state Energy Minister (Mumbai)

2. Chairman of MSEB and President of DPC (Mumbai)

3. Ministers of Power and Natural Gas (New Delhi)

4. Representatives of GE and Bechtel (Mumbai)

5. Key political leaders e.g. Sharad  

      Pawar of National Congress 

      Party

6. Others such as key lenders, customers, govt. officials


Personal visits and / telephone calls by Enron India CEO and management

Personal visit by Sanjay Bhatnagar plus personal letter from Joe Sutton  

Personal visit by Sanjay Bhatnagar plus personal letter from Joe Sutton 

Personal visit by Wade Cline and Ashok Mehta

Personal letter from Joe Sutton / Sanjay Bhatnagar with follow up call 

Personal visits and / or letters

Personal visits and / or letters 


Below individuals and India PR team

Jane Wilson & Sanjay Bhatnagar

Jane Wilson & Sanjay Bhatnagar

Ashok Mehta & Wade Cline

Jane Wilson and Sanjay Bhatnagar

Jane Wilson and Sanjay Bhatnagar

TBD


Set up appointments with relevant stakeholders two  days prior to release 

Day after Announcement - Mid morning 

As above

Day after Announcement - Mid morning 

Day after Announcement

Day after Announcement

Day after Announcement

Week One: 

INDIA BUSINESS UNIT FOCUS (BUYER)




Action
Description
Responsibility
Timing

Q&A update
Update internal Q&As for India
India PR team
On-going






News room
If applicable update FAQs: Enron India and Corp. website
Corp. PR/BU PR
On-going






Spokesperson (process continues)
These individuals need:

· Repeated/updated messages

· Q&As

· Mumbai spokespersons handle local media inquiries re specific India issues

· Houston spokespersons international media inquires re specific India issues 

· Media inquiries re all other issues referred to Corp. spokespersons


Mumbai (local)

· Sanjay Bhatnagar

· Jimmy Mogal

Houston (international)

· John Ambler

· Johan Zaayman

Enron Corp.

· Mark Palmer

· Karen Denne
On-going

Action
Description
Responsibility
Timing

Stakeholders

Other lenders, partners, govt. officials and Head of Business Associations such as CII, FICCI, US-India Chamber 
Personal visit and / or contact secondary stakeholders (deliver letter, phone call)
CEO and Top Management, India PR team
Second, third and fourth day after announcement






Media tracking
Track all news stories on wire services, TV, etc

Distribute clips to India leadership team, copy to Enron Corp. 
India PR team 


Daily after announcement






Interviews in country, e.g.

1.   Economic Times

2. Business India

3. Others, where applicable
Local interviews conducted with CEO and other spokespersons. 
India PR team to coordinate, Sanjay Bhatnagar
Second day and during week of announcement 






Stakeholder reaction
Evaluation from management team on their findings and reaction by stakeholders to new entity. Determine whether a visit by Corp. or Joe Sutton is needed to meet with key partners or other stakeholders.
Top Management and India PR team
Second day and during week of announcement

Day 1-2: The Announcement (internal)

CORPORATE FOCUS 

(SELLER)

Action
Description
Responsibility
Timing

Voice mail – notification of all employee meeting  (Houston employees)
Message from Enron Corp CEO and / or Newco CEO  
BU, Corp PR & HR, Ken Lay or Joe Sutton
Day of Announcement (Prior to release – exact time TBD)






Email – employee notification

(All Houston and international  employees)
Message from Enron Corp CEO and / or Newco CEO.  Include employee Q&As
BU, Corp. PR & HR, Ken Lay and / or Joe Sutton
Day of Announcement (Coincide with release)






All employee meeting (possible, tele conferencing, webcasting, video)  (All Houston employees and international employees)
Briefing to employees Enron Corp CEO and / or Newco CEO, defining benefits of the transaction
Corp, BU PR &HR, Ken Lay and / or Joe Sutton
Day of Announcement (One hour before or after  release)

INDIA BUSINESS UNIT FOCUS (BUYER)




Action
Description
Responsibility
Timing

Business Unit Management Team briefing


Management Team briefed in confidence by BU CEO about deal and upcoming internal and external communication roll-out
Sanjay Bhatnagar, HR, PR
Day of Announcement (Five hours prior to release)

Approx. 9:00 p.m. IST






In country employee meeting in 

Mumbai with teleconferencing or video link to New Delhi / Bangalore Ahmedabad 
CEO to meet with employees, defining benefits of the transaction. Answer general questions re deal and HR issues 
Top Management and HR
Day after announcement (Seven hours after release)

Approx. 9:00 a.m. IST

Action
Description
Responsibility
Timing

Feedback forum including eSpeak by Joe Sutton and HR
Collect suggestions, ideas, etc. from employees (could be a web-based tool). Enron intranet used for updates, new leadership details and policies. 
Corp PR, India PR team, HR, Joe Sutton, Sanjay Bhatnagar
Rest of week (next five days)

