Re: Deerfield Beach Facility:/Estimated Time Frames and Legal Fees for Obtaining Necessary Approvals


Greenberg Traurig

Memorandum
To
Via Email


Kay Mann, Esq.


Ben Jacoby


Steven Krimsky

From
Kerri L. Barsh, Esq.

Date
September 8, 2001
Re
Deerfield Beach Facility/


Estimated Time Frames and Legal Fees for Obtaining Necessary Approvals

Set forth below is a synopsis of the legal fees and time frames associated with securing the required developmental approvals or resolving all outstanding challenges to such approvals, as necessary for the construction and operation of the Deerfield Beach power plant.  At your request, we have included a range of the best and worst case scenarios for each of the approvals enumerated below and a brief explanation of any assumptions made to arrive at our conclusions.  At the end of each section of this memorandum, I have consolidated the various components into a single chart.  To prepare this memorandum, I have elicited the input of Debbie Orshefsky, Ryan Reetz, Elliot Scherker, Jeff Gilbert and Michael Cherniga, relative to their particular areas of expertise.  

In this memorandum, we have focused upon four areas of concern – namely, (i

 SEQ L4 \h \r0  QUOTE 
i
) the ongoing and annexation issues pertinent to the site development; (ii

 SEQ L4 \h \r0  QUOTE 
ii
) the pending air quality permit challenge before an administrative law judge; (iii

 SEQ L4 \h \r0  QUOTE 
iii
) the Broward County ordinance imposing a moratorium on the issuance of all licenses for power plants; and (iv

 SEQ L4 \h \r0  QUOTE 
iv
) the pending land use litigation initiated by Coconut Creek.

I. 
TIME CONSTRAINTS
For each of the four issues of concern, I have outlined below the projected time frames and milestones associated with the project approval process.  Please note that a number of the projections are simply estimates, based upon our prior experience in similar circumstances. 

A.
Zoning And Annexation Issues
	Key Deadlines:
	December 15, 2001 
	Deadline for obtaining final site plan approval.  “sign off” or DRC approval is lost;

	
	May 2002
	Earliest date by with Broward County Commission could cure the lack of Special Act authority required for independent, air permitting authority by enactment of a new Special Act;

	
	December 2002
	Earliest date under the Annexation Agreement by which the City of Deerfield Beach can change the zoning; and 

	
	March 15, 2003
	Deadline for obtaining building permit or site plan approval expires.


The dates enumerated above are concrete deadlines, with the exception of the May 2002 time frame for legislatively curing the County’s lack of air permitting authority over power plants. 

B.
Air Permit Challenge
	Best Case:
	Administrative Hearing Completion 
	End of November 2001
;

	
	Final Order
	April 2001 (4 months);

	
	Filing of Appeal
	May 2001 (1 month); and

	
	If Appellate Review is sought
	November 2001 – November 2002 (best to worst case ranges for conclusion of appeal) (6-18 months).

	
	
	

	Worst Case:
	Administrative Hearing Completion
	January 2002
;

	
	Final Order
	October, 2002 (8 months);

	
	Filing of Appeal
	November 2002 (1 month); and 

	
	If Appellate Review is sought 
	May 2003 – May 2004 (best to worst case ranges for conclusion of appeals) (6-18 months).


C.
Broward County Moratorium Issues
	Best Case:
	Filing of Declaratory Statement 
	October 2001 (depending on DEP discussions);

	
	Issuance of Statement after Publication
	Approximately January 2002;

	
	Filing of Appeal
	February 2002; and 

	
	If Appellate Review is sought
	August 2002 – August 2003 (best to worst case ranges for conclusion of appeals) (6-18 months).

	
	
	

	Worst Case
:
	Filing of Declaratory Statement 
	November 2001 (depending upon DEP discussions);

	
	If Petition for Administrative Hearing is filed
	December 2001 (filing with prescribed time frames after publication of request); 

	
	Administrative Hearing
	December 2002 (includes pre-hearing motion practice and hearing); and 

	
	If Appellate Review is sought
	Mid June 2003 – Mid June 2004 (best to worst case ranges for conclusion of appeals) (6-18 months). 


D.
Coconut Creek Lawsuit
	Best Case:
	Successful Motion to Dismiss
	October 8, 2001 (written order should be issued in a reasonable period of time thereafter). 

	
	
	

	
	If Appellate Review or Other Challenge to Order on Motion to Dismiss is sought
	April 2002-April 2003 (6-18 months).  

	Worst Case:


	Trial
	April 2003 – April 2005 (based upon the holding of a trial, after the denial of Enron’s motion to dismiss and unsuccessful appellate review) (1-2 years).  

	
	
	

	
	If Appellate Review is sought
	October 2003- October 2006 (based upon completion of a trial, to be held within the dates estimated above) (6-18 months).


The worst-case time estimate set forth above is quite speculative, given the early stage of the litigation and the number of litigation alternatives available, as outlined in the letter dated August 9, 2001, from Debbie to Kay.  A more precise estimate can be provided once we ascertain which, if any claims, survive Enron’s pending Motion to Dismiss, scheduled for hearing on October 8, 2001. 

E.
Time Constraints Recap
	Zoning and Annexation Issues
	December 15, 2001 
	Site plan approval deadline.   

	
	
	

	
	December 2002   
	Earliest date for any zoning change.

	
	
	

	
	May 2002 
	Earliest date for County to cure lack of air permitting authority. 

	
	
	

	
	March 15, 2003 
	Building permit issuance deadline.

	
	
	

	Air Permit Challenge
	May 2001 – 

November 2002 
	Final Order, exclusive of appeals.

	
	
	

	Coconut Creek Lawsuit
	November 2001 
	Successful dismissal, exclusive of any challenge. 

	
	
	

	
	May 2002 - May 2003 
	Successful resolution of motion to dismiss via appeal, certiorari or mandamus, exclusive of any further challenge.

	
	
	

	Broward County Moratorium Issues
	Mid February 2001 – Mid March 2001 
	Declaratory Statement issuance, exclusive of appeals or other challenges, administrative or judicial.


II.
LEGAL FEES

At your request, we have provided an estimate of the legal fees for obtaining the remaining developmental approvals or resolving the outstanding obstacles to obtaining such approvals.  Again, we have attempted to provide you with a reasonably accurate projection of the range of fees involved, notwithstanding the fact that the two pending litigation matters are just underway.

	A.
Zoning and Annexation

	

	
	Best Case: 
	$60,000 (exclusive of any appeal, Section 163.3215 claim, or other challenge), and

	

	
	Worst Case: 
	$85,000 (exclusive of any appeal, Section 163.3215 claim, or other challenge).


The majority of the work necessary to obtain final site plan approval by December 15, 2001, is primarily technical and the legal fees attributable to that effort are expected to be nominal.  Obtaining a building permit; however, will require a significant amount of work, which will not commence in full until we receive some level of comfort on the issuance of the air permit and favorable resolution of the Coconut Creek litigation.

	B.
Air Permit Challenge

	
	Best Case: 
	$150,000 (excluding appeal);

	

	
	Worst Case:  
	$500,000 (excluding appeal); and

	

	
	If Appellate Review is sought:  
	Add $35,000 to $60,000.


As you are aware, administrative litigation may prove complex or relatively simple, depending upon the level of opposition by the petitioners and the level of support by the Department of Environmental Protection.  The wide range of best to worst cost estimates provided above, reflects the uncertainty inherent at this early stage of the administrative hearing.  Please note that, in our letter dated August 14, 2001, we estimated that the legal fees for a hearing with an average level of opposition would be $200,000.


	C.
Coconut Creek Lawsuit

	
	Best Case:  
	$12,000 - $15,000 
	Granting of Motions to Dismiss

	
	
	

	
	With the following challenges:
	

	
	
	

	
	Defense of Appeal:  
	Add $30,000 - $50,000

	
	
	

	
	Defense of Certiorari Petition:  
	Add $40,000 - $60,000.

	
	
	

	
	Certiorari Petition or Petition by Writ of Mandamus:  
	Add $40,000 - $60,000

	
	
	

	
	Worst Case:   
	Add $100,000 - $500,000
	Full-blown trial, in event that motions to dismiss are denied and appellate review is unsuccessful.


	D.
Broward County Moratorium Issues

	
	Best Case:  
	
	$35,000

	
	
	
	

	
	Worst Case:  
	
	$50,000

	
	
	

	
	If Petition for Administrative Hearing is filed:  
	Add $100,000 - $250,000

	
	
	

	
	If appellate Review is sought:  
	Add $35,000-$60,000


The anticipated legal fees associated with an administrative hearing on the declaratory statement are lower than our prior estimates, based upon the fact that such a hearing would likely be narrow in scope and less factually intensive.

	E.  Legal Fees Recap

	
	Zoning and Annexation Issues:  
	$60,000-$85,000 (exclusive of challenges).

	
	

	
	Air Permit Challenge:  
	$150,000-$500,000 (exclusive of challenges).

	
	

	
	Coconut Creek Litigation:  
	$12,000-$72,000 (exclusive of a trial and based upon successful motion to dismiss and/or successful appellate-type review).

	
	

	
	Broward County Moratorium Issues:  
	$35,000-$60,000 (exclusive of appeals or administrative challenges).

	
	

	
	TOTAL
	$247,000 -$717,000 (exclusive of appeals or other challenges, judicial or administrative).


I trust that the foregoing has addressed your questions and has provided you with information helpful to your decision-making process.  Please contact me if I can be of further assistance on any of the matters contained herein.  Should you desire to reach me this weekend, please call me at (305) 632-0649 (cellular) or (305) 532-5140 (home). 

cc:
Debbie M. Orshefsky, Esq. (by fax)


Jeffrey Gilbert, Esq. (by e-mail)


C. Ryan Reetz, Esq. (by e-mail)


Elliot H. Scherker, Esq. (by e-mail)


Paul A. Savage, Esq. (by e-mail)

� Please note that we have not yet received final dates for the administrative hearing.  Thus, for purposes of the best case analysis, I have assumed completion of the hearing by the end of November 2001, assuming that the Administrative Law Judge will agree to a bifurcated hearing with the final portion of the hearing occurring on the dates in November for which he is currently available. 





� As noted above, because we do not have the final hearing dates, I have assumed that we can commence and conclude the hearing by the end of January 2002, given the ALJ’s present availability at that time. 


� The Broward County moratorium is currently scheduled to expire in May 2002, unless extended by the County Commission.  Consequently, should the County fail to extend the moratorium, Enron could elect not to proceed with any administrative or judicial litigation beyond the May 2002 expiration date. 





PAGE  
7

