
[image: image3.jpg]





[image: image2.png]




[image: image2.png]
[image: image3.jpg]
[image: image4.png]



[image: image5.png]



Contents

3Revision History


4Introduction


4Document Purpose


4Document Scope


4Stakeholders


Document Input
4
5Executive Summary


6Current Business Environment


7Proposed Business Environment


8Project Scope


8In Scope


8Not In Scope


8Benefits


Technical
8
Business
8
10Risks


10Project Schedule/Cost


10Project Quality


Project Requirements
10
project change management
10
11Assumptions


12Constraints


13Alternatives Considered


14Project Structure


15Resources / Timeline


15Resources


15Estimated Timeline


16Project Definition Number Request Form


16Project Information


16Estimated Costs


16WBS Components Needed


17Approval & Sign-off


18Project Number Assignment





Revision History


	Rev #
	Name
	Date
	Description of Changes

	1.0
	Monica Clay
	11/16/01
	Document Creation

	
	
	
	

	
	
	
	

	
	
	
	


Introduction

Document Purpose

The purpose of this Statement of Work is to provide a clear understanding of the business needs, project vision, scope and estimated costs associated with the project.  This document is tailored to equip the Business Sponsors and development team with adequate information to authorize development efforts.

Document Scope

The scope of this document includes a description of the current business, environment, proposed business environment and the scope of the project that will get the business from the current state to the proposed state.  Associated benefits, risks, estimated costs and prospective project timeline are also included.

This Statement of Work will be considered the first document of the Inception phase of the project.  Throughout this phase other documents deemed necessary for a successful completion of the project will be created.

Stakeholders

	
	Name
	Title

	Business
	
	

	     Business Sponsor
	Geoffrey Storey
	Director

	
	Jeff Gossett
	Director

	
	Kam Keiser
	Manager

	IT
	
	

	     IT Sponsor
	Stephen Stock
	Sr. Director

	
	Zhiyong Wei
	Sr. Director

	
	Jeremy Wong
	CGS Manager

	
	Sean Yang
	Technical Manager

	
	Karima Husain
	Project Manager

	
	
	


Document Input

	Name

	Karima Husain

	Sean Yang

	Mark Swaim

	

	


Executive Summary


The Consolidated Gas System project is intended to re-address the current gas deal capture and valuation systems due to new business requirements and to retire redundant legacy applications.  These legacy applications are not a part of the mainstream technology, which hinders expeditious modifications/enhancements and holds the systems to a non-standard way of communicating.  The new gas valuation system will utilize the components of the Global Valuation Framework to provide one valuation system for all gas valuation needs.

A piece of this large project entails revamping the way reports are generated and distributed to end-users.  Currently, reports are received from CPR and ERMS.  The reports are not customizable, not easy to find in the systems, and difficult to generate when needed.  A database was created by the end-users to shield themselves from the everyday hassles of creating reports. It contains the main reports they use for day-to-day business.   This database, WeaponX, meets their needs but has issues in itself.  The users are still not able to view all the reports they would like to see.   Another issue with this database is there is no version control.  The database lives on each desktop with no centralized storage for updates.

The users are in need of a more scalable and stable system that generates reports in a highly customizable fashion.  The Consolidated Gas System is prepared to deliver the previously stated and more.  The proposed solution will be done in a phased approach.  This will allow for current systems to handle the daily operations, while the new system moves into position without compromising business activities.

Current Business Environment


Gas risk managers and traders currently use CPR, WeaponX and ERMS to collect the reports they need from day-to-day.  CPR provides the basic information needed to review portfolios, make necessary corrections, and officialize portfolios.  CPR receives data feeds from ERMS and Sitara.  The reports generated contain a maximum of two months of data.  Risk managers find this inadequate to conduct business operations effectively.  It is relatively inflexible in the reports it provides and how they are provided.  Users often have to collect and merge data from different reports into an Excel spreadsheet and then manipulate the data to get the information they need.  This requires a large amount of manual effort on the user’s part.  Other issues with the CPR systems are:

· There is difficulty adding new reports to the system.

· There is difficulty modifying existing reports.

· Manual report distribution sometimes causes reports to be unavailable when needed. 

· Multiple linking among Excel files causes multiple reports to fail if one of the links is broken.

· Reports are too difficult to locate within the system query structure.

WeaponX, an Access database, was created to reduce the number of issues the risk managers face when generating reports.  The creation of the system increased proficiency.  WeaponX produces standard, pre-built reports.  The reports cover deal details, daily P&L, counterparty summaries, etc.  Although this reporting tool is more effective it has its limitations.

· The database does not contain all the elements that are used in equations.  The users have to rely on the ERMS database for additional information.  This is very time consuming.

· There is no security; therefore, anyone can access the database.

· The Desk Level Summary Report has two views because one view (Included Everything) gives all the information needed but inaccurately.  The Excludes Everything view removes the Transport and MTM information.

The user would like to see everything without skewing curve data.

· The database has to be on individual’s desktop to utilize.  Without a centralized location for the database there is no version control.

· There is no system administrator assigned for maintenance and updates.

· The database is populated with twelve (12) reports that are most common among risk managers and traders.  It does not allow users to create new reports.

· The following is a list of the most frequently used reports.

· Desk Level Summary Report

· Curve Shift Report

· New Deal Report

· Change Deal Report

Proposed Business Environment


The Consolidated Gas System (CGS) is intended to address the current gas deal capture and valuation system.  This new system will retire legacy applications in the current gas functionalities, and create a more advanced technical architecture.  This effort will address the immediate needs of the business community, and provide long-term benefits to the users.

There is a need to provide close to real time scalable, reliable, reusable, and ease of maintenance and functionality.  This new gas valuation development will utilize the components of the Global Valuation Framework.

Valuation Manager will be an object based reporting tool providing reporting with a single source reporting.  Valuation Manager will capture and store data for reporting purposes.  It will minimize the manual processes used to generate needed reports.  The user will have the ability to download the reports into an Excel spreadsheet for further data manipulation.  Deal views and portfolios will be enhanced.  A user-friendly front end GUI will be used to calculate books and generate reports.  The reports will be considered the liaison between the users and the valuation system.

The diagram below shows at a high level the process of the system.  Deals will be captured and the raw data will be sent to Valuation Manager and a Service Engine.  The Service Engine and Valuation Manager will listen to the same message from the deal capture system.  The Service Engine will provide Valuation Manager with calculated results.  Valuation Manager has the ability to return data to the Service Engine for updated information.  Security will be handled by the Deal Capture system to mandate report generation and distribution.
Reports Process


[image: image1.wmf]Deal Capture

System

EOL

TDS

Reports

Valuation Manager

Service Engine


All users will be able to view and value the deals at the book or portfolio level as the curve changes.  Values will be updated real time.  Risk managers will be able to view the latest values any time during the day.  Values will be officialized once they are evaluated.  Reports will be generated using Oracle Reporting.
Project Scope


In Scope

The scope will include the design, construction and delivery of a deal valuation reporting system.  The exact requirements will be documented in detail in the Requirement’s Document.  The following will be addressed:

Architecture

· The architecture will support the general reporting functions and the data that is provided.
· The chosen interface will be supported.
· The framework will be parallel to that of Global Valuation.
· Security to all functions and levels of data will be supplied appropriately.
Reporting Functions

· The interface will be built using HTML and Delphi.

· Reports will be easy to generate.

· Maintenance for many reporting errors will be easier to fix by the user.

· Individual users will be able to customize their reports list.

· Reports can be saved as a .pdf, .csv, or html file for viewing at a later date.

· Reports can be downloaded into an Excel spreadsheet for further manipulation.

· Reports will be able to be mailed to other users.

Officialization

· Officialization will be done at the portfolio level.  For each portfolio only one trader can be assigned; therefore, the system will allow officialization by trader.
Not In Scope

· Different views for data will require additional programming.  This will be reserved for another phase.

· There will not be a single button to officialize an entire desk.

· Reconciliation of reports from Sitara and TAGG will be possible with the inception of the financial deals to the project.

· Sitara reports will remain for the initial phase.  All reports presently generated using Sitara will continue to be generated using Sitara.  

Benefits


The following are benefits of the proposed system from a technical and business perspective.

Technical

· There would be lower post implementation maintenance costs.

· Easy to implement future modifications

· More scalable and stable

· Reports would be in a centralized location.

· Security control

· Version control

· Administrator assigned

· Eliminates report distribution problems

· The number of development languages will be reduced by creating one system to handle many jobs.

Business

· There would be a flexible reporting system using the latest technology.

· There would be an easier way to generate reports.

· There would be automation in creating reusable reports.

· Legacy systems such as CPR and ERMS will be retired.

· Value pricing and volume optionality is not available.

· Deals get booked to a mid-curve, not necessarily by the curve used in TAGG.

Risks


Many of the risks have been met and dealt with for the Global Valuation project.  This reduces the number of risks this project should encounter. The following is a list of possible risks.

1. Project Schedule/Cost

2. Project Quality

3. Project Requirements

4. Project Change Management

Project Schedule/Cost

The project has the potential to get off schedule and cost due to unforeseen circumstances.  Due to circumstances that are uncontrollable this risk has a medium rating.  Although, the framework has been laid out and requirements are being gathered there may be changes in specifications that may fall outside the scope of the project.  Management will be responsible for controlling changes in the scope.  Staying on schedule and in budget are both large parts in a successful project.

Project Quality

The quality of the project can be seen from different views.  From an end-user perspective the quality of the project is gauged by its usability, how efficient and effective the system proves to be.  The stakeholders will find quality defined in terms of rate of return.  Was the effort worth the return?  The development team sees quality from the eyes of the end-users, the group being serviced.  Qualifications are met if the end-users are satisfied.  This risk is low because all precautions are being taken to present a qualified system.

Project Requirements

Requirements have been gathered for the Global Valuation project, which CGS mirrors.  Many of the requirements are similar.  Interviews can be seen as a validation of previously gathered information; therefore, this risk has a low rating.

Project Change Management

Employees, end-users, are the backbone of any company.  Without their buy-in any project has the potential to face risks.  This risk has a medium rating because a successful project requires willing participants, users.  An effort has to be made gaining user confidence in the new system and making them a part of the process as a whole.  End-user interviews and training are ways to include them and reduce the risks.

Assumptions


· Development resources will be available in a timely manner. 

· Business sponsors will be available for questions and approvals in a timely manner.

Constraints


· Dedicated resources will be needed throughout the life of the project.

· The CGS project cannot impact the existing systems maintenance, production support, and modifications/enhancements.

· There may be limited access to stakeholders and end-users.

Alternatives Considered


During the planning stages of this project the only other viable alternative was to enhance the present systems.  The existing systems are familiar to the developer and end-users.  Although these systems are familiar, they are time consuming to maintain and hard to modify.  Familiarity is not most important with end-users.  All groups need an effective and efficient system.

Project Structure


The phases are included in a complete process are:


Inception:
Project Vision (Statement of Work)




Requirements Gathering




Preliminary Scheduling


Elaboration:
Detailed Design




Proof of Concept


Construction:
Implementation in a test environment


Transition:
Released into production

Project documentation will be created using templates from the Project Framework in Livelink.  Documents will be kept on the O:\ drive (following the path: O:\Consolidated_Gas\Gas Reporting) for usage by all and version control.

Meetings will be held everyday for the first couple of weeks to generate ideas and work through the Inception phase quickly.  As the project progresses the number of meetings per week will lessen.  The focus of the meetings will be on design, issues, and knowledge sharing.

The project team will consist of business stakeholders, IT stakeholders, a project manager, a technical manager, a system architect, two developers, a database administrator, a business analyst and experts in various areas when called upon.

Resources / Timeline


This section would include the initial and projected personnel (by role if specific resources are not yet identified).  Additionally, an estimated timeline for the project would be included (by phase and iteration).  A high-level cost estimate would be included with as much detail as known at the time.

Resources

	Role
	Resource
	Estimated Time Commitment

	Developer
	Sanjeev Gupta
	15 weeks (starting 12/12/01)

	Developer
	Farid Mithani
	19 weeks (starting 11/ 05/01)

	
	
	

	
	
	


Preliminary Estimated Timeline

A detailed timeline with be circulated throughout the project team within the next 2 weeks.

	Project Phase/Deliverable
	Duration
	Iteration End Date

	Inception
	Statement of Work
	2 weeks
	November 19, 2001

	
	Requirements Document
	2 weeks
	November 21, 2001

	
	Preliminary Scheduling
	2 weeks
	November 19, 2001

	Elaboration
	Detailed Design
	19 weeks
	February 28, 2002

	
	Proof of Concept
	
	

	
	
	
	

	
	
	
	

	
	
	
	


Project Definition Number Request Form
                                            

Project Information

	Project Name 
	Consolidated Gas System - Reports
	IT Project Manager 
	Karima Husain

	Project Start Date 
	11/05/01
	Est. Complete Date
	February 28, 2002

	Business Issue 
	The gas capture system and valuation systems need to be re-addressed strategically to adapt to new business requirements, retire redundant legacy systems, and reengineer technical architecture.  With this, the reporting generation will also be revamped to allow end users an easier and more effective way to receive data.

	Business Benefit 
	The new system will allow more flexible reporting generation that is described in the Benefits Section of the SOW.

	Responsible Cost Ctr.  
	103154

	IT Team Members 
	Listed above in the Resource section


Estimated Costs  (Please refer to the SOW for the Consolidated Gas System “overall” project.)

	Est. Hardware Cost (.90)
	

	Est. Software Cost (.91)
	

	Est. Enron Labor (.92) 
	

	Est. Contract Expenses (.93) 
	

	Est. Other Cost (.94) 
	

	Est. Total Cost 
	


WBS Components Needed  (Please refer to the SOW for the Consolidated Gas System “overall” project.)

– Please check (X) those that apply.

	Project Def.
	Project Type
	Home Department
	Cost Type

	C.xxxxxx
	
	.01 (Capital)
	
	.11 (103156/J. Johnson) 
	
	.90 (Hardware)
	

	E.xxxxxx 
	
	.02 (Expense) 
	
	.12 (103154/S. Stock) 
	
	.91 (Software)
	

	R.xxxxxx
	
	.06 (Maintenance)
	
	.13 (103157/R. Rao) 
	
	.92 (Enron Labor) 
	

	
	
	
	
	.14 (103153/J. Wong) 
	
	.93 (Contract Expenses) 
	

	
	
	
	
	.15 (103152/R. Burchfield) 
	
	.94 (Other Expenses) 
	

	
	
	
	
	.16 (103158/T. Yanowski) 
	
	
	

	
	
	
	
	.27 (103803&103366/H. Elrod) 
	
	
	


The following expense Project Definition Number was used to complete this Statement of Work document.  Close it upon assigning a new capital Project Definition Number: ______________________________  

Approval & Sign-off
 

 By signing this document, the Business Unit Sponsor agrees with the costs to be incurred during the life of the project that is outlined in this document.   The Business Unit Sponsor should provide project set up information, which is available from their accounting team.  Project work will not begin until project set up information and approval is provided.  

	Sponsor and Allocation Information

	Business Unit
	Enron North America

	BU Company #
	0413

	BU Cost Center*
	106298

	BU Commercial Team       (if applicable)
	Geoffrey Storey

Jeff Gossett

Kam Keiser


*If multiple cost centers benefit from this project, provide an allocation methodology and approvals from all sponsors.  Otherwise it is assumed that 100% of the costs will be directed to the cost center provided.    

Business Sponsor(s)


_______________________ 

Date_______________

Geoffrey Storey (Business Sponsor)



_______________________ 

Date ______________



Jeff Gossett (Product Manager)



_______________________ 

Date ______________



Kam Keiser (Product Manager)


IT Sponsor(s)



_______________________ 

Date ______________

Stephen Stock (IT Sponsor)




_______________________ 

Date ______________

Karima Husain (IT Project Manager)



Project Number Assignment


To be completed by ENW Accounting. 

	Project Definition #
	

	Date Assigned
	

	ENW Accountant
	


Statement of Work





Consolidated Gas System


Reports





On behalf of:


Enron Net Works











C. xxxxxxx





C. xxxxxxx























Enron Net Works
2
Project Phase: Inception

_1066820808.vsd

