Mr. Ben Jacoby

Enron North America

September 21, 2000

Page Two

g



S&S  Energy Products

Lee L. Johnson 


A GE Power Systems Business

General Manager North American Sales
P. O. Box 4414,  Houston, TX  77210-4414
E-Mail:  lee.johnson@ss.ps.ge.com

713-803-0952     Fax: 713-869-8365


September 28, 2000

Mr. Ben Jacoby

Enron North America, Agent for WestLB

1400 Smith Street

Houston, TX  77002

SUBJECT:
LM6000 Units #1 through 6 and Units #9 through 14

REFERENCE:
Contract ENA-2-99 (the “Contract”)

Dear Ben,

Currently, we have completed manufacturing fourteen of the twenty-four units. Recently, we provided the required Notice of Readiness to Ship that typically enables title transfer of the units referenced above per the terms of the Contract.  However, in the course of inspecting these units certain non-conformances and punch list items have been identified, and such items require corrective action by GE.  GE and Enron (as Agent) are working together to finalize this punch list. Based on the agreement contained in this letter, ENA (as Agent) agrees to accept GE’s notice of readiness to ship concerning these units.  

The agreement is as follows:

· GE will take the necessary corrective action prior to delivery of the units to the appropriate job sites, or as otherwise agreed to by GE and Enron, in accordance with Section 10.2.3 and Section 9.5 of the Contract.  If such corrections are not made prior to delivery of the units to the job sites, it shall be deemed that the Guaranteed Unit Delivery Dates for those units were not met.  

· Acceptance of the notice of readiness to ship does not constitute “acceptance” of the units.

· GE will maintain the insurance for risk of loss in transportation and storage.  

· GE will waive all storage costs related to the referenced units that would accrue through May of 2001. 

· GE agrees that by signing this letter Enron is not waiving any rights it or WestLB has regarding the equipment, including any rights to liquidated damages under the Contract, nor have the applicable Guaranteed Unit Delivery Dates been extended.

Please sign below if this letter correctly describes our agreement.

Sincerely yours,

Lee Johnson

General Manager

North American Sales

LJ:cs

Cc:  Kay Mann – Enron


Acknowledged and agreed:

Mike Storm - SSEP







Signed:____________________________







Title:______________________________







Date:______________________________







Enron North America, as Agent for Purchaser






Westdeutsche Landesbank Girozentrale,

New York Branch
