Crescendo Energy, LLC 

March 19, 2001

3-19-01 Status Report – Colorado Project

Page 3

CRESCENDO ENERGY, LLC

COLORADO PROJECT STATUS REPORT

3/19/01

1.0
SAN ARROYO VPP RESERVE REPORT

· Submitted package to NSA on PNP reserves.  

· NSA initiated its review on 3-15-01.

2.0
WILDHORSE ASSETS ACQUISITION

· Contacted by Cantera Resources, Inc., the successful bidder for the Wildhorse assets. 

· Cantera indicated desire to initiate serious discussions for moving the San Arroyo Entrada gas to the Badger Wash Gas Plant as well as “partnering” with Crescendo for gathering other area low-Btu gas.

3.0
WILDHORSE LITIGATION

· Preparing a detailed write up of each Contractual issue for use by legal.  

4.0
RESERVE ACQUISITIONS

4.1
North Badger Wash Entrada Pod

· Samson is forwarding a detailed list of acreage and interest of properties they would like to divest in the area.  Expect the list this week.  This acreage would be pulled out of a proposed bid package currently being assembled.

· Received a detailed list of acreage and interest from Maralex of all the acreage Maralex desires to sell (or farm-out) in the area.  This would include wells (low-Btu gas) in the Lipan Wash and Persigo Wash fields east of Badger Wash.  Crescendo is evaluating these leasehold positions.

· Strang & Associates has approximately 240 acres in the primary target area.  They also have an additional 706 acres in the area to be included in the acquistion.  Anticipate $15 per acre for a total cost of approximately $14,200.  Expect to get final agreement this week.

· Tom Brown owns approximately 240 acres in the North Pod area.  Verbal indication to landman is that TBI is willing to sell and we would get 100% interest in this acreage.  No price set yet, further discussion set later this week.  Also discussing additional South Canyon acreage for farm-out.

· Completed acquisition of Palo acreage. Palo is also proposing to farm-out an additional 1000 acreages in the area to us.  Currently evaluating and negotiating that arrangement.

· Sale notification for unleased BLM acreage nominated in this Pod is expected week of March 26, 2001.  Tentative sale date is May 10th.

4.2
Tom Brown South Canyon Assets

· Crescendo has reviewed its Reserve Evaluation Package with Chris Clark.  Crescendo to run sensitivities on porosity cut-off. 

· Crescendo will wait until execution of the PSA for the sale of the gathering assets before approaching.

4.3
CDX

· CDX has recently acquired large undeveloped acreage positions in the area previously owned by Retamco.  CDX is looking for a partner to develop large acreage position in the entire area.

· Met with CDX on February 26.  Crescendo is actively pursuing acquisition of South Canyon/Carbonera properties with two low-Btu shut-in gas wells and some undeveloped acreage.  Also would like to evaluate Moon Ridge acreage and acreage just north of San Arroyo field.  Moon Ridge acreage expected to have both good gas and low-Btu gas.

4.4
Beartooth

· Beartooth owners are discussing our proposal to acquire the assets in the area.  We have requested list of wells with working and net interests and undeveloped acreage in the area.  Waiting on response from Beartooth.

· Beartooth holds acreage adjacent to Lone Mountain’s Bar-X Entrada reserves. 

4.5
Harley Dome O & G / Helium Rights 

· Executed PSA with RMOC Holdings for acquisition of the oil and gas rights at Harley Dome.  A down payment of $11,250 has been put in escrow.  Acquisition price is $225,000.  Currently performing due diligence.

· Proceeding with negotiations with helium rights owner for acquisition of the helium rights (or processing) in the area.  Execution of the PSA gives Crescendo additional leverage in negotiations with the Helium Rights owner.

· Crescendo is formalizing geology and reserves, and plans to submit a funding request package to Crescendo Energy Members. This package will include the acquisition and development of the Harley Dome field as well as the acquisition of helium rights and helium recovery at the Badger Wash Gas Plant. 

4.6
Bridle Entrada Pod

· Landman working with National Fuel to farm-in Bridle Entrada Pod and other Bridle/South Canyon properties.  Waiting on detailed lease information from National Fuels.  Landman has meeting with National Fuels this week.

· Unleased BLM acreage nominated for this Pod has been accepted by the BLM.  Expect sale notification to be during 2nd quarter, 2000.

5.0
THIRD PARTY GAS PROCESSING PROPOSALS

· Written proposal sent to Lone Mountain week of January 12.  

· Lone Mountain has indicated it is seeking investor approval to proceed with project.  Due to his travel plans, we won’t hear from Jim Routson until the last week in March.

· Crescendo has requested assistance from ENA to modify a standard ENA processing agreement for this project.

6.0
BADGER WASH GAS PLANT

· BCCK has issued purchase order for Amine Plant.

· The sales tax issue review indicates sales taxes would be minimal.  Crescendo is waiting on final contract mark-ups of existing/proposed contracts from ENA tax experts. 

· Plan of Development and ROW application has been submitted for the plant and the Badger Wash gathering system.  

· Grand Valley Power has initiated the engineering design and ROW for the power line to feed the gas plant (at the Badger Wash site).  Crescendo has paid a $25,000 deposit to GVP for this work.

· Submitted application to Williams for new interconnect service for the Plant.  Williams expects to respond with estimate and timing within 3 weeks.

· Reviewed recommendation and bid tab for rental residue gas compressors for the Plant.  Concur with BCCK recommendation to go with a Universal proposal for 3 33% machines.  Evaluating maximum throughput per machine to determine if two machines can be used initially until additional gas (other than Badger Wash) is secured.  Evaluation expected to be complete by end of week.

· BCCK to issue new schedule based on February release date shortly. 

7.0
FIELD WORK

7.1
Workovers

· Waiting on weather and equipment to acidize new perfs on the San Arroyo #31.  Presently selling 35 mcfd from the new zone only.  Previously, the well was making 15 mcfd.

· San Arroyo #12 well is selling 460 mcfd from new perfs only.  Old zone will be added later.  Economics based on 148 mcfd increase from the new zone.   

· Completed water shut-off procedure in Upper Entrada on the San Arroyo #1 well.  Presently testing 760 mscfd and 50 bwpd at 180 psig ftp.  Prior to workover, well tested at 685 mcfd and 206 bwpd at 60 psig ftp. 

· First rig is on the San Arroyo #5 well to repair tubing/casing leak and test the Entrada formation.  Upon completion of this well, rig will be moved to San Arroyo #40 for Entrada testing.

· Second rig is on the San Arroyo #17 for a perf addition.  Waiting on acid breakdown of new perfs, scheduled for Tuesday, March 20th.   Upon completion of this well, rig will be moved to Badger Wash for Entrada tests in wells #31-1 and the #4.  

7.2
Production Tests (Gasjacks) 

· The Gasjack unit is being moved to the San Arroyo #32 well.  

