Confidential/DRAFT #2/AUG-3

ESA BUSINESS UNIT

Day 1-2: The Announcement (external)

Brazil and Argentina are two hours ahead of CST (3:30 p.m. in Houston is 5:30 p.m. in Sao Paulo and Buenos Aires.)

Bolivia is one hour ahead of CST (3:30 p.m. in Houston is 4:30 p.m. in Santa Cruz.)

CORPORATE FOCUS 

(SELLER)



Action
Description
Responsibility
Timing

Issue Press Release
Distribution to media contacts in U.S and international (will be issued in Spanish and Portuguese)

Following release, BU CEOs to hold 

Conference call with selected  newspapers. 
Corp. PR / BU PR teams

JB/DC to speak to reporters from newspapers in Brazil, Argentina and Bolivia.
Day of Announcement, between 3:00 and 4:00 p.m. (CST)






Analyst & Media Call in Houston


Key players would discuss details of the transaction to the media 

(option: KL alone or KL, JS/JS)
Corp. PR
Day of Announcement

Between 3:00 and 4:00 p.m. (CST)






Newsroom 
On-line distribution of press release and a few standard FAQs: Business Unit and Corp. website
Corp. PR / BU PR team
Day of Announcement, one hour after release

ESA BUSINESS UNIT FOCUS (BUYER)




                   Action
                   Description 
              Responsibility
          Timing

Spokesperson


These individuals need:

· Key Messages

· Q&As

· In country spokespersons handle  local media 

· International media inquires handled by ESA CEOs and Houston PR

· Media inquiries re all other issues referred to Corp. spokespersons 
Houston PR team

Houston PR team

ESA: JB/DC

Handle for Brazil, Argentina: and Bolivia:

· JB/DC

· KM

Enron Corp.

· Mark Palmer

· Karen Denne


On-going

Action
Description
Responsibility
Timing

Stakeholders 

1. Brazil:

· Minister of Energy

· ANEEL

· ANP

· Governor of Mato Grosso 

· SP State Energy Secretary and Regulatory Agency

2. Argentina

· Minister of Energy

· ENARGAS

3. Bolivia

· Minister of Hydrocarbons

· Minister of Environment

· SIRESE
Letter/Personal Visit/Call
Individuals below

JB/DC

LP

OG

MG

SH
Set up appointments with relevant stakeholders one or two days prior to date of announcement 

Day after Announcement 

Day after Announcement

Day after Announcement

Day after Announcement 

Day after Announcement 



Week One: 

ESA BUSINESS UNIT FOCUS (BUYER)




Action
Description
Responsibility
Timing

Q&A update
Update internal Q&As for ESA
ESA PR 
On-going






News room
If applicable update FAQs  on Corp. website
Corp. PR
On-going






Spokesperson (process continues)


These individuals need:

· Repeated/updated messages

· Q&As

· In country spokespersons handle  local media 

· International media inquires handled by ESA CEOs and Houston PR 

· Media inquiries re all other issues referred to Corp. spokespersons


ESA: Brazil: JB/DC  Argentina: MG 

Bolivia: SH

· JB/DC

· KM

Enron Corp.

· Mark Palmer

· Karen Denne


On-going

Action
Description
Responsibility
Timing

Stakeholders

1. Partners 

Brazil: 

Cuiaba (GasMat/GasBol)

CEG/CEGRio

Gaspart

BBPL (TBG/TBS)

Argentina:

TGS

Bolivia:

Transredes Shareholders

Other Stakeholders in Brazil, Argentina and Bolivia:

· Government officials

· Customers

· Lenders

· Suppliers

· Business/Industry Associations

· NGOs


Letter/Personal Visit/Call 

Letter/Personal Visit/Call 

Letter/Personal Visit/Call 

Letters/Visits and/or Calls BU managers (JB, JK, JB, DB, BW, RW, OG, PW, SH, MG)                
LP

RW

RW

PW

PW

SH 

BU Managers (JB, JK, JB, DB, BW, RW, OG, PW, SH, MG)
Second, third and fourth day after announcement






Media tracking
Track all news stories on wire services, TV, etc

Distribute clips to ESA leadership team, copy to Enron Corp. 
ESA PR team (KM, AD, MO, TA)


Daily after announcement






Press Interviews in country


Local interviews conducted with CEOs 


Country PR Offices to coordinate for JB/DC


Second day and during week of announcement 



Action
Description
Responsibility
Timing

Stakeholder reaction
Evaluation from business unit heads on their findings and reaction by stakeholders to new entity. Determine whether a visit by JB, DC or  Joe Sutton is needed to meet with key partners or other stakeholders.
Management teams and country PR team
Second day and during week of announcement

Day 1-2: The Announcement (internal)

CORPORATE FOCUS 

(SELLER)

Action
Description
Responsibility
Timing

Voice mail notification of all Houston employee meeting 
Message from Enron Corp CEO and / or Newco CEO  
BU, Corp PR & HR, Ken Lay or Joe Sutton
Day of Announcement /Prior to release 






Email – employee notification

(All Houston and international  employees)
Message from Enron Corp CEO and / or Newco CEO.  Include employee Q&As
BU, Corp. PR & HR, Ken Lay and / or Joe Sutton
Day of Announcement (Coincide with release)






All employee meeting (possible, tele conferencing, webcasting, video)  (All Houston employees and international employees)
Briefing to employees Enron Corp CEO and / or Newco CEO, defining benefits of the transaction
Corp, BU PR &HR, Ken Lay and / or Joe Sutton
Day of Announcement (One hour before or after  release)

ESA BUSINESS UNIT FOCUS (BUYER)




Action
Description
Responsibility
Timing

ESA CEOs brief business unit heads


Business unit heads briefed in confidence by ESA CEOs about deal and upcoming internal and external communication roll-out
JB/DC, JB, MP, KM
Day of Announcement (12 hours prior to release)






In country employee meetings in Sao Paulo, Rio, Cuiaba, Salvador, Buenos Aires, Santa Cruz and other locations in region where asset/office is located


Business unit heads to meet with employees, defining benefits of the transaction. Answer general questions re deal and HR issues 
Business unit heads and HR


Day after announcement – morning (times vary with location)








Feedback forum including eSpeak by Joe Sutton and HR
Collect suggestions, ideas, etc. from employees (could be a web-based tool). Enron intranet used for updates, new leadership details and policies. 
Corp PR, ESA PR team, HR, Joe Sutton, JB/DC, business unit heads
Rest of week (next five days)

KEY: 
JB-Jim Bannantine


DC-Diomedes Christodoulou


OG-Orlando Gonzalez


JB-Jose Bestard


LP-Laine Powell


SH-Steve Hopper


MG-Mike Guerriero


PW-Pete Weidler


RW-Rick Waddell


JK-Joe Kishkill


DB-Don Black


BW-Brett Wiggs


MP-Miguel Padron


KM-Keith Miceli


AD-Adriana Dominguez


TA-Teresita Arandia


MO-Marta Ortiz


1
9

