Proprietary and Confidential


ETS Asset Development

PROJECT SUN DEVIL

EXECUTIVE SUMMARY

I.  Description / Scope

Project Sun Devil is a $911 million expansion of Transwestern Pipeline’s interstate natural gas system.  The project is designed to move incremental San Juan and Rocky mountain gas production through 490 miles of new pipe looping and compression to serve growing Phoenix, AZ and Southern California markets.

The project begins in San Juan County, NM by looping TW’s existing San Juan lateral.  The 36-inch loop would start at the Blanco hub going south to the Gallup compressor station.   Modifications would need to be made at both the Bloomfield and Gallup, NM compressors plus modifications to the Blanco hub facilities.  A new compressor may also be required at the Standing Rock location in the Navajo territory depending on customer demand.

The mainline looping going west from Gallup will consist of 224 miles of 36-inch pipe.  At Flagstaff, AZ, a new 169 mile 36” lateral will be built running south to Phoenix in Maricopa County, AZ.  To minimize cultural and environmental impacts, the Phoenix lateral will follow existing rights-of-way where possible.

At Phoenix, the lateral would loop to the west to access the growing gas-fired electric generation market and a newly proposed salt dome storage cavern.  Phoenix area gas demand is expected to grow by over 1.5 Bcf/day by 2003 with the start-up of these new generators.  

The project would be sold according to the path and capacities shown below:

I. A.  Capacities 

San Juan Lateral 


780,000 MMBtu/d

Thoreau west to Cal Border

310,000 “         “

Phoenix, AZ



500,000 “         “

I. B.  Timing:

Binding Open-season closed August 30, 2001

FERC application September 2002

Submit binding contracts and EIS to FERC by October 2002

Pipe in-service date Q3 2004

II.  Commercial Summary

II. A. Gas Market

The Project’s goal is to deliver incremental gas supplies from the transport-constrained San Juan basin to the growing Phoenix market.  The Phoenix area has been the 2nd fastest growing region in the continental U.S. for the last several years.  The area has also been electric supply constrained and local utilities import as much as 25% of their generation needs annually.    

To address area growth, local utilities and independent power producers have successfully petitioned the Arizona Corporation Commission to allow new large-scale gas-fired generation plants to be constructed.  Developers such as Sempra, PG&E, Duke, Reliant Energy, Panda International, and AZ Public Service have all broken ground on new generation projects (see attached plant listing in Section II E).

The problem these new generators face is the lack of firm pipeline transport capacity.  Some generators hold firm capacity on El Paso Natural Gas (EPNG) due to their existing full-requirements contracts; others have had to rely on the secondary release market or marketers who hold firm transport.  Incremental transport demand from these new generators is projected to be as high as 1.5 Bcf/day.

II. B.  Transport Market

To date, EPNG has been the sole pipeline serving the needs of Phoenix.  EPNG shippers source gas supply from both the Permian and San Juan basins.  Population growth in the Southwest over the last several years has put a severe strain on EPNG’s capacity, especially in peak summer cooling and winter heating demand periods.  This was evidenced most recently during the winter of 2000-01 when shippers holding firm contracts were cut upwards of 40% of their contract demand and gas sold at Cal border in excess of $60.00 MMBtu.  These figures do not include the anticipated demands created by the new electric generators when they begin plant start up in 2002-03.

As a result of 2000 – 2001 winter transport debacle, EPNG shippers have protested to FERC to revise the method in which EPNG allocates its system.  Shippers have also accused EPNG of over-subscribing its pipeline capacity.  Shippers estimate EPNG being short capacity ranging from 300,000 MMBtu/d to as much as 1 Bcf/d, again, exclusive of the new demands from local area generators.

Part of the constraint on EPNG is due to the Full Requirements (FR) contracts held by LDC’s, generators, and some industrial concerns.  Under the FR contracts, EPNG is obligated to serve 100% of the FR needs, sometimes at the expense of contract demand (CD) customers.  FERC is currently exploring ways to either abrogate or restructure these FR contracts.  Settlement is expected to occur sometime in the first half of 2002.

II. C. Competition

The following chart illustrates the rate differences between existing El Paso transportation and proposed Sun Devil rates plus a combined Sonoran / Sun Devil project rate.  The biggest cost issue for prospective shippers on Sun Devil to this point has been fuel rates.  

[image: image1.wmf]Fuel @

El Paso

Reservation

Resv Adder*

Commodity

ACA/GRI

GRI Surcharge

3.47%

Total

SJ - Arizona

0.25171

$    

 

0.03522

$    

 

0.01960

$     

 

0.00910

$  

 

0.00296

$    

 

0.07981

$  

 

0.39840

$      

 

Perm - Arizona

0.25171

$    

 

0.03522

$    

 

0.02230

$     

 

0.00910

$  

 

0.00296

$    

 

0.08675

$  

 

0.40804

$      

 

Mainline Shorthaul Max rate

0.10988

$    

 

0.01335

$    

 

0.00300

$     

 

0.00910

$  

 

0.00296

$    

 

0.00920

$  

 

0.14749

$      

 

* Reservation adder ends 1/1/04

Transwestern - Sun Devil

4.75%

20 yr, 1 part rate

0.5340

$      

 

0.00910

$  

 

0.00296

$    

 

0.1093

$    

 

0.6553

$       

 

KMI Flagstaff

Sun Devil

Subtotal Resv

1.05%

Sonoran / TW

0.280

$       

 

0.236

$       

 

0.516

$        

 

0.00910

$  

 

0.00296

$    

 

0.0242

$    

 

0.5402

$       

 

Natural Gas Price

San Juan

2.30

$         

 

Permian

2.50

$         

 


EPNG

El Paso Natural Gas has two mainline transmission systems, north and south, that traverse Arizona flowing east to west.  El Paso has several options to compete with Sun Devil.  To compete on a heads-up basis, El Paso would need to construct a similar project of similar size from the San Juan basin.  Any further expansion of EPNG’s north system is unlikely due to current pipe diameter constraints.  Another critical factor is EPNG has only recently begun re-negotiating their ROW contract with the Native American Indian tribes on whose property a majority of the north system lies.  El Paso would be cautious to put any new assets at risk until this ROW is settled.  TW settled its Navajo ROW in 2001, so we have a basis for knowing how much ROW will cost for the Project.

In 2000, EPNG purchased the All American crude oil pipe system and converted it to natural gas service (effective August 2001).  All American roughly parallels the existing EPNG south system.  By adding compressor stations to All American, EPNG could boost capacity by as much as 500,000 MMBtu/d to the California border.  Estimated cost of this expansion is $330 million.  However, the gas source would be the Permian basin and this new capacity would not be enough to serve all the market needs.

Sonoran

Kinder-Morgan – KMI, with their partner Calpine, have proposed a new 750,000 MMBtu/day gas transmission system (the Sonoran Project) that parallels the existing TW system in the San Juan basin all the way to the California border at Needles (phase I).  A large portion of Sonoran Phase I literally would reside in the same Navajo ROW as TW.  Sonoran Phase II proposes to run north from Needles up to Sacramento, CA.  KMI desires to compete with the PGT system in California to meet the needs of new California electric generators.  

With the currently depressed western electric market and Calpine’s recently announced cutback in new project development, it may be that this project is no longer viable.  KMI informed us they were going out for a second open season in January 2002, but to date we have not seen anything.  In addition, Williams has re-floated their Ruby Pipeline project that will compete directly with Sonoran for the northern California market.  Williams has the advantage in that they will source cheaper gas to northern California via Opal, Wyoming than will Sonoran from San Juan.

Desert Crossing

This new 10 Bcf storage project is sponsored by Salt River Project, Sempra Energy, and Allegheny Energy.  The sponsors hope to build, based on a successful open season, a high-capacity salt dome storage cavern near Kingman, AZ.  The project would source gas via a new lateral from Kern River, and re-deliver gas to existing lines owned by TW, El Paso, PG&E, So-Cal, and Questar.  They also propose to build a new 200-mile lateral south from Kingman and tie into El Paso’s south system.  The sponsors then hope to move gas both east (via displacement) and west to electric generation plants.  Storage rates are $0.19/MMBtu plus another $.24/MMBtu for pipeline transport.  The project is expected to be built in 2.5 Bcf increments.

Copper Eagle

This 10 Bcf storage project was announced in the fall of 2000 and is located on the west side of Phoenix on a salt dome near Luke Air Force Base.  The sponsors include Arizona Public Service, Crystal Gas, and the French utility, Gaz de France.  Designed to serve the high peaking needs of Phoenix area power generators, it is proposed to be built in 2.5 Bcf increments.  Projected rates are $0.40/MMBtu plus injection and withdrawal fees.  Their issue, in addition to the brine disposal during construction, is getting pipeline capacity to fill the storage without a Phoenix area expansion project such as Sun Devil.  The sponsors expect to file their FERC application in March 2002.

Pataya / Red Lake

This 12 Bcf storage project is proposed by SouthWest Gas and Aquila Energy.  Pataya is located in the same salt formation as Desert Crossing near Kingman.  They propose to build the facility in increments of 6 Bcf and claim to have all the necessary water and disposal permits necessary.  Pataya proposes to source and redeliver gas to TW and El Paso.

II. D.  Gas Supply

The Sun Devil project will source gas from the prolific San Juan production basin plus use existing TW interconnects with pipelines connected to Rocky Mountain producers.  Historically, San Juan-sourced gas prices have been depressed relative to Permian gas due to the lack of San Juan transport capacity. Both TW and EPNG systems in the San Juan basin have been completely sold out for several years and maintain 95+% utilization rates.  

San Juan and Rocky Mountain supply projections completed by a 3rd party consultant indicate enough supply reserves exist to fill the demands of the Project.  However, there is not enough supply to fill both Sun Devil and KMI’s Sonoran project.  TW would also be able to source a small amount of incremental supply from the Panhandle or Permian basins.

II. E.  Prospective Shippers

The table below outlines the prospective shippers for the Sun Devil project and the electric generation plants proposed or under construction.

	Sun Devil Power Generators
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	In-Service
	
	MMBtu/d
	Sun Devil 

	Developer
	Plant
	Cap. Mw
	Date
	Status
	Gas Demand
	Est. Demand

	AZ Public Service
	W Phoenix
	        366 
	Old
	Operating
	          97,262 
	

	AZ Public Service
	W Phoenix
	        120 
	6/1/01
	Operating
	          20,736 
	

	SRP
	Agua Fria
	        600 
	Old
	Operating
	          97,600 
	          30,000 

	Duke
	Arlington Valley
	        550 
	6/1/02
	Under Construction
	        125,000 
	          50,000 

	Pinnacle West
	Redhawk
	     1,160 
	6/1/02
	Under Construction
	        210,000 
	        100,000 

	Sempra Energy
	Mesquite
	     1,300 
	1/1/03
	Under Construction
	        220,490 
	 ?? 

	Panda Energy
	Gila Bend
	     2,300 
	3/1/03
	Under Construction
	        390,098 
	        100,000 

	PG&E
	Harquahala Valley
	     1,083 
	6/1/03
	Under Construction
	        178,825 
	 ?? 

	Dynegy, Xcel, SRP
	Kyrene
	        265 
	6/1/03
	Advanced Devlpmt
	          45,315 
	          20,000 

	Pinnacle West
	West Phoenix
	        500 
	6/1/03
	Under Construction
	          86,352 
	          50,000 

	Energy Dev Group
	Gallup
	     1,200 
	7/1/04
	Early Development
	        216,000 
	        216,000 

	
	
	     9,444 
	
	
	     1,687,678 
	        566,000 


III. Project Economics

III. A. Assumptions

The project assumes a 15% return on equity using an 80/20 debt/equity structure on a $911million capital cost.  Debt interest rate is estimated at 7.5% with an economic project life of 30 years and 100% load factor.  Fuel is estimated at the current TW fuel rate of 4.75% for the first few years of the project life then converting to a fuel tracker with the next TW rate case in 2006.  O&M expense escalates at 3% per annum.  Near worst-case scenarios for ROW acquisition have been used considering the 220 miles of construction through Native American tribal lands.  This assumption is valid considering TW’s recent re-negotiation of Tribal ROW.  The rate schedule below is based on levelized assumptions for the various terms:

[image: image2.wmf]Pipe Material

168,064,100

        

 

18%

Construction

290,934,619

        

 

32%

Engineering

33,087,533

          

 

4%

ROW

64,989,049

          

 

7%

Escalation / Overheads

165,565,736

        

 

18%

Gross Receipts

22,647,874

          

 

2%

Compression

166,386,175

        

 

18%

911,675,086

$      

 

100%


IV. Project Cost

IV. A. Engineering

The project cost estimate is based on 2001 dollars and is escalated for inflation to the time period when construction will begin.  The estimate is considered a “Level A+” estimate that, barring unforeseen issues, should not increase any higher.  For a more detailed and exacting Level B estimate, additional development monies would need to be spent.  Below is a description by pipe segment of the facilities required:

•San Juan lateral – 780,000 MMBtu/d
–97 miles of 36” loop

–Standing Rock compressor station


–Compressor mods at Bloomfield, Bisti, and Gallup

•Mainline  – 810,000 MMBtu/d

–224 miles of 36” loop

–New compressor at station 4, 1.5, and Kingman

–Compressor mods at stations 2 and 3

•New Phoenix lateral  - 500,000 MMBtu/d

–168.8 miles of 36” line, no compression

–Delivers to Copper Eagle storage, Panda lateral from El Paso south system

[image: image3.emf]Years 15 20 25 30

San Juan 0.153 $     0.149 $     0.145 $     0.142 $    

Main Line 0.169 $     0.150 $     0.140 $     0.127 $    

Phoenix (incl. Panda lateral) 0.245 $     0.236 $     0.230 $     0.225 $    

Total Rate MMBtu 0.567 $     0.535 $     0.515 $     0.494 $    

Sun Devil Project Costs:

IV. B. Environmental

Third-party contractors were commissioned to perform an initial site survey along the proposed ROW path.  Inquiries were made to local state agencies and conservation groups; no material “deal-killer” issues were discovered.

V. Regulatory

A budget has been established for costs necessary to get the Sun Devil project application filed with the Federal Energy Regulatory Commission.  The $8,750,000 budget includes costs for regulatory filing, right-of-way due diligence, field surveys, aerial photography, environmental due diligence, and project engineering.

VI. Administration


Team Members (see attached page)


Project costs spent as of January 22, 2002 equal $100,976.70 of $200,000 budget.


File directory (see attached page)

� EMBED Excel.Chart.8 \s ���





� EMBED Excel.Sheet.8  ���








Jkh:Sun Devil summary
Page 6 of 7

[image: image4.wmf]Pipe Material

168,064,100

        

 

18%

Construction

290,934,619

        

 

32%

Engineering

33,087,533

          

 

4%

ROW

64,989,049

          

 

7%

Escalation / Overheads

165,565,736

        

 

18%

Gross Receipts

22,647,874

          

 

2%

Compression

166,386,175

        

 

18%

911,675,086

$      

 

100%

[image: image5.wmf]Fuel @

El Paso

Reservation

Resv Adder*

Commodity

ACA/GRI

GRI Surcharge

3.47%

Total

SJ - Arizona

0.25171

$    

 

0.03522

$    

 

0.01960

$     

 

0.00910

$  

 

0.00296

$    

 

0.07981

$  

 

0.39840

$      

 

Perm - Arizona

0.25171

$    

 

0.03522

$    

 

0.02230

$     

 

0.00910

$  

 

0.00296

$    

 

0.08675

$  

 

0.40804

$      

 

Mainline Shorthaul Max rate

0.10988

$    

 

0.01335

$    

 

0.00300

$     

 

0.00910

$  

 

0.00296

$    

 

0.00920

$  

 

0.14749

$      

 

* Reservation adder ends 1/1/04

Transwestern - Sun Devil

4.75%

20 yr, 1 part rate

0.5340

$      

 

0.00910

$  

 

0.00296

$    

 

0.1093

$    

 

0.6553

$       

 

KMI Flagstaff

Sun Devil

Subtotal Resv

1.05%

Sonoran / TW

0.280

$       

 

0.236

$       

 

0.516

$        

 

0.00910

$  

 

0.00296

$    

 

0.0242

$    

 

0.5402

$       

 

Natural Gas Price

San Juan

2.30

$         

 

Permian

2.50

$         

 

_1073465434.xls
Pre-Pay

		

		Year				1		2		3		4		5		6		7		8		9		10		11		12		13		14		15		16		17		18		19		20

						$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247		$   22,319,247

		NPV		$256,000,000

		Volume: MMBtu/d		200,000

		Rate $/MMBtu		$   0.30574

		Discount Factor		6%

		Cash Pre-Pay Target		$   256,000,000

		Assumptions:





Compare

		

																Fuel @				Net after Resv

		El Paso				Reservation		Resv Adder*		Commodity		ACA/GRI		GRI Surcharge		3.47%		Total		Adder ends

				SJ - Arizona		$   0.25171		$   0.03522		$   0.01960		$   0.00910		$   0.00296		$   0.07981		$   0.39840		$   0.36318

				Perm - Arizona		$   0.25171		$   0.03522		$   0.02230		$   0.00910		$   0.00296		$   0.08675		$   0.40804		$   0.37282

				Mainline Shorthaul Max rate		$   0.10988		$   0.01335		$   0.00300		$   0.00910		$   0.00296		$   0.00920		$   0.14749		$   0.13414

				* Reservation adder ends 1/1/04

		Transwestern - Sun Devil														4.75%

				20 yr, 1 part rate		$   0.5340						$   0.00910		$   0.00296		$   0.1092		$   0.6553

				SFV (25 yr, 80/20)		$   0.3400				$   0.2200		$   0.0092		$   0.0030		$   0.1092				$   0.6815

						KMI Flagstaff		Sun Devil		Subtotal Resv						1.05%

		Sonoran / TW				$   0.280		$   0.236		$   0.516		$   0.00910		$   0.00296		$   0.0242		$   0.5402

		Natural Gas Price

				San Juan		$   2.30

				Permian		$   2.50



&L&F&R&D



Sheet3

		






_1073393381.xls
Base

		Sun Devil Project Costs

		Base Case

				San Juan		Cost/Mile				ML Loop		Cost/Mile				Phoenix lateral		Cost/Mile				Panda Extension		Cost/Mile				Total

		Pipe material		32,052,398		330,539				63,682,336		284,296				37,539,978		281,114				10,829,238		306,864				$   144,999,900

		Coatings		4,299,511		44,339				9,572,841		42,736				5,692,752		42,630				3,007,870		85,233				$   22,702,678

		BOP Material		332,844		3,432				447,944		2,000				468,244		3,506				138,144		3,915				$   1,396,115

		Subtotal pipe costs		36,684,753		378,310				73,703,121		329,032				43,700,974		327,250				13,975,252		396,012				$   169,098,692

		Freight		2,567,933		26,482				5,159,218		23,032				3,070,156		22,991				1,028,164		29,135				$   11,897,975

		Construction		57,074,838		588,582				122,004,457		544,663				74,811,079		560,215				25,218,774		714,615				$   280,802,608

		Total Raw material costs		96,327,524		993,374				200,866,796		896,727				121,582,209		910,455				40,222,190		1,139,762				$   461,799,276

																														% of Direct cost

		Engineering		2,576,674		26,572				5,934,091		26,491				3,623,899		27,137				1,043,336		29,565				$   13,258,201		2.87%

		As-builts D&R		166,980		1,722				387,750		1,731				230,514		1,726				62,370		1,767				$   852,793		0.18%

		Project Mgmt		725,543		7,482				1,674,612		7,476				1,000,370		7,491				263,834		7,476				$   3,686,808		0.80%

		Const Mgmt		971,331		10,017				2,242,002		10,009				1,339,178		10,028				352,330		9,984				$   4,934,895		1.07%

		Builders risk insurance		108,501		1,119				218,486		975				127,425		954				44,307		1,256				$   501,768		0.11%

		District labor		485,000		5,002				1,120,000		5,000				665,000		4,980				175,000		4,959				$   2,459,981		0.53%

		Environmental		1,494,702		15,414				3,449,893		15,401				2,060,877		15,433				543,528		15,402				$   7,595,248		1.64%

		ROW		18,293,613		188,652				28,207,165		125,925				11,746,235		87,960				6,742,036		191,047				$   65,391,587		14.16%

		Indirect Costs		24,822,344		255,980				43,233,999		193,009				20,793,498		155,710				9,226,741		261,455				$   98,681,280		21.37%

		Subtotal Costs		121,149,868		1,249,354				244,100,795		1,089,736				142,375,707		1,066,165				49,448,931		1,401,217				$   560,480,556

																														% of Subtotal

		Escalation		8,594,355		88,629				17,306,307		77,260				10,093,345		75,583				3,509,536		99,448				$   39,745,015		7.09%

		Contingency		12,925,922		133,298				26,028,710		116,200				15,180,405		113,677				5,278,347		149,571				$   59,776,559		10.67%

		Overhead		2,853,403		29,426				5,748,716		25,664				3,352,989		25,108				1,164,736		33,005				$   13,200,042		2.36%

		AFUDC		11,641,884		120,057				23,454,762		104,709				13,680,195		102,443				4,752,124		134,659				$   53,856,173		9.61%

		Gross Receipts		10,496,293		108,243				7,409,298		33,077				3,508,389		26,272				1,233,894		34,964				$   22,815,466		4.07%

		Subtotal		46,511,857		479,652				79,947,793		356,910				45,815,323		343,083				15,938,637		451,647				$   189,393,255		33.79%

		Total Pipe costs		167,661,725		1,729,006				324,048,588		1,446,645				188,191,030		1,409,248				65,387,568		1,852,864				$   749,873,811

		Compression

		Standing Rock		25,345,871						29,661,977						Station 4

		Bloomfield		29,801,328						4,866,197						Station 3

		Gallup		6,377,259						4,124,518						Station 2

		Blanco Hub		1,746,987						29,181,251						Station 1.5

		Bisti		2,611,238						29,406,162						Kingman

		Needles		3,263,387

		Total Compression		69,146,070						97,240,105																		$   166,386,175

		Grand Total Project																										$   916,259,986

		Miles		97						224						134						35						$   490



&L&F&C&A&R&D



Compression

		Sun Devil Project Costs

		Case II - Compression reduction, no district labor, escalation, or AFUDC

				San Juan		Cost/Mile				ML Loop		Cost/Mile				Phoenix lateral		Cost/Mile				Panda Extension		Cost/Mile				Total

		Pipe material		32,052,398		330,539				63,682,336		284,296				37,539,978		281,114				10,829,238		306,864				$   144,999,900

		Coatings		4,299,511		44,339				9,572,841		42,736				5,692,752		42,630				3,007,870		85,233				$   22,702,678

		BOP Material		332,844		3,432				447,944		2,000				468,244		3,506				138,144		3,915				$   1,396,115

		Subtotal pipe costs		36,684,753		378,310				73,703,121		329,032				43,700,974		327,250				13,975,252		396,012				$   169,098,692

		Freight		2,567,933		26,482				5,159,218		23,032				3,070,156		22,991				1,028,164		29,135				$   11,897,975

		Construction		57,074,838		588,582				122,004,457		544,663				74,811,079		560,215				25,218,774		714,615				$   280,802,608

		Total Raw material costs		96,327,524		993,374				200,866,796		896,727				121,582,209		910,455				40,222,190		1,139,762				$   461,799,276

																														% of Direct cost

		Engineering		2,576,674		26,572				5,934,091		26,491				3,623,899		27,137				1,043,336		29,565				$   13,258,201		2.87%

		As-builts D&R		166,980		1,722				387,750		1,731				230,514		1,726				62,370		1,767				$   852,793		0.18%

		Project Mgmt		725,543		7,482				1,674,612		7,476				1,000,370		7,491				263,834		7,476				$   3,686,808		0.80%

		Const Mgmt		971,331		10,017				2,242,002		10,009				1,339,178		10,028				352,330		9,984				$   4,934,895		1.07%

		Builders risk insurance		108,501		1,119				218,486		975				127,425		954				44,307		1,256				$   501,768		0.11%

		District labor				- 0						- 0						- 0						- 0				$   - 0		0.00%

		Environmental		1,494,702		15,414				3,449,893		15,401				2,060,877		15,433				543,528		15,402				$   7,595,248		1.64%

		ROW		18,293,613		188,652				28,207,165		125,925				11,746,235		87,960				6,742,036		191,047				$   65,391,587		14.16%

		Indirect Costs		24,337,344		250,978				42,113,999		188,009				20,128,498		150,730				9,051,741		256,496				$   96,221,299		20.84%

		Subtotal Costs		120,664,868		1,244,353				242,980,795		1,084,736				141,710,707		1,061,185				49,273,931		1,396,258				$   558,020,575

																														% of Subtotal

		Escalation				- 0						- 0						- 0						- 0				$   - 0		0.00%

		Contingency		12,925,922		133,298				26,028,710		116,200				15,180,405		113,677				5,278,347		149,571				$   59,776,559		10.71%

		Overhead		2,853,403		29,426				5,748,716		25,664				3,352,989		25,108				1,164,736		33,005				$   13,200,042		2.37%

		AFUDC				- 0						- 0						- 0						- 0				$   - 0		0.00%

		Gross Receipts		10,496,293		108,243				7,409,298		33,077				3,508,389		26,272				1,233,894		34,964				$   22,815,466		4.09%

		Subtotal		26,275,618		270,966				39,186,724		174,941				22,041,783		165,058				7,676,977		217,540				$   95,792,067		17.17%

		Total Pipe costs		146,940,486		1,515,319				282,167,519		1,259,676				163,752,490		1,226,243				56,950,908		1,613,797				$   653,812,641

		Compression

		Standing Rock		- 0						- 0						Station 4

		Bloomfield		- 0						4,866,197						Station 3

		Gallup		6,377,259						4,124,518						Station 2

		Blanco Hub		1,746,987						- 0						Station 1.5

		Bisti		2,611,238						- 0						Kingman

		Needles		- 0

		Total Compression		10,735,484						8,990,715																		$   19,726,199

		Grand Total Project																										$   673,538,840

		Miles		97						224						134						35						$   490



&L&F&C&A&R&D



Sheet3

		

				$

		Pipe Material		168,064,100		18%

		Construction		290,934,619		32%

		Engineering		33,087,533		4%

		ROW		64,989,049		7%

		Escalation / Overheads		165,565,736		18%

		Gross Receipts		22,647,874		2%

		Compression		166,386,175		18%

				$   911,675,086		100%






