Interoffice

Memorandum

-DRAFT-
Establishment on TOCOM
DRAFT of June 22, 2001
Page 2

[image: image1.png]



	To:
	Joe Hirl
	
	

	
	
	
	

	From:
	Jan-Erland Bekeng
	Department:
	Enron Japan

	Copy:
	Morten Erik Pettersen, Jane McBride, Susan Musch
	
	

	Subject:
	Establishment on TOCOM
	Date:
	June 26, 2001


This memo is discussing different options on how to establish a membership on Tokyo Commodity Exchange (TOCOM), the cost attached to each option, equity/funding needs for each option and the time it takes to implement each option. 

EXECUTIVE SUMMARY

The schedule contains a summary of the different options discussed below (All numbers in Thousand USD):

	Options
	Startup Costs/Funding
	Minimum Equity Needs
	Audit/Disclosure
	Tax
	Timing
	Other

	1) Establish regular TOCOM membership in a SPV
	Dep. 120

Cost 310

Funding 430
	160
	TOCOM activities isolated from other Enron activities in Japan
	Fin. and Phys. mixed in one company, causing Phys. subject to immediate US Taxation.


	12 weeks
	Initial funding needs covers equity needs.

US Tax exposure isolated from other Enron activities in Japan.

	2) Establish regular TOCOM membership in EJ
	Dep. 120

Cost 310

Funding 430
	15,000
	TOCOM activities blended with other Enron activities in Japan
	Fin. and Phys. mixed in one company, causing Phys. subject to immediate US Taxation.
	10 weeks
	Initial funding needs do not cover equity needs.



	3) Establish regular TOCOM membership in EJM
	Dep. 120

Cost 310

Funding 430
	80
	TOCOM activities blended with other Enron activities in Japan
	Fin. and Phys. mixed in one company, causing Phys. subject to immediate US Taxation.
	10 weeks
	Initial funding needs covers equity needs

	4) Establish Broker TOCOM membership
	Dep. 140

Cost 310

Funding 450
	EJ 15,000

SPV 650
	TOCOM activities blended with other Enron activities in Japan, if not set up in a SPV
	Fin. and Phys. segregated, avoiding immediate US taxation
	EJ 10 weeks

SPV 12 weeks
	Initial funding needs do not cover equity needs.

More disclosure.

More Middle Office work.

Difficult initially to decide if deal is F or P

Needs Broker License

	5) Establish two regular TOCOM memberships, one for EJ and on for EJM
	Dep. 280

Cost 620

Funding 900
	15,080
	TOCOM activities blended with other Enron activities in Japan, if not set up in a SPV
	Fin. and Phys. segregated, avoiding immediate US taxation
	10 weeks
	Initial funding needs do not cover equity needs.



	6) Establish two regular TOCOM memberships, two separate SPV’s
	Dep. 280

Cost 620

Funding 900
	320
	TOCOM activities isolated from other Enron activities in Japan
	Fin. and Phys. segregated, avoiding immediate US taxation
	12 weeks
	Initial funding needs covers equity needs

More Middle Office work


Background

The Gasoline and Kerosene Futures (Futures) traded on TOCOM has physical and only physical delivery if held open until it matures. If trades with the same maturity is bought and sold, the netted positions are settled in cash. 95% of the trading is estimated to be netted out before it goes to delivery. In the startup phase, considered to be the first 6 months of active trading, all trades are expected to be netted and settled in cash. 

Tax

The distinction between Physical and Financial is material from a US Tax point of view. This is to avoid double taxation, tax on profits both in the US and Japan. From a US Tax point of view it is vital to separate Financial trading from Physical trading, because of the Anti-Tax Deferral Provisions (see attached tax memo). These provisions clearly state that the activity performed on TOCOM is subject to immediate US Taxation, even though no dividends are distributed back to the US. There are two relevant exemptions that can be used to avoid this:

1) Qualified Sales Exception for Physical Commodities

2) Dealer Exception for Financial Instruments

The first exemption is subject to an 85% qualifying test, which means that if the ratio of Physical to Financial is less than 85% all of the Physical activity is subject to immediate US taxation. The second exemption clearly demands a cash settlement. Thus the easiest way to avoid immediate US Taxation is to segregate these two activities in separate legal entities. The issue arises when you have both Physical and Financial activities in one legal entity.

US Tax Definition of Futures traded on TOCOM

Under a pure economic definition, the Futures traded on TOCM are clearly physical. In lieu of the US tax code, the Futures traded on TOCOM are clearly physical if held open, and Financial if netted out. This creates a separation problem related to the US Tax code.

Legal Entity Structure of Enron Japan

To cope with segregation issue mentioned above, Enron Japan is structured with two separate legal entities. Enron Japan Corp. (EJ), which handles all financial activities as well as employment entity, and G&A’s. Enron Japan Marketing Corp. (EJM) is set up to handle all Physical activities.

Membership options on TOCOM

Membership is divided into two Groups: those who can trade only for their own accounts, and those who are authorized to act as Broker Members and trade both for their own accounts and their customers accounts. The schedule below provides the startup cost for the two different types of memberships in USD (JPY/USD = 123).

	 
	 
	 
	 
	 

	 
	 
	 
	Member
	Broker Member

	 
	 
	 
	 
	 

	Deposits (Refundable)
	 
	117,886 
	139,837 

	Costs
	 
	 
	308,171 
	308,659 

	Total Funding Needs
	 
	426,057 
	448,496 

	 
	 
	 
	 
	 

	 
	 
	 
	 
	 

	Exchange related Deposits (Refundable)
	117,886 
	139,837 

	 
	 
	 
	 
	 

	Share
	 
	 
	8,130 
	40,650 

	Initial membership deposit
	 
	40,650 
	0 

	Membership trust money
	 
	8,130 
	8,130 

	Special deposit for default Gasoline (Initial)
	20,325 
	40,650 

	Special deposit for default Kerosene (Initial)
	40,650 
	40,650 

	Guarantee Funds for Brokerage Operations
	0 
	9,756 

	 
	 
	 
	 
	 

	Computer related Expenses (1 Terminal)
	248,780 
	249,268 

	 
	 
	 
	 
	 

	Trading Software License
	 
	243,902 
	243,902 

	Initial installation Terminal and Printer
	2,439 
	2,439 

	Half Annual Membership Fee
	2,439 
	2,927 

	 
	 
	 
	 
	 

	Other Setup Expenses
	 
	59,390 
	59,390 

	 
	 
	 
	 
	 

	Legal - Baker & McKenzie
	24,390 
	24,390 

	IT – Thunderball
	 
	35,000 
	35,000 


Net Asset (Equity) requirement on TOCOM

Net Assets of the member on TOCOM defines the number of contracts tradable. Net Assets is defined as Total Assets – Debt (Including Intercom any debt). The minimum Net Asset requirement for a Regular Member is USD 162,601 (JPY 20,000,000) and for a Broker Member is USD 650,406 (JPY 80,000,000). There are no restrictions on the equity of a member. The company is free to use the injected capital to any purpose. The current Net Asset situation in EJ is USD (15,000,000) and in EJM is USD 80,000. If the company meets the minimum Net Asset requirement as a regular member it can buy/sell 300 contracts each on Gasoline and Kerosene. If the company meets the minimum Net Asset requirement as a Broker Member it can buy/sell 2,000 contracts each on Gasoline and Kerosene.

Time to establish

The target is to establish the TOCOM membership as fast as possible. With this in mind one must not forget that certain aspects of the establishment process will take time. 

1) To establish a SPV (KK) in Japan takes around 4 weeks. 

2) To inject new equity into an already established company takes around two weeks.

3) Pre application to METI takes around one week

4) Final application to TOCOM takes around 6-8 weeks

One of the first two must be in place before 3) and 4) can start. Mid. office systems (Thunderball) estimated to be ready for testing early August.

Audit and disclosure

According to TOCOM’s articles of association, Article 30 permits the Exchange to audit a member’s books upon demand, and the Exchange may enter the member’s premises to obtain the books.

Assignment of contracts

The TOCOM membership entity cannot assign TOCOM contracts over to other non-membership entities. Thus not allowing for transfer of Physical delivery obligation if needed. Thus one can hedge the price risk with an OTC contract, but not the Physical risk.

Options for establishment on TOCOM

1) Establish regular TOCOM membership in a SPV

a. Pro’s

i. Clean start

ii. Isolate US Tax risk, and eliminate contamination towards other activities in already established entities

iii. Startup funding needs is enough to cover initial net asset requirement

iv. In case of an audit from the Exchange, this activity is isolate in one company, not allowing them insight into other Enron activities in Japan 

b. Con’s

i. Takes an additional 4 weeks to establish, shelf companies do not exist in Japan, compared to 2 weeks for equity injection for already established companies

ii. Physical activity may be subject to immediate US Taxation

iii. Not able to segregate Physical from Financial

c. Costs/funding/equity

i. USD 117,866 in refundable deposits

ii. USD 308,171 in startup costs

iii. Minimum USD 160,000 in equity injection to cover minimum net asset requirement

2) Establish regular TOCOM membership in EJ

a. Pro’s

i. Already established, thus 2 weeks only for equity injection instead of 4 weeks to establish a new company

b. Con’s

i. Physical activity mixed with other Financial activity from other business areas

ii. Physical activity may be subject to immediate US Taxation

iii. Startup funding needs is not enough to cover initial net asset requirement

iv. Not able to segregate Physical from Financial

v. In case of an audit from the Exchange, they can look into other activities of Enron in Japan

c. Costs/funding/equity

i. USD 117,866 in refundable deposits

ii. USD 308,171 in startup costs

iii. Minimum USD 15,000,000 in equity injection to cover minimum net asset requirement

3) Establish regular TOCOM membership in EJM

a. Pro’s

i. Startup funding needs is enough to cover initial net asset requirement

ii. Already established, thus 2 weeks only for equity injection instead of 4 weeks to establish a new company

b. Con’s

i. Financial activity mixed with other Physical activity, might destroy the 85% test for the whole company, which houses other activities than crude and liquids

ii. Not able to segregate Physical from Financial

iii. In case of an audit from the Exchange, they can look into other activities of Enron in Japan

c. Costs/funding/equity

i. USD 117,866 in refundable deposits

ii. USD 308,171 in startup costs

iii. Minimum USD 80,000 in equity injection to cover minimum net asset requirement

4) Establish Broker TOCOM membership

a. Pro’s

i. Able to segregate Physical from Financial (Able to trade either Physical for EJM’s own account or Financial for EJ’s own account, and then trade Financial on EJ’s behalf or Physical for EJM’s behalf)

b. Con’s

i. Slightly higher startup costs

ii. More disclosure

iii. More Middle Office work

iv. Higher Net Asset requirements

v. Startup funding needs is not enough to cover initial net asset requirement

vi. Hard to decide when trade is done by trader if he wants to take Physical delivery

vii. Needs employee with broker license

viii. In case of an audit from the Exchange, they can look into other activities of Enron in Japan

c. Costs/funding/equity

i. USD 139,837 in refundable deposits

ii. USD 308,659 in startup costs

iii. Minimum USD 650,000 in equity injection to cover minimum net asset requirement

5) Establish two regular TOCOM memberships, one for EJ and on for EJM

a. Pro’s

i. Able to segregate Physical from Financial

ii. Already established, thus 2 weeks only for equity injection instead of 4 weeks to establish a new company

b. Con’s

i. Double startup costs

ii. Startup funding needs is not enough to cover initial net asset requirement

iii. Hard to decide when trade is done by trader if he wants to take Physical delivery

iv. Double administrative work

v. In case of an audit from the Exchange, they can look into other activities of Enron in Japan

c. Costs/funding/equity

i. USD 279,674 in refundable deposits

ii. USD 617,318 in startup costs

iii. Minimum USD 15,080,000 in equity injection to cover minimum net asset requirement

6) Establish two regular TOCOM memberships, two separate SPV’s

a. Pro’s

i. Able to segregate Physical from Financial

ii. Startup funding needs is enough to cover initial net asset requirement

iii. In case of an audit from the Exchange, this activity is isolate in one company, not allowing them insight into other Enron activities in Japan

b. Con’s


i. Takes an additional 4 weeks to establish, shelf companies do not exist in Japan, compared to 2 weeks for equity injection for already established companies

ii. Double administrative work

c. Costs/funding/equity

i. USD 279,674 in refundable deposits

ii. USD 617,318 in startup costs

iii. Minimum USD 320,000 in equity injection to cover minimum net asset requirement

Respect
Integrity
Communication
Excellence
Form 000-469-E(7/92)

Your Personal Best Makes Enron Best
Communicate- Facts Are Friendly

Better, Faster, Simpler

Form 000-469-1 (5/92)


