TRANWESTERN PIPELINE 

MAINLINE EXPANSION OPTIONS

February 6, 2001


LONG TERM  (12-24 MONTHS)

OPTIONS
FACILITY DESCRIPTIONS
FLOW (*)

mmcfd
COSTS $MM
TIMING

months
ADVANTAGES
DISADVANTAGES
REMARKS

1

 
Install 152,000 HP (ISO): Scope consists of installation of one 38,000 HP (ISO) unit installed at Stations 1-4.


150

(177)


99.6


15-17
· Air Permit will take 6-9 months 

· Additional 4000 HP/unit

· No downtime required for modifications to existing units


· Tie-in downtime is 3-5 days/station

· $30.8M more than

Option 2

· Limited by pipeline capacity
Modification to existing units not required.  Existing units to be abandoned.

Total O&M cost is $2.8M/yr

Throughput Loss:

200 mmcf/d (construction)

220 mmcf/d (operations)

2


Install 62,800 HP (ISO):

Scope consists of installation of one 15,700 HP (ISO) unit installed in parallel to the existing units, and compressor modifications to all twelve existing units at Stations 1-4.


140

(168)


68.8


12-19
· $30.8M less than

Option 1

· Can handle variation of flow
· Downtime is 4 weeks per unit for unit  modifications plus 3-5 days/ station for tie-ins

· Air permit will take 12-18 months

· Acoustic study required
Modifications to existing units required. This is estimated at $8M and is included in cost. 

Total O&M cost is $5.4M/yr.

Throughput Loss:

150 mmcf/d (construction)

140 mmcf/d (operations)

(*)  Incremental flow above current certificated capacity of 1090 mmcf/d with 825 psig delivery pressure at SOCAL Needles.   

The additional flow number indicated in parenthesis is the incremental capacity with 800 psig delivery pressure at SOCAL Needles.

SHORT TERM   (0-6 MONTHS)

OPTIONS
FACILITY DESCRIPTION
FLOW (*) mmcfd
COSTS $MM
TIMING


REMARKS

1
Application of Nalco/Exxon’s Enerflow to reduce friction on pipeline downstream of Station 5.

60
3.0/year
12-18 hr

reduced flow
From Station 5 to Needles. Solvents other than diesel will be employed (e.g. methanol, condensates).  
Throughput Loss:

400 mmcf/d (mainline)

2 
Install a launcher and receiver at the Bisti Compressor Station on the San Juan Lateral.

10
1.7
48-hr

shutdown
Efficiency increase of 4% is assumed. This will eliminate the need for Gallup modifications. Assumes contract fuel physical flow on San Juan Lateral to be 20 mmcf/d.

Throughput Loss:

850 mmcf/d  (San Juan Lateral)


3

 
Add inlet air cooling for ambient rating HP - consider ground water loop system or evaporative cooler.
7
2.4


1 week per unit
Install turbocharger inlet air cooling to reduce inlet air temperatures from 80 to 55 degrees F to generate approximately 3% incremental HP at each station.  (per unit cost $200,000 x 3 = $600,000 per station)

Throughput Loss:                                                    LEVEL “A” ESTIMATE
75-225 mmcf/d  



4
Add small pocket loading and poppet valves at Stations 1, 2, and 4.
11
1.38


8 hrs/unit

downtime
To be scheduled with other operations outages. Install small pocket loader on each unit (per unit cost $20,000 x 3 = $60,000 per station). Efficiency increase of 3% is assumed.
Throughput Loss:                                                    LEVEL “A” ESTIMATE
75-225 mmcf/d



5 
Decrease the SOCAL Needles delivery pressure to 800 psig.

8-28
-
-
Marketing to discuss options with SOCAL to reduce delivery pressure to 800 psig.

Incremental flow is dependent upon available HP and the long-term or short-term option that is applied.

(*)  Incremental flow above current certificated capacity of 1090 mmcf/d with 825 psig delivery pressure at SOCAL Needles.   

Asante Jan 01 v1




2/6/01 12:25 PM

