LONG-TERM NATURAL GAS PURCHASES TIME SCHEDULE


FOR THE CITY OF LAS CRUCES, NEW MEXICO AND


RIO GRANDE NATURAL GAS ASSOCIATION

Request for Qualifications

8/1
Advertisement to press



AUG. 1

8/5
1st add





AUG. 5 

8/12
2nd add





AUG. 12 

8/16
Registration of bidders



AUG. 16 

8/17
Addendum if any




AUG. 17 

9/18
Receipt of qualifications and draft contracts

SEPT. 18

9/28 
Members meet and qualify bidders
                             SEPT. 28

 Invitation to BiD

10/17
Invitation to Bid mailed



OCT. 17

10/31
 Questions received



OCT. 31

11/17
Addendum (if any faxed)



NOV. 17

01/16/02
Receipt of bids




JAN. 16,2002 

01/17   
Open bids at 2:00 p.m.

                            JAN. 17

01/23
Members review bids



JAN. 23

04/24      Negotiate final agreement                                            APR. 24

04/29
Members recommend awards


APR. 29

05/6
Council and Board award contracts


MAY 6

07/10     Contracts executed



JULY 10

08/15
Agency agreements, Passport, Visa to El Paso
AUG. 15

9/1
New service begins



Sept. 1, 2002

