ETS E&C DEVELOPMENT OPPURTUNITY

DECISION BRIEFING


TRAILBLAZER STATIONS 601, 602 AND 603

RECOMMENDATION

THAT WE PURSUE A 3RD PARTY LUMP SUM TURNKEY BIDDING OPPORTUNITY FOR TRAILBLAZER PIPELINE COMPANY (KINDER-MORGAN).

CUSTOMER

TRAILBLAZER PIPELINE, WITH THE FOLLOWING OWNERSHIP

· 33% 
 
Enron

· 67%

Kinder-Morgan

SCOPE & ESTIMATED PROJECT SIZE / PROFIT

· ENGINEERING & CONSTRUCTION OF 3 NEW COMPRESSOR STATIONS

· Station 601
LOGAN CO. COLORADO 

2-15,000 HP TURBINES

· Station 602
LINCOLN CO. NEBRASKA

1-10,000 HP ELECTRIC ADDITION

· Station 603
KEARNEY CO. NEBRASKA
2-10,000 HP ELECTRIC

· INITIAL ORDER OF MAGNITUDE ESTIMATE 

· Kinder Morgan Budget - $55MM

· EAMR Estimate $45-48 MM 

· EXPECTED EARNINGS

· $1MM IN 2001

· $2MM IN 2002

PROJECT SCHEDULE

NOTICE TO PROCEED (NTP)
01/15/01


START CONSTRUCTION

07/01/01 (FERC scheduled 06/01/01)

READY FOR SERVICE

06/01/02 all 3 stations per RFQ






12/1/01 potential for 2 stations -  3rd station 02/01/02

CONTRACTUAL STRUCTURE / SCOPE SPLIT

· RFQ options for Engineering and Procurement Assistance, LSTK and Lease

· EAMR to Bid LSTK (Potential for ECS to bid Lease/Operate)

· WE TAKE ENGINEERING, PROCUREMENT AND CONSTRUCTION RISK

· UPRATE OF EXISTING UNIT AT STATION 602 IS T&M

· DEAL SIMILAR TO PREVIOUS VENTURE WITH TRAILBLAZER STATION 602 (1997)

· WILL UTILIZE OUTSIDE ENGINEERING FIRM WITH TRAILBLAZER EXPERIENCE

·  UEI BIDDING E&PA SEPARATE - 

· WE WILL BE RESPONSIBLE FOR FUNDING PROJECT CASH FLOW after progress payments

· RFQ REQUESTED STANDBY LETTER OF CREDIT FOR APPROX. $2.0 MM

PROPOSAL MILESTONES

· COMPLETE PROPOSAL W/ PRICING
5 December 2000

· FINAL RAC APPROVAL




· BID DUE




15 December 2000

· EXPECTED AWARD / NTP


15 January 2001

PROPOSAL COSTS

$50,000 – EAMR RISK IF WE LOSE BID

COMPETITION

POTENTIALLY SEVERAL LOCAL E&C COMPANIES, MOST ARE BIDDING E&PA ONLY.

· UEI


· GIEC

· PPP

· MASTER

· FORERUNNER

· TRIGON-SHEHAN

· EPSTEIN

· WILBANKS

· MUSTANG



HISTORY

· SIMILAR TO STATION 602 SUCCESSFULLY COMPLETED FOR NGPL IN 1997 

· ACTUALLY EARNED $2mm PROFIT VS. BUDGET PROFIT OF $1mm (1 STATION)

· GOOD RELATIONSHIP WITH KM/NGPL, A KEY OWNER AND OPERATOR OF TRAILBLAZER

· EECC WAS SUCCESSFUL IN SIMILAR BIDDING SITUATION AGAINST SIMILIAR COMPETITION

RISKS & MITIGATIONS

RISK
MITIGATION
NORMAL PROJECT EXECUTION RISKS
EXPERIENCE & CONTINGENCY

PAYMENT
REGULATED PIPELINE WITH PARTIAL ENRON OWNERSHIP[

BID ADVANTAGES

EECC CONSTRUCTED TRAILBLAZER STATION 602

KM PERSONNEL KNOWN TO ETS PERSONNEL

NGPL/KM STANDARDS SPECIFIED (SIMILAR TO ENRON SPECIFICATIONS)

STANDARD ENRON PRODUCT OFFERING – WILL UTILIZE EQUIPMENT SPECS AND PRICING FROM FGT PHASE 4 & 5

PAGE 4 OF 4




27 November 2000

