AGREEMENT

By and Between

ENRON NORTH AMERICA CORP.

AND 

GENERAL ELECTRIC COMPANY

For The

COYOTE SPRINGS 2 LLC POWER PROJECT

GAS TURBINE GENERATOR PACKAGE
TABLE OF CONTENTS

1ARTICLE I.  DEFINITIONS

ARTICLE II.  RESPONSIBILITIES OF PURCHASER
10
2.1   Purchaser Responsibilities
10
2.2   Purchaser Conduct
10
ARTICLE III.  RESPONSIBILITIES OF SELLER
10
3.1   General Obligations
10
3.2   Delivery of Equipment and Documentation
11
3.2.1   Delivery to Delivery Point
11
3.2.2   Not Used
11
3.2.3   Impact Recorders
11
3.2.4   Maximize Assembly
11
3.2.5  Documentation Delivery
11
3.3   Relevant Information
11
3.4   Hazardous Materials Notification
12
3.5   Employment of Trained and Experienced Personnel
12
3.6   Not Used.
12
3.7   Guarantee
12
3.8   Compliance with Governmental Rules and the Requirements of this Agreement
12
3.9   Approved Vendors
14
3.10  Packing and Insurance Surveyor
14
3.10.1   Packing Recommendation
15
3.10.2   Insurability Certificate
15
3.10.3   Notice of Shipment
15
3.10.4   Compliance with Recommendation
16
3.10.5   Coordination
16
3.11  Financing and Insurance Assistance
16
3.12  Purchaser Permit Support
16
3.13  Order Definition Meeting
16
3.14  Spare Parts
16
3.14.1   Commissioning Spares
16
3.14.2  Operating Spares
16
3.15  Key Personnel
17
ARTICLE IV.  RESPONSIBILITY FOR INFORMATION
17
4.1   Purchaser Supplied Information
17
ARTICLE V.  PURCHASE AMOUNT AND OTHER CHARGES
17
5.1   Purchase Amount
17
5.1.1   Purchase Amount
17
5.2   Taxes and Contributions
17
5.2.1   Seller Responsibility for Personal Taxes
17
5.2.2   Seller's Responsibility for Taxes
17
5.2.3   Taxes in the Project State
18
5.2.4   Tax Penalties
18
5.3   Changes to the Purchase Amount.
18
5.4   Cancellation
19
5.4.1   Cancellation by Purchaser
19
5.4.2   Marketing Agreement
19
5.5   Suspension or Change of Delivery
19
ARTICLE VI.  PAYMENT TERMS
20
6.1   Payment of Purchase Amount
20
6.1.1   Payment Periods.
20
6.1.2   Payment Milestones
20
6.1.3   Retention
21
6.2   Payment Disputes
21
6.3   Payments Withheld or Offset
21
6.3.1   Payments Withheld
21
6.3.2   Offset for Liquidated Damages
22
6.4   Payment of Liquidated Damages
22
6.4.1  Payment of Document Delivery Damages
22
6.4.2   Payment of Delivery Liquidated Damages
22
6.4.3   Payment of Take Over Liquidated Damages
22
6.4.4   Payment of Performance Liquidated Damages
23
6.5   Not Used
23
6.6   Lien Release
23
6.7   Invoices
23
6.7.1   Contract Reference
23
6.7.2   Payee and Address for Invoices
23
6.7.3   Date of Receipt
24
6.8   Method of Payment
24
6.9   Payments Not Acceptance of Work
24
ARTICLE VII.  NOTICE TO PROCEED AND TERMINATION
24
7.1   Notice to Proceed
24
7.2   Not Used
24
7.3   Termination
24
ARTICLE VIII.  RESERVED
25
ARTICLE IX.  INSPECTION AND CORRECTION OF WORK
25
9.1   Inspections
25
9.2   Resident Facilities
25
9.3   Quality Plan
25
9.4   Notice
26
9.5   Correction of Equipment
26
9.6   Additional Factory Testing
26
9.7   Release for Delivery
26
ARTICLE X.  DELIVERY AND PERFORMANCE
27
10.1   Delivery of Documentation
27
10.1.1   Delivery of Final O & M Instructions
27
10.2   Delivery of Equipment
27
10.2.1   Guaranteed Delivery Date
28
10.2.1.1   Delivery to the Delivery Point
28
10.2.1.2   Delivery Restrictions
28
10.2.2   Inventory Upon Delivery
28
10.2.3   Delivery
28
10.2.4   Extensions of the Guaranteed Delivery Date
28
10.2.5   Offloading Responsibilities
29
10.3   Delay Liquidated Damages
29
10.3.1   Delivery Liquidated Damages
29
10.3.2   Take Over Liquidated Damages
30
10.3.3   Invoicing for Delivery and Take Over Liquidated Damages
31
10.4.1  Exhaust Gas Temperature Guarantee
31
10.4.2  Exhaust Gas Energy Guarantee
31
10.4.3  Specific Performance Exhaust Gas Temperature Guarantee
31
10.4.4  Specific Performance Exhaust Gas Energy Guarantee
31
10.4.5  Interaction of  Exhaust Gas Energy and Exhaust Gas Temperature with Turbine Net Output
31
10.5   Sound Level Specific Performance Guarantees
31
10.5.1 Specific Performance Near Source Sound Level Guarantee
32
10.5.2  Specific Performance Far Field Sound Level Guarantee
32
10.5.3  Sound Level Test
32
10.6   Specific Performance Emissions Guarantee
32
10.7   Electrical Output Guarantees
32
10.7.1  Electrical Output Guarantee
32
10.7.2  Specific Performance Electrical Output Guarantee
32
10.8   Heat Rate Guarantees
32
10.8.1  Heat Rate Guarantee
32
10.8.2  Specific Performance Heat Rate Guarantee
32
10.9   Performance Liquidated Damages
33
10.9.1  Output Liquidated Damages
33
10.9.2   Heat Rate Liquidated Damages
33
10.9.3   Exhaust Gas Temperature and Energy Liquidated Damages
33
10.9.3.1  Exhaust Gas Temperature Liquidated Damages
33
10.9.3.2  Exhaust Gas Energy Liquidated Damages
33
10.9.4   Performance Test Required
33
10.9.5   Setting Out of Performance Liquidated Damages
33
10.9.6   Most Recent Performance Test
33
10.9.7   Seller's Improvement of Performance
34
10.9.8   Reduction in Performance Liquidated Damages
34
10.10   Maximum Liabilities for Liquidated Damages
35
10.10.1  Maximum Document Delivery Liquidated Damages
35
10.10.2  Maximum Delivery Liquidated Damages
35
10.10.3  Maximum Take Over Liquidated Damages
35
10.10.4  Maximum Output Liquidated Damages
35
10.10.5  Maximum Heat Rate Liquidated Damages
35
10.10.7  Maximum Aggregate Exhaust Gas Energy Damages
35
10.10.8  Maximum Aggregate Liquidated Damages
36
10.11   Liquidated Damages Not Penalty
36
10.12   Performance Tests and Sound Level Tests
36
10.12.1   Not Used
36
10.12.2   Election to Conduct a Performance Test
36
10.12.3   Specific Performance Achievement
36
10.12.4   Timing of Tests
37
10.12.5   Seller Presence at Tests
37
10.12.6   Test Results
37
10.12.7   Performance Test Procedures
37
10.12.8   Reconduct of Tests
38
10.12.9   Not Used
38
10.12.10  Fittings, Instrumentation and Test Uncertainty
38
10.12.11  Consumable Spare Parts During Retests
39
10.13  Remedies For Failure to Meet Specific Performance Requirements
39
10.13.1  Corrective Actions
39
10.13.2  Failure to Achieve Specific Performance
39
10.14  Acceptance
39
10.15  Readiness for Testing
40
10.16  Unit Serial Numbers
40
ARTICLE XI.  CHANGE ORDER
41
11.1   Adjustment of Purchase Amount
41
11.2   Purchaser Requested Change Order
41
11.3   Seller Requested Change Order
41
11.4   Not Used
41
11.5   Disputes
42
11.6   Change Order Pricing
42
11.6.1  Method of Pricing
42
ARTICLE XII.  INTENTIONALLY OMITTED
42
ARTICLE XIII.  ORDER OF PRECEDENCE
42
13.1   Order of Precedence
42
ARTICLE XIV.  WARRANTY
42
14.1   Seller's Warranty
42
14.1.1   Primary Warranty Period
42
14.1.2   Warranty Clarification
43
14.1.3   Warranty Breach Notice
44
14.2   Extended Warranty Period
44
14.2.1   Continued Warranty on Corrections or Repairs Performed During the Primary Warranty Period
44
14.2.2   Extension of Warranty Due to Unavailability
44
14.3   Obligations, Responsibilities and Recourse
44
14.4   Not Used
45
14.5   Limited Warranty
45
14.6   Repairs and Alterations by Others
45
14.7   Termination of Warranty
45
ARTICLE XV.  RISK OF LOSS AND TITLE
46
15.1   Risk of Loss
46
15.2   Title
46
15.2.1   Passage of Title
46
15.2.2   Infringement Cures and Defense
46
15.3   Seller's Drawings, Etc. for Use by Purchaser
47
15.4   Licensing Procedure
47
ARTICLE XVI.  TRAINING AND TECHNICAL DIRECTION OF INSTALLATION
48
ARTICLE XVII.  DEFAULT
48
17.1   Events of Default by Seller
48
17.2   Purchaser's Remedies Against Seller
49
17.3   General Obligations
49
17.4   Payment Obligations
50
17.4.1   Determination of Obligations
50
17.4.2   Damages and Expenses
50
17.4.3   Cover Damages
50
17.4.4   Settlement
51
17.5   Events of Default by Purchaser
51
17.6   Seller Remedies
52
ARTICLE XVIII.  FORCE MAJEURE
52
18.1   Failure to Perform Due to an Event of Force Majeure
52
18.2   Events of Force Majeure
52
18.3   Notice of Event of Force Majeure
53
18.4   Events of Force Majeure
53
18.5   Certain Events Not Excused
54
18.6   Continued Performance
54
18.7   Not Used
54
18.8   Event of Force Majeure ‑ Delays
54
18.9   Event of Force Majeure ‑ Cost
55
18.10   Cancellation for Force Majeure
55
18.11   Payment on Cancellation for Force Majeure
55
ARTICLE XIX.  INSURANCE
55
19.1   Insurance ‑ General
55
19.1.1   All Risk
55
19.1.2   Workers Compensation and Employers Liability Insurance
55
19.1.3   Commercial General Liability Insurance
56
19.1.4   Hull and Protection and Indemnity Insurance
56
19.1.5   Business Automobile Liability Insurance
56
19.1.6   Aircraft Liability Insurance
57
19.1.7   Excess Umbrella Liability Coverage
57
19.1.8   Vendors
57
19.1.9   Certificate of Insurance
57
19.1.10  Other Requirements
57
19.1.11  Vendor Waiver of Subrogation
58
19.1.12  Compliance with Insurance
58
19.1.13  Limitation
58
19.2   Purchaser's Insurance
59
19.2.1   Cargo Insurance
59
19.2.2   Builder’s All Risk Insurance
59
ARTICLE XX.  INDEMNIFICATION
59
20.1   Third Party
59
20.2   Survival of Obligation
60
ARTICLE XXI.  NON‑DISCLOSURE OF INFORMATION
61
21.1   Proprietary Information
61
21.2   Press Releases
61
21.3   Confidentiality
61
ARTICLE XXII.  ASSIGNMENT
63
22.1   Assignment by Seller
63
22.2
Assignment by Purchaser or Agent
63
ARTICLE XXIII.  RELATIONSHIP OF THE PARTIES
65
23.1   Independent Contractor
65
23.2   Responsibilities of Seller as Principal for its Employees
65
23.3
Purchaser and Agent
66
ARTICLE XXIV.  LIENS AND CLAIMS
66
ARTICLE XXV.  NOTICES AND COMMUNICATIONS
67
25.1   Notices
67
25.2   Effectiveness of Notices
67
25.3   Technical Communications
67
ARTICLE XXVI.  ARBITRATION
67
26.1   Negotiation of Disputes and Disagreements
67
26.2   Arbitration Resolution
68
26.3   Continuation of Work
68
ARTICLE XXVII.  LIMITATION OF LIABILITY
69
27.1   Maximum Liability
69
27.2   Consequential Losses
69
27.3   Releases Valid in All Events
69
ARTICLE XXVIII.  DRUG AND ALCOHOL‑FREE WORKPLACE
70
ARTICLE XXIX.  PROJECT PLANNING AND CONTROLS
70
ARTICLE XXX.  MISCELLANEOUS
70
30.1   Validity and Enforceability
70
30.2   Governing Law
71
30.3   Entire Agreement
71
30.4   Agreement Modification
71
30.5   Waiver
71
30.6   Headings
71
30.7   Third‑Party Beneficiaries
71
30.8   Counterparts
71
30.9   Equal Employment Opportunity
71
30.10  Cooperation on Site
71
30.11   Avoidance of Nuclear Use
72
30.12   Miscellaneous Representations and Warranties
72
EXHIBIT A  BASIS CONDITIONS
75
EXHIBIT A-1 BASIS FUEL
77
EXHIBIT A-2 SELLER FUEL SPECIFICATION
78
EXHIBIT B  SCOPE OF WORK/SPECIFICATION
79
EXHIBIT B‑1  SPECIFICATION
80
EXHIBIT B-2 GUARANTEED DELIVERY DATE
81
EXHIBIT B‑3 PERFORMANCE GUARANTEES AND SPECIFIC PERFORMANCE GUARANTEES
82
EXHIBIT B‑4  APPROVED VENDORS
85
EXHIBIT B-5 NOT USED
88
EXHIBIT B-6 LIQUIDATED DAMAGES
89
EXHIBIT C-1  SELLER PARENT GUARANTEE
91
EXHIBIT C-2 PURCHASER’S GUARANTEE
93
EXHIBIT D  SAMPLE LETTER OF CREDIT
94
EXHIBIT E  COMMUNICATIONS
96
EXHIBIT F  PERFORMANCE TEST GUIDELINES
98
EXHIBIT F-1  SOUND LEVEL TEST GUIDELINES
103
EXHIBIT F-2 EMISSIONS TEST GUIDELINES
105
EXHIBIT G-1  PERFORMANCE TEST CERTIFICATE
109
EXHIBIT H-1  TECHNICAL DIRECTION OF INSTALLATION
111
EXHIBIT H-2  TRAINING
117
EXHIBIT I  CANCELLATION CHARGE
126
EXHIBIT I-1 MILESTONE PAYMENT SCHEDULE
128
EXHIBIT J  QUALITY
130
EXHIBIT K  PROJECT PLANNING
135
EXHIBIT L  EQUIPMENT REQUIRING INSURABILITY CERTIFICATE
138
EXHIBIT M-1  SPARE PARTS
139
EXHIBIT M-2 COMMISSIONING SPARES AND SPECIAL TOOLS
140
EXHIBIT N-1  PURCHASE AMOUNT RECONCILIATION
141
EXHIBIT N-2  OPTIONS
143
EXHIBIT O  HAZARDOUS MATERIAL NOTIFICATION
144
EXHIBIT P  UNIT SERIAL NUMBER
146
EXHIBIT Q RESERVED
147
EXHIBIT R  OBSERVATION POINTS
148
EXHIBIT S  FINAL WAIVER  OF LIENS FORM
149
EXHIBIT T  DOCUMENT DELIVERY SCHEDULE AND DOCUMENT DELIVERY STATUS
153



AGREEMENT
This Agreement is made and entered into as of this ____ day of _______, 2000, by and between WESTDEUTSCHE LANDESBANK GIROZENTRALE, NEW YORK BRANCH (“Purchaser” or “WestLB”), acting through its agent, ENRON NORTH AMERICA CORP., a corporation incorporated under the laws of the State of Delaware, with offices located at 1400 Smith Street, P.O. Box 1188, Houston, Texas  77251-1188 (“Agent”) and GENERAL ELECTRIC COMPANY, a corporation incorporated under the laws of the State of New York, with offices located at 1 River Road, Schenectady, New York 12345, (“Seller”).

RECITAL

WHEREAS, Purchaser has assigned and delegated certain of its rights, responsibilities and obligations under this Agreement to Agent, and Agent has accepted that assignment and delegation as set forth in more detail in Section 23.3; and

WHEREAS, Purchaser has the need to acquire one (1) Frame 7FA Dry Low NOx gas turbine generator package (“GTG”) for a nominally rated 260 megawatt “MW” combined cycle cogeneration plant located near Boardman, Oregon (the “Facility”), scheduled to be completed by June 1, 2002, the “Time for Completion”); and

      WHEREAS, Seller is in the business of designing, engineering, manufacturing, and supplying GTG packages; and

      WHEREAS, Purchaser wishes to contract with Seller for the design, engineering, manufacture, and supply of one (1) Frame 7FA Dry Low NOx GTG equipment for the Facility and other services related thereto; and

      WHEREAS, the parties desire to set forth the terms and conditions under which Seller will provide and Purchaser will pay for such package and related services;

      NOW, THEREFORE, in consideration of the mutual covenants herein contained, and intending to be legally bound, the parties hereto agree as follows:

ARTICLE I.  DEFINITIONStc \l1 "ARTICLE I.  DEFINITIONS
Capitalized terms used in this Agreement without other definition shall have the meanings specified in this Article I, unless the context requires otherwise.

As used in this Agreement, the terms “herein”, “herewith” and “hereof” are references to this Agreement, taken as a whole, the term “includes” or “including” shall mean “including, without limitation,” and references to a “Section”, “subsection”, “clause”, “Article”, “Exhibit”, “Appendix” or “Schedule” shall mean a Section, subsection, clause, Article, Exhibit, Appendix or Schedule of this Agreement, as the case may be, unless in any such case the context requires otherwise.  All references to a given agreement, instrument or other document shall be a reference to that agreement, instrument or other document as modified, amended, supplemented and restated through the date as of which such reference is made, and reference to a law, regulation or ordinance includes any amendment or modification thereof.  A reference to a person includes its successors and permitted assigns.  The singular shall include the plural and the masculine shall include the feminine, and vice versa.  

The terms and the definitions set forth herein apply when capitalized.

1 Acceptance.  Shall have the meaning as set forth in Section 10.14.

1 Adjusted Electrical Output.  Shall mean the Electrical Output adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.

1 Adjusted Emissions.  Shall mean the emissions when operated on natural gas as measured during the Performance Tests and adjusted to Basis Conditions by the methods described in Exhibit F.

1 Adjusted Exhaust Gas Energy.  Shall mean the Exhaust Gas Energy of the Unit as measured during a Performance Test and adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.

1 Adjusted Exhaust Gas Temperature.  Shall mean the Exhaust Gas Temperature of the Unit as measured during a Performance Test and adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.

1 Adjusted Heat Rate.  Shall mean the Heat Rate when adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.

1 Affected Party.  Shall have the meaning set forth in Section 18.1.

1 Affiliate.  Shall mean a person or entity who, with respect to a specified  person or entity, directly or indirectly through one or more intermediaries controls, or is controlled by, or is under common control with, the person or entity specified.

1 Agent.  Shall have the meaning as set forth in the Preamble on Page 1.

1 Agreement or Contract.  Shall mean this Agreement, including all Exhibits attached hereto and the Specification, as amended from time to time as provided herein.

1 Applicable Laws.  Shall mean any applicable national, municipal or local statute, ordinance or other law, regulation or by-law or any rule, code or direction or any license, consent, permit, authorization or other approval including any conditions attached thereto (whether relating to the environment or otherwise) of the government of the United States or of any public body or authority, local or national agency, department, inspector, ministry, official or public or statutory person (whether autonomous or not) which has appropriate jurisdiction.  

1 Base Load.  Shall mean the operation of the Unit at 100% Electrical Output for the prevailing ambient temperature, relative humidity, barometric pressure, fuel heating value, temperature limitation, rated frequency and voltage.

1 Basis Conditions.  Shall mean the conditions set forth in Exhibit A which are the basis for the Guaranteed Levels and Specific Performance Levels. 

1 BTU.  Shall mean British Thermal Unit, where one (1) BTU is equal to 1055.056 joules. 

1 Cancellation Charge.  Shall have the meaning as set forth in Section 5.4.1(c).

1 Change in Law.  Shall mean any change in, or binding change in the judicial or administrative interpretation of, or adoption of, any Applicable Law, which is implemented after the Effective Date, and which has an adverse affect on Seller’s ability to perform its obligations under this Agreement; provided, however, that a change in any federal, commonwealth, state or local income or franchise tax law, workers’ compensation, or payroll or withholding tax law shall not constitute a change in law hereunder. 

1 Change Order.  Shall have the meaning as set forth in Section 11.2.

1 Commissioning Period.  Shall have the meaning as set forth in Section 10.3.2(b).

1 Day or day.  Shall mean a calendar day, including weekdays, weekends, and holidays. 

1 Delivery Liquidated Damages.  Shall have the meaning as set forth in Section 10.3.1.

1 Delivery Point.  Shall mean the delivery of the Units to the nearest accessible rail siding (using appropriate available rolling stock and infrastructure, etc.), or for trucked items, to the Purchaser’s designated storage facility near the Site in Coyote Springs (using conventional vehicles carrying allowable loads over existing roads with no infrastructure changes or improvements).

1 Document Delivery Date.  Shall have the meaning as set forth in Section 10.1.

1 Document Liquidated Damages.  Shall have the meaning as set forth in Section 10.1.

1 Due Date.  Shall have the meaning as set forth in Section 10.1.

1 Effective Date.  Shall have the meaning as set forth in the Preamble on Page 1.

1 Electrical Output.  Shall mean the electric output of the Unit measured at the generator terminals during a Performance Test (after deducting for actual auxiliary loads associated with the Unit).

1 Electrical Output Guarantee.  Shall have the meaning as set forth in Exhibit B-3, Section B.3.4.1.

1 Equipment.  Shall mean the Unit and all other material and supplies including the control systems described in Exhibits B-1 and B-2 to be furnished by Seller pursuant to the Scope of Work.

1 Event of Force Majeure.  Shall have the meaning as defined in Section 18.4.

1 Event of Purchaser Default.  Shall have the meaning as defined in Section 17.5.

1 Event of Seller Default.  Shall have the meaning as defined in Section 17.1.

1 Excess Termination Costs.  Shall have the meaning set forth in Section 17.4.3.

1 Exhaust Gas Energy.  Shall mean the exhaust energy of the Unit measured or calculated at the gas turbine exhaust outlet during a Performance Test.

1 Exhaust Gas Energy Guarantee.  Shall have the meaning as set forth in Exhibit B-3.1.3.

1 Exhaust Gas Energy Liquidated Damages.  Shall have the meaning as set forth in Exhibit B-6, Section B.6.7. 

1 Exhaust Gas Temperature.  Shall mean the exhaust temperature of the Unit measured at the gas turbine exhaust outlet during a Performance Test.

1 Exhaust Gas Temperature Guarantee.  Shall have the meaning as set forth in Exhibit B-3.1.1.

1 Exhaust Gas Temperature Liquidated Damages.  Shall have the meaning as set forth in Exhibit B-6, Section B.6.6. 

1 Extended Warranty Period.  Shall have the meaning as set forth in Section 14.2.1.

1 Facility.  Shall have the meaning as set forth in the Recitals. 

1 Far Field Sound Level Guarantee.  Shall have the meaning as set forth in Exhibit B-3.

1 Guaranteed Levels.  Shall mean the Electrical Output Guarantee, Heat Rate Guarantee, Exhaust Gas Temperature Guarantee and Exhaust Gas Energy Guarantee.

1 Guaranteed Delivery Date(s).  Shall have the meaning as set forth in Section 10.2.1.

1 Hazardous Materials.  Shall mean any hazardous substance or hazardous waste as defined in the Comprehensive Environmental Response, Compensation and Liability Act of 1980, as amended, the Resource Conservation and Recovery Act, as amended, the Hazardous Waste Transportation Act, as amended, and regulations promulgated pursuant to these Acts and any similar law or regulation in the United States or  equivalent laws and regulations issued by  U.S. federal and state governmental entities defining hazardous substances or hazardous waste, and any equipment containing polychlorinated biphenyls or asbestos that may become friable.

1 Heat Rate.  Shall mean the actual fuel energy consumed during the Performance Test determined from the actual lower heating value of the fuel multiplied by the quantity of fuel consumed and expressed in BTU, divided by the integrated Electrical Output measured in kWh at the generator terminals during the Performance Tests in accordance with the testing guidelines set forth in Exhibit F, expressed as BTU/kWh(LHV).

1 Heat Rate Guarantee.  Shall have the meaning as set forth in Exhibit B-3, Section B.3.5.1. 

1 Heat Rate Liquidated Damages.  Shall have the meaning as set forth in Exhibit B-3. 

1 Import Duties.  Shall, subject to Section 5.2.3, mean any taxes, customs, duties, fees, imposts, assessments, value added tax, and governmental charges that are payable upon or in relation to the importation of the Unit, drawings or designs into the United States. 

1 Installation Period.  Shall mean the period of 36 months from the receipt of the last Major Component of the Unit to the Delivery Point.

1 Insurability Certificate.  Shall have the meaning as set forth in Section 3.10.2.

1 Insurance Representative.  Shall have the meaning as set forth in Section 3.10.1.

1 Interest Rate.  Shall mean the Prime Rate as published by Citibank, N.A. at its New York City office plus two percent (2%) per annum, provided however, that the rate of interest hereunder shall never exceed the highest applicable lawful rate.  

1 kW.  Shall mean kilowatt.

1 kWh or kwh.  Shall mean kilowatt hour.

1 Lender.  Shall mean any financial institution or financier from which Purchaser is obtaining or has obtained financing in connection with the Facility and associated facilities and services.

1 Liquidated Damages.  Shall mean any or all Take Over Liquidated Damages, Document Liquidated Damages, Delivery Liquidated Damages and/or Performance Liquidated Damages.

1 Major Components.  Shall mean and consist of the following Unit components: Inlet Air System (including chiller coils and excluding inlet filter cartridges), Combustion Gas Turbine, Generator, PEECC, Combustion Turbine Accessory Skid and Exhaust Expansion Joint.

1 Marketing Agreement.  Shall have the meaning as set forth in Section 5.4.2.

1 Milestone.  Shall mean an event that triggers a responsibility of Purchaser to pay a Milestone Payment Amount as set forth and listed in Section 6.1.2

1 Milestone Payment Amount.  Shall mean the percentage of the  Purchase Amount due to Seller from Purchaser as set forth in Exhibit I-1.

1 Near Source Sound Level Guarantee.  Shall have the meaning as set forth in Exhibit B-3.

1 Net Cancellation Charge.  Shall have the meaning as set forth in Section 5.4.1(d).

1 Notice.  Shall mean any notification of one party hereto by the other party hereto with respect to any matter arising under or in connection with this Agreement, to be given as provided in Exhibit E.

1 Notice to Proceed.  Shall have the meaning as set forth in Section 7.1.

1 O&M Spares.  Shall have the meaning as set forth in Section 3.14.2.

1 Output Liquidated Damages.  Shall have the meaning as set forth in Section 10.9.1.1

1 Owner.  Shall mean Coyote Springs, 2, LLC.

1 Performance Liquidated Damages.  Shall mean the Output Liquidated Damages, Heat Rate Liquidated Damages, Exhaust Energy Liquidated Damages and Exhaust Temperature Liquidated Damages. 

1 Performance Test.  Shall mean the test(s) conducted at the Site on the Unit in accordance with the Test Procedures to determine Emissions, Heat Rate, Electrical Output, and Sound Levels.

1 Performance Test Completion Certificate.  Shall mean the certificate prepared by Purchaser in the format attached hereto as Exhibit G‑2 and provided to Seller, certifying the results of the Performance Tests that have been completed and quantifying Performance Liquidated Damages, if any, due.

1 Performance Test Certificate.  Shall mean the certificate prepared by Purchaser in the format attached hereto as Exhibit G‑1 and provided to Seller, certifying that a Performance Test has been completed and setting forth the results thereof in such detail to reflect the performance of the  Unit as tested with respect to Electrical Output, Emissions, Heat Rate, and Sound Levels.

1 Power Purchaser.  Shall mean the applicable utility or any power purchaser which has entered into contract with an Affiliate of Purchaser to purchase power from the Facility.

1 Purchaser’s Quality Assurance Manager.  Shall mean the person designated by Purchaser to approve the release to ship Major Components.

1 Primary Warranty Period.  Shall have the meaning as set forth in Section 14.1.1.

1 Project Manager.  Shall mean the project manager designated by Seller pursuant to Section 3.3(a) hereof.  

1 Proper Scope Value.  Shall have the meaning as set forth in Section 17.4.1.

1 Punchlist.  Shall mean the list of the incomplete or deficient work or materials associated with Seller’s Scope of Work, which is comprised of those items which are minor in nature and do not affect the performance of the Equipment, safety or personnel working on or operating the Equipment or the ability of the Equipment to be used for its intended purpose.  Such Punchlist shall be produced by Seller and approved by Purchaser.

1 Purchase Amount.  Shall mean the amount payable to Seller set forth in Section 5.1, as adjusted pursuant to the terms of this Agreement.

1 Purchaser.  Shall have the meaning of the entity defined as Purchaser in the Preamble and its successors and permitted assigns.

1 Purchaser’s Representative.  Shall mean the individual designated by Purchaser pursuant to Section 2.1(a)  hereof, who shall have the responsibility and authority specifically delegated to such individual by Purchaser and made known in writing to Seller.

1 Refund Amount.  Shall have the meaning as set forth in Section 17.4.1.

1 Retention Amount.  Shall have the meaning as set forth in Section 6.1.3.

1 Retention Letter of Credit.  Shall have the meaning as set forth in Section 6.1.3.

1 Scope of Supply.  Shall have the meaning as set forth in Exhibit B-1.

1 Scope of Work.  Shall mean all design, engineering, manufacture, delivery, transportation, technical direction of installation, training, other services, Equipment, drawings, documentation, supplies and materials to be performed and/or furnished by Seller (including that provided by its Vendors) pursuant to this Agreement or would have been reasonably expected to be supplied by a prudent supplier to ensure the successful operation of the Unit.

1 Scope Value Due.  Shall have the meaning as set forth in Section 17.4.1.

1 Seller.  Shall mean have the meaning of Seller as defined in the Preamble and its successors and permitted assigns.

1 Shortfall.  Shall mean the amount by which the Unit fails to meet a Guaranteed Level or a Specific Performance Level as applicable.  Such shortfall shall be measured in the same units as the respective guarantee.

1 Site.  Shall mean any part of the land where the Facility is to be constructed.

1 Sound Level Guarantees.  Shall mean the Specific Performance guarantees of the Far Field Sound Level Guarantee and the Near Source Sound Level Guarantee.

1 Sound Level Test.  Shall have the meaning as set forth in Exhibit B-3.

1 Sound Level Test Procedures.  Shall mean the test procedures used to measure Sound Levels as set forth in Exhibit F-1.

1 Sound Levels.  Shall mean the near source sound levels and the far field sound levels of the  Unit as measured during a Performance Test or Sound Level Test.

1 Spare Parts Amount.  Shall have the meaning as set forth in Section 3.14.2.

1 Specific Performance.  Shall mean, whether used by itself or as part of another defined term, an obligation that Seller must fulfill or achieve, or otherwise be in breach of its obligations hereunder.  Seller shall not be able to pay Liquidated Damages in lieu of meeting such specific performance requirements.

1 Specific Performance Electrical Output Guarantee.  Shall mean Specific Performance Electrical Output Guarantee as set forth in Exhibit B-3, Section B.3.4.2.  

1 Specific Performance Exhaust Gas Energy Guarantee.  Shall have the meaning  as set forth in Exhibit B-3, Section B.3.1.4.

1 Specific Performance Exhaust Gas Temperature Guarantee.  Shall have the meaning as set forth in Exhibit B-3, Section B.3.1.2.

1 Specific Performance Heat Rate Guarantee.  Shall have the meaning  as set forth in Exhibit B-3, Section B.3.5.2.

1 Specific Performance Levels.  Shall mean the Specific Performance Electrical Output Guarantee, Specific Performance  Heat Rate Guarantee, Exhaust Gas Energy Guarantee, Exhaust Gas Temperature Guarantee, Emissions Guarantee and Sound Level Guarantees.

1 Specification.  Shall mean the specification as issued by Purchaser for the design, manufacture, assembly set forth in Exhibit B, and the specification by Seller for the supply of the Unit as set forth in Exhibit B‑1.

1 Take Over.  Shall mean the Facility being deemed to have achieved Substantial Completion as set forth in the Owner Contract (substantial Completion meaning, accepted for commercial operation).

1 Take Over Liquidated Damages.  Shall have the meaning as set forth in Section 10.3.2.

1 Technical Direction of Installation.  Shall have the meaning and scope as set forth in Exhibit H-1.

1  Termination Costs.  Shall have the meaning as set forth in Section 17.4.2.

1 Termination Settlement.  Shall have the meaning as set forth in Section 17.4.4.

1 Test Procedures.  Shall have the meaning as set forth in Section 10.12.7.

1 Time for Completion.  Shall have the meaning set forth in the Recitals.

1 Training.  Shall have the meaning and scope as set forth in Exhibit H-2.

1 Unit.  Shall mean the gas turbine generator package already defined in the recitals of this Agreement.

1 Delivery Date.  Shall mean the date on which Seller delivers the Unit to the Delivery Point in accordance with Section 10.2.3 subject to the provisions of Section 3.10.

1 Vendor.  Shall mean any vendor, supplier or subcontractor utilized by Seller in the performance of the Scope of Work hereunder.  

1 Warranty Period.  Shall mean the Primary Warranty Period, and if applicable, the Extended Warranty Period collectively.

1 WestLB.  Shall have the meaning as set forth in the Preamble on Page 1.

ARTICLE II.  RESPONSIBILITIES OF PURCHASER AND AGENTtc \l1 "ARTICLE II.  RESPONSIBILITIES OF PURCHASER
2.1   Purchaser and Agent Responsibilitiestc \l2 "2.1   Purchaser Responsibilities.  Purchaser recognizes and acknowledges the duty to reasonably cooperate with Seller, and agrees not to wrongfully interfere with Seller’s agents, employees or Vendors during the performance of this Agreement.  Without limiting the generality of the foregoing, Purchaser and Agent (as the case may be) shall be responsible for the following matters and actions to be performed on a timely basis:

(a) Agent shall designate a Purchaser’s Representative and deliver a notice to Seller identifying Purchaser’s Representative, within thirty (30) days of the latest date of signature of this Agreement, who shall act as the primary point of contact for Seller with respect to the prosecution of the Scope of Work;

(b) Agent shall deliver a notice within thirty (30) days of [the latest date of signature of] this Agreement to Seller identifying such persons within Purchaser’s organization that have authority to approve Change Orders; and

(c) Purchaser shall pay to Seller the sums required to be paid by Purchaser pursuant to the terms of this Agreement.

(d) the Unit shall be installed, operated and maintained by either Purchaser or Agent as identified in Exhibit B-1, and as otherwise stated in the Agreement.

2.2   Purchaser Conduct TC "2.2   Purchaser Conduct" \f C \l "2" .  Each of Agent and Purchaser will comply with applicable regulatory requirements and Applicable Laws which pertain to Purchaser or Agent’s obligations under this Agreement. Unless otherwise agreed, Agent shall procure or cause to be procured the permits necessary for the installation and operation of the Equipment at the Site.

ARTICLE III.  RESPONSIBILITIES OF SELLERtc \l1 "ARTICLE III.  RESPONSIBILITIES OF SELLER
3.1   General Obligationstc \l2 "3.1   General Obligations.  Except as expressly set forth in this Agreement, Seller shall provide the new materials and supplies, technical and professional personnel and supervision at Seller’s facilities and as required for Seller to fulfill its transportation responsibilities, tools and equipment, and the services required for performance and timely completion of the Scope of Work, and shall be responsible for timely completing the Scope of Work in accordance with the terms of this Agreement, including all Exhibits.

References in the Specification to equipment, material, articles or patented processes by trade name, make, or catalog number, shall be regarded as the standard of quality to be met by Seller.  Seller may, subject to written notification to Purchaser, use any equipment, material, article, or process that is operationally, technically and functionally equivalent to that named in the Specification.  For the avoidance of doubt, all equipment, materials and components, whether or not specifically referenced in the Specification or elsewhere in the Agreement, which are incorporated by Seller or its Vendors  into the Scope of Work, shall be new, unrepaired and suitable for the purpose for which it is intended except as otherwise allowed pursuant to this Agreement.

3.2   Delivery of Equipment and Documentationtc \l2 "3.2   Delivery of Equipment and Documentation.  

3.2.1   Delivery to Delivery Pointtc \l3 "3.2.1   Delivery to Delivery Point.  Except as provided in Section 3.2.2, or Section 3.2.3, Seller shall deliver the Equipment to the Delivery Point (except as otherwise specifically set forth in the Agreement) in accordance with Section 10.2.

3.2.2   Not Usedtc \l3 "3.2.2   Not Used.

3.2.3   Impact Recorderstc \l3 "3.2.3   Impact Recorders.  Seller shall provide Purchaser with details of procedures pertaining to securing the Unit’s rotors during transportation.  If as a result of such review if Purchaser reasonable determines that impact recorders are required, Seller shall do so within the Purchase Amount.

3.2.4   Maximize Assemblytc \l3 "3.2.4   Maximize Assembly. Seller shall factory assemble the auxiliary items of Equipment into the skid configuration to the greatest practical extent considering the requirements of safe transportation of the Equipment, so as to minimize on-Site assemble, installation and erection time.  In the event Seller is not able to achieve skid assembly, Seller shall notify Purchaser of the difficulty and Seller and Purchaser shall seek a reasonable resolution.

3.2.5  Documentation Deliverytc \l3 "3.2.5  Documentation Delivery.  Seller shall deliver documentation as set forth in Section 10.1 by the dates set forth therein.

3.3   Relevant Informationtc \l2 "3.3   Relevant Information.  Seller shall provide on a timely basis to Purchaser information reasonably necessary to fulfill Seller’s obligations pursuant to this Agreement, including, without limitation:

(e) at the order definition meeting (the “ODM”) pursuant to Section 3.13, the identity of a project manager (the “Project Manager”) who shall have full supervision over the completion of  the Scope of Work and who shall act as the primary point of contact with Purchaser regarding all matters relating to the Scope of Work; 

(f) such information as is requested by Purchaser in dealing with the Power Purchaser and/or any governmental authority in matters relating to the Scope of Work.  Such obligation shall not include information such as grid or power generation studies for the total power system; and 

(g) the project management plan proposed for this Agreement to include, but shall not limited to, staffing, milestones, scheduling, quality control, transportation, technical interface, and other mutually agreed matters required to successfully manage the project to conclusion.

3.4   Hazardous Materials Notificationtc \l2 "3.4   Hazardous Materials Notification.  

(h) Seller warrants to Purchaser that in relation to the Scope of Work, it will use reasonable skill and care to ensure that there will not be Hazardous Material specified or incorporated into the Scope of Work; provided that where in the opinion of Seller this results in any conflict with any relevant statutory requirements or where the Scope of Work would be prejudiced through lack of suitable alternatives, then Seller shall immediately notify Purchaser in writing specifying the conflict or prejudice which has arisen and the substance which Seller wishes to stipulate or use and Seller shall not stipulate or use the same without, in each case, the prior written consent of Purchaser which shall not be unreasonably withheld.

(i) Seller shall immediately upon the request of Purchaser certify in writing that to the best of its knowledge that no Hazardous Materials have been specified or incorporated in the Scope of Work. In the event Seller, with Purchaser’s approval, incorporates any Hazardous Materials into the Equipment, Seller shall provide Purchaser with notification as set forth in Exhibit O.

3.5   Employment of Trained and Experienced Personneltc \l2 "3.5   Employment of Trained and Experienced Personnel.  Seller shall be responsible for employing and utilizing personnel and for ensuring that its Vendors employ and utilize personnel who possess the proper training and experience and are capable of performing the tasks for which they are employed or utilized. 

3.6   Not Used.tc \l2 "3.6   Not Used. 

3.7   Guaranteetc \l2 "3.7   Guarantee.  As a condition precedent to the effectiveness of any assignment pursuant to Section 22.1, Seller shall deliver to Purchaser an unconditional guarantee in the form set forth in  Exhibit [C-2]  hereto, which shall guarantee full payment and performance of all Seller obligations under this Agreement as due in accordance with the terms of this Agreement.  

3.8   Compliance with Governmental Rules and the Requirements of this Agreementtc \l2 "3.8   Compliance with Governmental Rules and the Requirements of this Agreement.  Seller shall comply with all Applicable Laws including but not limited to those described in the categories enumerated below.

(j) Seller Conduct.  Seller shall comply with applicable regulatory requirements including, without limitation, all Applicable Laws issued or promulgated by units of government and regulatory bodies with jurisdiction over any aspect of the performance of this Agreement by Seller. Seller shall not act in violation of the U.S. Foreign Corrupt Practices Act or similar law of the United States, and in connection therewith shall not make any payments, loans, or gifts directly or indirectly, to or for the use or benefit of any official employee, agency or instrumentality of any government, political party or candidate thereof, or any other person or entity, the payment of which would violate the laws or policies of the United States, or the country or countries in which the Scope of Work is performed, in whole or in part.  Seller shall possess or procure all permits, certificates, and licenses necessary to allow Seller to perform this Agreement at all Seller or Vendor locations of performance and shall ensure that Vendors have all permits, certificates, and licenses necessary for such Vendors to perform under this Agreement. Seller shall answer promptly and in reasonable detail any questionnaire or other written or oral communications, to the extent the same pertain to compliance with this Section 3.8 (a) or (b) whether such questionnaires or communications are from Purchaser, their outside auditors, or other representatives.  Seller further agrees to pay any government assessed penalties, fines, and charges, and associated damages, costs, losses, and expenses (including, without limitation, court costs and attorneys’ fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, in connection with, arising out of or related to any noncompliance of Seller’s performance of this Agreement or any portion thereof with any or all of the above laws, regulations, rules, orders, codes, criteria, standards, ordinances or resolutions.  

(k) Employment Practices.

(1) Seller agrees that it shall be at all times during the term of this Agreement in full compliance with all Applicable Laws relative to Seller’s employment of employees and agents of Seller.

(2) Seller agrees to pay any government assessed penalties, fines, and charges, and associated damages, costs, losses, expenses (including, without limitation, court costs and attorneys’ fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, based on, in connection with, related to or arising from Seller’s noncompliance with this Section 3.8(b).

(l) Scope of Work to Comply with Applicable Laws and Specifications.  Subject to the provisions of Section  3.8(c)(4):

(1) Seller shall cause the Scope of Work to comply with Applicable Laws that were:

(i) in effect on the Effective Date; or 

(ii) were not yet in effect on the Effective Date, but at such time a change to such valid Applicable Laws, issued or promulgated by units of government and regulatory bodies had passed but was not yet effective;

Seller shall also comply with the Specification in effect on the date this Agreement is signed.  In the event Seller fails to cause the Scope of Work to so comply with the Specification and Applicable Laws, Seller shall correct such noncomplying Scope of Work or portion thereof as necessary to comply with the above.  Seller shall bear the costs of correction of such noncomplying Scope of Work.  In the event that Purchaser reasonably determines that Seller is either not capable of performing the corrections or not capable of performing such corrections in time to meet Purchaser’s requirements, Purchaser may, at Seller’s expense, have the corrections made by a third party or make them itself; provided, however prior to Purchaser having the corrections performed by a third party or itself Purchaser shall have provided Seller notice of its determination that it believes Seller is not capable of such performance of work or performing such corrections in a timely manner. 

(2)
In the event that Seller does not comply with the Specification or Applicable Law, and Purchaser at its sole determination agrees Seller cannot reasonably incorporate the changes necessary for Seller to comply, Purchaser, in its sole discretion, may either terminate the Contract in accordance with the Article XVII, or direct Seller to complete the Equipment without such changes, in which case Purchaser shall assume full responsibility for obtaining any necessary waivers from the appropriate federal, state or local authorities.

(3)
Seller shall, on a reasonable efforts basis, advise Purchaser of pending Applicable Laws so that Purchaser may make an informed decision as to whether to have the Equipment designed in anticipation of such pending change as it affects the Scope of Work.

(4)
In the event a Change in Law occurs subsequent to the times set forth in Section 3.8c(1), Seller shall prepare a request for a Change Order to Purchaser identifying the nature of the change, including any resultant extensions of time to the performance of the Scope of Work and the Purchase Amount.  In the event that Purchaser elects to not have Seller comply with such change, Purchaser shall indemnify Seller for such failure of the Scope of Work to comply with such new law requirement.

3.9   Approved Vendorstc \l2 "3.9   Approved Vendors.  Purchaser agrees that Seller may utilize the Vendors for performance of the Scope of Work as listed in Exhibit B-4.

 3.10  Packing and Insurance Surveyortc \l2 "3.10  Packing and Insurance Surveyor.  

3.10.1   Packing Recommendationtc \l3 "3.10.1   Packing Recommendation.  Seller shall perform all packaging of the Equipment to the highest commercial standard practices of the industry to prevent damage during its handling and transportation to the Delivery Point.  Seller shall respond to and comply with Purchaser’s insurance representative’s (salvage association or similar insurance surveyor as appointed by Purchaser) (the “Insurance Representative”) recommendations concerning:

 (i)
packaging of the Equipment; 

(ii)
Seller’s execution of the load plan on its transport to preclude damage during transit;

(iii)
transshipment;

(iv)
movement to the Delivery Point, including route surveys; and

(v)
tandem barges will not be allowed.

Seller shall immediately notify Purchaser of any unreasonable recommendations.

3.10.2   Insurability Certificatetc \l3 "3.10.2   Insurability Certificate.  Seller expressly acknowledges and agrees that it will not commence transport of the items of Equipment unless;

(i)
the Insurance Representative conducts a load plan and load survey and issues an insurance certificate, (the “Insurability Certificate”) attesting that its recommendations were carried out for such shipment with respect to the Equipment listed in Exhibit L; or

(ii)
Purchaser’s Representative expressly waives such requirement for that shipment.

3.10.3   Notice of Shipmenttc \l3 "3.10.3   Notice of Shipment.  Seller recognizes that failing to comply with this Section may jeopardize Purchaser’s insurance program.  Seller shall provide Purchaser’s Representative with reasonable advance notice of the expected packing date and the expected loading date of any such shipment, and shall provide two business days advance notice of the actual packing date and the actual loading date of such shipment.  Purchaser may designate its Insurance Representatives as recipient of such notice.  Provided Seller has provided Purchaser with such notice by such notice dates, if the Insurance Representative is not available to perform the necessary inspections on the dates of loading indicated in Seller’s final notice, or the recommendations of the Insurance Representative are mutually agreed by Seller and Purchaser to have been unreasonable, Purchaser shall extend the Guaranteed Delivery Date to the extent Seller is delayed by such unavailability or unreasonable recommendations, and shall compensate Seller for any applicable costs including demurrage attributable thereto.  Seller shall provide the Insurance Representative with a load and transportation plan forty five (45) days prior to loading. Seller acknowledges that all efforts and delays (other than as set forth in this Section 3.10) associated with receiving the Insurability Certificate shall not be grounds for extension to the Guaranteed Delivery Date(s). 

3.10.4   Compliance with Recommendationtc \l3 "3.10.4   Compliance with Recommendation.  Seller’s compliance with the Insurance Representative’s recommendations shall not relieve Seller of its responsibility for risk of loss and damage of the Equipment in accordance with this Agreement through delivery to the Delivery Point.

3.10.5   Coordinationtc \l3 "3.10.5   Coordination.  Seller agrees to host a transportation coordination meeting at its facility no later than 45 days prior to shipment of the first Major Component on a mutually agreed date.  Purchaser shall coordinate attendance by its Insurance Representative.

3.11  Financing and Insurance Assistancetc \l2 "3.11  Financing and Insurance Assistance.  Seller shall provide such information as Purchaser may reasonably request in connection with obtaining financing and insurance for the Facility including without limitation providing information related to design, engineering and status of the completion of the Scope of Work and Seller’s credentials and experience, and as required perform reasonable travel.  Purchaser shall reimburse Seller at commercially reasonable rates for its time in providing information not related to the Scope of Work.  Lender and the Lender’s engineers and consultants shall have the right to participate in all inspections conducted by Purchaser under this Agreement and to attend all tests of the Equipment.  At Purchaser’s request, Seller shall furnish to Lender copies of notices given to Purchaser hereunder. 

3.12  Purchaser Permit Supporttc \l2 "3.12  Purchaser Permit Support.  Seller shall provide all information, data and documents in a timely fashion that Purchaser may reasonably require for Purchaser to obtain Facility permits.

3.13  Order Definition Meetingtc \l2 "3.13  Order Definition Meeting.  Seller agrees to host an ODM at its facility to finalize project scope issues for the purpose of Seller issue of ancillary equipment order and commencement of detailed engineering.  The parties agree that such equipment order releases and detailed engineering shall not proceed prior to the completion of the ODM except as may be mutually agreed or otherwise required in the Agreement.

3.14  Spare Partstc \l2 "3.14  Spare Parts.

3.14.1   Commissioning Sparestc \l3 "3.14.1   Commissioning Spares.  Seller’s representative priced list of start-up and commissioning spares and a representative list of special tools needed during start-up and commissioning are set forth in Exhibit M-2.  Seller shall provide to Purchaser at no additional charge: (i) all spare parts necessary to achieve start up, commissioning, performance testing, and (ii) all installation and maintenance tools that are not normally found available in the market place.

3.14.2  Operating Sparestc \l3 "3.14.2  Operating Spares.  Set forth in Exhibit M-1 is a priced listing of operating and maintenance spare parts (the “O&M Spares”) for the Unit.  In addition to the Purchase Amount, Purchaser may elect to purchase any quantity or type of spare parts listed in Exhibit M-1 through the validity period stated in the footer of Exhibit M-1.  Spare parts that are covered by this Section 3.14.2 that are ordered by Purchaser shall be delivered FOB factory in accordance with Exhibit M-1.  The purchase value of any ordered spare parts covered by this Section 3.14.2  shall not be included in the Purchase Amount, and will be referred to as the “Spare Parts Amount”.  Purchaser’s purchase or lack of purchase of O&M Spares  under this Agreement shall not preclude Purchaser, or Purchaser’s operator, from purchasing such spare parts under separate agreement with Seller.

3.15  Key Personneltc \l2 "3.15  Key Personnel.  Seller shall provide Purchaser with biographical data for the Project Manager, and lead technical advisor for TDI.  If, in the reasonable opinion of Purchaser, Purchaser determines such a key person is not adequately performing, Purchaser may require Seller to remove such person from work on the Scope of Work under this Agreement and replace such person with a satisfactory replacement.

ARTICLE IV.  RESPONSIBILITY FOR INFORMATIONtc \l1 "ARTICLE IV.  RESPONSIBILITY FOR INFORMATION
4.1   Purchaser Supplied Informationtc \l2 "4.1   Purchaser Supplied Information.  Except to the extent that the information provided by Purchaser to Seller is in the form of a specification or performance requirement specifically called out in this Agreement or performance requirements which Purchaser is obligated to provide under the Agreement, it is Seller’s responsibility to ensure that the information provided to Seller by Purchaser is accurate, correct, complete and fit for the particular purpose(s) for which Seller utilizes it. 

ARTICLE V.  PURCHASE AMOUNT AND OTHER CHARGEStc \l1 "ARTICLE V.  PURCHASE AMOUNT AND OTHER CHARGES
5.1   Purchase Amounttc \l2 "5.1   Purchase Amount. 

5.1.1   Purchase Amounttc \l3 "5.1.1   Purchase Amount.  The purchase amount as set forth in Exhibit N-1 (the “Purchase Amount”) shall be Seller’s full compensation for Seller’s performance of the Scope of Work including but not limited to Seller delivering the Equipment to the Delivery Point, as provided hereunder, which shall be paid in accordance with Article VI.  The Purchase Amount is subject to increases or decreases only as provided in Section 5.3 or Change Orders with respect to the Scope of Work approved in accordance with Article XI.  The Purchase Amount shall be complete compensation for Seller to perform its obligations under this Agreement.

Exhibit N-1 sets forth a full reconciliation of the Purchase Amount.  Exhibit N-2 lists options of the Purchaser, prices and times by which the options must be exercised by Purchaser.  If an option is exercised by Purchaser, the applicable option amount shall be used to adjust the Purchase Amount. 

5.2   Taxes and Contributionstc \l2 "5.2   Taxes and Contributions.

5.2.1   Seller Responsibility for Personal Taxestc \l3 "5.2.1   Seller Responsibility for Personal Taxes.  Seller assumes full responsibility for and agrees to pay all contributions and taxes payable under all Applicable Laws pertaining to social security laws, unemployment compensation laws and income tax laws as they apply to Seller’s and Vendor’s employees engaged in the performance of the Scope of Work.  Seller acknowledges that Purchaser has no responsibility for such taxes as they apply to Seller, Seller’s employees or the employees of Vendors.

5.2.2   Seller’s Responsibility for Taxestc \l3 "5.2.2   Seller's Responsibility for Taxes.  Except as provided for in Section 5.2.3 Seller agrees to pay, and shall be responsible for, within the Purchase Amount, corporate income tax, export duties, Import Duties, customs clearance, sales taxes, or other similar taxes associated with the design, manufacture and delivery of the Equipment to the Delivery Point and the performance of the Scope of Work assessed by any federal, state country, local or other legal taxing authority and any of its subdivisions, and to pay any and all valid sales or use taxes levied on general office, engineering and drafting supplies, materials, equipment, and services performed by Seller hereunder.

5.2.3   Taxes in the Project Statetc \l3 "5.2.3   Taxes in the Project State.  The Purchase Amount excludes any US state or local jurisdiction imposed property, license privilege, sales, use, excise, gross receipts, valued added, or similar tax which may now or hereafter be applicable to, measured by, or imposed upon with respect to the transaction, Seller’s Scope of Work, its sale, its value, its presence in the project state’s taxing jurisdiction or its use, or any services performed in connection therewith.  Such taxes are for the account of Purchaser and Purchaser agrees to pay any such tax when due or reimburse Seller within twenty five (25) days after the date of Seller’s invoice Purchaser for any such tax which it is required to pay.  Should Purchaser be exempted from any such tax it shall provide Seller with certification prior to transfer of title of such Work, or at the time the certification is obtained, whichever first occurs.

5.2.4   Tax Penaltiestc \l3 "5.2.4   Tax Penalties.  Seller further agrees to pay any tax, interest, penalty, fines, costs, losses and expenses (including, without limitation, court costs and attorney’s fees) of whatever kind, which Purchaser may incur, be required by law to pay, or be liable for as a result of, arising from, in connection with, related to or based on any failure to withhold any amounts from any payments made or any amounts which Seller fails to pay in connection with, as a result of, arising from or based on the Scope of Work  or otherwise comply with this Section, except and to the extent such failure is attributable to Purchaser’s negligent act or failure to act, in which case Purchaser shall be responsible for and agrees to pay the portion of such tax related amounts as referred to above as are attributable to Purchaser’s negligent act or failure to act.   

5.3   Changes to the Purchase Amount.tc \l2 "5.3   Changes to the Purchase Amount.  The Purchase Amount may only be adjusted in the following circumstances:

(a)
Change in Law requiring changes as provided in Section 3.8c(4);

(b)
suspension pursuant to Section 5.5;

(c)
breach or default of Contract by Purchaser or Seller;

(d)
not used;

(e)
an Event of Force Majeure in which Purchaser is the Affected Party; exceeding a duration in the aggregate of 30 Days in accordance with Section 18.9; and

(f)
Change Orders issued pursuant to Article XI; and

(g)
Purchaser exercising options such as cancellation pursuant to Section 5.4.1 of this Agreement.

Seller’s entitlement to an increase in the Purchase Amount shall be conditional upon:

 (h)
its having used reasonable endeavors to mitigate the cost increase (except for Purchaser’s exercise of options or Purchaser instructing Seller in its performance of any option, then compliance would not be considered a breach of this provision);

(i)
its having given notice in accordance with the terms of this Agreement; and

(j)
the cost increase not being attributable to its default

5.4   Cancellationtc \l2 "5.4   Cancellation.

5.4.1   Cancellation by Purchasertc \l3 "5.4.1   Cancellation by Purchaser.  Purchaser may cancel this Agreement at any time in whole or in part, without cause and for its own convenience, upon written notice to Seller.  If Purchaser cancels this Agreement under this Section 5.4.1, then Purchaser shall pay Seller the Cancellation Charge applicable to the canceled Unit in accordance with Exhibit I within thirty (30) days after the effective date of such cancellation.  If Purchaser cancels this Agreement pursuant to this Section 5.4.1, Seller shall retain title to the Equipment unless title has passed or will pass to Purchaser pursuant to Article XV.  For the avoidance of doubt Seller will not cease manufacture of the Unit for reasons of Purchaser cancellation or suspension.

5.4.2   Marketing Agreementtc \l3 "5.4.2   Marketing Agreement.  In the event the project is canceled and Purchaser decides to complete the Unit, at Purchaser’s request, Purchaser and Seller may enter into an agreement in which the parties will cooperate to sell the Unit to which Purchaser has taken title.

5.5   Suspension or Change of Deliverytc \l2 "5.5   Suspension or Change of Delivery. 

5.5.1   Purchaser shall be entitled to suspend delivery to the Delivery Point and make such changes to the Delivery Point as it may deem necessary in accordance with Section 5.5.2 and Section 10.2.1.

5.5.2   If Purchaser instructs Seller by written notice, such notice to be no later than ninety (90) days prior to the shipment of the Unit and the Major Components thereof, and the Equipment or any part of the Equipment cannot be shipped to the Delivery Point in accordance with the Agreement when ready, due to any cause not attributable to Seller, Seller shall ship such Equipment to such other locations in the U.S. as Purchaser shall designate.  Cost increases or decreases which are directly associated with delivering the Unit to a changed Delivery Point such as offloading, transshipments or change of mode of transport, shall be grounds for a Change Order.  If such Equipment is directed by Purchaser to be placed in storage, including storage at the facility where manufactured, the following conditions shall apply: (1) for the purpose of assessing Liquidated Damages and final payment, Seller’s delivery obligation shall be deemed fulfilled and title shall thereupon pass to Purchaser if it had not already passed; (2) any amounts otherwise payable to Seller upon delivery shall be payable upon presentation of Seller’s invoices pursuant to Section 6.1.1; (3) all expenses incurred by Seller, such as preparation for and placement into storage, handling, inspection, preservation, insurance, storage, removal charges and any taxes (anything to the contrary in the Agreement notwithstanding), shall be added by Change Order and payable by Purchaser upon submission of Seller’s invoices pursuant to Section 6.1.1; and (4) if the Unit is placed in storage other than at its final use point, when conditions permit, Seller shall arrange on behalf of Purchaser and at Purchaser’s expense for any additional or incremental costs of shipment of the Equipment not then included in Seller’s Scope of Work.  In the event, as a result of direction by Purchaser, to store the Equipment in lieu of shipping to the Delivery Point and to retain care and custody, Seller will also retain risk of damage and loss.

ARTICLE VI.  PAYMENT TERMStc \l1 "ARTICLE VI.  PAYMENT TERMS
6.1   Payment of Purchase Amounttc \l2 "6.1   Payment of Purchase Amount.

6.1.1   Payment Periods.tc \l3 "6.1.1   Payment Periods.  Payment of the Milestone Payment Amount, unless otherwise noted in [Exhibit I-1], shall be due and payable by Purchaser to Seller on the dates set forth in [_________], provided that:

(i)
Seller has achieved the applicable Milestone; and 

(ii)
Purchaser has received a properly prepared invoice for such Milestone Payment Amount and any other documentation supporting said payments thirty (30) days prior to the Payment Date.

Payment of the Spare Parts Amount, to the extent Purchaser orders O&M Spares, shall be due and payable by Purchaser to Seller within thirty (30) days of:

(x)
Seller’s proper delivery of all of the O&M Spares to Purchaser’s carrier at the factory; and

(y)
Purchaser’s receipt of a properly prepared invoice for such Spare Parts Amount.

6.1.2   Payment Milestonestc \l3 "6.1.2   Payment Milestones.  The detailed payment milestone schedule is set forth in [Exhibit I-1].

Payment of the final five percent (5%) of the Purchase Amount is subject to Section 6.1.3.

For foreign sourced Major Components, with respect to actions triggered by shipment, shipment shall be understood to occur upon clearance from customs at the U.S. port of import and departure to the Site.

6.1.3   Retentiontc \l3 "6.1.3   Retention.  As set out in the payment schedule set forth in Section 6.1.2 Purchaser shall retain the last five percent (5%) of the Purchase Amount (the “Retention Amount”) until the expiry of the Primary Warranty Period; provided, however, Purchaser shall pay Seller the Retention Amount as earned when:

(i)
Seller satisfies the requirements set forth in Section 6.6; and

(ii)
Seller provides the Retention Letter of Credit in the amount of five (5%) percent of the Purchase Amount.

Seller shall present as the “Retention Letter of Credit” an irrevocable on demand retention letter of credit for the full amount of the Retention Amount in a form generally in accordance with the sample set forth in Exhibit D from U.S. bank located in the U.S. acceptable to Purchaser.

6.2   Payment Disputestc \l2 "6.2   Payment Disputes.  Payment of any invoices or portions of invoices shall not prejudice the right of Purchaser to protest or question the correctness thereof or Seller’s compliance with the terms of this Agreement and the Scope of Work or any portion thereof or prejudice or constitute a waiver of any right of Purchaser hereunder.  Any amount questioned by either party and found to be in such party’s favor shall be refunded or paid, as appropriate.  In the event an amount is withheld because of a dispute, and it is subsequently determined that the disputed amount or a portion of the disputed amount was due and payable, interest shall accrue at the Interest Rate commencing on the date the payment would have been payable if the dispute had not occurred.  Seller’s acceptance of partial payment of the Purchase Amount shall not be deemed to constitute a waiver of the right to receive amounts which are then in dispute, and Seller and Purchaser shall use their best efforts to resolve all disputed amounts as soon as practicable.  Any undisputed amounts not paid when due shall bear interest at the Interest Rate.

6.3   Payments Withheld or Offsettc \l2 "6.3   Payments Withheld or Offset.

6.3.1   Payments Withheldtc \l3 "6.3.1   Payments Withheld.  Purchaser may, following notice to Seller of its intent to withhold, and Seller not having eliminated the basis for the withholding within thirty (30) days of Purchaser’s notice, withhold payment on an invoice or a portion thereof, in an amount and to such extent as may be reasonably necessary, subject to the dispute resolution provisions of Article XXVI, to protect Purchaser from loss because of:

(m) defective work or Equipment not remedied pursuant to Section 9.5 or the warranty provisions of Article XIV;

(n) third party suits, stop notices or liens for which Seller is liable under this Agreement, whether directly or pursuant to any indemnification obligation hereunder, (other than those provided for by insurance, bonds or other security) made on or filed with Purchaser or with respect to the Site or the project and not cleared by Seller by payment, deposit or otherwise to the reasonable satisfaction of Purchaser within ten (10) days after receipt by Seller of written notice from Purchaser requesting such action; and

(o) uninsured damage to Purchaser or Vendor any which results solely from Seller’s failure to obtain or maintain the insurance required by the provisions of Article XIX or from any action or inaction by Seller or any Vendor which excuses any insurer from liability for any loss or claim otherwise covered by insurance.

In the event a payment is improperly withheld or not paid when due and payable, such payment amounts due and payable shall accrue interest at the Interest Rate commencing on the date that payment would have been payable, had the withholding not occurred.

6.3.2   Offset for Liquidated Damagestc \l3 "6.3.2   Offset for Liquidated Damages.  Purchaser shall have the right to offset from  any payments due to Seller  (or draw against the Retention Amount or Retention Letter of Credit in cases where no amounts remain to be invoiced), any amounts due to Purchaser from Seller, including, but not limited to, the amount of any Liquidated Damages due from Seller.  In the event the Liquidated Damages exceed the payment amount, Retention Amount or remaining value of the Retention Letter of Credit, Purchaser shall retain the payment amount and invoice the excess amount of Liquidated Damages in accordance with Section 6.4.  In the event Purchaser offsets a Liquidated Damage which Seller disputes and it is subsequently determined that amount or a portion of the disputed amount should not have been offset, interest on the portion of the offset that should not have been offset shall accrue at the Interest Rate commencing on the date the payment that was offset would have been payable if the amount had not been offset.

6.4   Payment of Liquidated Damagestc \l2 "6.4   Payment of Liquidated Damages.  

6.4.1  Payment of Document Delivery Damagestc \l3 "6.4.1  Payment of Document Delivery Damages.  Purchaser may upon the fifth (5th) day of each month, invoice Seller for any Document Delivery Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such Document Delivery Liquidated Damages, Seller shall pay such invoiced amount within thirty (30) days of receipt of Purchaser’s invoice. 

6.4.2   Payment of Delivery Liquidated Damagestc \l3 "6.4.2   Payment of Delivery Liquidated Damages.  Purchaser may upon the fifth (5th) day of each month, invoice Seller for any Delivery Liquidated Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such Delivery Liquidated Damages, Seller shall pay such invoiced amount within thirty (30) days of receipt of Purchaser’s invoice.

6.4.3   Payment of Take Over Liquidated Damagestc \l3 "6.4.3   Payment of Take Over Liquidated Damages.  Purchaser may upon the fifth (5th) day of each month invoice Seller for any Take Over Liquidated Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such Take Over Liquidated Damages, Seller shall pay such invoiced amount within thirty (30) days of receipt of Purchaser’s invoice.

6.4.4   Payment of Performance Liquidated Damagestc \l3 "6.4.4   Payment of Performance Liquidated Damages.  Performance Liquidated Damages, if any, shall be calculated in accordance with Section 10.9.1 and set out in the Unit’s Performance Test Completion Certificate as prepared by Purchaser after completion of the Performance Test demonstrating that the Unit has not met the Guaranteed Levels.  Purchaser may invoice Seller for Performance Liquidated Damages upon completion of the Performance Test on the Unit.  Purchaser may invoice for Performance Liquidated Damages regardless of whether or not Seller has achieved the Specific Performance Levels that correspond with the Guaranteed Levels.  In the event that the Performance Test which is the basis for the Performance Liquidated Damages occurred after Take Over, the effective date of delivery of the invoice shall be the date of delivery of the invoice to Seller.  Payment of the Performance Liquidated Damages shall be due within thirty (30) days of the effective date of delivery of the invoice.

6.5   Not Usedtc \l2 "6.5   Not Used.

6.6   Lien Releasetc \l2 "6.6   Lien Release.  Seller represents that all amounts reflected on invoices submitted by Seller for payment are accurate, just, due and owing under the terms of this Agreement.  Purchaser shall not be required to make a milestone payment unless such invoice is accompanied with its affirmation warranting that all services, equipment, materials and information for which Seller seeks payment are free and clear of liens, claims, security interests and encumbrances arising in favor of Seller and its Vendors, and other persons or entities able to make a claim by reason of having provided labor, materials or equipment relating to performance of this Agreement or any portion thereof.  Seller agrees and represents that in submitting an invoice, Seller waives and releases all liens, claims, security interests and other encumbrances arising in favor of Seller by reason of having provided labor, materials or equipment relating to performance of this Agreement or any portion thereof, to the extent of such invoice.  In the case of payment of the Retention Amount, Seller shall not be entitled to final payment of such Retention Amount unless and until Seller submits to Purchaser:

(i)
an affidavit in the form set forth in Exhibit S; and

(ii)
a release and waiver of liens, claims, security interests and encumbrances for payment for labor, material and services arising out of the Scope of Work for Seller.

6.7   Invoicestc \l2 "6.7   Invoices.

6.7.1   Contract Referencetc \l3 "6.7.1   Contract Reference.  Each invoice will reference the project name and contract number as shown in [Exhibit I-1].

6.7.2   Payee and Address for Invoicestc \l3 "6.7.2   Payee and Address for Invoices.  Invoices will be made out as payable by and mailed or hand carried to the address set forth in Exhibit I-1 following the Milestone Payment Schedule. 

Purchaser anticipates that the mailing address of the invoice may change, and agrees to notify Seller of such change prior to the change. 

6.7.3   Date of Receipttc \l3 "6.7.3   Date of Receipt.  Date of receipt of invoice by Purchaser will be evidenced by date stamp, or other generally accepted date receipting system.

6.8   Method of Paymenttc \l2 "6.8   Method of Payment.  Payment will be made by electronic wire transfer, unless otherwise requested by Seller, to a United States bank within the United States.  Seller’s invoices must provide all necessary information (including Tax I.D. and account number) to enable Purchaser to effect such payment.

6.9   Payments Not Acceptance of Worktc \l2 "6.9   Payments Not Acceptance of Work.  No payment made by Purchaser hereunder shall be considered or deemed to represent that Purchaser has inspected the work or Equipment or checked the quality or quantity thereof or that Purchaser knows or has ascertained how or for what purpose Seller has used sums previously paid, and shall not be deemed or construed as an approval or acceptance of any work or Equipment or Seller’s compliance with any other of its obligations under this Agreement or as a waiver of any claim or right Purchaser may have hereunder.

ARTICLE VII.  NOTICE TO PROCEED AND TERMINATIONtc \l1 "ARTICLE VII.  NOTICE TO PROCEED AND TERMINATION
7.1   Notice to Proceedtc \l2 "7.1   Notice to Proceed.  The full notice to proceed shall be deemed, as of the Effective Date, to have been issued by Purchaser (the “Notice to Proceed”).  Such notice authorized Seller to proceed with the full Scope of Work subject to the terms of this Agreement.

7.2   Not Usedtc \l2 "7.2   Not Used.  

7.3   Terminationtc \l2 "7.3   Termination.  This Agreement shall terminate upon the earlier of:

(i)
the cancellation by Purchaser of all the Scope of Work under Section 5.4; or

(ii)
termination due to an event of default by Seller or Purchaser under Article XVII; or

(iii)
when all obligations of the Parties under this Agreement are complete; or

(iv)
cancellation for an Event of Force Majeure under Section 18.10

after payments by both parties of amounts due by each party under this Agreement; provided, however, that the rights and obligations of the parties under Articles XVII (Default), XX (Indemnification), XXI (Non‑Disclosure of Information), Section 30.2 (Governing Law), XXVI (Arbitration) and XXVII (Limitation of Liability) shall survive termination of the Agreement; except that, if termination occurs under (i) or (ii) above, obligations under Article XIV (Warranties) shall also survive.

ARTICLE VIII.  RESERVEDtc \l1 "ARTICLE VIII.  RESERVED
ARTICLE IX.  INSPECTION AND CORRECTION OF WORKtc \l1 "ARTICLE IX.  INSPECTION AND CORRECTION OF WORK
9.1   Inspectionstc \l2 "9.1   Inspections.  Seller shall provide Purchaser and Lender, or their designated representatives access to the Scope of Work at all reasonable times wherever in preparation or progress and shall work closely with Purchaser in performing this Agreement.  Purchaser, or its designated representatives, shall have the right  from time to time during this Agreement to observe, inspect, examine and review, Seller’s performance of this Agreement.  Purchaser’s or its designated representative’s (provided such representative is not employed, affiliated or in competitive activities with Seller) rights to inspect under this Section 9.1 shall include but not be limited to manufacturing schedules; compliance with Specification; workmanship; dimensional tolerances; production tests; production inspections; assembly of components; panel inspection and testing; or witnessing testing of Equipment at any stage of design, procurement, production, or manufacture at  Seller’s works or those of its Vendors to verify that the Equipment conforms to the specified requirements of this Agreement. However, any observance, inspection or review of performance of this Agreement shall not constitute or be deemed to be actual control or a right to control Seller, its employees, agents, personnel, Affiliates, or Vendors.  Purchaser’s or its designated representative’s inspection of any part of the Equipment shall in no way affect Seller’s obligation to perform the Scope of Work in accordance with the Specification and all other terms of this Agreement, and any audit, examination, inspection, review, or testing by Purchaser shall not constitute acceptance or prejudice, be a waiver, or be deemed to be a waiver of any of Purchaser’s rights hereunder or of its rights to reject defective performance of this Agreement or release Seller from any obligation under this Agreement.  Seller shall not be required to provide Purchaser or Purchaser’s representative access to area’s where Seller is performing proprietary work unless a portion of the Scope of Work is being performed in such an area.  In such event Seller may take measures as it deems appropriate to isolate other ongoing proprietary work from Purchaser’s or Purchaser’s representative’s view, or if not practical, Purchaser agrees to enter into a mutually agreeable Confidentiality Agreement pertaining to such proprietary work.

9.2   Resident Facilitiestc \l2 "9.2   Resident Facilities.  If reasonably requested by Purchaser,  Seller will provide facilities as reasonably available for a resident quality representative in Seller’s works and those of its Vendors who are manufacturing Major Components.  

9.3   Quality Plantc \l2 "9.3   Quality Plan.  Seller shall maintain a quality plan compliant with ISO 9001, 1994 and with the quality assurance plan set forth in Exhibit J, detailing:

(i)
specific authorities and responsibilities;

(ii)
procedures, methods and work instructions; and

(iii)
inspection and test plans.

In the event of a conflict between Exhibit J, ISO 9001, 1994 and Seller’s quality system, the order of precedence shall be, ISO 9001, 1994, Seller’s quality system and Exhibit J.

9.4   Noticetc \l2 "9.4   Notice.   By no later than ninety (90) days after the latest date of signing of the Agreement, Seller shall prepare its proposed schedule of witness test points set forth in Exhibit R, excluding those that have transpired on the Unit being manufactured, (in such case test and inspection results shall be provided) for Purchaser’s review and approval, which approval shall not be unreasonably withheld.  Seller shall provide Purchaser with a notice of the date of a witness test point not less than fourteen (14) days prior to such date.

9.5   Correction of Equipmenttc \l2 "9.5   Correction of Equipment.  Prior to Acceptance, Seller shall, at its sole cost and expense and with exception of defects included in the Punchlist, promptly correct any part of the Equipment which is defective or not in accordance with this Agreement, regardless of the stage of its completion or the time or place of discovery of such defects  and regardless of whether Purchaser has previously paid for or accepted such part of the Equipment through oversight or otherwise. Seller shall replace or correct such defective work or condition such that the Equipment is in accordance with this Agreement, including the Specification.  Seller may repair (making an item functional, but not necessarily conforming the work to its original specification) the Equipment or a portion of the Equipment only with Purchaser’s written consent.  Seller agrees to complete the Punchlist to the satisfaction of Purchaser.  In the event Seller does not complete such Punchlist either (i) to the standards of the Agreement, or (ii) within a reasonable period of time, but not later than the end of the Primary Warranty Period, Purchaser may, after prior written notice to Seller, draw down against the Retention Letter of Credit the estimated value of the uncompleted work in order to have such work completed by others.

9.6   Additional Factory Testingtc \l2 "9.6   Additional Factory Testing.  Purchaser may request Seller to repeat a test, perform the test using more precise instrumentation than planned, or conduct a test not in Seller’s standard factory test program.  In the event as a result of such Purchaser requested test requirement the Equipment is found to not be compliant with the requirements of this Agreement, Seller shall correct such noncompliance and the cost and time associated with such Purchaser test requirement shall be to Seller’s account.  If the Equipment is found to be compliant with this Agreement, Seller shall be eligible for a Change Order arising out of such Purchaser test requirement.

9.7   Release for Deliverytc \l2 "9.7   Release for Delivery.  In addition to other conditions set forth in this Agreement, prior to Seller performing any Major Component packing and prior to actual shipment, Seller shall provide, seven (7) days in advance, notice of such packing and request in writing to Purchaser’s Quality Assurance Manager for release to ship such Major Components.  Purchaser’s approval shall not be unreasonably withheld provided Seller has met the requirements of this Agreement.  In the event Purchaser fails to respond to Seller’s notice of intent to pack and ship the Major Component, Seller will proceed to perform packing and will complete staging at Seller’s facility pursuant to the notice.

ARTICLE X.  DELIVERY AND PERFORMANCEtc \l1 "ARTICLE X.  DELIVERY AND PERFORMANCE
10.1   Delivery of Documentationtc \l2 "10.1   Delivery of Documentation.  In addition to the documentation specifically described within the Articles of this Agreement, Seller shall supply the documentation deliverables as set forth in Exhibit T by the due dates therein.  In the event Seller fails to deliver any item of documentation annotated in Exhibit T with an asterisk (*) by its respective due date (the “Due Date”) Liquidated Damages (“Document Liquidated Damages”) shall be assessed by Purchaser and Seller agrees to pay Purchaser at the rates per day per such document from the respective Due Date until the actual date of delivery of such item of documentation as set forth in Exhibit B-6 (the “Document Delivery Date”).

For the purpose of accessing Document Liquidated Damages, the Document Delivery Date shall be the date Seller delivers such document to Purchaser, provided that upon Purchaser’s review of such document Purchaser reasonably determines and assigns a “Status 1”, “Status 2” or “Status 4”.  In the event that Purchaser reasonably determines and assigns a “Status 3” to a document the Document Delivery Date shall not occur until the date of resubmission which results in Purchaser assigning a “Status 1”, “Status 2”, or “Status 4”.  As soon as Purchaser determines that a document will receive a “Status 3” it will notify Seller of such determination.  The criteria for Status 1,2,3, and 4 are set out in Exhibit T including the following:

(i)
Upon delivery of each item of documentation Purchaser shall use its best efforts to  review the document and provide Seller the applicable status code and comments within ten (10) business days of receipt;

(ii)
Upon receipt of any comments from Purchaser, Seller shall use its best efforts to correct and resubmit such returned documentation within ten (10) business days; and

(iii)
If Purchaser does not provide comments within the ten (10) business Day period after receipt, the document shall be deemed to be assigned a Status 1.

Purchaser’s review of any drawing or document hereunder shall not be construed as constituting approval of Seller’s work, nor shall Purchaser’s failure to review or failure to comment be construed as approval or disapproval.  Seller at all times shall retain responsibility for a Scope of Work that meets the requirements of this Agreement, regardless of whether or not Purchaser has reviewed Seller’s drawings or documents.  Changes to the documentation for the convenience of Purchaser, which can be accommodated by Seller shall be adopted pursuant to Article XI of the Agreement.

10.1.1   Delivery of Final O & M Instructionstc \l3 "10.1.1   Delivery of Final O & M Instructions.  Seller shall provide the final operations and maintenance instruction books within forty five (45) to eighty five (85) days after the delivery of the Unit.  Purchaser may offset Liquidated Damages due to late delivery of the O & M instruction manuals in accordance with Section 6.3.2 upon the completion of delivery.

10.2   Delivery of Equipmenttc \l2 "10.2   Delivery of Equipment.

10.2.1   Guaranteed Delivery Datetc \l3 "10.2.1   Guaranteed Delivery Date.

10.2.1.1   Delivery to the Delivery Pointtc \l3 "10.2.1.1   Delivery to the Delivery Point.  Seller shall cause the Equipment to be delivered in an undamaged condition in accordance with the Specification to the Delivery Point no later than the date set forth in Exhibit B-2, Schedule I (the “Guaranteed Delivery Date”).

10.2.1.2   Delivery Restrictionstc \l3 "10.2.1.2   Delivery Restrictions.  Seller shall use appropriately licensed and insurable carriers. Seller’s carries shall not be permitted to transport equipment utilizing tandem tows.

10.2.2   Inventory Upon Deliverytc \l3 "10.2.2   Inventory Upon Delivery.  Seller shall be required and Purchaser shall have the right to inspect the Equipment for completeness, condition and packing upon delivery to the Delivery Point, and Seller shall immediately inform Purchaser of any damage discovered.

10.2.3   Deliverytc \l3 "10.2.3   Delivery.  Delivery of the Unit shall be considered complete for the purposes of Delivery Liquidated Damages when the last Major Component of the Unit is delivered (and other such items of Equipment as reasonably necessary so as to not impede the continuous progress of installation and erection of the Unit) to the Delivery Point, in a complete and undamaged condition.   Purchaser shall have the right to inspect the Equipment for completeness, condition and packing prior to loading on Seller’s transport.  Purchaser shall have the right to inspect the Equipment for completeness and condition upon delivery to the Delivery Point, for the purposes of determining actual delivery.  Purchaser reserves the right to reject damaged Equipment at any location.  In the event a portion of the Equipment is damaged or defective upon delivery to the Delivery Point, Purchaser after making an initial assessment of the damage and consulting with Seller as to how such damage or defect will affect the installation, operation, performance, reliability, efficiency, and warranty of the damaged Equipment may either (i) reasonably determine that such damage or defect is such that the preceding criteria is so adversely affected that Purchaser cannot accept delivery of the damaged Equipment and declare that delivery has not occurred, or (ii) after taking into account such criteria and Seller’s proposed plan for correcting such damage or defect in accordance with Section 9.5, declare that delivery has occurred.  In the event Purchaser discovers such a damage or defect it shall notify Seller of such as soon as practical.

10.2.4   Extensions of the Guaranteed Delivery Datetc \l3 "10.2.4   Extensions of the Guaranteed Delivery Date.

10.2.4.1  A Guaranteed Delivery Date may only be extended if there has been a delay due to:


a)
a Change Order requested by Purchaser;


b)
an Event of Force Majeure;

(c)
a material breach of the Contract or default (as defined in Section 17.5) thereunder by Purchaser; or

(d)
a Change in Law requiring changes as provided in Section 3.8c(4);

10.2.4.2   Seller’s entitlement to an extension of time shall be conditional upon:


(a)
its having used reasonable endeavors to mitigate the delay;


(b)
its having given notice in accordance with the terms of this Agreement; and


(c)
the delay not being attributable to its default.

10.2.5   Offloading Responsibilitiestc \l3 "10.2.5   Offloading Responsibilities.  Purchaser shall be responsible for promptly offloading the Equipment from Seller’s mode of transportation (i) within 48 hours after arrival at the Delivery Point of railcar, and (ii) with 60 hours after arrival at the Delivery Point of loaded trailers.  Subject to thirty (30) days advance written notice from Seller to Purchaser of the delivery of the Equipment at the Delivery Point, Purchaser shall reimburse Seller any demurrage charges caused by its failure of this obligation.

10.3   Delay Liquidated Damagestc \l2 "10.3   Delay Liquidated Damages.

10.3.1   Delivery Liquidated Damagestc \l3 "10.3.1   Delivery Liquidated Damages.  For each day that Seller delivers the Unit as defined in Section 10.2.3 to the Delivery Point (the “Delivery Date”), after the Guaranteed Delivery Date, Purchaser may assess and Seller shall pay to Purchaser delivery liquidated damages at the rates per day (the”Delivery Liquidated Damages”) for such lateness as set forth in Exhibit B-6.

For the avoidance of doubt, no Delivery Liquidated Damages shall be assessable as a result of Seller delivering an non-Major Component of the Unit after its Guaranteed Delivery Date, unless such non-Major Component is shown by Purchaser to impede the continuous progress of installation or erection of the Unit.  The Delivery Liquidated Damages rate assessable on the late non-Major Component that impedes installation or erection after the Guaranteed Delivery Date shall be the rate assessable per Exhibit B-6, Section B.6.2 for each such day of impedance until the completion of delivery.

Example:  The Delivery Date of one non-Major Component to the Delivery Point is sixty days after the  Guaranteed Delivery Date.  The Delivery Date of a second non-Major Component is seventy days after the Guaranteed Delivery Date.  The Delivery Date of the last Major Component to the Delivery Point is thirty six days after the Guaranteed Delivery Date.  The first late delivered non-Major Component did not impede installation until the thirtieth day after the Guaranteed Delivery Date.  The second late delivered non-Major Component did not impede erection until the fiftieth day after the Guaranteed Delivery Date.  Seller will be assessed Delivery Liquidated Damages as calculated below:

Major Component:


35 x $22,500 = $787,500
First non-Major Component:

34 x $0.00     =  $0.00





25 x $22,500 =  $562,500
Second non-Major Component:
49 x $0.00     =  $0.00





20 x $22,500 =$450,000


Total Delivery Liquidated Damages due  = $1,800,000.00

10.3.2   Take Over Liquidated Damagestc \l3 "10.3.2   Take Over Liquidated Damages.  Purchaser may assess and Seller agrees to pay liquidated damages (the “Take Over Liquidated Damages”) as set forth in Exhibit B-6 for each day that the Facility fails to achieve Take Over by the Time for Completion as a result of any or all of the following:

(i)
the Unit is unable to be commissioned and/or operated reliably (such inability being within Seller’s sole responsibility as defined herein), but only after the expiration of the Commissioning Period; or

(ii)
the Unit demonstrating performance below the Specific Performance Levels,

Assessment of such Take Over Liquidated Damages is subject to the following:

(a)
Purchaser elects at its sole discretion not to place the Unit in Commercial operation;

 (b)
Purchaser allows thirty (30) days from first fired roll of the Unit to complete Unit commissioning check outs, any needed replacement, adjustments or corrections to make the Unit ready for testing (the “Commissioning Period”);

(c)
Purchaser makes reasonable efforts to provide the necessary time and operating loads for Seller and Purchaser to commission and check out the Unit.  Seller’s time and load requirement shall not be to the exclusion of the needs of other Facility equipment being commissioned.  Purchaser shall coordinate the most advantageous utilization of time and assets whenever conflicting requirements exist and such situations shall not be deemed delay by Purchaser;

(d)
Subject to (e) below, Purchaser may not assess Take Over Liquidated Damages prior to the expiry of the Commissioning Period;

(e)
In the event Seller fails to use its best efforts to minimize time to make corrections, adjustments or repairs to the deficiently performing Unit during the Commissioning Period, Purchaser shall have the right to void the Commissioning Period and assess Take Over Liquidated Damages without regard for the period afforded by the Commissioning Period;

(f)
Purchaser provides prompt oral notice of delays affecting commissioning;

(g)
Purchaser provides Seller its commissioning schedule no less than forty five (45) days prior to commencement on the Unit and provides periodic updates thereto;

(h)
In the event Purchaser is not subject to similar delay liquidated damages with Owner, then Seller will not be subject to Take Over Liquidated Damages; and

(i)
In the event that Purchaser is subject to similar delay liquidated damages with Owner, then Seller shall pay Take Over Liquidated Damages in accordance with this Section 10.3.2.

10.3.2.1 Seller shall use reasonable efforts to obtain, or assist Purchaser (if Purchaser so elects) in obtaining, a permit variance or modification which will enable the Facility to operate in the event the Unit does not meet the Sound Level Guarantees or Emissions Guarantee.

In the event that the Unit fails to meet the Emissions Guarantee or a Sound Level Guarantee, in parallel with Seller’s efforts to remedy Guaranteed Levels, Purchaser and Seller agree to pursue alternate remedies including, at the Seller’s expense, improving or modifying other Facility components in order to mitigate the effects of the Unit on the Facility’s performance.  Such alternate remedies must be mutually agreed to by Seller and Purchaser.

10.3.3   Invoicing for Delivery and Take Over Liquidated Damagestc \l3 "10.3.3   Invoicing for Delivery and Take Over Liquidated Damages.  Except to the extent of an offset in accordance with Section 6.3 invoicing for and payment of Document, Delivery and Take Over Liquidated Damages shall be in accordance with Section 6.4.

10.4.1  Exhaust Gas Temperature Guaranteetc \l3 "10.4.1  Exhaust Gas Temperature Guarantee.  As a Specific Performance obligation, Seller shall guarantee the Exhaust Gas Temperature of the Unit as set forth in Exhibit B-3, Section B.3.1.1.

10.4.2  Exhaust Gas Energy Guaranteetc \l3 "10.4.2  Exhaust Gas Energy Guarantee.  As a Specific Performance obligation Seller shall guarantee the Exhaust Gas Energy of the Unit as set forth in Exhibit B-3, Section B.3.1.3.

10.4.3  Specific Performance Exhaust Gas Temperature Guaranteetc \l3 "10.4.3  Specific Performance Exhaust Gas Temperature Guarantee.  As a Specific Performance obligation, Seller shall guarantee the Exhaust Gas Temperature of the Unit as set forth in Exhibit B-3, Section B.3.1.2.

10.4.4  Specific Performance Exhaust Gas Energy Guaranteetc \l3 "10.4.4  Specific Performance Exhaust Gas Energy Guarantee.  As a Specific Performance obligation, Seller shall guarantee the Exhaust Gas Energy of the Unit as set forth in Exhibit B-3, Section B.3.1.4.

10.4.5  Interaction of  Exhaust Gas Energy and Exhaust Gas Temperature with Turbine Net Outputtc \l3 "10.4.5  Interaction of  Exhaust Gas Energy and Exhaust Gas Temperature with Turbine Net Output.  Exhaust heat measurement will be performed per the guidelines of ASME PTC 4.4.  The Exhaust Gas Energy Guarantee will be corrected to account for Adjusted Electrical Output in excess of the Electrical Output Guarantee.

10.5   Sound Level Specific Performance Guaranteestc \l2 "10.5   Sound Level Specific Performance Guarantees.

10.5.1 Specific Performance Near Source Sound Level Guaranteetc \l3 "10.5.1 Specific Performance Near Source Sound Level Guarantee.  As a Specific Performance obligation, Seller shall provide the Near Source Sound Level Guarantee as set forth in Exhibit B-3, Section B.3.2.1.

 10.5.2  Specific Performance Far Field Sound Level Guaranteetc \l3 "10.5.2  Specific Performance Far Field Sound Level Guarantee.  As a Specific Performance obligation, Seller shall provide the Far Field Sound Level Guarantee as set forth in Exhibit B-3, Section B.3.2.2.

10.5.3  Sound Level Testtc \l3 "10.5.3  Sound Level Test  .  Purchaser shall conduct tests at the Site to measure the Sound Levels generated by the Equipment in accordance with the procedures set out in Exhibit F-1 (the “Sound Level Test”).

(i)
The Test Procedures pertaining to Sound Level Guarantees shall take into account corrections for environmental conditions and sound produced by other Facility equipment in determining the sound levels produced by the Unit.

(ii)
Purchaser will, (a) provide all instrumentation (including special test instrumentation), operations, labor, consumables and fuel required for the Sound Level Test, (b) provide sufficient load during the Sound Level Test, (c) read and record the Sound Level Test data, and (d) calculate the Sound Level Test results, all at no cost to Seller.

(iii)
Seller (a) have the right of representation at the Sound Level Test, (b) have the right to take its own data, (c) will have access to all data resulting from the Sound Level Test, and (d) verify the calculated Sound Level Test results.

10.6   Specific Performance Emissions Guaranteetc \l2 "10.6   Specific Performance Emissions Guarantee.  As a Specific Performance obligation, Seller shall provide the Emissions Guarantee as set forth in Exhibit B-3, Section B.3.3.1.

10.7   Electrical Output Guaranteestc \l2 "10.7   Electrical Output Guarantees.

10.7.1  Electrical Output Guaranteetc \l3 "10.7.1  Electrical Output Guarantee.  Seller shall meet the Electrical Output Guarantee obligation as set forth in Exhibit B-3, Section B.3.4.1.

10.7.2  Specific Performance Electrical Output Guaranteetc \l3 "10.7.2  Specific Performance Electrical Output Guarantee.  As a Specific Performance obligation, Seller shall meet the Specific Performance Electrical Output Guarantee as set forth in Exhibit B-3, Section B.3.4.2.

10.8   Heat Rate Guaranteestc \l2 "10.8   Heat Rate Guarantees.

10.8.1  Heat Rate Guaranteetc \l3 "10.8.1  Heat Rate Guarantee.  Seller shall meet the Heat Rate Guarantee obligation as set forth in Exhibit B-3, Section B.3.5.1.  

10.8.2  Specific Performance Heat Rate Guaranteetc \l3 "10.8.2  Specific Performance Heat Rate Guarantee.  As a Specific Performance obligation, Seller shall meet the Specific Performance Heat Rate Guarantee as set forth in Exhibit B-3, Section B.3.5.2.

10.9   Performance Liquidated Damagestc \l2 "10.9   Performance Liquidated Damages.

10.9.1  Output Liquidated Damagestc \l3 "10.9.1  Output Liquidated Damages.  Provided Seller’s Equipment has demonstrated that it meets  the Specific Performance Electrical Output Guarantee, liquidated damages shall be assessed by Purchaser, and Seller agrees to pay, at a rate set forth in Exhibit B-6, Section B.6.4 for each kW that the Adjusted Electrical Output of the Unit (as measured during the most recent Performance Test) is less than the Electrical Output Guarantee (the “Output Liquidated Damages”). 

10.9.2   Heat Rate Liquidated Damagestc \l3 "10.9.2   Heat Rate Liquidated Damages.  Provided Seller’s Equipment has demonstrated that it meets the Specific Performance Heat Rate Guarantee, liquidated damages shall be assessed by Purchaser, and Seller agrees to pay, at a rate set forth in Exhibit B-6, Section B.6.5 for each Btu/kWh (LHV) that the Adjusted Heat Rate for the Unit (as measured during the most recent Performance Test) exceeds the Heat Rate Guarantee (the “Heat Rate Liquidated Damages”).

10.9.3   Exhaust Gas Temperature and Energy Liquidated Damagestc \l3 "10.9.3   Exhaust Gas Temperature and Energy Liquidated Damages.

10.9.3.1  Exhaust Gas Temperature Liquidated Damagestc \l4 "10.9.3.1  Exhaust Gas Temperature Liquidated Damages.  Provided Seller’s Equipment has demonstrated that it meets  the Specific Performance Exhaust Gas Temperature Guarantee, liquidated damages shall be assessed by Purchaser, and Seller agrees to pay, at the rate set forth in Exhibit B-6, Section B.6.6 for each 0F that the Adjusted Exhaust Gas Temperature of the Unit (as measured during the most recent Performance Test) is less than the Exhaust Gas Temperature Guarantee (the “Exhaust Gas Temperature Liquidated Damages”). 

10.9.3.2  Exhaust Gas Energy Liquidated Damagestc \l4 "10.9.3.2  Exhaust Gas Energy Liquidated Damages.  Provided Seller’s Equipment has demonstrated that it meets the Specific Performance Exhaust Gas Energy Guarantee, liquidated damages shall be assessed by Purchaser, and Seller agrees to pay, at the rate set forth in Exhibit B-6, Section B.6.6.7 for each MMBTU/hr that the Adjusted Gas Energy of the Unit (as measured during the most recent Performance Test) is less than the Exhaust Energy Guarantee (the “Exhaust Gas Energy Liquidated Damages”). 

10.9.4   Performance Test Requiredtc \l3 "10.9.4   Performance Test Required.  No Performance Liquidated Damages shall be payable if no Performance Test has been conducted.

10.9.5   Setting Out of Performance Liquidated Damagestc \l3 "10.9.5   Setting Out of Performance Liquidated Damages.  Performance Liquidated Damages, if any, shall be due and payable by Seller pursuant to Section 6.4 in accordance with the rates set forth in this Section 10.9 and the calculations set forth in the Performance Test Completion Certificate prepared by Purchaser.  Performance Liquidated Damages shall be paid upon completion of the Performance Test.

10.9.6   Most Recent Performance Testtc \l3 "10.9.6   Most Recent Performance Test.  Performance Liquidated Damages shall be assessed by Purchaser, and Seller agrees to pay on the results of the most recent Performance Test, including any reperformance of the Performance Tests in accordance with Section 10.12.8, regardless of whether the performance improves or worsens upon the later Performance Test. 

10.9.7   Seller’s Improvement of Performancetc \l3 "10.9.7   Seller's Improvement of Performance.  In the event the Unit fails to meet a Guaranteed Level but does meet the Take Over Performance criteria set forth in Section 10.3.2, Seller shall use its reasonable best efforts, for a period of one hundred and eighty (180) days after the Unit is placed into commercial operation, to cause the Unit to meet the Guaranteed Levels.  Prior to commercial operation of the Facility, Purchaser shall provide Seller a reasonable opportunity to implement such changes or improvements; however, it is understood by both parties that Purchaser will not be required to delay commencement of commercial operation of the Facility for the purpose of Seller making such changes or improvements.  After Purchaser places the Unit into commercial operations, Purchaser shall provide Seller reasonable opportunity to make such corrections or improvements during scheduled and unscheduled outages.

10.9.8   Reduction in Performance Liquidated Damagestc \l3 "10.9.8   Reduction in Performance Liquidated Damages.  In the event Seller improves the Unit’s guaranteed performance for which Performance Liquidated Damages are payable after Purchaser has:

(i)
made an offset in accordance with Section 6.3 against payments due Seller to cover Performance Liquidated Damages; and/or

(ii)
been paid Performance Liquidated Damages by Seller, Purchaser shall reduce the offset or refund Liquidated Damages as set forth in Section 10.9.8.1 and Section 10.9.8.2.

  (A) If:

(i)
the Shortfall has not prevented Purchaser from placing the Unit into commercial operations; 

(ii)
such corrections are made and are complete prior to commercial operation of the Unit; and 

(iii)
such corrections cause a reduction in the performance Shortfall,

then Purchaser shall:

(iv)
refund to Seller an amount equal to the Performance Liquidated Damages associated with such reduction in the Shortfall; and/or 

(v)
reduce the offset associated with such reduced Shortfall;

however, such reduction in offset or amount of refund shall not exceed the amount actually offset in accordance with Section 6.3 or paid in accordance with Section 6.4 for such Shortfall, or

  (B)  If: 

(i)
such Shortfall has prevented Purchaser from placing the Unit or Facility into commercial operation; or 

(ii)
the corrections to reduce a Shortfall are completed after the Unit or Facility goes into commercial operations, and such corrections are completed within One Hundred Eighty (180) days after the Facility went into commercial operations, and such corrections cause a reduction in the Shortfall;

then Purchaser shall:

(iii)
refund to Seller an amount equal to the Performance Liquidated Damages associated with such reduction in the Shortfall; and/or 

(iv)
reduce the offset associated with such reduced Shortfall.

10.10   Maximum Liabilities for Liquidated Damagestc \l2 "10.10   Maximum Liabilities for Liquidated Damages.

10.10.1  Maximum Document Delivery Liquidated Damagestc \l3 "10.10.1  Maximum Document Delivery Liquidated Damages.  Seller’s maximum liability for Document Delivery Liquidated Damages shall be two hundred thousand ($200,000) U.S. dollars.

10.10.2  Maximum Delivery Liquidated Damagestc \l3 "10.10.2  Maximum Delivery Liquidated Damages.  Seller’s maximum aggregate liability for Delivery Liquidated Damages shall be twenty percent (20%) of the Purchase Amount.

10.10.3  Maximum Take Over Liquidated Damagestc \l3 "10.10.3  Maximum Take Over Liquidated Damages.  Seller’s maximum liability for Take Over Liquidated Damages shall be twenty percent (20%) of the Purchase Amount.

10.10.4  Maximum Output Liquidated Damagestc \l3 "10.10.4  Maximum Output Liquidated Damages.  Seller’s maximum liability for Output Liquidated Damages shall be ten percent (10%) of the Purchase Amount.

10.10.5  Maximum Heat Rate Liquidated Damagestc \l3 "10.10.5  Maximum Heat Rate Liquidated Damages.  Seller’s maximum liability for Heat Rate Liquidated Damages shall be fifteen percent (15%) of the Purchase Amount.

10.10.6  Maximum Aggregate Take Over Liquidated Damages and Delivery Liquidated Damages.  Seller’s maximum liability for Take Over Liquidated Damages and Delivery Liquidated Damages shall be twenty percent (20%) of the Purchase Amount.

10.10.7  Maximum Aggregate Exhaust Gas Energy Damagestc \l3 "10.10.7  Maximum Aggregate Exhaust Gas Energy Damages and Exhaust Gas Temperature Liquidated Damages.  Seller’s maximum liability for Exhaust Gas Energy Liquidated Damages and Exhaust Gas Temperature Liquidated Damages shall be ten percent (10%) of the Purchase Amount.

10.10.8  Maximum Aggregate Liquidated Damagestc \l3 "10.10.8  Maximum Aggregate Liquidated Damages.  Notwithstanding Section 10.1, Section 10.3 and Section 10.9, Seller’s maximum aggregate liability for Liquidated Damages, if any, under this Agreement shall be thirty percent (30%) of the Purchase Amount.

10.11   Liquidated Damages Not Penaltytc \l2 "10.11   Liquidated Damages Not Penalty.  The parties acknowledge and agree that because of the unique nature of the Equipment and the time requirements for performance:

(i)
Purchaser shall be damaged by:

(a) Seller failing to accomplish delivery of documents in accordance with Section 10.1;

(b) Seller failing to deliver the Unit by the Guaranteed Delivery Date;

(c) The Unit’s performance causing Purchaser a delay in Take Over of the Unit; and/or

(d) Seller failing to cause the Unit to achieve Guaranteed Levels,

(the “Liquidated Damages Events”);

(ii)
it would be impracticable or extremely difficult to fix the actual damages resulting from late delivery or failure to meet the Guaranteed Levels;

 (iii)
any sums which would be payable under this Article X are in the nature of liquidated damages, and not a penalty, and are fair and reasonable; and 

(iv)
such payment represents a reasonable estimate of fair compensation for the losses that may reasonably be anticipated from such Liquidated Damages Events.  Such payments are compensation solely for Liquidated Damages Events and shall not prejudice any other rights of Purchaser hereunder and shall not relieve Seller of its obligations hereunder.

10.12   Performance Tests and Sound Level Teststc \l2 "10.12   Performance Tests and Sound Level Tests.

10.12.1   Not Usedtc \l3 "10.12.1   Not Used.

10.12.2   Election to Conduct a Performance Testtc \l3 "10.12.2   Election to Conduct a Performance Test.  At Purchaser’s sole discretion, Purchaser may elect to waive the conduct of the Performance Test.  Regardless whether Purchaser waives the Performance Test, Purchaser may at its sole discretion choose to conduct the Performance Test for the purpose of evaluating Seller’s attainment of the Guaranteed Levels or Specific Performance Levels prior to the expiry of the Installation Period.

10.12.3   Specific Performance Achievementtc \l3 "10.12.3   Specific Performance Achievement.  In the event that as a result of the Performance Test, it is reasonably evident that the Equipment is performing significantly out of compliance with a Specific Performance Level; Purchaser may require Seller to take corrective actions in accordance with Section 10.12.8 without the benefit of Performance Test or Sound Level Test results; otherwise, Performance Test or Sound Level Test results will be required to be the basis of such action. 

10.12.4   Timing of Teststc \l3 "10.12.4   Timing of Tests.

10.12.4.1  Purchaser may conduct or cause a Performance Test or Sound Level Test to be conducted on the Unit after Seller’s representative certifies that the Unit to the best of his knowledge: 

(i)
is properly installed;

(ii)
can be safely tested; and 

(iii)
has been and may be run up to full load. 

10.12.4.2  In the event that a Performance Test or Sound Level Test has been conducted on the Unit within the Installation Period and corrective measures or modifications have been performed, if Purchaser elects to conduct a retest in accordance with Section 10.12.8, it shall conduct such retest within thirty (30) days of the completion of such corrective measures or modifications.   

Unit performance shall not be adjusted for degradation unless the Unit has been operated for more than two hundred (200) operating hours at the time of conduct of the initial Performance Test.  Operating hours necessary to diagnose the Unit’s failure to operate in accordance with the requirements of this Agreement shall not be added to the hour count.  Operating hours associated with the conduct of Performance Tests, shall be added to the hour count.  Methods of correcting for degradation shall be set out in the Performance Test Procedures.

10.12.5   Seller Presence at Teststc \l3 "10.12.5   Seller Presence at Tests.  Seller shall have the right to be present or to have a representative present at each Performance Test and Sound Level Test.  Purchaser shall provide Seller with a thirty (30) days initial notice and a five (5) days confirmation notice in advance of each Performance Test. 

10.12.6   Test Resultstc \l3 "10.12.6   Test Results.  Upon the completion of each Performance Test, or Sound Level Test; Purchaser will issue a Performance Test Certificate setting forth the results achieved during such test.

10.12.7   Performance Test Procedurestc \l3 "10.12.7   Performance Test Procedures.  Guidelines for the conduct of the Performance Tests are set forth in Exhibit F hereto.  No later than six (6) months after the ODM, Seller will submit to Purchaser a complete set of recommended procedures for the conduct of the Performance Tests and Sound Level Tests (the “Test Procedures”) and for verification of all major systems.  Purchaser shall review and respond to Seller’s recommended Test Procedures within  thirty (30) days of the submission.  In the event the Test Procedures are not approved by Purchaser in such response, the parties shall meet to finalize the Test Procedures within thirty (30) days of Purchaser’s response. The Performance Test shall be conducted in accordance with the ASME PTC 22 and ASME PTC 4.4 with specific changes as identified in this Agreement. 

10.12.8   Reconduct of Teststc \l3 "10.12.8   Reconduct of Tests.  In the event that Seller has made repairs or has taken other corrective action to correct a Shortfall subsequent to the conduct of the Performance Test or Sound Level Test, Purchaser at its sole reasonable discretion may require the conduct of another Performance Test(s) or Sound Level Test to: 

 (i)
demonstrate that such repairs or corrective actions have caused the Equipment to now meet the previously failed Specific Performance Level or Guaranteed Level which such repairs or corrective actions were intended to correct; and/or

(ii)
demonstrate that such repairs or corrective actions have not caused the performance of the Equipment as it pertains to the Specific Performance Levels to degrade so that the Equipment no longer meets the Specific Performance Levels; and/or

(iii)
demonstrate that such repairs or corrective actions have not caused the performance of the Equipment as it pertains to the Guaranteed Levels to degrade since the last Performance Test or Sound Level Test.

10.12.9   Not Usedtc \l3 "10.12.9   Not Used.

10.12.10  Fittings, Instrumentation and Test Uncertaintytc \l3 "10.12.10  Fittings, Instrumentation and Test Uncertainty. 

(i)
Seller shall be responsible for ensuring that the Unit is designed and manufactured with the proper fittings, orifices, and connections necessary to permit the conduct of the Performance Tests in accordance with the Test Procedures.  Seller shall also be responsible for identifying to Purchaser the necessary fittings, orifices, and connections that should be installed in the remainder of the Facility to allow a proper Performance Test to be conducted. 

(ii)
The parties anticipate using station instrumentation for performance testing.  The Performance Test shall be conducted using a combination of special test instruments and appropriate station instruments meeting the intent of the applicable test codes, but all instruments used to calculate the test results shall meet the calibration and accuracy requirements of the test code.  Calibration of all of these instruments shall be traceable to NIST, or equivalent international standards, with calibration  documentation supplied according to NIST standards and procedures.  In the event that Purchaser elects to conduct the first Performance Test on the Unit, the cost of the necessary instrumentation that is not Facility instrumentation shall be borne by Purchaser, and in the case of subsequent Performance Tests caused by Seller’s Equipment not meeting a Guaranteed Level or Specific Performance Level the cost of instrumentation shall be to Seller’s account.

 (iii)
Seller will be allowed to account for test uncertainty when comparing the Adjusted Electrical Output to the Electrical Output Guarantee and the Specific Performance Electrical Output Guarantee, and the Adjusted Heat Rate to the Heat Rate Guarantee.  The definition of and calculation of the test uncertainty shall be in accordance with ASME PTC 22, ASME PTC 19.1 and the Performance Test guidelines set forth in Exhibit F.  The parties agree to use ninety-five percent (95%) coverage as set forth in PTC 19.1 for the basis of uncertainty calculations.

10.12.11  Consumable Spare Parts During Reteststc \l3 "10.12.11  Consumable Spare Parts During Retests.  The cost of consumable spare parts during retests caused by Seller’s failure to achieve Guaranteed Levels or Specific Performance Levels shall be to Seller’s account.  

10.13  Remedies For Failure to Meet Specific Performance Requirementstc \l2 "10.13  Remedies For Failure to Meet Specific Performance Requirements.

10.13.1  Corrective Actionstc \l3 "10.13.1  Corrective Actions.  If the Unit fails to satisfy one or more of the Specific Performance Levels or a Guaranteed Level, Purchaser will, if Seller so requests and if Take Over has not occurred, operate the Facility or cause the Facility to be operated at the loads and conditions necessary to allow Seller to determine the causes of the nonconformity, if any, and the expedient remedial action.

Following the Performance Test as applicable, or additional running of the Facility for such diagnostic purposes, Seller shall at its own expense:

(i)
repair at the Site such parts of the Unit; or

(ii)
remove the defective parts and provide and install the new parts, 

to cause the Unit to meet Specific Performance Levels.

If the Unit still fails to satisfy Specific Performance Levels, Seller shall at its own expense make such further repair or replacement until the Unit meets Specific Performance Levels.  In no event shall Purchaser be required to operate Equipment in violation of Applicable Laws.

10.13.2  Failure to Achieve Specific Performancetc \l3 "10.13.2  Failure to Achieve Specific Performance.  In the event of any failure to achieve the Specific Performance Levels within one hundred eighty (180) days of the completion of the Unit’s  Performance Test, Purchaser shall have the right to terminate the Agreement in accordance with Sections 7.3, 17.2, 17.3 and 17.4.

10.14  Acceptancetc \l2 "10.14  Acceptance.  Acceptance shall occur when each of the following have occurred: 

(a)
the earliest of:

(i)
if, through no fault of Seller, a Performance Test or Sound Level Test on the Unit has not been conducted by the end of the Installation Period (except as provided in Section 10.12.4.2); or

(ii)
upon the issuance of a Performance Test Completion Certificate by Purchaser evidencing that the Specific Performance Levels and the Guaranteed Levels have been achieved (such Performance Test Completion Certificate to be issued within thirty (30) days after successful completion of testing); or

(iii)
in the event that the Unit has passed the Specific Performance Levels, but not the Guaranteed Levels and (1) Seller has for a period of one hundred eighty (180) days after provisional acceptance of the Unit made reasonable best efforts to improve the Unit’s performance and still have met the Specific Performance Levels, but not the Guaranteed Levels, and, (2) Seller has paid Liquidated Damages in accordance with Section 6.3 hereof with respect to any Guaranteed Levels not achieved;

(b)
all special tools provided hereunder shall have been delivered to Purchaser; and

(c)
Seller has delivered to Purchaser a waiver of liens in form as shown in Exhibit-S that have been or could have been placed upon the Equipment and that there are no outstanding claims of Seller or any Vendor with respect to the Equipment;

(d)
Seller has paid any Take Over Liquidated Damages due; and

(e)
Seller has paid any Delivery Liquidated Damages due.

Upon the occurrence of these events, Seller may submit a certificate to Purchaser indicating it has achieved Acceptance.  Purchaser shall within ten (10) days of receipt of such certificate, either sign such certificate acknowledging concurrence or reject such certificate specifically stating the reasons for such rejection.

10.15  Readiness for Testingtc \l2 "10.15  Readiness for Testing.  Upon Seller’s certification that the Unit is substantially complete, installed in accordance with Seller’s installation instructions and that the Unit is safe to operate, the Unit at Purchaser’s sole option, shall be tested by Purchaser in accordance with the Test Procedures.  Seller’s TD of I Manager and Purchaser’s Site Manager shall conduct a pre-commissioning meeting at the Site, as soon as practical prior to start of commissioning.  The parties shall agree upon the pre-commissioning test criteria to demonstrate the Unit’s readiness for Performance Tests and Facility tests.

10.16  Unit Serial Numberstc \l2 "10.16  Unit Serial Numbers.  Seller has identified the Unit serial numbers which are listed in Exhibit P.  Seller may not change such serial numbers without Purchaser’s prior written agreement. Purchaser shall only withhold such written agreement if, based upon the reasons given by Seller and verified by Purchaser, Purchaser reasonably believes that such change would result in a delay of the Unit.

ARTICLE XI.  CHANGE ORDERtc \l1 "ARTICLE XI.  CHANGE ORDER
11.1   Adjustment of Purchase Amounttc \l2 "11.1   Adjustment of Purchase Amount.  The Purchase Amount shall be subject to adjustment solely for (a) Purchaser‑requested changes in the Scope of Work, and (b) Seller requested changes in the Scope of Work which are approved by Purchaser.

11.2   Purchaser Requested Change Ordertc \l2 "11.2   Purchaser Requested Change Order.  If Purchaser desires to make any change in the Scope of Work (a “Change Order”), Purchaser shall advise Seller, and Purchaser and Seller shall consult concerning the estimated cost and impact on the Guaranteed Delivery Date(s) set forth in Exhibit B-2, and the Purchase Amount. Thereafter, Purchaser may request, and Seller shall upon receipt of such reasonable request prepare, a detailed estimate of the cost of such change, taking into account the effect of such change on the Scope of Work and other agreed upon and contemplated Change Orders.  Purchaser shall review Seller’s estimate, and if Purchaser accepts or the parties otherwise agree as to the Change Order, it shall be endorsed by Purchaser.  Thereafter, the parties shall promptly adjust the Guaranteed Delivery Date(s) set forth in Exhibit B-2, and the Purchase Amount and any other Exhibits requiring adjustment to reflect the Change Order.  In the event Seller proceeds with any proposed changes in the Scope of Work prior to execution of a Change Order, Seller shall do so at its own risk.  Purchaser has no obligation to pay Seller for any additional cost and Seller is not entitled to any extension of time for performance as a result of any change implemented by Seller without an executed Change Order.  Modifications or changes in the Specification which are within the general scope of the Contract documents may be made at any time by Purchaser’s Representative written order to Seller.

11.3   Seller Requested Change Ordertc \l2 "11.3   Seller Requested Change Order.  If Seller determines that a condition or the occurrence of an event requires a change in the Scope of Work, Seller shall within fifteen (15) days of being aware of the occurrence or condition of the event prepare and deliver to Purchaser a request for a Change Order which shall describe such condition or event in detail.  Within fifteen (15) days following delivery of such request, or such other period as may be agreed upon by the parties, Seller shall submit the proposed adjustment to the Scope of Work, the Guaranteed Delivery Date(s) as set forth in Exhibit B-2 and/or the Purchase Amount requested by it.  Following receipt of such request, Purchaser shall determine in its sole and exclusive discretion whether any changes to the Scope of Work, the Guaranteed Delivery Date(s) set forth in Exhibit B-2 and/or the Purchase Amount shall be effected, but failure by Purchaser to approve any such changes  shall not affect or modify any of Seller’s obligations hereunder or cause an increase in the Purchase Amount and/or extension of the Guaranteed Delivery Date(s).  If Seller proposes changes in the Scope of Work to Purchaser, Seller shall not make such changes without receiving the prior written consent of Purchaser which shall be reflected on a Change Order, in accordance with the procedures as described in Section 11.2.

11.4   Not Usedtc \l2 "11.4   Not Used.

11.5   Disputestc \l2 "11.5   Disputes.  In the event of an unresolved dispute regarding a Change Order, the parties agree that the matter shall be submitted to dispute resolution in accordance with Article XXVI. 

11.6   Change Order Pricingtc \l2 "11.6   Change Order Pricing.

11.6.1  Method of Pricingtc \l3 "11.6.1  Method of Pricing.  All changes to this Agreement shall be either lump sum, or unit price.

ARTICLE XII.  INTENTIONALLY OMITTEDtc \l1 "ARTICLE XII.  INTENTIONALLY OMITTED 

ARTICLE XIII.  ORDER OF PRECEDENCEtc \l1 "ARTICLE XIII.  ORDER OF PRECEDENCE
13.1   Order of Precedencetc \l2 "13.1   Order of Precedence.  This Agreement shall be read as a whole and in the event of a conflict between documents, the following order of precedence shall govern:


a:  Articles I through XXX


b:  Exhibits, other than Exhibits B and B-1


c: Exhibits B and B-1


d:  Seller’s and its Vendor’s O&M Manuals made part of this Agreement by reference.

ARTICLE XIV.  WARRANTYtc \l1 "ARTICLE XIV.  WARRANTY
14.1   Seller’s Warrantytc \l2 "14.1   Seller's Warranty.

14.1.1   Primary Warranty Periodtc \l3 "14.1.1   Primary Warranty Period.  Seller warrants, with respect to the Unit on a continuing basis, for one (1) year commencing upon the earlier of:

(i)
Acceptance; or

(ii)
the date the Unit is placed into commercial operation,

but in no event to commence later than end of the Installation Period (the “Primary Warranty Period”) that: 

(a)
the Equipment and all other materials and articles furnished hereunder are new, unrepaired (except as permitted by Purchaser) and of suitable grade for the purpose intended;

(b)
the Scope of Work was performed in a good and workmanlike manner and in  accordance with the degree of care, skill and diligence consistent with industry standards, the Equipment is free defects in materials and/or workmanship and the Equipment is designed and fit or the purpose of generating electric power when operated in accordance with Seller’s specific operation instructions and, in the absence thereof, in accordance with generally accepted operation practices of the electric power producing industry; or 

(c)
the Equipment conforms to the Specification and other requirements of this Agreement.

(d)
that the computer hardware and software that is part of said Equipment and any information technology contained therein will accurately process date and time data within the Warranty Period and neither performance nor functionality of the said Equipment will be affected materially by dates within the Warranty Period.  If any failure to accurately process date and time data occurs on or before the end of the Warranty Period, Seller will, at its option, modify or replace the non-conforming Equipment.  Seller shall have no responsibility for, and does not warrant against, any such failure of the Equipment that is directly or indirectly caused by the failure of products used with the Equipment to function properly, use of data or information that is inaccurate or incompatible with the Equipment’s interfaces, requirements, or specifications, or use of the Equipment other than in accordance with written instructions of Seller;

14.1.2   Warranty Clarificationtc \l3 "14.1.2   Warranty Clarification.  Seller shall have no obligation for correction, repair or replacement of the Equipment in accordance with this Article XIV to the extent that a defect is the result of:

(i)
normal wear and tear; 

(ii)
normal degradation in the performance of the Equipment; 

(iii)
Purchaser’s misuse or negligence;

(iv)
installation, use or service of the Equipment or any relevant part thereof by Purchaser or its contractors other than in conformance with Seller’s or its Vendor’s specifications, O & M Manuals or other written instructions (except as specifically set forth in this Agreement); or 

 (v)
a  Purchaser directed change in the design or construction of the Equipment which Seller reasonably disputes as not being in accordance with good workmanship or generally accepted professional engineering standards, provided that Seller has given Purchaser written notice of its dispute prior to performing any such change and such dispute ultimately is resolved in Seller’s favor.

Seller also shall have no obligation for defects in the Equipment under item (ii) of this Section 14.1.1 to the extent that, after the commencement of the Warranty Period, such defect arises out of Purchaser’s failure to: 

(vi)
operate or maintain the Equipment in accordance with good engineering practice and accepted codes and standards and in accordance with the provisions of the operation or maintenance instructions provided by Seller to Purchaser; or 

(vii)
notify Seller within a reasonable time after an Equipment defect becomes apparent, (such notice not to be later than thirty (30) days from the date supervisory level personnel of Purchaser responsible for the Facility become aware of such defect).

14.1.3   Warranty Breach Noticetc \l3 "14.1.3   Warranty Breach Notice.  In the event Purchaser believes that a defect has arisen, Purchaser shall notify Seller of such a defect in writing (fax notification followed by mailed notice) describing the nature of the breach.

14.2   Extended Warranty Periodtc \l2 "14.2   Extended Warranty Period.

14.2.1   Continued Warranty on Corrections or Repairs Performed During the Primary Warranty Periodtc \l3 "14.2.1   Continued Warranty on Corrections or Repairs Performed During the Primary Warranty Period.  With respect to any portion of the Equipment corrected, repaired, modified or replaced as a result of a defect manifesting during the Primary Warranty Period,  Seller shall warrant such portion of the Equipment for a period of twelve (12) months from the date of such modification or correction (the “Extended Warranty Period”), but in no event shall the Extended Warranty Period extend more than twenty four months beyond the Primary Warranty Period and except as set forth in Section 14.2.2 warranty obligations of Seller with respect to the Unit shall extend beyond the first to occur of (a) twenty four months beyond the Primary Warranty Period for the Unit or (b ) forty eight (48) months beyond the date of delivery of the Unit to the Delivery Point, as determined pursuant to Section 10.2. 

14.2.2   Extension of Warranty Due to Unavailabilitytc \l3 "14.2.2   Extension of Warranty Due to Unavailability.  The Primary Warranty Period or Extended Warranty Period shall be extended by a period equal to the period during which the Unit (or that part in which the defect or damage has appeared or occurred) cannot be fully used  by reason of that defect or damage, provided always that it shall not extended longer than three (3) years from Acceptance of the applicable Unit.

14.3   Obligations, Responsibilities and Recoursetc \l2 "14.3   Obligations, Responsibilities and Recourse.  If the warranties set forth in Section 14.1 hereof are breached, Seller shall repair, replace, and/or correct the applicable portion of the Scope of Work immediately or on an expedited basis such that it meets the requirements of this Agreement but at no cost to Purchaser.  Seller shall provide a service engineer to begin corrective action on the Equipment as soon as reasonably possible after receipt by Seller of Purchaser’s notice referred to in Section 14.1.4 but not later than five (5) days after receipt of such notice.  Seller shall at its sole expense disassemble, remove, replace and reinstall the Equipment to the extent necessary while minimizing the downtime required for Seller to perform its warranty obligation.  Purchaser shall provide Seller with full and free access to the Facility to perform its warranty obligations under this Agreement, so long as such access does not unreasonably interfere with operation of the Facility.  Any change to parts or equipment that would alter conformance with the Specification may be made only with prior written approval of Purchaser in accordance with the terms of Article XI hereof.  If, after notification of such defect, in materials or workmanship, Seller shall unreasonably delay the commencement, continuance or completion of making good such defect(s), Purchaser may then, following written notice to Seller, correct such defect(s) in accordance with this Agreement, and Seller shall be liable for all reasonable costs, charges and expenses incurred by Purchaser in connection with such reasonable repair or replacement and shall forthwith pay to Purchaser an amount equal to such costs, charges and expenses upon receipt of invoices certified by Purchaser.  In an emergency where delay would cause serious risk of loss or damage, and notice to and corrective action by Seller is not possible in a timely manner, Purchaser may take such actions as necessary to mitigate such risk and correct the deficiency with oral notice followed immediately with written confirmation of the notice to Seller in accordance with Section 14.1.4.  Such emergency actions shall be to the account of Seller.  Seller shall not be responsible for removal of permanent structures or disassembly of equipment not in Seller’s Scope of Work.

14.4   Not Usedtc \l2 "14.4   Not Used.

14.5   Limited Warrantytc \l2 "14.5   Limited Warranty.  THE WARRANTIES AND REMEDIES FOR BREACH OF WARRANTY CONTAINED IN THIS AGREEMENT ARE THE EXCLUSIVE WARRANTIES AND REMEDIES BY SELLER APPLICABLE TO THE EQUIPMENT AND ARE EXPRESSLY IN LIEU OF ANY OTHER WARRANTIES, EXPRESSED OR IMPLIED, INCLUDING ANY IMPLIED WARRANTY OF SATISFACTORY QUALITY (MERCHANTABILITY) OR FITNESS FOR A PARTICULAR PURPOSE, OR ANY OTHER WARRANTY EXPRESSED OR IMPLIED AGAINST VICES OR DEFECTS, LATENT  OR OTHERWISE.  SELLER NEITHER ASSUMES NOR AUTHORIZES ANY OTHER PERSON TO ASSUME FOR IT ANY OTHER WARRANTY OBLIGATION IN CONNECTION WITH THE EQUIPMENT OR ANY PART THEREOF. 

14.6   Repairs and Alterations by Otherstc \l2 "14.6   Repairs and Alterations by Others.  Notwithstanding the foregoing, Seller shall have no obligation hereunder if the Equipment becomes defective in whole or in part as a result of repairs not made by Seller (unless Seller has defaulted in making such repairs), or as a result of the Equipment not having been operated and maintained in accordance with Seller’s operating limitations and maintenance instructions, or accepted industrial practice.  In the event that Purchaser or a third party undertakes major unauthorized alterations or repairs to the Equipment (other than normal maintenance as set out in Seller’s instruction manuals, approved emergency repairs, and replacing defective parts with Seller approved spares) without Seller’s written consent, any warranty applicable to the Equipment adversely affected by such alterations or repairs shall be terminated.

14.7   Termination of Warrantytc \l2 "14.7   Termination of Warranty.  If a defect covered by the warranty is discovered by Purchaser and Purchaser does not:

(i)
immediately take reasonable action to mitigate the damage consequent to the occurrence of the defect; and

 (ii)
allow Seller to correct the defect,

Seller shall not be responsible for repair of that part of the damage attributed to Purchaser’s failure to take such action.

ARTICLE XV.  RISK OF LOSS AND TITLEtc \l1 "ARTICLE XV.  RISK OF LOSS AND TITLE
15.1   Risk of Losstc \l2 "15.1   Risk of Loss.  Seller shall bear the risk of loss and damage with respect to an item of Equipment until delivery of such of Equipment to the Delivery Point, in accordance with Section 10.2 hereof.  Risk of loss for a particular item of Equipment shall transfer from Seller to Purchaser upon Purchaser commencing first lift of such item of Equipment from Seller’s mode of transport after delivery to the Delivery Point.   

15.2   Titletc \l2 "15.2   Title.

15.2.1   Passage of Titletc \l3 "15.2.1   Passage of Title.  Title to Equipment, Spare Parts, drawings, specifications, O&M manuals and like materials prepared specifically for the Scope of Work under this Agreement will pass from Seller to Purchaser when the U.S. manufactured Equipment is ready for shipment.  In the case where Major Components are not manufactured in the U.S., title to such Major Components will pass to Purchaser at the foreign port of export immediately after clearance of the foreign customs.  Seller shall be the importer of record for all such non-U.S. manufactured Major Components, and will be responsible for all import duties and costs associated with clearing U.S. customs.  Seller warrants that legal title to and ownership of the Equipment (including, subject to the use and disclosure limitations in Article XXI, all calculations, as‑built, arrangements drawings, detailed engineering drawings and other drawings and documentation required by Purchaser in connection with the operation and maintenance of the Equipment) shall be free and clear of any and all liens, claims, security interests or other encumbrances when title thereto passes to Purchaser.  Title to Seller’s standard drawings and documents which are provided to Purchaser shall remain with Seller, provided however Seller grants permission without charge to Purchaser, Lender, Purchaser’s Operator and subsequent owners and operators to use such documents as set out in Section 15.3.

15.2.2   Infringement Cures and Defensetc \l3 "15.2.2   Infringement Cures and Defense.  In the event a suit or proceeding is brought against Purchaser, Lender, Purchaser’s Facility operator or their affiliates, (the “Patent Indemnitees”) for infringement of any patent, copyright, trademark, trade secret or other intellectual property right, Seller shall indemnify and hold harmless Patent Indemnitees, their authorized agent, and anyone directly or indirectly employed by either of them from and against all claims, damages, losses and expenses (including attorneys’ fees) arising out of any infringement of patent rights or copyrights incident to the use or production of the Equipment or incorporation therein of any invention, design process, product or device not specified in the Contract, and shall defend all such claims in connection with any alleged infringement of such rights.  Seller shall pay all costs and expenses of any such action or suit or threat thereof, including compensation and expenses of experts and counsel of its choice and selection and Seller shall also pay and hold Patent Indemnities free and harmless from expenses incurred or any damages or other sums awarded or assessed in any such action or suit including costs resulting from imposition of any injunction against Patent Indemnitees.  Patent Indemnitees may be represented by counsel of their own selection and expense, but agree to cooperate fully in the defense of any such action or suit and to furnish all the evidence in its control.

Nothing herein shall authorize Seller to settle any such suit or action as referred to in this Section 15.2.2 without prior authorization from the affected Patent Indemnitee if, by such settlement, the affected Patent Indemnitee shall be obliged to make any monetary payment, part with any property or any interest therein, to assume any obligation or restriction upon operation of the Equipment or Facility or production of electricity to be subject to any injunction or to grant licenses or other rights under its patent or other industrial or intellectual property rights or surrender or release any other rights, remedies, interests or claims.

In the event a Patent Indemnitee is as a result of such suit or proceeding prevented from using such alleged infringing Equipment or other deliverables, Seller shall undertake and conclude as quickly as reasonably possible at its option and expense one of the following courses of action:

(i)
obtain the right to continued use of the Equipment or other deliverables under this agreement;

(ii)
correct or modify the infringing aspect of the Equipment or other deliverables under this Agreement so that it becomes non-infringing; or

(iii)
replace the infringing Equipment or other deliverables under this Agreement with equivalent non-infringing Equipment or other deliverables.

THIS SECTION IS AN EXCLUSIVE STATEMENT OF ALL THE DUTIES OF THE PARTIES RELATING TO PATENTS AND DIRECT OR CONTRIBUTORY PATENT INFRINGEMENT AND OF ALL THE REMEDIES OF PURCHASER RELATING TO ANY CLAIM, SUIT, OR PROCEEDING INVOLVING PATENTS.  Compliance with this Section as provided herein shall constitute fulfillment of all liabilities of the parties under the Contract with respect to patents, copyright, trademark, trade secret or other intellectual property rights.

15.3   Seller’s Drawings, Etc. for Use by Purchasertc \l2 "15.3   Seller's Drawings, Etc. for Use by Purchaser.  All drawings, documents, engineering and other data furnished or to be furnished by Seller in performing the Scope of Work may be used by Purchaser, Purchaser’s Facility operator or a subsequent owner for the purpose of designing, procuring, constructing, operating, maintaining, repairing and altering the Equipment and Facility.

15.4   Licensing Proceduretc \l2 "15.4   Licensing Procedure.  Seller grants Purchaser a non-exclusive license to use the Equipment supplied under this Agreement for operating, maintaining and repairing the Facility.  Purchaser shall have no right to the source code; provided, however in the event Seller or Seller’s vendor discontinue maintenance of such Equipment, Seller shall on a best efforts basis attempt to obtain such source code for Purchaser.  The non-exclusive license granted herein to Purchaser may be transferred by Purchaser to Purchaser’s Facility operator, Lender(s), or successor owners of the Facility (for the sole purpose of operating the Facility).

Seller and/or its licensors shall at all times remain owners of the software/firmware licensed.

ARTICLE XVI.  TRAINING AND TECHNICAL DIRECTION OF INSTALLATIONtc \l1 "ARTICLE XVI.  TRAINING AND TECHNICAL DIRECTION OF INSTALLATION
Seller shall provide technical direction of installation of the Equipment in accordance with Exhibit H-1.  Seller shall provide on Site operation and maintenance training for Purchaser’s operations and maintenance personnel in accordance with Exhibit H-2.  Purchaser shall be responsible for the travel and per diem costs of its personnel and for providing or procuring all training facilities on or in the immediate vicinity of the Site.

ARTICLE XVII.  DEFAULTtc \l1 "ARTICLE XVII.  DEFAULT
17.1   Events of Default by Sellertc \l2 "17.1   Events of Default by Seller.  Seller shall be in default hereunder upon the occurrence of any one of the following events, which shall be events of default (each an “Event of Seller Default”) if not cured within thirty (30) days following delivery to Seller of a notice of such event from Purchaser, or, if not curable in such thirty (30) Day period, if Seller has not commenced the cure within such period and does not thereafter diligently pursue such cure, provided that in no event shall such extended cure period exceed 180 days unless otherwise mutually agreed and further subject to (c)(3) and (d) below and provided that the event described in paragraph (d) below shall be an Event of Seller Default upon its occurrence:

(a)
Seller shall have assigned or transferred this Agreement or any right or interest herein except as expressly permitted by this Agreement; or

(b)
representations made by Seller in this Agreement are found to be materially false or misleading, or;

(c)
Seller shall have defaulted in its performance under any material provision of this Agreement.  The parties agree that Purchaser may not terminate for default based upon the Unit’s failure to meet Guaranteed Levels if Seller has caused the Unit to meet Specific Performance Levels.  Purchaser may terminate this Agreement for default in the event:

(1)  Seller’s liability for Delivery Liquidated Damages exceeds ten percent (10%) of the Purchase Amount; or 

(2) Seller’s liability for Take Over Liquidated Damages exceeds ten percent (10%) of the Purchase Amount; or

(3) Seller fails to cause the Unit to achieve a Specific Performance Level within 180 days after Purchaser conducts a Performance Test or Sound Level Test; or

 (d)
any proceeding is instituted against Seller seeking to adjudicate Seller as a  bankrupt or insolvent, or Seller makes a general assignment for the benefit of its creditors, or a receiver is appointed on account of the insolvency of Seller, or Seller files a petition seeking to take advantage of any other law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts and, in the case of any such proceeding instituted against Seller (but not by Seller), such proceeding is not dismissed within sixty (60) days of such filing. 

17.2   Purchaser’s Remedies Against Sellertc \l2 "17.2   Purchaser's Remedies Against Seller.  The provisions of Article XXVI hereof notwithstanding, and without limitation of Purchaser’s rights under Article X for those Liquidated Damages paid or due prior to an Event of Seller Default, if an Event of Seller Default shall have occurred and be continuing, Purchaser or its assignee shall have the right to terminate this Agreement in whole or in part by delivery of a notice of termination to Seller.  In the case of Event of Seller Default as set forth in Section 17.1 (c) (1) or (2), Purchaser shall be entitled to such Liquidated Damages plus other amounts as associated with the termination.

17.3   General Obligationstc \l2 "17.3   General Obligations.  If Purchaser elects to terminate this Agreement pursuant to Section 17.2 hereof, Seller shall, at Purchaser’s request and at Seller’s expense, subject to Section 27.1 hereof,  either: 

(a)
promptly refund all amounts paid to date and pay Cover Damages plus Termination Costs described in Sections 17.4.2(i) and 17.4.2(iv) described below, provided, however, that if and to the extent title to Equipment has passed to Purchaser, Seller shall have the right to retrieve such Equipment at its cost; or

(b)
perform the following services relative to the Scope of Work so affected;

(1)
assist  Purchaser in preparing an inventory of all Equipment and documentation to which Purchaser has not already taken title;

(2)
assign to Purchaser, or to any person designated by Purchaser without any right to compensation not otherwise provided for herein, title to all portions of the Equipment and documentation not already owned by Purchaser, together with all subcontracts and other contractual agreements (including warranties) as may be designated by Purchaser, all of which subcontracts and contractual agreements shall be so authorizations, approvals and rights to complete and to use the Equipment under patents and other proprietary or intellectual property rights then held by Seller or its Vendors pertaining to the Equipment;

(3)
afford to Purchaser all design, expertise and other information as may be  necessary for the operation of the Equipment for which title has passed to Purchaser (subject to the requirements of Section 21.1 hereof); and

 (4)
supply any proprietary components or procure and supply substituted nonproprietary components need for the completion and operation of the Equipment.

17.4   Payment Obligationstc \l2 "17.4   Payment Obligations. 

17.4.1   Determination of Obligationstc \l3 "17.4.1   Determination of Obligations.  If Purchaser terminates this Agreement pursuant to Section 17.2 hereof, and requests delivery of the Equipment and the materials and services described in Section 17.3.(b) above, Purchaser shall determine the value of that portion of the Scope of Work, which has been properly completed, if any (the “Proper Scope Value”).  If Purchaser has paid Seller an amount greater than the Proper Scope Value the difference between the amount paid to Seller and the  Proper Scope Value (the “Refund Amount”) shall be settled between the parties in accordance with Section 17.4.4 below.  If the amount paid by Purchaser to Seller is less than the Proper Scope Value, the difference between the amount paid and the Proper Scope Value (the “Scope Value Due”) shall be settled between the parties in accordance with Section 17.4.4 below.  If Seller disagrees with Purchaser’s determination of the Proper Scope Value, such dispute shall be resolved in accordance with Article XVI. 

17.4.2   Damages and Expensestc \l3 "17.4.2   Damages and Expenses.  Purchaser shall determine the total damages and reasonable and necessary expenses incurred in connection with:

(i)
the termination of this Agreement (including all legal fees and expenses for,  inter alia, the negotiation of an agreement with an alternate supplier);

 (ii)
if Section 17.3(b) hereof is applicable, any rework, modifications or replacement of the Equipment to cause it to comply with the requirements of this Agreement;

(iii)
if Section 17.3(b) hereof is applicable, the completion of the Scope of Work and all associated incidental costs, and

(iv)
amounts otherwise due Purchaser from Seller pursuant to this Agreement (including but not limited to Liquidated Damages and Take Over Liquidated Damages).

The total of items (i) through (iv) above shall be referred to as the “Termination Costs”.

17.4.3   Cover Damagestc \l3 "17.4.3   Cover Damages.  If Section 17.3(a) hereof is applicable, the amount of “Cover Damages” shall be the difference between the Purchase Amount under this Agreement and the purchase price payable by Purchaser for a replacement contract for a substantially similar gas turbine generator and the other equipment and materials included in the Scope of Work under this Agreement, suitable for the Facility and substantially meeting the specifications set forth in this Agreement, plus incremental transportation costs incurred.  Purchaser agrees that it has a duty to mitigate any damages and that it shall use commercially reasonable efforts to minimize Cover Damages it may incur as a result of procuring a replacement contract in the event of termination hereunder. 

17.4.4   Settlementtc \l3 "17.4.4   Settlement.   Upon determining the Proper Scope Value and the Termination Costs, if any, the termination settlement (the “Termination Settlement”) shall be determined and invoiced as follows:

(a)
if Section 17.3(a) is applicable, the Termination Settlement shall be the amounts described in Section 17.3(a).


(b)
if Section 17.3(b) hereof is applicable, the Termination Settlement shall be as follows:

(i)
if the Scope Value Due is greater than zero (0), and if

(a)
the Termination Costs are greater than the Scope Value Due, Seller shall pay Purchaser the difference of the Termination Costs less the Scope Value Due, or

(b)
the Scope Value Due is greater than the Termination Cost, Purchaser shall pay Seller the difference of the Scope Value Due less the Termination Costs.

(ii)
if the Refund Amount is greater than zero (0), then Seller shall pay Purchaser the sum of the Refund Amount plus the Termination Costs.

(iii)
if the Refund Amount and the Scope Value Due are each zero (0), Seller shall pay Purchaser the Termination Costs.

Seller or Purchaser, as applicable, shall make payment of an invoice received for Termination Settlement within thirty (30) Days of receipt of such invoice.  Any such Termination Settlement not paid when due shall accrue interest at the Interest Rate.

17.5   Events of Default by Purchasertc \l2 "17.5   Events of Default by Purchaser.  Purchaser shall be in default hereunder upon the occurrence of any one of the following events, which shall be events of default (each an “Event of Purchaser Default”) if not cured within thirty (30) days following delivery to Purchaser of a notice of such event from Seller or if not curable in such thirty (30) day period, if Purchaser has not commenced the cure within such period and does not thereafter diligently pursue such cure, provided that the event described in paragraph (d) below shall be an Event of Purchaser Default upon its occurrence:

(a)
Purchaser shall have assigned or transferred this Agreement or any right or interest herein except as expressly permitted by this Agreement;

(b)
any representation made by Purchaser in this Agreement shall have been materially false or misleading when made;

(c)
Purchaser shall have defaulted in its performance under any material provision of this Agreement; or 

(d)
any proceeding is instituted against Purchaser seeking to adjudicate Purchaser as a bankrupt or insolvent, or Purchaser makes a general assignment for the benefit of its creditors, or a receiver is appointed on account of the insolvency of Purchaser, or Purchaser files a petition seeking to take advantage of any other law relating to bankruptcy, insolvency, winding up or composition or readjustment of debts and in the case of any such proceeding instituted against Purchaser (but not by Purchaser) such proceeding is not dismissed within sixty (60) days of such filing.

17.6   Seller Remediestc \l2 "17.6   Seller Remedies.  The provisions of Article XXVI hereof notwithstanding, if an Event of Purchaser Default shall have occurred and be continuing, Seller shall have the right to terminate this Agreement by delivery of a notice of termination to Purchaser, in addition to any rights and remedies that may be available at law or in equity.

ARTICLE XVIII.  FORCE MAJEUREtc \l1 "ARTICLE XVIII.  FORCE MAJEURE 

18.1   Failure to Perform Due to an Event of Force Majeuretc \l2 "18.1   Failure to Perform Due to an Event of Force Majeure.  Subject to the terms of this Article XVIII, either party shall be excused from performance and shall not be considered to be in default with respect to any obligation hereunder, to the extent such party’s (the “Affected Party”) failure of performance is due to an Event of Force Majeure.  

18.2   Events of Force Majeuretc \l2 "18.2   Events of Force Majeure.  Events of Force Majeure shall be limited to the circumstances set forth in Section 18.4 (the “Event of Force Majeure”)  but only if, and to the extent:

(i)
such circumstance is not within the reasonable control of the party affected;

(ii)
such circumstance, despite the exercise of reasonable diligence, can not be prevented, avoided or removed by such party;

(iii)
such circumstance prevents the Affected Party from fulfilling its obligations under the Agreement;

(iv)
the Affected Party has taken all reasonable precautions, due care and reasonable alternative measures in order to avoid the effect of such event on the affected party’s ability to fulfil its obligations under the Agreement and to mitigate the consequences thereof; and

(v)
such event is not the result of any failure of such party to perform any of its obligations under the Agreement.  

18.3   Notice of Event of Force Majeuretc \l2 "18.3   Notice of Event of Force Majeure.  As soon as possible following the date of commencement of any Event of Force Majeure, if either party desires to invoke such Event of Force Majeure as a cause for delay in the performance of any obligation hereunder or as potential adjustment of the Purchase Amount, it shall promptly (but not later than three (3) days upon learning of such Event of Force Majeure), advise the other party in writing of such date.  Notices shall be in accordance with Section 25.1.  Within seven (7) days, the Affected Party shall provide in writing a description the event and reasonable alternative measures which the Affected Party has taken in order to avoid the effect of such event on such party’s ability to fulfill its obligations under the Contract and to mitigate the consequences thereof, and the nature and expected duration of such Event of Force Majeure.  The Affected Party shall provide additional information concerning the event as reasonably requested by  the other party (including, without limitation, updating of any information already provided under this Section 18.3).  As soon as practicable after the commencement of the Event of Force Majeure, the Affected Party shall allow the other party’s professional advisers access to its premises and equipment to enable the other party to assess the event and the steps to avoid or remove the circumstances constituting the event.  Within a reasonable time following the date of termination of such Event of Force Majeure, the Affected Party shall submit to the other party as soon as practicable, reasonable proof of the nature of such delay and its effect upon the Guaranteed  Delivery Date, or the basis for an adjustment of the Purchase Amount.  The burden of proof to demonstrate that an Event of Force Majeure has occurred and affects the Affected Party’s ability to perform, rests with the Affected Party.  The parties will meet within ten (10) days after receipt of the notice by the unaffected party to discuss appropriate measures that should be taken.  The parties shall thereupon consult with one another concerning the effect of such Event of Force Majeure and an extension of the Guaranteed Delivery Date(s) described in Section 10.2.1 or, if applicable, an adjustment in the Purchase Amount described in Section 5.1.1 shall be made by the parties to take into account such effect on the ability of Purchaser and Seller to reschedule project activities to avoid or minimize overall delays or additional costs resulting from the Event of Force Majeure.  The parties:

(i)
shall make all reasonable efforts to prevent and reduce to a minimum and mitigate the effect of any delay or potential adjustment of the Purchase Amount occasioned by any Event of Force Majeure including recourse to alternate acceptable source of services, equipment and materials and construction equipment; and

(ii)
shall use their best efforts to ensure resumption of normal performance of this Agreement after the occurrence of any Event of Force Majeure and shall perform their obligations to the maximum extent practicable as agreed between the parties.

18.4   Events of Force Majeuretc \l2 "18.4   Events of Force Majeure.  Subject to the provisions of Sections 18.2 and 18.5, Events of Force Majeure shall mean the following:

(a)
explosions, fires, nuclear radiation contamination, hurricanes, earthquakes, floods, natural disasters, epidemics, other acts of God, and any other similar circumstances;

(b)
war and other hostilities (whether declared or not), revolution, public disorders, insurrection, rebellion, sabotage, acts of public officials or terrorist action;

(c)
any action or relative material inaction taken by any national or local government or judicial authority after the date of this Agreement, including without limitation any order, legislation, enactment, judgement, ruling or decision; or

 (d)
national or regional strikes (to the extent affecting the Seller’s performance of Scope of Work) and strikes specific to the Site or to Seller’s and its approved Vendor’s (as listed in Exhibit B-4) manufacturing facilities.

18.5   Certain Events Not Excusedtc \l2 "18.5   Certain Events Not Excused.  Notwithstanding that an Event of Force Majeure may otherwise exist, the provisions of this Article XVIII shall not excuse: 

(a)
late delivery of equipment or materials caused by Seller, or caused by any of the subcontractors of Seller if Seller could have avoided such late delivery by exercising all reasonable endeavors as a prudent equipment supplier;

(b)
late performance by Seller caused by Seller’s failure to engage qualified subcontractors and suppliers or to hire an adequate number of personnel or labor or by inefficiencies on the part of Seller; or

(c)
delays resulting from reasonably foreseeable unfavorable weather or reasonably foreseeable unsuitable ground conditions.

18.6   Continued Performancetc \l2 "18.6   Continued Performance.  Upon the occurrence of any Event of Force Majeure, the parties shall endeavor to continue to perform their obligations under the Contract so far as reasonably practicable and Seller shall during the period of such circumstances protect and secure the works in such manner as Purchaser shall require.  Seller shall notify Purchaser of the steps he proposes to take including any reasonable alternative means for performance of the works not prevented by the Event of Force Majeure. 

18.7   Not Usedtc \l2 "18.7   Not Used.  

18.8   Event of Force Majeure ‑ Delaystc \l2 "18.8   Event of Force Majeure ‑ Delays.  If either party becomes unable to perform all or part of its obligations under this Agreement because of an Event of Force Majeure, and the Affected Party has properly invoked and observed the provisions of Section 18.3 in respect thereof, the Affected Party shall be permitted a delay in the performance of its obligations affected by the Event of Force Majeure and an extension of the Guaranteed Delivery Date or the Installation Period as applicable.

18.9   Event of Force Majeure ‑ Costtc \l2 "18.9   Event of Force Majeure ‑ Cost.  Seller shall bear its own delay costs occasioned by any Event of Force Majeure for the first thirty (30) Day period during the occurrence or continuance of each such Event of Force Majeure.  If an Event of Force Majeure continues beyond such thirty (30) Day period in which Purchaser is the Affected Party, Seller shall be entitled, subject to the provisions of Section 11.3, to recover costs occasioned by each such Event of Force Majeure which accrue after each such thirty (30) Day period pursuant a Purchase Amount adjustment in accordance with Section 5.5 and Article XI hereof.

18.10   Cancellation for Force Majeuretc \l2 "18.10   Cancellation for Force Majeure.  Notwithstanding that Seller may have been granted under Section 10.2.4 an extension of a Guaranteed Delivery Date(s)  if by virtue of Section 18.1 either party shall be excused the performance of any obligation for a continuous period of one hundred eighty (180) days, then Purchaser may at any time thereafter, and provided such performance is still excused, by notice to Seller may terminate this Agreement.

18.11   Payment on Cancellation for Force Majeuretc \l2 "18.11   Payment on Cancellation for Force Majeure.  If the Agreement is canceled under Section 18.10, Seller shall be entitled to be paid pursuant to Section 5.4.1 and Section 5.4.2, plus the amount of any other expenditure which in the circumstances was reasonably incurred by Seller in the expectation of completing the whole of the Scope of Work; but shall not be entitled to any other payment including without limitation any payment in respect of anticipated profit on this Agreement.

ARTICLE XIX.  INSURANCEtc \l1 "ARTICLE XIX.  INSURANCE
19.1   Insurance ‑ Generaltc \l2 "19.1   Insurance ‑ General.  Seller shall procure at its own expense and maintain in full force and effect at all times throughout Seller’s performance under this Agreement to include Seller’s performance of its warranty obligation with responsible insurance carriers insurance as set forth in this Agreement.  Seller may establish programs of self insurance to the same minimum levels as set forth below, as allowed by law.

19.1.1   All Risktc \l3 "19.1.1   All Risk.  Seller shall purchase and maintain insurance to the full replacement cost of the Equipment during the process of fabrication, in the factory, and until transportation from Seller’s final assembly factory commences, for physical loss and damage including but not limited to theft, vandalism, and malicious mischief, collapse, water damage and such other perils as Seller deems appropriate.  Seller may self insure work during the fabrication process.

19.1.2   Workers Compensation and Employers Liability Insurancetc \l3 "19.1.2   Workers Compensation and Employers Liability Insurance.  Seller agrees to comply with workers compensation laws of each jurisdiction where the Scope of Work is performed, and to maintain a Workers Compensation and Employers Liability policy.   This policy shall be endorsed, if applicable, to provide all state coverage, alternate employer, voluntary compensation coverage and occupational disease with the limits set forth below. If the work is to be performed  on or near navigable U.S. waters, the policy shall include coverage for United State Longshoreman’s and Harbor Worker’s Act, Death on the High Seas Act, Jones Act, or their equivalent as required by the applicable laws in the jurisdiction where such work is performed.  



Workers Compensation
Statutory



Employers Liability

$1,000,000 Each Accident


$1,000,000 Disease 


Each Employee (Minimum)

19.1.3   Commercial General Liability Insurancetc \l3 "19.1.3   Commercial General Liability Insurance.  Seller shall maintain Commercial General Liability Insurance, endorsed to provide coverage for: Explosion, Collapse and Underground hazards; Contractual Liability (particularly applicable to the provisions of the “General Indemnity” section of this Agreement);  and Products and Completed Operations (for a minimum of one year after completion of the Scope of Work) with the following limits:   

Bodily Injury and
$1,000,000 Combined Single Limit 

Property Damage

Each Occurrence, (Minimum)

19.1.4   Hull and Protection and Indemnity Insurancetc \l3 "19.1.4   Hull and Protection and Indemnity Insurance.  Seller shall ensure that if any owned or non‑owned watercraft of any kind is used for performance of the Scope of Work, Hull and Protection and Indemnity Insurance shall be provided for the vessels in the amounts as follows:

Hull
Full replacement value of the watercraft.

P&I
$1,000,000 Each Occurrence or the full value of the vessel,


whichever is greater.

Such insurance may be provided by the vessel operator, by the vessel charter agreement, or by Seller as Seller deems appropriate.

19.1.5   Business Automobile Liability Insurancetc \l3 "19.1.5   Business Automobile Liability Insurance.  Seller shall provide Business Automobile Liability Insurance which shall include the following coverage for all owned, non‑owned and hired vehicles:

Bodily Injury   
$1,000,000 Each Person  (Minimum)





$1,000,000 Each Occurrence (Minimum)

Property Damage 

$1,000,000 Each Occurrence (Minimum)

or

Bodily Injury and 
$1,000,000 Combined Single Limit

Property Damage 
Each Occurrence (Minimum)  

19.1.6   Aircraft Liability Insurancetc \l3 "19.1.6   Aircraft Liability Insurance.  If the Scope of Work necessitates the use of Seller’s or Seller’s affiliate’s owned or leased aircraft, Seller shall provide Aircraft Liability Insurance which shall be endorsed to provide coverage for non‑owned as well as Guest Voluntary Settlement, with limits of:

Bodily Injury and
$10,000,000 Combined Single Limit

Property Damage
Each Occurrence.

Such insurance may be provided by the aircraft operator, by the aircraft charter agreement, or by Seller as Seller deems appropriate.

19.1.7   Excess Umbrella Liability Coveragetc \l3 "19.1.7   Excess Umbrella Liability Coverage.  Seller shall provide Excess Umbrella Liability coverage with minimum limits of:

Bodily Injury and
$5,000,000 Combined Single Limit 

Property Damage 
Each Occurrence. 

19.1.8   Vendorstc \l3 "19.1.8   Vendors.  Seller shall require its Vendors and others connected with the Scope of Work  to provide and maintain insurance at all times during the period that their agreement related to the Scope of Work under this Agreement is in force and effect at the Vendor’s, or other’s own cost, with insurance limits which at minimum meets levels as required for similar contracts and is customary for the applicable industry. 

19.1.9   Certificate of Insurancetc \l3 "19.1.9   Certificate of Insurance.  Within twenty (20) days of execution of this Agreement, Seller shall submit to Purchaser a Certificate of Insurance, in form satisfactory to Purchaser, evidencing that satisfactory coverage of the type and limits set forth herein above are in effect.  Policies providing such coverage shall contain provisions that no cancellation or material changes in the policies shall become effective except on sixty (60) days advance written notice thereof to Purchaser.  Irrespective of the requirements as to insurance to be carried as provided for herein, the insolvency, bankruptcy or failure of any insurance company carrying insurance of Seller, the failure  of any insurance company to pay claims accruing, shall not affect, negate or waive any of the provisions of this Agreement including, without exception, the indemnity obligations of Seller. 

19.1.10  Other Requirementstc \l3 "19.1.10  Other Requirements.  Seller shall be responsible for the payment of all deductible and self insurance retention amounts with respect to the insurance required to be maintained by it pursuant hereto, and all Seller policies shall apply as primary insurance without right of contribution of similar policies which may be maintained by Purchaser.  All Seller insurance shall:

(a)
Specify Purchaser and Lender, and such other parties as Purchaser may require as additional insured for all insurance coverage other than Worker’s Compensation Insurance, or its equivalent as required in jurisdictions other than the United States;

(b)
Provide that Purchaser shall have the right, but not any obligation, to pay any premiums if Seller shall fail to do so, and such payment of premiums by Purchaser shall be at Seller’s expense, either by direct charge or setoff;  

(c)
For all insurance coverage related to Scope of Work, waive any right of subrogation against Purchaser and Lender, their parent and affiliated companies and their directors, officers, employees and agents, and all other named and additional insured and any other right of the insurer to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of any liability of Purchaser or Lender, or any other named or additional insured; and

 (d)
For all other insurance other than as stated in (c) immediately above, waive any right of subrogation against Purchaser, Lender and all other named and additional insured and any other right of the insurer to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of Purchaser, or any other named or additional insured.  

19.1.11  Vendor Waiver of Subrogationtc \l3 "19.1.11  Vendor Waiver of Subrogation.  Seller agrees to require all policies of insurance which are in any way related to the Scope of Work and that are secured and maintained by Seller’s first tier Vendors to include clauses providing that each underwriter shall waive its rights of recovery, under subrogation or otherwise, against Purchaser and Lender, their parent and affiliated companies and their directors, officers, employees and agents (the “Purchaser Related Parties”) or alternatively shall indemnify and defend Purchaser Related Parties against such action if such action arises out of or is in any way related to this Agreement.

19.1.12  Compliance with Insurancetc \l3 "19.1.12  Compliance with Insurance.  Seller and its directors, officer, representatives, agents and employees shall comply with all the terms of the policies of insurance referred to in Section 19.1 and to the extent Seller is made aware of such terms, in any Delay in Start-Up and Business Interruption Insurance obtained by Purchaser.  Seller and its directors, officers, representatives, agents and employees shall comply with the procedures for claims, notification and administration under the aforesaid insurance policies and shall not do or omit to do anything which might render voidable policies of insurance or entitle insurers to avoid liabilities thereunder.  Seller shall ensure that all Major Subcontractors shall be subject to provisions identical to this Section 19.1.12.

19.1.13  Limitationtc \l3 "19.1.13  Limitation.

19.1.13.1  In the event that Seller breaches its obligations under the first two sentences of Section 19.1.11 of the Agreement and such breach results in an insurer avoiding, in relation to Seller, any policy of insurance obtained by Purchaser pursuant to Section 19.2 of the Agreement, Seller shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of Seller included in that policy pursuant to Section 19.2 shall not apply.

19.1.13.2  In the event that any Vendor fails to comply with the procedures for claims notification and administration under any policy of insurance obtained by Purchaser pursuant to Section 19.2 of the Agreement or does anything which might render any such policy of insurance voidable or entitle insurers to avoid liability thereunder and as a result thereof an insurer avoids in relation to that Vendor any such policy of insurance, that Vendor shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of that Vendor included in that policy pursuant to Section 19.2 of the Agreement shall not apply.

19.2   Purchaser’s Insurancetc \l2 "19.2   Purchaser's Insurance.  

19.2.1   Cargo Insurancetc \l3 "19.2.1   Cargo Insurance.  Purchaser shall provide or cause to be provided and maintained All Risk Marine Cargo Insurance for the period of transportation commencing upon transportation from factory where final assembly occurs prior to commencing delivery to Purchaser and ending upon delivery to the Delivery Point.  The maximum per occurrence deductible, shall be no more than $25,000.  Purchaser shall cause Seller to be an additional insured and provided a waiver of subrogation under such policy.

19.2.2   Builder’s All Risk Insurancetc \l3 "19.2.2   Builder’s All Risk Insurance  Purchaser shall provide, or cause to be provided and maintained, a Builder’s All Risk policy covering activities at the Site for the period of time that Seller performs TDI services at the Site.  Seller to the extent of its TDI services on the Site shall be named as an additional insured and provided a waiver of subrogation under such policy.

Seller shall have an opportunity to review and make reasonable comments to the Purchaser’s proposed insurance policies in respect to the Cargo insurance and Builder’s All Risk insurance.  Purchaser shall provide Seller one copy of the relevant portions of such final insurance policies as such policies become available.

ARTICLE XX.  INDEMNIFICATIONtc \l1 "ARTICLE XX.  INDEMNIFICATION
20.1   Third Partytc \l2 "20.1   Third Party.  With respect to claims brought by third parties against either Seller or Purchaser relating to the property or facilities with respect to which this Agreement pertains or the Scope of Work performed under this Agreement, Seller and Purchaser agree as follows:

(a)
Seller agrees to indemnify, protect, defend, and hold harmless Purchaser, its directors, Lenders, officers, employees, agents, and contractors, and the directors, officers employees, agents, and contractors of Purchaser’s parent and affiliated companies (collectively “Purchaser Indemnitees”), from and against any and all demands, claims, suits and causes of action and any and all liability, costs, expenses, and judgments incurred in connection therewith (including, without limitation, court costs and reasonable attorney’s fees), whether arising in equity, at common law, or by statute, or under the law of contracts, torts (including, without limitation, negligence and strict liability without regard to fault) for personal injury or damage to property of third parties (excluding Purchaser Indemnitees) or arising in favor of or brought by any of Seller’s employees, agents, subcontractors, or representatives, or by any governmental agency or any other third party (the “Purchaser Claimant”), based upon, in connection with, relating to or arising out of or alleged to arise out of Seller’s, its agents’, affiliates’, subcontractors’ or vendors’ negligence, and even if due in whole or in part to Purchaser’s concurrent negligence or fault or other fault, breach of contract or warranty, or strict liability without regard to fault; provided, however, that Seller’s contractual obligation of indemnification shall not extend to the percentage of the Purchaser Claimant’s damages or injuries attributable to Purchaser’s or Agent’s negligence or other fault, breach of contract or warranty, or to strict liability imposed upon Purchaser as a matter of law.  This indemnification obligation shall apply regardless of the amount of insurance coverage held by Seller, including that under any worker’s compensation act, disability act, or other act or law which would limit the amount or type of damages, compensation, or benefits payable by or for Seller, and shall not be limited by any insurance carried or provided by Seller  in accordance with this Agreement or otherwise.

(b)
In the event that both Seller, its agents, affiliates, subcontractors or vendors, and Purchaser are adjudicated negligent or otherwise at fault or strictly liable without fault with respect to damage or injuries sustained by the Seller Claimant or Purchaser Claimant, this contractual obligation of indemnification shall continue but each of Seller and Purchaser shall indemnify the other (the indemnitee) only for the percentage of responsibility of the damage or injuries adjudicated to be attributed to the indemnitor.

 (c)
The indemnitor’s contractual obligation of indemnification under this Agreement is subject to the conditions precedent that:

 (i) 
the party seeking indemnity shall provide written Notice of the third party claim, demand or cause of action promptly after such third party claim, demand or cause of action is received by the party seeking indemnity, such Notice shall be served on the other party on the earlier of fifteen (15) business days prior to the last Day for responding to such claim or action or the date which is one-half of the period allowed for responding to such claim or action; and

(ii)
the party with the duty to indemnify shall thereafter have the right to participate in the investigation, defense and resolution of such third party claim; and 



20.2   Survival of Obligationtc \l2 "20.2   Survival of Obligation.  The duty to indemnify under this Article will continue in full force and effect notwithstanding the expiration or termination of this Agreement.

ARTICLE XXI.  NON‑DISCLOSURE OF INFORMATIONtc \l1 "ARTICLE XXI.  NON‑DISCLOSURE OF INFORMATION
21.1   Proprietary Informationtc \l2 "21.1   Proprietary Information.  Without prejudice to Section 21.3, any information concerning the parties which is designated in writing as proprietary and/or confidential and disclosed to the other party incident to the performance of the Scope of Work pursuant to this Agreement is disclosed in confidence and the transferee shall not publish or otherwise disclose it to others without the written approval of the transfer or, provided, however, that nothing herein shall limit either party’s rights to disclose data which: 

(a)
was developed on its own or furnished to it prior to this Agreement without restriction;

(b)
becomes generally available to the public through no fault of either party; or

(c)
is received by either party from a third party without restriction and not in breach of this Agreement.

Proprietary and/or confidential information disclosed hereunder shall only be used by the transferee in the performance of its obligations hereunder or as expressly permitted under this Agreement.  Each party shall take such actions to protect proprietary and/or confidential information disclosed by the other party as are consistent with its practices to protect its own proprietary and/or confidential information.

Furthermore Purchaser or Seller may provide any such information to any governmental authority having jurisdiction and asserting a right to obtain such information, but only to the extent required to do so by law. This clause shall survive the termination of this Agreement. 

21.2   Press Releasestc \l2 "21.2   Press Releases.  Seller agrees that it is in Purchaser’s interest to limit information of strategic value disseminated to the independent power industry regarding this Facility.  To the extent that Seller desires to issue press releases, advertisements in the trade press, tombstones in the financial or trade press then Seller must obtain Purchaser’s written release to do so.

21.3   Confidentialitytc \l2 "21.3   Confidentiality.  Seller acknowledges that Purchaser’s business is highly competitive and that Purchaser’s books, records, documents and technical information concerning its products, equipment, services, processes, procurement procedures, pricing techniques, the names of and other information (such as credit and financial data) concerning Purchaser’s customers and business affiliates, all comprise confidential business information and trade secrets of Purchaser which are valuable, special and unique proprietary assets.  Seller further acknowledges that protection of Purchaser’s confidential business information and trade secrets against unauthorized disclosure and use is of critical importance to Purchaser in maintaining its competitive position.  Accordingly, Seller hereby agrees that it will not, at any time during or after the term of this Agreement, make any unauthorized disclosure of any confidential business information or trade secrets of Purchaser or make any use thereof, except for the benefit of, and on behalf of Purchaser.  However, Seller’s obligation under this Section 21.3 shall not extend to information which is or becomes part of the public domain or is available to the public by publication or otherwise through no wrongful act or omission or noncompliance with this Section by Seller or its agents.  The provisions of this Section 21.3 shall survive the termination of this Agreement.  Seller agrees and acknowledges that money damages would not be sufficient to remedy  for any breach of this Section 21.3 by Seller, and Purchaser shall be entitled to specific performance and injunctive relief as remedies for such breach or any threatened breach.  Such remedies shall not be deemed the exclusive remedies for a breach of this Section 21.3 by Seller but shall be in addition to all remedies available at law or in equity to Purchaser including recovery of damages from Seller.  For the purposes of this paragraph, the term “Purchaser” shall also include Affiliates of Purchaser.

Seller shall deliver to Purchaser all Purchaser confidential information provided or disclosed to or used or acquired by Seller, including all information developed, derived, or created therefrom, or portions thereof, upon the earlier of:

(i)
the ending of the need for the information for performance of the Scope of Work; or

(ii)
Purchaser’s request;

(iii)
the completion of the Scope of Work for which it was provided, disclosed used or acquired; or

(iv)
cancellation, termination or suspension of this Agreement.

Seller may retain a single copy of all information upon which its Scope of Work is based for record purposes only.  In the event Seller, with Purchaser’s consent, releases Purchaser’s confidential information to a third party, Seller shall require such third party to enter into a confidentiality agreement similar to this Section 21.3 with Seller, and Seller shall retrieve all such released confidential information, including any and all copies of the confidential information and all information developed, derived, or created therefrom, upon the earlier of the events set forth above in this Section. 

No documents, data, materials or information available to Seller as set forth in this Section 21.3 or produced in whole or in part under this Agreement shall be the subject of an application for copyright by or on behalf of Seller without the prior written consent of Purchaser.

Either party shall be entitled to disclose the terms and conditions of this Agreement and any data or information acquired by it under or pursuant to this Agreement without the prior consent of the other party:

(a)
to any Affiliate of such party;

(b)
to any outside consultants or advisers engaged by or on behalf of such party in connection with the Works or the financing or operation of the Facility and acting in that capacity;

(c)
to any operator of the Facility, Lenders or permitted assignees;

(d)
to the extent required by the rules of a relevant and recognized stock exchange;

(e)
to the extent required by law or pursuant to an order of any court of competent jurisdiction, provided that the original disclosing party is given notice and adequate time to seek a protective order applicable to the information before it is disclosed;

(f)
to any insurer under a policy of insurance required to be taken out by either party under the Agreement; or

(g)
to directors, employees and officers of such party;

provided that:

(h)
the disclosing party determines in good faith that the recipient has a legitimate need to see such data or information; and

(i)
the recipient has been made aware of and has agreed to be bound by the requirements of this Article XXI.

ARTICLE XXII.  ASSIGNMENTtc \l1 "ARTICLE XXII.  ASSIGNMENT
22.1   Assignment by Sellertc \l2 "22.1   Assignment by Seller.  This Agreement may be assigned by Seller without Purchaser’s consent to a wholly owned subsidiary of Seller’s ultimate parent company subject to Section 3.7.  This Agreement may not be assigned by Seller to any other entity without the prior written consent of Purchaser, which shall not be unreasonably withheld.

22.2
Assignment by Purchaser or Agent TC "22.2
Assignment by Purchaser or Agent" \f C \l "2" .  This Agreement or any right or obligation contained herein may be assigned, from time to time, by Purchaser or Agent without Seller’s consent to the following:

(i)
Agent (in the case of an assignment by Purchaser) or an Affiliate of either Purchaser or Agent;  

(ii)
a joint venture, partnership, limited liability company, or other similar entity in which Agent or any of its  Affiliates is a venturer, partner or participant with no less than a nineteen and one-half percent (19.5%) equity interest;

(iii)
any Lender or financial institution providing financing to Purchaser or Agent, either of their respective Affiliates or any permitted assignee in connection with the Equipment or the Facility;

(iv)
any party (1) for which Agent or any of its Affiliates has agreed to construct or develop a Facility using the Equipment or (2) to which Agent or any of its Affiliates has agreed to convey a power plant project which it has under development; 

(v)
any contractor or developer which is retained by Agent or any of its Affiliates to construct or develop a Facility using the Equipment; or

(vi) any other party if such proposed assignee:  

(p) has substantially the same or better credit quality than Agent or, if not,  (A) the proposed assignee provides appropriate guaranties, letters of credit or other assurances of payment issued by an entity or person with substantially the same or better credit quality than Agent or (B) the assignor agrees to remain liable for all future liability under this Agreement;

(q) is not a direct competitor of Seller in the turbine manufacturing business;

(r) is not an adverse party to Seller in any material litigation; or

(s) if purchasing any Equipment (or its rights thereto), is purchasing such Equipment (or rights thereto) as part of a transaction in which (x) Purchaser, Agent or any of its Affiliates is providing related goods and/or services to such assignee, and (y) Purchaser or Agent is not merely acting as a broker or market maker with respect to such Equipment (or rights thereto).  Purchaser or Agent shall have the right to assign or pledge, from time to time, all or any portion of their respective right, title and interest in, to and under the Agreement as collateral for financing of any Facility without Seller’s consent.

Except for (i) through (vi) above, this Agreement or any rights and/or obligations hereunder may not be assigned by Purchaser or Agent to other parties without the prior written consent of Seller which shall not be unreasonably withheld, conditioned or delayed.  Seller agrees to respond to any request for consent within thirty (30) Days following its receipt of such request.  Any failure to respond within the foregoing time period shall be deemed to be a grant by Seller of its consent to the proposed assignment. In the event of assignment to a party as described in (v) or (vi) above, Purchaser will receive a guaranty in a form substantially similar to the one Seller’s parent has provided. The guaranty shall be from a company with a credit rating of BBB+ or better. 

When duly assigned in accordance with this Section 22.2 (including, following any collateral assignment, upon foreclosure by any collateral assignee), (i) this Agreement or the rights and/or obligations so assigned shall be binding upon and shall inure to the benefit of the assignee (and all rights and/or obligations so assigned, including, without limitation, any and all warranty rights, shall be assigned to the assignee as if such assignee were an original party hereto), (ii) the assignor shall be irrevocably relieved of and forever discharged from all liability under this Agreement so long as the assignee executes an assumption of such liabilities, and (iii) the Seller shall look only to such assignee for the performance of the obligations so assigned.  Any assignment by Purchaser or Agent other than as permitted herein shall be void and without force or effect.

[Upon any permitted assignment of the rights under this Agreement to acquire a Unit or Units, and the assumption (in accordance with the terms hereof) of the obligations related thereto, Seller shall enter into a separate purchase agreement with the permitted assignee (each, a “Facility Agreement”). The  terms of each Facility Agreement will be in strict conformity with the terms and conditions of this Agreement, except for site specific changes as agreed by the Seller and such assignee. In no way shall the Facility Agreement increase the liability or responsibility of Seller, Purchaser, or Agent under this Agreement. Further, the following sections shall not be altered, modified, qualified, conditioned or limited in any manner: Article XV (Risk of Loss and Title), Article XVIII (Force Majeure), Article XXI (Non-Disclosure of Information), Section 30.2 (Governing Law), Article XXVI (Arbitration), Article XXVII (Limitation of Liability), Article XIV (Warranty), Article X (Delivery and Performance). The parties agree that Section 3.14 will not be inserted into any Facility Agreement. The indemnity provision in each Facility Agreement shall be in accordance with Exhibit E.]

The parties hereto further agree and acknowledge that the foregoing provisions relating to this assignment will only control the assignment of Purchaser’s or Agent’s rights under this Agreement prior to the date upon which the Equipment achieves Takeover.  Following such date, Purchaser or Agent shall be permitted, without Seller’s consent, to: (i) assign its rights under this Agreement, (ii) convey any ownership interest that it may have in the Facility and/or (iii) convey any equity interest that it may have in the entity which owns the Facility.

ARTICLE XXIII.  RELATIONSHIP OF THE PARTIEStc \l1 "ARTICLE XXIII.  RELATIONSHIP OF THE PARTIES
23.1   Independent Contractortc \l2 "23.1   Independent Contractor.  Seller undertakes performance of this Agreement as an independent contractor.  Nothing herein shall create a relationship of employer and employee, joint venture, or partnership between Purchaser and Seller, its agents, representatives, employees Affiliates, Vendors or subcontractors, for any purpose whatsoever.  Nothing herein shall create a relationship of principal and agent between Purchaser and Seller, its agents, employees, representatives or subcontractors.  Neither party shall have the authority to bind or obligate the other in any manner as a result of the relationship created hereby.  Purchaser shall not have the right to control the manner(s) or prescribe the method(s) by which Seller performs this Agreement.  Seller shall be wholly responsible for supervision and the methods of performance.  Seller is entirely and solely responsible for its acts and the acts of its agents, employees, representatives, Affiliates, and Vendors engaged in the performance of this Agreement.  Seller shall provide qualified personnel who shall be and remain solely the employees of Seller, and at no time or in any manner shall said personnel be considered as or deemed to be employees of Purchaser.  Purchaser’s general coordinative efforts, suggestions and procedures with respect to the Scope of Work and Purchaser’s right of inspection, review and observation of the performance of this Agreement shall not make Seller or its employees, employees of Purchaser.

23.2   Responsibilities of Seller as Principal for its Employeestc \l2 "23.2   Responsibilities of Seller as Principal for its Employees.  Seller has complete and sole responsibility as a principal for its agents, Vendors and all other hires to perform or assist in performing the Scope of Work. 

23.3
Purchaser and Agent TC "23.3
Purchaser and Agent" \f C \l "2" .   PURCHASER REPRESENTS AND WARRANTS THAT IT HAS APPOINTED AGENT AS ITS SOLE AND EXCLUSIVE ACQUISITION AGENT WITH RESPECT TO THIS AGREEMENT, HAS ASSIGNED TO AGENT ALL OF THE RIGHTS OF PURCHASER UNDER THIS AGREEMENT (INCLUDING THOSE DESCRIBED IN SECTION 2.1), AND HAS DELEGATED TO AGENT ALL OF THE RESPONSIBILITIES AND OBLIGATIONS OF PURCHASER UNDER THIS AGREEMENT (OTHER THAN ANY PAYMENT OBLIGATIONS HEREUNDER AND ANY INDEMNIFICATION OBLIGATIONS HEREUNDER).  AGENT REPRESENTS AND WARRANTS THAT IT HAS ACCEPTED APPOINTMENT AS PURCHASER’S SOLE AND EXCLUSIVE ACQUISITION AGENT WITH RESPECT TO THIS AGREEMENT.   NOTWITHSTANDING ANY OTHER TERM OR PROVISION OF THIS AGREEMENT, SELLER AGREES, ACCEPTS, ACKNOWLEDGES AND COVENANTS, FOR ITSELF, ITS SUCCESSORS AND ASSIGNS, (I) THAT PURCHASER HAS APPOINTED AGENT AS ITS SOLE AND  EXCLUSIVE ACQUISITION AGENT WITH RESPECT TO THIS AGREEMENT, AND AGENT HAS ACCEPTED SUCH APPOINTMENT, AND  (II) THAT IT SHALL NOT SEEK OR CLAIM RECOURSE AGAINST OR  PAYMENT FROM PURCHASER FOR ANY REASON WITH RESPECT TO OR ARISING FROM OR RELATED TO AGENT’S ACTIONS OR OMISSIONS WITH RESPECT TO THIS AGREEMENT OTHER THAN FOR THE PAYMENT OF THE PURCHASE AMOUNT HEREUNDER.

Without limiting the generality of the foregoing, Seller acknowledges and agrees that it shall deal only with Agent with respect to the subject matter of this Agreement (including, without limitation, delivering Equipment or entering into any amendments, modifications or supplements of or to this Agreement) and in no event, without the prior written consent of Agent, shall Seller deliver any Equipment to Purchaser or enter into any contract, undertaking or other agreement with Purchaser (other than this Agreement), amend, modify or supplement this Agreement or take directions from or give instructions to the Purchaser (other than ministerial communications relating to the payment of the amounts described herein), in each case with respect to the subject matter of this Agreement.
ARTICLE XXIV.  LIENS AND CLAIMStc \l1 "ARTICLE XXIV.  LIENS AND CLAIMS
Seller shall not directly or indirectly create, incur, assume or suffer to be created by it or any Vendors, employees, laborers, materialmen or other suppliers of goods or services any claim, lien, security interest, charge or other encumbrance on the Equipment or any part thereof or interest therein and Seller shall immediately notify Purchaser of the assertion of any lien, claim, security interest or other encumbrance against the Equipment or any part thereof.  Seller shall remove immediately any lien, claim, security interest or other encumbrances against Purchaser, Purchaser’s property, or Purchaser’s Affiliates’ property, or the Equipment arising in favor of Seller or its Vendors or other persons or entities by reason of having provided labor, materials or equipment related to performance of this Agreement and to pay any damages, costs, losses and expenses (including, without limitation, court costs and attorneys’ fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, in connection with, arising out of, or related to any such lien, claim, security interest or other encumbrance.  In the event of a lien from a Vendor, supplier or service provided is levied, Seller shall immediately post a letter of credit acceptable to Purchaser against such lien.  Upon the failure of Seller promptly to pay or discharge any lien claim, security interest or other encumbrance as required hereby within twenty (20) days of notice of the existence thereof from any source, Purchaser may, but shall not be obligated to, pay or discharge such lien claim, security interest or other encumbrance and, upon the payment or discharge thereof, shall be entitled to recover from Seller the amount thereof together with all expenses incurred by Purchaser in connection with such payment or discharge.  

ARTICLE XXV.  NOTICES AND COMMUNICATIONStc \l1 "ARTICLE XXV.  NOTICES AND COMMUNICATIONS
25.1   Noticestc \l2 "25.1   Notices.  Any notice pursuant to the terms and conditions of this Agreement shall be in writing and either:

(a)
delivered personally;

(b)
sent by certified mail, (return receipt requested);

(c)
sent by a recognized overnight mail or courier service with delivery receipt required; or

(d)
sent by confirmed facsimile transfer:

      Commercial ‑ Legal:

If to Seller:

See Exhibit E.1

If to Purchaser:

See Exhibit E.1

Either party may change its address or the person to be notified by a notice delivered in accordance with this section.

25.2   Effectiveness of Noticestc \l2 "25.2   Effectiveness of Notices.  Notices shall be effective when received  at the address specified.

25.3   Technical Communicationstc \l2 "25.3   Technical Communications.  Notwithstanding communications and notices addresses as set forth in Exhibit E.1, the parties will route routine and technical communications as set forth in Exhibit E.2:

If to Seller:

See Exhibit E.2

If to Purchaser:

See Exhibit E.2

ARTICLE XXVI.  ARBITRATIONtc \l1 "ARTICLE XXVI.  ARBITRATION
26.1   Negotiation of Disputes and Disagreementstc \l2 "26.1   Negotiation of Disputes and Disagreements.  In the event of any dispute or disagreement arising out of or relating to the implementation or performance of this Agreement, which the parties hereto have been unable to settle or agree upon within a period of thirty (30) days after the dispute or disagreement arises, each party shall nominate a senior officer of its management to meet at a mutually agreed time and place not later than forty five (45) days after the dispute or disagreement has arisen to attempt to resolve such dispute or disagreement.  Should a resolution of such dispute or disagreement not be obtained within fifteen (15) days after the meeting of senior officers for such purpose, or if such meeting does not take place within sixty (60) days after the dispute or disagreement has arisen either party may then by notice to the other submit the dispute to arbitration in accordance with the provisions of Section 26.2.

26.2   Arbitration Resolutiontc \l2 "26.2   Arbitration Resolution.  With respect to arbitration resolution, the parties agree that:

(a)
In the event of dispute between Purchaser and Seller concerning the interpretation of any provision of this Agreement or the performance of any of the terms of this Agreement such matter or matters in dispute shall be finally settled under the arbitration rules of the American Arbitration Association by three arbitrators, one appointed by each party, and the third, who shall be the chairman will be selected by the two appointed arbitrators and failing agreement by the chairman of the American Arbitration Association.  The language of the arbitration shall be English.  The place of arbitration shall be in New York City at a location to be mutually agreed upon by the parties.

(b)
The decision of the arbitrators shall be final and binding upon the parties;

(c)
If any dispute to be referred to arbitration under this agreement raises issues which are, as mutually agreed, substantially the same as or connected with issues raised in a dispute between any other dispute between the parties (and their successor in title and assigns), then such latter dispute shall constitute a “related dispute”;

(d)
If a related dispute has already been referred to arbitration in accordance with arbitration provisions identical (mutatis mutandis) to this clause:

or, if the dispute under this agreement has already been referred to arbitration under this clause, then:

 (i)
the dispute under this Agreement shall be referred to the arbitrators appointed to determine the related dispute; and

(ii)
the arbitrators shall have power to join one or more defendants or third parties or consolidate actions as provided by applicable law.

26.3   Continuation of Worktc \l2 "26.3   Continuation of Work.  Pending final resolution of any dispute, Purchaser and Seller shall continue to fulfill their respective obligations hereunder.

ARTICLE XXVII.  LIMITATION OF LIABILITYtc \l1 "ARTICLE XXVII.  LIMITATION OF LIABILITY
27.1   Maximum Liabilitytc \l2 "27.1   Maximum Liability.  Seller’s maximum aggregate liability for claims by Purchaser arising out of Seller’s performance of this Agreement whether arising from tort (including negligence), breach of contract or any other cause of action, including Liquidated Damages, shall be one hundred (100%) of the Purchase Amount; provided, however, that this limitation on liability shall not include any liability for or apply to any of the following categories of liability of Seller: 

(i)
under Article XX Section 20.1(Indemnification);

(ii)
under Article XXIV (Liens and Claims);

(iii)
under Section 15.2; and

(iv)
resulting from the gross negligence or wilful misconduct of the Seller, its agents and employees.

which liabilities shall not be limited.  All liability of Seller with respect to the Unit shall terminate six (6) years after delivery of the Unit to the Delivery Point, as determined pursuant to Section 10.2, and all liability of Seller under this Agreement shall terminate six (6) years after delivery of the Unit to the Delivery Point, as determined in accordance with Section 10.2.

27.2   Consequential Lossestc \l2 "27.2   Consequential Losses.  Except for liquidated damages specifically provided for herein, in no event, whether as a result of breach of contract, breach of warranty, tort liability (including negligence or strict liability), strict liability, or otherwise, and whether arising before or after completion of the Scope of Work, shall either party be liable to the other party for special, indirect, exemplary or consequential losses of any nature whatsoever, including losses or damages caused by reason of unavailability of the Equipment, shutdowns or service interruptions, loss of use, loss of profits or revenue, inventory or use charges, cost of purchased or replacement power, interest charges or cost of capital or claims of a party’s customers.  Except for cancellation fees specifically provided for herein, in no event, whether as a result of breach of contract, tort liability (including negligence or strict liability), strict liability or otherwise, shall a party be liable hereunder for special, indirect, exemplary or consequential damages of any nature whatsoever, including, but not limited to, loss of use, loss of profits or revenue, or inventory or use charges. 

27.3   Releases Valid in All Eventstc \l2 "27.3   Releases Valid in All Events.  Except as otherwise specifically set forth herein, releases, disclaimers and limitations on liability expressed herein shall apply even in the event of the negligence, strict liability, fault or breach of contract (including other legal bases of responsibility such as fundamental breach) of the party whose liability is released, disclaimed or limited.

27.4   If Seller furnishes Purchaser with advice or assistance which is not required by this Agreement, the furnishing of such advice or assistance will not subject Seller to any liability whether in contract, warranty, tort (including negligence), strict liability, indemnity or otherwise.

ARTICLE XXVIII.  DRUG AND ALCOHOL‑FREE WORKPLACEtc \l1 "ARTICLE XXVIII.  DRUG AND ALCOHOL‑FREE WORKPLACE
The parties desire to provide a safe and productive work environment.  The parties believe that the use, possession and/or distribution of illegal/unauthorized drugs and alcohol presents a serious threat to the safety of employees, visitors and others at the job site, or other premises owned, leased, or occupied by Purchaser.  All Seller’s and Seller’s Vendors’ employees associated with the Scope of Work under this Agreement must agree to compliance with Purchaser’s drug and alcohol policy Number 1200-2, dated September 11, 1995 including: 

(1)
while on or entering the Site or other premises owned, leased, or occupied by Purchaser, search of personal and professional possessions, including but not limited to automobiles, trucks, briefcases, lunch boxes, and person for illegal drugs.  Failure to consent to such search shall be grounds for immediate removal from the Site or other premises owned, leased, or occupied by Purchaser;

(2)
drug testing at any time while on the Site or other premises owned, leased or occupied by Purchaser.  Failure to do so or failing any such test shall be grounds for immediate removal from the Site or other premises owned, leased, or occupied by Purchaser; and

(3)
failure of a Seller’s or Vendor’s employee to agree and abide by these requirements will be grounds for immediate removal from the job site or other premises owned, leased, or occupied by Purchaser from any work site or location under the control of Purchaser that is associated with the Scope of Work under this Agreement.

ARTICLE XXIX.  PROJECT PLANNING AND CONTROLStc \l1 "ARTICLE XXIX.  PROJECT PLANNING AND CONTROLS
Exhibit K sets forth the Project Planning and Control system for tracking the progress of the Scope of Work.  Seller shall establish a program, submit reports and data as set forth therein.  

ARTICLE XXX.  MISCELLANEOUStc \l1 "ARTICLE XXX.  MISCELLANEOUS
30.1   Validity and Enforceabilitytc \l2 "30.1   Validity and Enforceability.  The invalidity or unenforceability of any portion or provision of this Agreement shall not affect the validity or enforceability of any other portion or provision.  Any invalid or unenforceable portion or provision shall be deemed severed from this Agreement, and the balance of the Agreement shall be construed and enforced as if the Agreement did not contain such invalid or unenforceable portion or provision.  Notwithstanding the provisions of the preceding sentence, should any term or provision of this Agreement be found invalid by any governmental authority having jurisdiction thereof, the parties shall immediately renegotiate in good faith such term or provision of the Agreement to eliminate such invalidity.

30.2   Governing Lawtc \l2 "30.2   Governing Law.  This Agreement, its interpretation and any disputes relating to, arising out of or connected with this Agreement, shall be governed by the laws of the State of New York, without regard to its conflicts of law provisions.

30.3   Entire Agreementtc \l2 "30.3   Entire Agreement.  This Agreement, and the Exhibits attached hereto constitute the entire agreement between the parties with respect to the subject matter hereof, and there are no oral or written understandings, representations or commitments of any kind, express or implied, not set forth herein.  This Agreement supersedes all prior agreements between the parties with respect to the subject matter hereof. 

30.4   Agreement Modificationtc \l2 "30.4   Agreement Modification.  No oral or written modification of this Agreement either before or after its execution shall be of any force or effect unless such modification is in writing and signed by the party to be bound thereby. 

30.5   Waivertc \l2 "30.5   Waiver.  The waiver by any party of any breach or failure to enforce any of the terms, covenants or conditions of this Agreement shall not in any way affect, limit, modify or waive the future enforcement of such terms, covenants or conditions. 

30.6   Headingstc \l2 "30.6   Headings.  The headings contained herein are included solely for the convenience of the parties and are not to be used as a basis for interpreting the various sections of this Agreement.

30.7   Third‑Party Beneficiariestc \l2 "30.7   Third‑Party Beneficiaries.  The provisions of this Agreement are intended for the sole benefit of Purchaser and Seller, and there are no third‑party beneficiaries other than assignees contemplated by the terms herein. 

30.8   Counterpartstc \l2 "30.8   Counterparts.  This Agreement may be executed in counterparts, each of which when so executed and delivered shall be an original, and all of which, when taken together, shall constitute one and the same instrument. 

30.9   Equal Employment Opportunitytc \l2 "30.9   Equal Employment Opportunity.  To the extent performance if any Scope of Work is performed in the United States, the parties hereto agree that the provisions of Executive Order 11246, as amended, and the Rehabilitation Act of 1973 (Section 503, Public Law 93‑112, as amended), the Vietnam Era Veteran’s Readjustment Assistance Act of 1974, as amended (including the provisions of the “Equal Opportunity” clauses), and the regulations promulgated pursuant to the above, are hereby incorporated into this Agreement by reference as if fully set out. 

30.10  Cooperation on Sitetc \l2 "30.10  Cooperation on Site. To the extent Seller is required to perform services on Site it shall cooperate with other contractors on Site so as to coordinate work and schedules.

30.11   Avoidance of Nuclear Usetc \l2 "30.11   Avoidance of Nuclear Use.  The Equipment sold hereunder is not intended for application (and shall not be used) in connection with the use or handling of nuclear material or the construction or operation of a nuclear installation.  Purchaser warrants that it shall not use such Equipment for such purposes, or permit others to use such Equipment, while such Equipment is owned by Purchaser, for such purposes unless such use is agreed to in writing by the Seller.  If, in breach of the foregoing, any such use occurs, Seller disclaims all liability for any nuclear or other damage, injury or contamination, and Purchaser shall indemnify Seller against any such liability, whether arising as a result of breach of contract, warranty, tort (including negligence), strict liability, indemnity or otherwise.

30.12   Miscellaneous Representations and Warrantiestc \l2 "30.12   Miscellaneous Representations and Warranties.  The parties represent and warrant to each other that as of the date of this Agreement: 

(a)
the party is duly incorporated, organized, existing and in good standing under the laws of New York; (in the case of Seller) or Delaware (in the case of Purchaser); the party  possesses all requisite power and authority to enter into and perform this Agreement, to carry out the transactions contemplated herein, and to conduct business in each of the locations where any portion of the Scope of Work is to be performed; and has all legal power and authority to own and use its properties and to transact the business in which it is engaged and holds or expects to obtain all franchises, licenses, and permits required therefor;

 (b)
the party’s execution, delivery, and performance of this Agreement have been duly authorized by, and are in accordance with, its articles of incorporation and by‑laws; this Agreement has been duly executed and delivered for it by the signatories so authorized; and this Agreement constitutes the party’s legal, valid, and binding obligation;

(c)
no suit, claim, action, arbitration, or legal, administrative or other proceeding is pending or threatened against the party that would affect the validity or enforceability of this Agreement, the ability of the party to fulfill its commitments hereunder in any material respect, or that could result in any material adverse change in the business or financial condition of the party;

(d)
Equipment of the same type and model number which is sold by Seller or its Affiliates to other clients is of the same manufacturing technology, includes the same principal components and has not demonstrated trends of failure; and

(e)
the party is not in breach of, in default under, or in violation of, any applicable statute, law, ordinance, decree, rule, or regulation of any governmental authority, or the provisions of  its articles of incorporation or by‑laws or any franchise or license, or in breach of, in default under, or in violation of, any provision of any indenture or any evidence of indebtedness or security therefor, lease, contract, license or other agreement by which it is bound if such breach, default or violation may result in a material adverse effect on the business or financial condition of the party; and the execution and delivery of this Agreement and the performance of its obligations hereunder will not constitute or result in any such breach, default or violation.

IN WITNESS WHEREOF, the parties have caused this Agreement to be executed as of the date and the year first above written.





Enron North America Corp.,





as Purchaser





By:  ____________________________                                        





Title:  _________________________                                     





Date:  __________________________                                       





General Electric Company,





 as Seller




By:  ____________________________                                        





Title:  _________________________                                     





Date:  __________________________                                       

EXHIBIT A  BASIS CONDITIONStc \l1 "EXHIBIT A  BASIS CONDITIONS
Performance guarantee conditions for the GTG shall be as set forth below:

Fuel
Natural Gas
Units of Measure

Fuel Composition
See Exhibit A-1


Load
Base Load


Ambient Temperature (dry bulb)
55
oF

Barometric Pressure
14.55
PSIA

Ambient Relative Humidity
55
%

Fuel LHV @ 80 deg F
20,659
BTU/lb

Fuel Temperature
365
oF

Inlet Loss (Static)
3
In. H20

Exhaust Loss (Static)
16
In. H20

Generator Power Factor (Lagging/Leading)
0.85


Generator Frequency
60
Hertz





EXHIBIT A-1 BASIS FUELtc \l1 "EXHIBIT A-1 BASIS FUEL
Component



Mol Percent
Methane C1
95.173
Ethane C2
2.898
Propane C3
0.074


Iso-Butane C4
0.010


n-Butane C5
0.011
Iso-Pentane C5
0.003


n-Pentane C5
0.001
Hexane and above C6+
0.001
Nitrogen N2
1.146



Carbon Dioxide CO2
0.682




Total

100.00

EXHIBIT A-2 SELLER FUEL SPECIFICATIONtc \l1 "EXHIBIT A-2 SELLER FUEL SPECIFICATION
The Unit shall be capable of operating with natural gas fuels meeting the requirements in GEI 41040F dated January 1999, (Attachment 1).

Purchaser shall be required to comply with Seller’s specification for Gas Turbine Compressor Washing Liquid Washing Recommendations for Gas Turbines with Pulsed Water Wash Systems, Reference GEK-107122A (Attachment 2).

EXHIBIT B  SCOPE OF WORK/SPECIFICATIONtc \l1 "EXHIBIT B  SCOPE OF WORK/SPECIFICATION
Attached is Purchaser’s Specification Revision 3, dated May 9, 2000.

EXHIBIT B‑1  SPECIFICATIONtc \l1 "EXHIBIT B‑1  SPECIFICATION
Attached is Seller’s specification for the Scope of Work, Reference 90782AG revision 0, dated April, 2000.

EXHIBIT B-2 GUARANTEED DELIVERY DATEtc \l1 "EXHIBIT B-2 GUARANTEED DELIVERY DATE
SCHEDULE I
Item:




Guaranteed Delivery Dates:

Gas Turbine


June 15, 2001

Generator
July 15, 2001

EXHIBIT B‑3 PERFORMANCE GUARANTEES AND SPECIFIC PERFORMANCE GUARANTEEStc \l1 "EXHIBIT B‑3 PERFORMANCE GUARANTEES AND SPECIFIC PERFORMANCE GUARANTEES
B.3.1

Specific Performance Exhaust Gas Temperature and Energy Guarantees.

B-3.1.1
Exhaust Gas Temperature Guarantee.  Seller guarantees that the Adjusted Exhaust Gas Temperature of the Unit as measured during the most recent Performance Test shall not be less than 1110 degrees Fahrenheit (0F) (the “Exhaust Gas Temperature Guarantee”).

 B-3.1.2
Specific Performance Exhaust Gas Temperature Guarantee.  As a Specific Performance Obligation Seller guarantees that the Adjusted Exhaust Gas Temperature of the Unit as measured during the most recent Performance Test shall not be less than 1092 degrees Fahrenheit (0F) and shall not be greater than 1130 0F (the “Specific Performance Exhaust Gas Temperature Guarantee”).  Subject to the provisions of Section 10.12.8 if the Adjusted Exhaust Gas Temperature of the Unit is within the preceding specified range, Seller will be considered to have satisfactorily caused the Unit to meet the Specific Performance requirement associated with the Specific Performance Exhaust Gas Temperature Guarantee. 

B-3.1.3
Exhaust Gas Energy Guarantee.  As a Specific Performance obligation Seller guarantees that the Adjusted Exhaust Gas Energy of the Unit as measured or calculated during the most recent Performance Test of the Unit shall be greater than or equal to 952.0 x 106 BTU/hr (LHV) (the “Exhaust Energy Guarantee”).

 B-3.1.4
Specific Performance Exhaust Gas Energy Guarantee.  As a Specific Performance obligation Seller guarantees that the Adjusted Exhaust Gas Energy of the Unit as measured or calculated during the most recent Performance Test of the Unit shall be greater than or equal to 926.9 x 106 BTU/hr (LHV) (the “Specific Performance Exhaust Energy Guarantee”).  Subject to the provisions of Section 10.12.8, if the Adjusted Exhaust Energy of the Unit is greater than or equal to the Specific Performance Exhaust Energy Guarantee, Seller will be considered to have satisfactorily caused the Unit to have met the Specific Performance requirement associated with Specific Performance Exhaust Energy Guarantee. 

B.3.2
 Specific Performance Sound Level Guarantees. 

B.3.2.1   Near Source Sound Level Guarantee.  As a Specific Performance obligation Seller guarantees that the near field average A-weighted sound pressure levels of each Unit shall not exceed 85dB(A) (referenced to 20 micropascals) (the “Near Source Sound Level Guarantee”) when measured during a Performance Test or Sound Level Test in accordance with the Sound Level Test Procedures at one and half (1.5) meters above any working elevation and one (1) meter from the surface. 

The Near Source Sound Level Guarantee is limited to normal continuous sound sources within the Scope of Work.

B.3.2.2   Far Field Sound Level Guarantee.  As a Specific Performance obligation, Seller guarantees that the far field average A-weighted sound pressure level of the Unit (referenced to 20 micropascals) as installed and erected shall not exceed 67 dB(A) at 400 feet (the values at the stated distances from the nearest edge of the Unit) (the “Far Field Sound Level Guarantee”) when measured during a Performance Test or Sound Level Test while operating at steady state loads from 50 to 100 percent in accordance with the Sound Level Test Procedure.

B.3.3
Specific Performance Exhaust Emissions Guarantee.
B.3.3.1  Emissions Guarantee.  As a Specific Performance obligation Seller guarantees that the Adjusted Emissions of the Unit when the Unit is operated (i) between 20 0F and 90 0F, from 50% load through Base Load, between 0% and 100% humidity and at all other Basis Conditions (the “Emissions Guarantee”) will not be greater than the following values:

Category

Value



Units of Measure
NOx


9



ppmvd @ 15% O2
CO


9



ppmvd

PM 10

18



lb/hr

VOC’s
1.4



ppmvw

Subject to the provisions of Section 10.12.8 if the Adjusted Emissions of the Unit are less than or equal to the  Emissions Guarantee, Seller will be considered to have satisfactorily caused the Unit to have met the Specific Performance requirement associated with the Emissions Guarantee. 

B.3.4  Electrical Output Guarantees.

B.3.4.1  Electrical Output Guarantee.  Seller guarantees that the Adjusted Electrical Output, as demonstrated during the most recent Performance Test, shall be equal to or greater than 169,450 kW (after deducting the Unit’s auxiliary Loads) (the “Electrical Output Guarantee”).

B.3.4.2  Specific Performance Electrical Output Guarantee.  As a Specific Performance obligation, Seller guarantees that the Adjusted Electrical Output of the Unit, as demonstrated during the most recent Performance Test, shall be equal to or  greater than 164,964 kW (after deducting the Unit’s  auxiliary loads) (the “Specific Performance Electrical Output Guarantee”).

B.3.5  Heat Rate Guarantees.

B.3.5.1  Heat Rate Guarantee.  Seller guarantees that the Adjusted net Heat Rate of the Unit, as demonstrated during the most recent Performance Test, shall not exceed 9380 BTU/kWh (LHV) (the “Heat Rate Guarantee”).  The Heat Rate Guarantee is net of the Unit’s auxiliary loads. 

B.3.5.2  Specific Performance Heat Rate Guarantee.  As a Specific Performance obligation Seller guarantees that the net Adjusted Heat Rate of the Unit, as demonstrated during the most recent Performance Test, shall not be more than 9656 BTU/kWh (LHV) (the “Specific Performance Heat Rate Guarantee”).  The Heat Rate Guarantee is net of the Unit’s auxiliary loads. 

EXHIBIT B‑4  APPROVED VENDORStc \l1 "EXHIBIT B‑4  APPROVED VENDORS
APPROVED VENDORS

Inlet Filter House
Braden Steel


Tulsa, OK

Donaldson

Baldwin, WI

Pneumafil Corp.

Charlotte, NC

J & G Steel
Sapupla, OK

Gas Valve Module
Mitten Fluid

Syracuse, NY

Becon

So. Windsor, CT

Hebeler


Tonawanda, NY

Gilkes




Control Center



MEPCO



Inlet Duct
Braden Steel
Tulsa, OK

C&W Fabricators

Gardner,MA

Donaldson

Baldwin, WI

J&G Steel

Sapupla, OK

CO2 Tank
Ansul Preferred

Chemetron


Swansboro, GA

PEECC (including Mark VI and EX2000),GLAC and GNAC
GE Breaker


Philadelphia, PA

Atkinson Industries

Koonst Wagner



Central Electric

PEMCO

Delta Unibus


GE Canada

PACS Industries

Mt. Vernon, OH

Calvert

Hatch

Brush

Electric Power Sys

Generator
GE

Elin

Hitachi

Toshiba

Brush

Water Wash Skid
Hebeler


Tonawanda, NY

MEF

Enpro

Manufacturas

Mitten


Syracuse, NY

Ogden

Midland

Jord

Hilliard


Elmira, NY


Braden



Accessory Base
GE

Avondale Shipyard

Gilkes

Kvaerner Processes

Oakwell Compressor

Harder Mechanic

Mittener


Hebeler


Tonawanda, NY

EXHIBIT B-5 NOT USEDtc \l1 "EXHIBIT B-5 NOT USED
EXHIBIT B-6 LIQUIDATED DAMAGEStc \l1 "EXHIBIT B-6 LIQUIDATED DAMAGES
B.6.1
Document Delivery Liquidated Damages (per Section 10.1):

1 through 30 days late - $500.00

31 through 90 days late - $1,000.00

91 + days late - $5,000.00

B.6.2
Delivery Liquidated Damages (per Section 10.3.1):

# Day Late


$/Day
1-7



$0

8 +



$22,500

B.6.3
Take Over Liquidated Damages (per Section 10.3.2):

Rate per Day

1 through 30: $60,000/day

31 +               $75,000/day

B.6.4
Output Liquidated Damages (per Section 10.9.1):

Rate per kW
Eight Hundred U.S. Dollars ($800)/kW

B.6.5
Heat Rate Liquidated Damages (per Section 10.9.2):

Rate per BTU/kWh (LHV)
Nineteen Thousand Five hundred U.S. Dollars ($19,500/BTU/kWh(LHV)

B.6.6  Exhaust Temperature Liquidated Damages (per Section 10.4.1):

Rate per 0F per Unit
One Hundred Ninety Six Thousand Three Hundred Seventeen U.S. Dollars ($196,317)

B.6.7 Exhaust Energy Liquidated Damages (per Section 10.4.4):

Rate per MMBtu/hr
One Hundred Forty Two Thousand Nine Hundred Eighty One U.S. Dollars ($142,981)

EXHIBIT C-1  SELLER PARENT GUARANTEEtc \l1 "EXHIBIT C-1  SELLER PARENT GUARANTEE
GUARANTEE

       THIS GUARANTEE, dated the ______ of ____________________, 19_____, is from [Seller’s Parent Company], a [           ] corporation (“XXX”), to Enron North America Corp. (“RECIPIENT”).

       WHEREAS, [Seller] is an affiliate of [Seller’s Parent Company] (“XXXX”); and

       WHEREAS, RECIPIENT and [Seller] are entering into the attached [----] Contract dated [------] herewith (the “Agreement”); and

       WHEREAS, [Seller’s Parent Company] has agreed to guarantee the performance of Seller under the Agreement in order to induce RECIPIENT to enter into the Agreement;

       NOW THEREFORE, [Seller’s Parent Company] hereby irrevocably and unconditionally guarantees to RECIPIENT the performance by [Seller] of all of its undertaking, covenants, indemnities and obligations under the Agreement to the extent and under the terms and conditions and subject to the limitations set forth in the Agreement.  [Seller’s Parent Company] hereby consents that at any time and from time to time without notice to [Seller’s Parent Company], the performance or observance by [Seller] of any term or covenant of the Agreement may be waived, the time of performance thereof extended, any provisions thereof amended and the rights of RECIPIENT hereunder assigned, without affecting the liability of [Seller’s Parent Company] hereunder.  [Seller’s Parent Company] may assert any and all defenses and limitations of liability possessed by [Seller], but excluding any defenses based upon invalid execution of the Agreement.

       This guarantee shall be governed by, and construed, interpreted and enforced in accordance with the substantive law of the State of New York, excluding any conflict of laws or principles which would result in a choice of law for this Guarantee other than New York law.  Further, the parties stipulate that this Guarantee is deemed to have been made and entered into by them in the State of New York.

      Guarantor shall waive any rights to subrogation/security and agrees to be bound by any findings of fact or final award or judgement made in an arbitration against Seller under the Agreement.

       This Guarantee and any liability or obligation created hereunder shall expire upon the expiration of all liability and obligations of [Seller] under the Agreement.

IN WITNESS WHEREOF, [Seller’s Parent Company] has caused this Guarantee to be executed as of the date first written above.

[SELLER’S PARENT COMPANY]

By:                                            





Printed Name:                                          





Title:                            

EXHIBIT C-2 PURCHASER’S GUARANTEEtc \l1 "EXHIBIT C-2 PURCHASER’S GUARANTEE

THIS GUARANTEE, dated the ____ of ____________, 19____, is from __________________, a ______________ corporation (“__________”), to a corporation under the laws of [---------] (“RECIPIENT”).


WHEREAS,__________________ is an affiliate of ________________________.; and


WHEREAS, RECIPIENT and __________________ entering into the attached Purchase Contract of even date herewith (the “Agreement”); and


WHEREAS,________ has agreed to guarantee the performance of ________________ under the Agreement in order to induce RECIPIENT to enter into the Agreement;


NOW THEREFORE, _______ hereby irrevocably and unconditionally guarantees to RECIPIENT the performance by _________________ of all of its undertaking, covenants, indemnities and obligations under the Agreement to the extent and under the terms and conditions and subject to the limitations set forth in the Agreement, provided that all of the obligations or RECIPIENT under the Agreement are met on a current basis. ______ hereby consents that at any time and from time to time term or covenant of the Agreement may be waived, the time of performance thereof extended, any provisions thereof amended and the rights of RECIPIENT hereunder assigned, without affecting the liability of _____ hereunder. _____  may assert any and all defenses and limitations of liability possessed by _______________, but excluding any defenses based upon invalid execution of the Agreement.


This guarantee shall be governed by, and construed, interpreted and enforced in accordance with the substantive law of the State of New York, excluding any conflict of laws or principles which would result in a choice of law for this Guarantee other than New York law. 


This Guarantee and any liability or obligation created hereunder shall expire upon the expiration of all liability and obligations of_____________________  under the Agreement.


IN WITNESS WHEREOF, ______ has caused this Guarantee to be executed as of the date first written above.

___________________________________

By: ________________________________

Printed Name: ______________________

Title: ______________________________

EXHIBIT D  SAMPLE LETTER OF CREDITtc \l1 "EXHIBIT D  SAMPLE LETTER OF CREDIT
Applicant:   [-------] (“Seller”)

Beneficiary:  Enron North America Corp. (“Beneficiary”)

Bank: [------- ] (“Bank”)

Expiry Date:  

Amount:       US ($--------)

I.
Funds under this irrevocable standby Letter of Credit are available to Beneficiary against presentation to us of Beneficiary’s draft drawn at sight on _____________, marked thereon “Drawn under standby Letter of Credit number________, and accompanied by the following documents:

 1.
Original Beneficiary’s statement purportedly signed by an authorized officers of Beneficiary (as determined at Beneficiary’s sole and absolute judgement) stating:  “Seller is in default of its obligation to perform in accordance with Section(s) [-------] of Contract No. [------------] (the “Agreement”), dated _________.  This statement is a demand for payment under irrevocable standby Letter of Credit number _______ notwithstanding any objection by Seller or any other person or entity whatsoever.”

2.
A copy of the written notice to Seller sent pursuant to Article XXV of the Agreement (a copy of the conformation of receipt shall be attached thereto) , dated at least thirty (30) days prior to presentation of any claim under this irrevocable standby Letter of Credit evidencing that Beneficiary gave the requisite written notification to Seller stating therein that Seller was in breach of a specified obligation under the Agreement and that it is [beneficiary] intent to drawdown [specify amount] in the event General Electric Company fails to cure or commence to cure such default within thirty (30) days from the date of this notice.

II.
Special Conditions:

1.
Payment under this irrevocable standby Letter of Credit will be made to an account in beneficiary’s name at such bank as beneficiary shall stipulate.  The amount or amounts demanded shall not exceed, in the aggregate, the amount of this Letter of Credit.

2.
Any payment made hereunder shall be made free and clear of and without deduction for, or on account of, any present or future taxes, levies, imposts, duties, charges, fees, commissions, deductions or withholdings of any nature whatsoever and by whomever imposed.

3.
Any reference to Contract/Bid item is for information purposes only and is not incorporated in nor made a part of this irrevocable standby Letter of Credit.

4.
Bank agrees and consents that this Contract may be modified, adjusted, amended, extended, suspended or shortened pursuant to Article XI of this Contract, and that  that this irrevocable standby Letter of Credit, subject to agreement of Beneficiary, Seller and Bank may be modified to comply with any such changed requirements of this Contract.

5.
Seller’s liability under this irrevocable standby Letter of Credit is limited to ([-------] United States Dollars [$-------]).  This irrevocable standby Letter of Credit shall expire at our counters [-------]     , 200[–].

6.
Demands may be made against this irrevocable standby Letter of Credit in one or more increments; however, the aggregate of such demands shall not exceed the amount set forth in Paragraph 5 of this irrevocable standby Letter of Credit.

We hereby engage with the beneficiary that draft(s) accompanied by documents drawn in strict compliance with the terms and conditions of this irrevocable standby Letter of Credit shall be duly honored by us if presented to us at our office located at _______________________on or before the expiration date.

This irrevocable standby Letter of Credit is subject to the uniform customs and practice for documentary credits (1993 revision), International Chamber of Commerce, Publication No. 500.  This irrevocable standby Letter of Credit shall be governed by, and construed in accordance with the laws of the State of New York.    

EXHIBIT E  COMMUNICATIONStc \l1 "EXHIBIT E  COMMUNICATIONS
E.1
Commercial ‑ Legal Notice Addresses:

If to Seller:

GE Power Systems



1 River Road Bldg. 36 - 3 East



Schenectady, New York 12345



Attn: Jeff Darst 



Phone: 518-385-0663



Fax: 518-385-8495



cc: Earl Hamil



Phone: 864-675-3132



Fax: 864-675-2400


If to Purchaser:
Enron North America Corp.




c/o NEPCO




11831 North Creek Parkway North




Bothell, WA. 98011




Attention: Gene Larson , Project Manager




Phone: 425-415-3000




Fax: 425-415-3095

E.2
Technical Communications Notice Addresses. 

If to Seller:

GE Power Systems



300 Garlington Road



Room 268



Greenville, South Carolina 29602



Attn: Earl Hamil



Phone: 864-675-3132



Fax: 864-675-2400



cc: Jeff  Darst 



Phone: 518-385-0663



Fax: 518-385-8495

If to Purchaser:
Enron North America Corp.



c/o NEPCO



11831 North Creek Parkway North



Bothell, WA. 98011



Attention: Carl Quist



Telephone: 425-869-3000



Fax: 425-869-3095



cc:
Enron Engineering & Construction Company




333 Clay Street, Suite 400




Houston, Texas 77002




Phone: 713-646-7550




Fax: 713-646-6597




Attn: 
Eric Booth





Coyote Springs @ Project Engineering Manager

EXHIBIT F  PERFORMANCE TEST GUIDELINEStc \l1 "EXHIBIT F  PERFORMANCE TEST GUIDELINES
A.
TEST PHILOSOPHY
I.
General

The performance guarantees for the Unit include the Specific Performance Guarantees and/or Performance Guarantees of Electric Output, Heat Rate, Exhaust Gas Temperature, and Exhaust Gas Energy, in accordance with the Agreement.  The performance test procedure will include three one (1) hour input/output test runs for each Unit utilizing a combination of installed station instrumentation and special test instruments to (i) observe and record of the parameters required to demonstrate or calculate performance and (ii) enable correction of the demonstrated or calculated performance to Basis Conditions (a “Test Run”).  All instruments used to measure parameters used to calculate the results of the Test shall meet the accuracy and calibration requirements of the Codes and Standards or as specified in this Exhibit F.

The Performance Test will be performed by the Purchaser.  The Seller will prepare a detailed Test Procedure, based on PTC 1-1999, PTC 22-1997, PTC 4.4-1981, PTC 19.1-1998 and appropriate related ASME Performance Test Codes and ASME Standards (the “Codes and Standards”), which will be submitted to Purchaser in accordance with Section 10.12.7.  Purchaser will perform calculations to determine Unit performance relative to Guaranteed Levels and Specific Performance Levels and will prepare test result certificates in the form as set forth in Exhibits G-1 and G-2 for submittal to Seller’s Representative.  Purchaser shall submit the details of the test calculations for Seller’s review and verification.

Performance Tests should be conducted as soon as possible after commissioning of the Unit.

II.
Procedure

The gas turbine generator will be operated at Base Load as defined in the Agreement.  The Test Procedures will include a demonstration of power capability, heat rate, exhaust energy, and exhaust temperature.  The Unit’s auxiliary equipment power consumption data will be measured to enable determination of net Electrical Output of the Unit.

The Performance Test Procedures will establish the methodology, based on the Codes and Standards, for calculating the Unit performance and for correcting the Unit’s measured Electrical Output (net), Heat Rate (net), Exhaust Gas Energy and Exhaust Gas Temperature from existing Site conditions to Basis Conditions for the purpose of comparing the Adjusted Electrical Output, Adjusted Heat Rate, Adjusted Exhaust Gas Energy and Adjusted Exhaust Gas Temperature values against Guaranteed Levels and Specific Performance Levels as applicable.  Unit specific correction curves needed to correct from Site conditions to Basis Conditions will be developed and included in the Performance Test Procedures.

It is the Seller’s responsibility to ensure that the Unit is operating on its control curve that defines Base Load at the time of the test.  There shall be no correction of Unit performance for deviations from the control curve.

In addition to the correction curves required for calculating the Test results the following correction curves will be supplied by Seller along with the Test Procedure for information only; however, Purchaser shall rely on the final control curve listed in item 8 below for confirmation that the Unit is operating at Base Load during a Performance Test:

1.
Correction to ISO Conditions (590F, 60% RH and at 14.7 psia):

Compressor Inlet Temperature vs. Power;

Compressor Inlet Temperature vs. Heat Rate;

Compressor Inlet Temperature vs. Fuel Flow;

Compressor Inlet Temperature vs. Exhaust Flow; and

Compressor Inlet Temperature vs. Exhaust Temperature.

2.
Ambient Pressure vs. Power.

3.
Performance Correction for Excess Inlet Loss for:

Power vs. Excess Inlet Loss; and

Heat Rate vs. Excess Inlet Loss.

4.
Performance Correction for Excess Exhaust losses for:

Power vs. Excess Exhaust Loss; and

Heat Rate vs. Excess Exhaust Loss.

5.
Performance Correction for Exhaust Temperature at Part Load with IGVs consistent with dry low NOx operation at various inlet temperatures.

6.
Performance Correction for Fuel Flow at Part Load with IGVs consistent with dry low NOx operation at various inlet temperatures.

7.
Performance Correction for Fuel Analysis:

For gas fuel, fuel analysis corrections will be made to the corrected performance using the customer version of General Electric Cycle Deck. No correction curves will be provided.  The following correction factors will be calculated:

Exhaust Energy;

Electrical Output; and

Heat Rate.

8.
Gas Turbine Control Curve:

Exhaust Temperature vs. Compressor Pressure Ratio; and

Exhaust Temperature vs. Compressor Discharge Pressure.

9.
Performance Correction for Speed (Hz) for:

Power; and

Heat Rate.

10.
Generator Loss Curve.

11.
Generator Losses vs. MW or MVAR.

B.
STANDARD FIELD PERFORMANCE TESTING PROCEDURE
I.
Scope.

The Test Procedure may follow Seller’s standard guidelines, GEK-28106A, “Standard Field Performance Testing Procedure”, to the extent that it meets the requirements of this Exhibit F. 

II.
Machine Condition

In accordance with Section 12.4.1 of the Agreement, Seller’s representative shall certify that the Unit is ready to test.

The Unit shall be tested when in new and clean condition subject to Section 10.12.4 of the Agreement.  The Seller’s representative shall determine, in its sole and reasonable discretion, based on the terms of this Agreement and the Test Procedures, whether the subject Equipment is in new and clean condition and ready to be tested.  For testing conducted after new and clean period as defined in Section 10.12.4.2 of the Agreement, Seller’s degradation curves, as set forth in this Agreement, shall be utilized.  GE standard degradation curves for power, heat rate and exhaust energy will be shifted to cross the x axis at the number of operating hours specified in Section 10.12.4.2.

If the Seller’s representative, in its sole reasonable discretion, determines that the subject Equipment is not in new and clean condition prior to the conduct of the Performance Test, the Equipment shall be cleaned in accordance with Seller’s recommendations set forth in Exhibit A-2, Attachment 2 (Seller reference GEK-107122A).

III.
PTC-22 Modifications and Clarifications

1.
A valid Test Run will consist of thirteen (13) sets of instrument readings taken at five (5) minute intervals over a sixty (60) minute time span after steady state conditions have been established as listed in PTC-22.

2.
Speed measurements are required and must be measured by an electronic tachometer or equal at the SPEEDTRONIC panel, and averaged for the Test Run.  Any corrections for frequency variation shall be applied to the calculation.

3.
Unit Electrical Output is to be measured by polyphase watthour meters (of revenue meter quality) at the generator terminals.  Revenue quality metering shall be provided by Purchaser.

4.
Gas Turbine exhaust temperature will be measured by control thermocouples mounted in the exhaust plenum with a maximum uncertainty of 5 _F.

5.
It is essential that the temperature indicating system be adjusted and calibrated in place with a known millivolt source prior to the test so that it reports reliable data

6.
Barometric Pressure at the test site shall be measured with a mercury or aneroid barometer with an accuracy in accordance with PTC-22.  A minimum reading accuracy of 0.01 inches of Hg is required. 

7.
Fuel Consumption:  Gas fuel is to be measured with a flat plate orifice or venturi installed in accordance with ASME MFC-3M or a turbine meter installed according to ASME MFC-4M standards.  Calculation of gas flow will be done in accordance with either ASME MFC-3M or MFC-4M as appropriate.  The upstream pressure will be measured with a precision test gage, the pressure drop with a gauge or transmitter, the gas temperature with a thermometer or thermocouple.

8.
Four (4) gas samples shall be taken from the fuel system during the test for laboratory analysis of composition according to ASTM D1945.

9.
The higher and lower heating values will be determined according to ASTM D 3588.  

10.
Inlet air condition will be measured with at least four (4) RTD’s with an uncertainty meeting PTC 22.

11.
Turbine exhaust static pressure at or near the turbine exhaust flange or other convenient location must be measured using at least two (2) disc type static pressure probes.

12.
All instruments to be used in the performance test shall be calibrated immediately prior to the performance test and checked immediately after the performance test.  The Parties to the Test will witness the calibrations and inspections.

IV.
Evaluation

The Performance Test Procedure will include the tolerance due to measurement uncertainties associated with each particular test result in accordance with Section 10.12.10 (iii) of the Agreement.

The Parties will agree on a method of determining the sufficiency of the inlet chiller coils to provide the desired inlet air cooling if applicable.  The results of this determination will be included in the calculation of the Test results and in the Performance Test report.

EXHIBIT F-1  SOUND LEVEL TEST GUIDELINEStc \l1 "EXHIBIT F-1  SOUND LEVEL TEST GUIDELINES
PERFORMANCE TEST GUIDELINES FOR NEAR SOURCE SOUND LEVELS

· Testing methodology shall be based on the latest version of ANSI/ASME PTC 36.  The final result shall be the arithmetic average of the SPL’s measured around the equipment after background and other corrections have been applied.  The equipment shall be in compliance if the final result does not exceed the noise limit(s) specified above.

· Equipment shall be operated in a new and clean condition as intended by the designers when measurements are taken.  All access compartments, doors, panels and other temporary openings shall be fully closed; all silencing hardware shall be fully installed; all systems designed to be airtight shall be sealed.

· If the above guaranteed SPC exceeds the measured background noise by 10dB(a), no correction shall be necessary.  Otherwise, corrections to the measured SPL shall be made per ANSI/ASME PTC 36 procedures.  Background noise is defined as the noise measured with all Seller supplied equipment off and all other plant equipment on.

· Intermittent noises such as steam safety blow off valves and filter pulse noise are not included in the above guarantee.

· Measurements shall be taken 3 feet (1 meter) away from the outermost surfaces of equipment, including piping, conduit, framework, barriers, Equipment enclosures and personnel protection devices if provided.

· Measurements shall not be taken in any location where there is an airflow velocity greater than 5 feet per second (1.5 meters per second), including nearby air intakes or exhausts.

· Free field conditions must be prevalent at measurement locations.  Testing and corrections to a free field shall be per ANSI/ASME PTC 36.

· Testing shall be done according to a test plan agreed to by both the Purchaser and Seller.  Such a plan shall be submitted to both the Purchaser and Seller at least 30 days prior to noise compliance testing.  The test results shall be submitted in the form of a test report that shall be made available to both the Purchaser and Seller.

Measurement responsibility shall be stated in the Contract.  Seller reserves the right to audit or parallel these measurements.

PERFORMANCE TEST GUIDELINES FOR FAR FIELD SOUND LEVELS (If Required)

· Testing methodology shall be based on the latest version of ANSI B133.8.  The final result shall be the arithmetic average of the SPL’s at the 8 measurement locations after background and other corrections have been applied.  The equipment shall be in compliance if the final result does not exceed the noise limit(s) specified above.

· Equipment shall be operated in a new and clean condition as intended by the designers when measurements are taken.  All access compartments, doors, panels and other temporary openings shall be fully closed; all silencing hardware shall be fully installed; all systems designed to be airtight shall be sealed.

· If the above guaranteed SPL exceeds the measured background noise by 10dB(A), no correction shall be necessary.  Otherwise, corrections to the measured SPL shall be made per ANSI B133.8 procedures.  Background noise is defined as the noise measured with all Seller supplied equipment off and all other plant equipment on.

· Intermittent noises such as steam safety blow of valves and filter pulse noised are not included in the above guarantee.

· Measurements shall be taken 5 feet +/- 2.5 feet (1.5  meters +/- .75 meters) above the ground.  Such measurement locations shall be on a flat elevation no more than 16 feet (5 meters) above or below the plant base elevation.

· Measurements shall not be taken in any location where there is an airflow velocity greater than 5 feet per second (1.5 meters per second), including nearby air intakes or exhausts.

· Measurement locations shall be chosen such that free field conditions exist at those locations.  Measurement locations shall not be closer than 12 feet (3.5 meters) to any nearby reflecting surfaces.

· Testing shall be done according to a test plan agreed to by bother the Purchaser and Seller.  Such a plan shall be submitted to both the Purchaser and Seller at least 30 days prior to noise compliance testing.  The test results shall be submitted in the form of a test report that shall be made available to both the Purchaser and Seller.

Measurement responsibility shall be Purchaser’s.  Seller reserves the right to audit or parallel these measurements.

EXHIBIT F-2 EMISSIONS TEST GUIDELINEStc \l1 "EXHIBIT F-2 EMISSIONS TEST GUIDELINES
GE POWER SYSTEMS

U.S. Standard Field Testing Procedure for Emission Compliance (Reference GEK-28172E)

Test Philosophy

Testing to demonstrate emission guarantees and for adjustment of the NOx reduction system (if required) will be performed using procedures which are mutually agreed between GE and the Purchaser.  Ge engineers and/or technical advisors may be present at the tests for procedural direction.  Test methods chosen are EPA methods which yield data on site immediately, wherever possible.

Emission Testing

A.
General

Emission testing identified herein shall be within Customer’s scope of supply using procedures which are mutually agreed.  Sampling for inlet pollutant concentrations may be required, at the sole discretion of GE, in order to demonstrate compliance with emission guarantees.  GE’s guarantees apply to the net increase of these pollutant emissions.
B.
Nitrogen Oxides Emissions
Before the official compliance testing is begun, the NOx reduction system will be adjusted to verify compliance with  NOx emission limits.  The gas turbine control system contains a pre-programmed schedule for either water or steam injection, this schedule may be adjusted to achieve an appropriate emission level approximately 5% to 10% below emission limits, and minimize the supply requirements.  Once the proper injection schedule has been established, this schedule is maintained throughout the testing, and it is programmed into the control system.

The NOx emission testing and related oxygen testing will be in accordance with U.S. EPA Method 20 presented in the Code of Federal Regulations.  Title 40, Part 60 (40CFR60 Appendix A and 40CFR60 Subpart GG -- Standards of Performance for Stationary Gas Turbines), with the following modifications, limitations and additions:

a.
The NOx instrument will be limited to a chemiluminescent type which meets 40CFR60 Appendix A, Method 7E.

b.
The span of the NOx analyzer will be set for appropriate spread of the expected  NOx readings, rather than the specified 300 ppm.

c.
Oxygen will be sampled simultaneously with all NOx readings since Subpart GG of 40CFR60 requires correction to 15% O2.  Method 3A from 40CFR60 Appendix A is used for the oxygen analysis.

d.
Section 60.33(c)  (i)of Subpart GG has been replaced by U.S. EPA Memorandum dated June 2, 1997 for GE gas turbines using either water or steam for NOx reduction.  The EPA memorandum approves the GE injection control algorithm in lieu of the Subpart GG ISO correction equation.

e.
Section 60.335(c) (i) is not applicable to gas turbines with dry low NOx combustors.

C.
Carbon Monoxide Emissions (If Required)
Sampling is the same as for NOx normally with the same line feeding the different instruments.  Method 10 per 40CFR60 appendix A is used, but only the continuous sample method per Section 5.1 is acceptable to GE.  A recorder is mandatory, not optional as per 5.3.9, with a span which gives an appropriate spread of the expected readings.

D.
Unburned Hydrocarbon Emissions (If Required)
Sampling and analysis must be on a wet basis to avoid condensing out the higher hydrocarbons.  Moisture determination by Method 4 (or Method 5) is necessary to convert results to dry basis.  Method 25A per 40CFR60 Appendix A is used for unburned hydrocarbons.  Results are presented as methane (CH4).  This method uses a flame ionization detector or analyzer.

E.
Particulate Matter Emissions (If Required)
Particulate matter emissions are determined by sampling, analysis and calculation in accordance with U.S. EPA Methods 5 and 5B with traversing per Methods 1 and 2 all from 40CFR60 Appendix A.  The following modifications and limitations on choices within the methods apply:

5. Sampling probe internal surfaces must be made of chemically inert and non-catalytic material such as quartz.

6. The filter material shall be quartz.

7. Nozzle, probe and filter must be heated to 248 to 273 0F per Method 5, or at least 10 0F higher than the dew point of sulfuric acid in the exhaust duct.  Use of Method 5B requires nozzle, probe and filter to be heated to 320 to 345 0F.

8. Probe wash shall be acetone per Method 5.

9. Sampling technique shall provide a fairly large exhaust gas sample, with an objective of 100 SC.

F.
Volatile Organic Emissions
When volatile organic emissions (non-methane, non-ethane hydrocarbons) are required, Method 18 per Section 7.2 is used.  This requires a gas chromatograph at the Site.  Seller requires calibration of the measurement train at the sampling probe.

G.
PM10 Emissions (If Required)
PM10 emissions are determined by sampling, analysis and calculation in accordance with U.S. EPA methods 5 for front half filterable particulate matter and Method 202 for back half condensible particulate mater with traversing per methods 1 and 2, all from 40CFR60, Appendix A except for Method 202.  Method 202 is from 40CFR51, Appendix M.  The following modifications and limitations within the methods apply:

1.
Sampling probe internal surfaces must be made of chemically inert and non-catalytic material such as quartz;

2.
The filter material shall be quartz;

3.
Nozzle, probe and filter must be heated to 248 0F to  273 0F per Method 5, or at least 10  0F higher than the dew point of sulfuric acid in the exhaust duct;

4.
Probe wash shall be acetone per Method 5;

5.
Sampling technique shall provide a fairly large exhaust gas sample, with an objective of 100 SCF;

6.
Impinger solution shall be extracted with ACS grade methylene chloride per method 202.

H.
Not Used
I.
Not Used
J.
Not Used
K.
Certification of Calibration Gases
All gases used in certification of instruments or performance of emissions guarantee demonstrations shall be analyzed and certified in a manner and by a laboratory mutually agreeable to GE and Purchaser.  Examples of acceptable certification are:

1.
U.S. EPA Standard Methods


2.
U.S. EPA Protocols


3.
U.S. National Bureau of Standards Certification Procedures

L.
Exhaust Gas Flow Determination
GE has established preferences for the determination of exhaust flow based on accuracy of the determination.  GE prefers the following:

The primary exhaust flow determination shall be by the F - factor method per 40CFR60, appendix A, Method 19 (as specified in Method 20 for gas turbine emissions).  The F - factor constants from Table 19-1 shall be applied in all cases where possible per Paragraph 3.1.

Where available, the compressor inlet air flow signal shall also be used to compute exhaust flow.  Exhaust flow on a dry basis is the turbine inlet air flow minus the water vapor plus the fuel flow minus the water formed from the combustion of hydrogen in the fuel.  Gas turbine inlet air is measured using the compressor inlet air scroll as a flow element.  The inlet scroll is calibrated during the factory tests of the gas turbine.

Flow measurements by Velocity Traverse, per 40CFR60, Appendix A, Methods 1 and 2, can result in errors of 25% or more in this application, and is not acceptable.

M.
Not Used

EXHIBIT G-1  PERFORMANCE TEST CERTIFICATEtc \l1 "EXHIBIT G-1  PERFORMANCE TEST CERTIFICATE
PERFORMANCE TEST CERTIFICATE
The undersigned duly authorized representative of (Name of Purchaser’s Company), under the provisions of the Purchase Contract between Enron North America Corp. and [--------------], dated (_______) the “Agreement” hereby certifies that:

1.
Performance Tests have been conducted pertaining to Electrical Output, Heat Rate, Sound Levels and Emissions of the gas turbine generator unit referred to in the Agreement (the “Unit”).  

2.  As set forth in the Agreement, Seller guaranteed that the Adjusted Electrical Output of the [turbine SNs] Unit will be at least [-----] kW when consuming natural gas for fuel, and that in any event Seller guaranteed that the Unit shall produce no less than [------] kW Adjusted Electrical Output when the Electrical Output is measured and adjusted in accordance with the Test Procedures and the Agreement.

The results of the Performance Tests show that the [turbine SNs] Unit produced an Adjusted Electrical Output of        .

[USE EITHER A OR B BELOW AS APPROPRIATE]
A.  The Adjusted Electrical Output above is greater than or equal to the Electrical Output Guarantee and therefore, Seller is not liable for Performance Liquidated Damages associated with Electrical Output.

B.  The Adjusted Electrical Output above is less than the Electrical Output Guarantee [               ], but greater than the aggregate Specific Performance Electrical Output Guarantee of [            ]; therefore, the undersigned has determined that the amount of Electrical Output Liquidated Damages to be assessed against the Seller for failure to meet Electrical Output Guarantee is U.S. $                         .

3.  As set forth in the Agreement, Seller guaranteed that the Adjusted Heat Rate of the [turbine SNs] Unit will be at least [-----] BTU/kWh(LHV) when consuming natural gas for fuel, and that in any event Seller guaranteed that the Unit shall demonstrate no less than [------] BTU/kWh(LHV) Adjusted Heat Rate when the Heat Rate is calculated and adjusted in accordance with the Test Procedures and the Agreement.  The results of the Performance Tests show that the [turbine SNs] Unit produced an Adjusted Heat Rate of        .

[USE EITHER A OR B BELOW AS APPROPRIATE]
A.  The Adjusted Heat Rate above is less than or equal to the Heat Rate Guarantee and therefore, Seller is not liable for Performance Liquidated Damages associated with Heat Rate.

B.  The Adjusted Heat Rate above is greater than the Heat Rate Guarantee [               ], but less than the Specific Performance Heat Rate Guarantee of [            ]; therefore, the undersigned has determined that the amount of Heat Rate Liquidated Damages to be assessed against the Seller for failure to meet the Heat Rate Guarantee is U.S. $                         .

EXHIBIT H-1  TECHNICAL DIRECTION OF INSTALLATIONtc \l1 "EXHIBIT H-1  TECHNICAL DIRECTION OF INSTALLATION
1.0
General.  The parties agree that as part of this Scope of Work Seller shall provide the requisite TDI support at the Site required for installation, start‑up and correction of problems related to waived shop testing and commissioning of the Equipment. 

2.0
Schedule.  Seller and Purchaser’s Representative shall coordinate the start and finish schedules of each of the TDI personnel.  Seller shall provide a maximum of 162 manweeks (straight time 40 hrs/week TDI advisors as required to support Purchaser’s receipt of Equipment, installation, startup, commissioning and correction of problems related to waived shop testing until certified ready for testing in accordance with the Agreement. Seller shall provide a bar chart for its manpower staffing in support of the construction schedule, which shall be adjusted from time to time by Seller and Purchaser as the work progresses.  Hours worked by Seller’s TDI personnel in excess of 40 hours straight time hours each week shall be deducted from the 162 manweek count, at the equivalent rate of one and one half straight time hours pursuant to Section 8 below.  Seller’s 40 hour work week is 8 hours per day, Monday through Friday

3.0
Cost.  Seller shall bear each and every expense for services provided by its TDI personnel including, but not limited to, international and local transportation, salary, lodging, per diem, taxes, work permits and expenses which costs are included within the Purchase Amount.  Any TDI activities associated with field testing and correction of the Unit which would normally be performed in the factory is included in Seller’s Scope of Work and is not counted against the 162 manweek count.

4.0
Supervision of Craft Labor.  Seller’s TDI personnel shall not be responsible for the productivity or quality of work performed by Purchaser’s contractors and shall not have direct supervision responsibility over craft labor.

5.0
Seller Technical Direction Office Facilities.  Purchaser shall provide:

(a)
A secure, furnished private jobsite office facility of sufficient size (near the Equipment) that can accommodate 3 to 4 field engineers per unit, where drawings, special tools, and other Seller proprietary materials and equipment can be kept and referred to or worked upon.

 (b)
Purchaser shall coordinate installation of four (4) direct phone lines to Seller’s jobsite office facility and Seller shall be responsible for payment of the monthly local and long distance service and usage charges to the telephone company.

(c)
Seller’s jobsite office facility shall have HVAC and contain furnishing equivalent to that in use by Purchaser and its other subcontractor’s suitable for supporting Seller’s work.  The facility shall have adequate lighting, electrically outlets and sanitary facilities shall be accessible.  Seller shall be required to comply with the Site security and safety requirements at all times including control, use and parking restrictions relevant to Seller’s personnel’s privately owned vehicles.     

6.0
Staffing Levels.

Seller shall provide Biographical data and other qualifications as requested by Purchaser’s project manager for review and approval of Seller’s lead advisor (such approval not to be unreasonably withheld).

Staffing shall include:

(a)
A lead technical advisor commencing no later than delivery of the Unit to the Delivery Point, and such person shall be an experienced GE turbine generator installation engineer who shall be capable of providing guidance and counsel for the following:

-
The effective guidance and counseling of the other Seller technical advisors to provide for broader utilization of their skills.

-
The integration of the assigned service work with the Purchaser representatives to assist in meeting scheduled startup, completion and operation dates.

-
The reporting of pertinent facts on failure of equipment warranted by Seller and its Vendors to the proper personnel to permit prompt and equitable settlement of warranty claims.

-
The submittal of timely reports on job progress and resolution of problems.

-
The planning, organization and direction of the other Seller personnel for the installation, startup, testing and warranty implementation of the supplied equipment.

-
The maintenance of installation records and job log book.

 (b)
Turbine Generator Installation team comprised of technical advisors skilled in mechanical erection of gas turbines and related equipment, electrical equipment installation and testing, SPEEDTRONIC Control System checkout, calibration and unit startup, and shall be capable of providing guidance and counsel for the following:

-
The inspection and unloading of the major components at the installation site and their placement on the foundations.

-
The setting of necessary shims between sole plates and the turbines.

-
The removal of shipping supports on the turbine and generator packages.

-
The installation of the turbine unit to the proper center line and elevation.

-
The alignment of the accessory equipment and generators to the turbines.

-
The installation and checkout of conduit, piping, control wiring and instrumentation between the turbines and Seller supplied auxiliary equipment and generators.

-
Checkout and initial operation of the turbine starting equipment.

-
The sequencing and checkout of the turbine SPEEDTRONIC Control Panels.

-
The installation and checkout of the generator excitation/electric systems.

-
The startup of the turbine unit with the Purchaser’s operating personnel.

-
Mark up two (2) sets of drawings to reflect the “as-built” condition of the equipment.  One (1) set for site records and one (1) set to be returned to GE Customer Service.

-
Installation and check out of all auxiliary and ancillary equipment provided under this Agreement.

-
Electrical checkout and powering of the control consoles and process unit.

-
Review main communication links between all control systems to assure proper system integrity.  Insure data highway links to all systems are operating properly.

-
Review of control system logic and main central control system graphics to assure proper integrity between all systems.  Make any modifications needed for proper plant control.

7.0
Additional Services

In addition to providing the expertise outlined above, Seller’s personnel shall be relied upon to answer questions and provide or obtain interpretation of manufacturer supplied instructions and drawings during the execution of work (construction, erection, commissioning, etc.).  Included in this category of support are:

(a)
Confirmation that specifications and instructions to be applied during construction, erection and commissioning by the different Vendors are met and that the specified results of tests and examinations are obtained;

 (b)
Corrections of construction/erection/commissioning software, if necessary, as far as design and engineering tasks are not concerned;

(c)
Confirmation that the necessary standard of quality has been sustained in all areas which could affect facts and information provided by Seller to Purchaser;

(d)
Immediate written objections to Purchaser’s representative if the standard of quality is jeopardized, and advise Purchaser’s representative in a timely manner on the implications where any work procedure may impair the Equipment warranty;

(e)
Troubleshooting, technical guidance and expertise during instrumentation and control systems loop and function checks;

(f)
Technical expertise for energization and synchronization activities performed during commissioning; and

(g)
Provide impromptu training to Facility operators during start up and commissioning.

8.0
Expected Work Week.  Purchaser anticipates that the normal work week on Site will consist of working six (6) days per week (Monday through Saturday) for ten (10) hours per shift each work day;  however, such work hours and days shall be adjusted to accommodate Purchaser’s general Site Seller’s work schedule.  It is the intent of the parties that Purchaser shall have the flexibility to require Seller’s personnel to work more or less hours per day than the standard work day in support of certain construction activities.  All time worked, except for those hours worked in support of the waived shop tests, shall be subtracted from the total of Seller’s obligation set forth in Section 1.0 above.  Total TDI hours worked in excess of the 162 manweeks, subject to Sections 2 and 3 above, shall be reimbursed to Seller pursuant to a Change Order, at the following rates:

Straight time (8hrs/day) = $230.00/hour

Overtime (excess of 8 hrs/day Sundays and Holidays) = $345.00/hour

Additional mandays purchased will be subject to:

- Required travel will be reimbursed at cost or in accordance with IRS mileage rates;

- Travel time will be invoiced at the applicable straight time or overtime rate; and

- Per diem will be applicable at the rate of $196.00 during all days commencing on departure from point of origin through return or its equivalent.

9.0
Replacement of Unsatisfactory Personnel.  If any of Seller’s personnel provided under this Agreement fail, in Purchaser’s reasonable judgement, to fulfill his duties as assigned by Seller, Seller shall cause such personnel to properly perform such duties, or at the request of Purchaser replace the personnel. In the event of a replacement:

-The replacement must be of equivalent qualifications to the person being replaced;

-Seller shall provide Purchaser a resume of the recommended replacement; 

-The replacement must be approved by Purchaser, prior to the replacement’s commencement of work, such approval, not to be unreasonably withheld; and 

-Seller shall bear all additional travel, living or other costs associated with removing the unsatisfactory individual and furnishing the replacement.

10.0
Supplemental Seller Personnel.  Seller’s personnel shall be direct employees of Seller, or Seller may elect to hire supplemental third party Sellers screened and trained by Seller.  In addition to any such screening and training, such personnel must have verifiable and demonstrable prior hands-on experience in installation or training as applicable to the work to be performed by such person. Seller shall provide Purchaser’s Representative resumes of all individuals selected by Seller as supplemental personnel pursuant to this Paragraph 9, and obtain Purchaser’s Representative’s prior approval of each individual’s assignment, such approval not to be unreasonably withheld.  

11.0
Change of Seller’s Personnel.  Seller and Purchaser recognize that changing of personnel during the performance of the Scope of Work can be disruptive and adversely affect the timely and proper performance of the Scope of Work; however, both Seller and Purchaser realize that under certain circumstances, Seller may, on an exception basis, need to substitute personnel in the course of performance of the Scope of Work.  Seller may, on an exception basis, substitute personnel; provided that the following shall apply:

-The replacement must be of equivalent capabilities to the person being replaced; 

-Seller shall provide Purchaser a resume of the recommended replacement; 

-Such change is for a compelling personal reason, or by mutual agreement the existing individual does not have the required skill;

-The replacement must be approved by Purchaser prior to the replacement’s commencement of work, such approval not to be unreasonably withheld, and, 

-Seller shall bear all additional travel, living or other costs associated with such change.

12.0
Debugging.  Seller shall provide with respect to TDI, normal debugging of problems encountered during installation, start-up and commissioning of the equipment.  In the event debugging reveals a factory defect, Seller shall provide Purchaser written observations regarding such defect.

13.0
Release of Seller’s Personnel.  If Technical Direction of Installation Representative is/are released from site by Purchaser while the installation is in progress, the same Technical Direction of Installation Representative may not be available to return but will be replaced with a qualified Technical Direction of Installation Representative within two weeks after Company’s receipt of written request from the Purchaser for Technical Direction of Installation Representative.

14.0
Purchaser’s Responsibilities.  Purchaser will take all necessary precautions, at all times, for the safety of Company personnel at site.  This includes, but is not limited to, indoctrination of Purchaser’s safety practices, energization/de-energization of all power systems (electrical, mechanical and hydraulic) using a lock-out tag procedure, and conducting periodic safety meetings during construction and start-up.

EXHIBIT H-2  TRAININGtc \l1 "EXHIBIT H-2  TRAINING
1.  Basic Familiarization Training.  Included in the Scope of Work, Seller will perform on the job training of Purchaser’s operator personnel utilizing its technical advisor staff throughout the performance of TD of I and separate from TD of I, Seller shall provide formal classroom familiarization training (5 days)  “Gas Turbine Familiarization Course”with a course content is as follows:

Objective
To familiarize operators and supervisory personnel to safely and properly operate a gas turbine-generator unit.

Emphasis is placed on the operator’s responsibilities with regard to the auxiliary systems, operational data taking, and data evaluation.  Operators are also instructed in how to interpret fault annunciation and how to determine if the annunciated fault can be remedied by operator action or by the assistance of instrumentation and/or maintenance personnel.

The course focuses on starting, loading, and specific operator checks of the various turbine support and auxiliary systems to ensure safe and reliable operation of the turbine unit, including the operation of the Gas Turbine SPEEDTRONIC TM Mark V Controls and the EX2000 Excitation.  In that Owner’s staff is familiar with the operating of comparable turbines but not with the Gas Turbine SPEEDTRONIC TM Mark V Controls and the EX2000 Excitation system, the familiarization course will provide greater focus on such systems and less on the basic operating procedures.

Content
The typical Gas Turbine Familiarization course covers the following areas:

· Unit Arrangement

--
Gas Turbine, Generator

· General Description

--
Gas Turbine and Generator Major Components

· Support Systems

--
Lube Oil

--
Hydraulic and Control

--
Cooling Water

--
Cooling and Sealing Air

--
Fuel(s)

--
Starting

--
Heating and Ventilation

--
Fire Protection

--
Generator Systems

· Control System

--
Control Panel Arrangement

--
Basic Control Functions and Operating Sequences

Students will be provided limited handout material extracted from Seller’s Instruction Manual.

2  Additional Optional Training Courses.  The optional training listed in Exhibit N-2, which is designed to be performed by Seller at the Site consists of the following:

a. GTG operation (2 weeks duration)

b. GTG maintenance (1 week duration)

c. GTG Mark V (2 weeks duration)

d.  EX2000 Excitation (1 week duration)

3  Lesson Outlines of Optional Training.  The lesson outlines of the above listed training are as follows:

Summary
A comprehensive training program is conducted for a selected number of Purchaser’s engineers, operations and maintenance personnel.  The training will be conducted at Purchaser’s job site.

The Purchaser’s personnel assigned for training must have prior general knowledge of power plant systems operation.

A Seller training coordinator is designated for the project who is familiar with overall plant design and system operations.  This person schedules and coordinates job site training, as well as integrates individual systems training into the overall plant operation.

The training programs will cover the areas specified below and detailed in this Exhibit H-2:

Training Material and Related Conditions (On-Site Training)
· Classes run daily (five days/week) and are limited to six (6) hours.  The actual class time, a.m. and p.m. hours, is dictated by the availability of the equipment and the students per the normal work schedule.  Each class time period should be agreed to by Purchaser’s management and Seller’s instructor(s) at the beginning of the program.  The six (6) hour class limitation will allow ample time for the instructor(s) to prepare the next session’s work plan.

· A maximum of twelve (12) students per class can be accommodated.

· English-speaking instructor(s) will be furnished for the course duration.

· Each student will be furnished a suitable bound course instruction and reference handbook in English; shipment costs have been included in the firm price quotes herein.  Any materials furnished are exclusively for the use of the Purchaser’s personnel.  This material is not for resale or to be distributed to third parties, nor is it to be copied or reproduced without Seller’s prior written permission.

· Any audio or video recording of Seller’s lecture material is prohibited unless Seller grants permission in writing in advance of the training program.

· The instructor(s) will retain all visual aids such as 35mm slides and transparencies used to conduct the course.

· The power plant equipment should preferably be operable and available to support this course of study.

· Seller shall be responsible for the instructors’ travel and living expenses.

· Purchaser will provide class room, audio visual equipment and computers as requested in advance.

Training Schedule
After engineering design has been finalized, training is conducted during a mutually-agreeable time.

Typical Course contents for the Major Plant Components
a.  Gas Turbine-Generator Operations
The objective of this course is to train operators and supervisory personnel to safely and properly operate gas turbine-generator unit.  This course develops a background in gas turbine-generator operation which enables participants to properly analyze operating problems and take the necessary corrective action.

Emphasis is placed on the operator’s responsibilities with regard to auxiliary systems, operations data acquisition and data evaluation.  Operators are also instructed to interpret fault annunciation and determine if the annunciated fault can be remedied by operator action or by the assistance of instrumentation and/or maintenance personnel.  

The course focuses on starting, loading and specific operator checks of the various turbine-generator support and auxiliary systems to ensure safe and reliable operation of the turbine-generator unit.

The typical Gas Turbine-Generator operations course covers the following areas:

· Gas Turbine-Generator Fundamentals

--
Basic theory of operation

--
Base and machine arrangement

· Support Systems Operation

--
Lube oil

--
Hydraulic and control oil

--
Cooling water

--
Fuel system(s)

--
Starting means

--
Heating and ventilation

--
Fire protection

--
Generator systems

· Control System

--
Arrangements

--
Control functions and operating sequences

--
Protection functions

· Operator Responsibilities

--
Data acquisition and evaluation

--
Operating limits

--
Required operator action on various annunciator indications

· Unit Operation

-- 
Startup

--
Normal operation

--
Shutdown

--
Emergency procedures

b.  Gas Turbine-Generator Systems Maintenance
This site specific course is designed to introduce operations and maintenance personnel to the routine preventative maintenance procedure of the turbine-generator support systems required to attain high levels of availability and reliability from the gas turbine-generator.  This course does not cover the turbine-generator disassembly inspections required for major mechanical maintenance.  Operating and maintenance personnel should attend this course together to develop a working relationship regarding the routine maintenance requirements of the unit.

The training will include detailed descriptions of the turbine-generator support systems.  This will include a functional description of the system as well as the routine maintenance requirements of the system.  If the course is held at the customer’s location it will include site visits to familiarize personnel with the location of the various system components and to allow personnel to correlate the system piping schematics to the system hardware.  The training will not incorporate any “hands-on” training or component disassembly.

The typical Gas Turbine-Generator Systems Maintenance course covers the following topics:

· Gas Turbine Introduction

--
Explanation of how a gas turbine works

--
Introduction to the customer-specific unit

· Gas Turbine-Generator Arrangements

--
Site turbine and accessory base arrangements and enclosures

--
Site generator arrangements and enclosures

· Support Systems Operator and Routine Maintenance

--
Inlet and Exhaust Systems including Generator Cooling Air and Inlet Bleed Heat

--
Lube Oil System

--
Hydraulic Oil System

--
Trip Oil System

--
Inlet Guide Vanes

--
Cooling Water System

--
Cooling and Sealing Air System

--
Fuel System

--
Starting System, including slow-roll/cooldown function

--
Heating and Ventilation Systems

--
Fire Protection System

--
Generator Auxiliary Systems (Brush Rigging, Coolers, High Voltage Bushings)

--
Water Wash System as a maintenance tool

c.  Gas Turbine SPEEDTRONIC Mark V Technicians Training
This site specific course is designed to enable engineers and competent instruments and control technicians to confidently calibrate the controls and diagnose problems in General Electric Gas Turbine SPEEDTRONIC control.

The typical Gas Turbine SPEEDTRONIC Mark V Controls course covers the following areas:

· Gas Turbine Control Fundamentals

--
Gas turbine principles of operation

--
Governing system requirements

· Gas Turbine Systems

--
Piping schematics

--
Electrical wiring diagrams

· Gas Turbine Control

--
Startup/speed/temperature/other controls

--
Protection

· Control Displays

--
User’s manual

· Control System Software

--
IDOS

--
File descriptions

· Micro Processor Initialization

--
Troubleshooting

· Valve Calibration (LVDT)

--
Input/output configuration screens

· Software Tools

--
Modifying and downloading control configuration

--
Data acquisition on Mark V interface

--
Software backup

· Troubleshooting

--
Gas turbine process alarms

--
Mark V panel diagnostic alarms

Course Duration : 2 weeks

The course duration will vary depending upon the student’s background and their familiarity with gas turbine controls and computer based control systems.

d.  Excitation for AC Generators
The objective of this course is to improve the ability of personnel to operate, maintain and test rotating and/or static excitation systems for medium and large AC generators.

The course focuses on the testing, maintenance, adjustment and operation of the excitation system in use.  Operational safety precautions are details for both personnel and equipment during troubleshooting and maintenance activities.

The typical Excitation for AC Generators course covers the following areas:

· Generator Fundamentals

--
AC generator theory

--
Exciter theory

--
AC generator operation curves

· System Components

--
Exciters

--
Regulators

· System Operation

--
Regulator

--
Off-line

--
On-lin

--
Parallel

--
Protection systems

· Maintenance and Troubleshooting

--
Test instruments

--
Print reading

EXHIBIT I  CANCELLATION CHARGEtc \l1 "EXHIBIT I  CANCELLATION CHARGE
In the event Purchaser cancels this Agreement, Purchaser’s liability for cancellation charges shall not exceed the values set forth below for cancellation of the Unit:

Cancellation Month
% of Purchase Amount

May 2000
14%

June 2000
15%

July 2000
20%

August 2000
25%

September 2000
30%

October 2000
34%

November 2000
34%

December 2000
34%

January 2001
34%

February 2001
34%

March 2001
34%

April 2001
98.5%

May 2001
100%

Notes:

1.
Seller shall maintain title to the Unit when cancellation occurs prior to shipment.

2.
Cancellation exposure is 100% of the value of the Unit after title has transferred.

3.
The value of the Unit shall increase or decrease as applicable as a result of increases or decreases to the Purchase Amount due to executed Change Orders.

EXHIBIT I-1 MILESTONE PAYMENT SCHEDULEtc \l1 "EXHIBIT I-1 MILESTONE PAYMENT SCHEDULE
Milestone Month (Not earlier than)
Milestone Event (Not earlier than)
Monthly % of Purchase Amount
Cumulative % of Purchase Amount


Payments to Date
10.17%
10.17%

Feb 25-00
Progress Payment
1.21%
11.38%

Mar 25-00
Progress Payment
5.72%
17.10%

Apr 25-00
Progress Payment
5.72%
22.82%

May 25-00
Progress Payment
5.72%
28.54%

Jun 25-00
Progress Payment
5.72%
34.26%

Jul 25-00
Progress Payment
5.72%
39.97%

Aug 25-00
Progress Payment
5.72%
45.69%

Sep 25-00
Progress Payment
5.72%
51.41%

Oct 25-00
Progress Payment
5.72%
57.13%

Nov 25-00
Progress Payment
5.72%
62.85%

Dec 25-00
Progress Payment
5.72%
68.57%

Jan 25-01
Progress Payment
5.72%
74.28%

Feb 25-01
Progress Payment
5.72%
80.00%

Mar 25-01
Ship CT
18.50%
98.50%

Apr 25-01
Ship Generator
1.5%
100.00%

IPS 90782

4/26/00

100%







EXHIBIT J  QUALITYtc \l1 "EXHIBIT J  QUALITY
1.0   QUALITY ASSURANCE AND CONTROL

1.1
Quality Assurance Arrangements
Seller, and its nominated Vendors shall work to defined quality assurance arrangements compliant with ISO 9001.  Seller shall indicate the results of any recent audits.

In addition to requirements detailed in ISO 9001, Seller shall:


Ensure that all quality related activities are planned and that adequate resources are made available for these activities.


Establish means by which all materials and components are identified through each stage of performance of the Scope of Work.  These measures will facilitate the traceability of materials as identified in the agreed Quality plans.


Arrange for the protection of the quality of the product to include delivery to the specified destination.

1.2
Vendors
Seller shall specify all Quality Assurance requirements to its Vendor and shall ensure that all Vendors comply with these requirements.

Seller shall undertake in respect of its nominated Vendors, where no such acceptable information is available or where the Vendor has not been subject to a quality audit within the previous 12 months, to carry out an audit of that Vendor in order to ensure that completion of works will be compliant with contract requirements.

Seller and its nominated Vendors maybe subject to a quality audit by Purchaser.

1.3
Quality Plans
Quality Plans shall be prepared by Seller for all areas of activity.  These quality plans shall be submitted to Purchaser for review.

The format of the Quality Plans shall be agreed with Purchaser.  Seller shall ensure that all activity is carried out in accordance with the Quality Plans and will notify Purchaser of any deviations as they occur. 

1.4
Review of Documents
Seller shall submit for review all Quality Plans and Design Documentation as may reasonably be required by Purchaser.  A schedule of drawings and documentation shall be maintained by Seller to show the current status and revision of each document.

1.5
Records
Seller shall maintain records as required by the quality plans.  All records including audit reports shall be made available for inspection by Purchaser, as required.

Seller shall generate records in a manner coincidental with the activities to which they refer, such that the quality status of each item can be readily verified.

All records shall be concisely compiled and coded.  They shall, in addition be clearly cross referenced to the parts or assemblies to which they refer.

Records shall in general, be available at the time of equipment delivery.  Such records shall include relevant certifications and build documentation together with any information which would facilitate the general traceability of component items or materials.

All records generated during the course of performance of the Scope of Work shall be retained by Seller for a minimum period of ten years from the date of Acceptance or supplied to Purchaser for its retention.

1.6
Seller’s Responsibility
Review and comment by Purchaser of the quality assurance procedures, quality plans, inspection and test arrangements operated by either Seller or his Vendors, will not relieve Seller of its obligation to provide Equipment which complies with the requirements of the Agreement.

2.0
QUALITY SURVEILLANCE

2.1
Quality Surveillance Requirements
Seller shall define the items which it proposes to Vendor together with all items for which quality plans (inspection and test plans) will be submitted.  Seller shall provide Purchaser’s Quality Assurance Manager the name of his representative authorized as having responsibility for resolving or obtaining resolution, of any problems arising in respect of the acceptability of raw materials, components, and assemblies.

Seller shall establish and maintain a documented inspection system capable of producing objective evidence that all material manufactured parts and assemblies comply with the quality requirements of the Contract. 

General information on the type of system in use by Seller shall be provided. 

Seller’s inspection system shall include procedures used for controlling the following functions:


Availability at inspection points of applicable drawings, instructions, etc and prompt removal of obsolete documents.


Maintenance and calibration of suitable inspection and test equipment, which should comply with requirements set out in ISO 9001


Inclusion (or referencing) on purchase orders of the necessary technical inspection and test details to meet the specified requirements and of Purchaser’s possible involvement at the Vendor’s facilities.


Incoming, in process and final inspection and inspection of packing and marking.


Means of identifying inspection status throughout manufacture.


Provisions of complete inspection and test records.

Seller shall submit for review within 30 days after the execution of this Agreement, a quality plan, excluding testing and inspection on work already completed as of such submission date, in which case test records will be provided, (inspection and test plan) defining the program of quality control and inspection activities which it or its Vendors will perform in order to ensure that the manufacture and completion of the plant complies with the specified requirements.  The quality plan may be of any form to suit Seller’s system, but it shall as a minimum:


Indicate each inspection and test point and its relative location in the production cycle including incoming, packing and site inspections.


Indicate mandatory Seller Factory hold points for an item or process before the work can proceed.

Seller shall include in all its orders to Vendors, a note advising that all materials and equipment are subject to inspection by Purchaser.

In order to verify compliance with engineering, procurement, manufacturing requirements and program, Purchaser shall have access at all times as arranged by Seller, to all places where materials or equipment are being prepared or manufactured, including the works of Vendor’s raw materials.

Inspection of the Equipment may be by Purchaser and may include the following activities:


Evaluation of Seller’s system and Quality Plans.


Periodic monitoring to confirm the effectiveness of and Seller’s compliance with the established system procedures, quality plan and inspection and test instructions.


Witnessing of inspections and test and/or verification of inspection records including:

a.
Compliance of raw material with specified requirements.

b.
Compliance of manufactured parts, assemblies and final items with specifications, drawings, standards and good engineering practice.

c.
Periodic inspection of Seller’s design manufacturing, installation work and the production of progress reports. 

d.
Witnessing of inspections and tests.

e.
Packing for shipment including check for completeness of shipment, handling requirements, and identification.

Seller’s compliance with equipment documentation, drawing, delivery and commissioning schedules shall be monitored by Purchaser.

Raw materials, components, shop assemblies and the installation thereof, shall be subject to inspection and test by Purchaser as required by the specification and the extent practicable at all times and places during the period of manufacture.

Seller shall keep Purchaser informed, in advance, of the time of starting and of the progress of the Scope of Work in its various stages so that arrangements can be made for inspection and for test.  He shall also provide without additional charge, all reasonable facilities and assistance for the safety and convenience of Purchaser in the performance of his duties.  All of the required tests shall be made to Seller’s expense, including the cost of all samples used.

In the event of the unreasonable postponement, by Seller, of tests previously scheduled, or of the necessity tests due to unsatisfactory results of the original tests, or other reasons attributable to Seller, Seller will bear the costs incurred by Purchaser of his nominated representative in re‑inspecting the non‑conforming item or its replacement. 

Seller’s and nominated Vendor’s quality assurance program shall identify and shall isolate items not conforming to the technical specification.  All such items shall be reported to Purchaser via a non‑conformance report which shall identify:


The identification of the item.


The relevant specification, drawing etc including revision number. 


A sketch of the non‑conformance.


The method by which the non‑conformance was identified.


The cause of the non‑conformance.


The proposal for resolution the con‑conformance.


A concession application including the technical justification and the appropriate supporting documents if applicable.


The proposed action to prevent re‑occurrence.

Seller shall not offer, unless otherwise agreed, any item of equipment for inspection to Purchaser until all planned inspections and tests to date have been completed to the satisfaction of Seller. 

Any non‑conformances identified by Purchaser may be notified by issue of Purchasers Non‑conformance Report to Seller.  Notification of re‑inspection shall not be made until the completed non‑conformance report together with any applicable concession application have been submitted to Purchaser. 

The inspection and tests by Purchaser of any components or lots thereof does not relieve Seller of any responsibility whatever regarding defects or other failures which maybe found before the end of the Primary Warranty Period. 

Seller shall provide a quality release certificate confirming compliance with the contract requirements and a data book containing relevant manufacturing and quality records. 

Seller shall furnish Purchaser with 4 copies of the data book.

The parties agree that, in light of the fast-track nature of the project for which this Unit is being supplied, and the advanced stage of manufacturing, Purchaser and Seller shall review the requirements, obligations and responsibilities set forth in this Exhibit J during two pre-inspection/quality meetings (one for the gas turbine, one for the generator). Seller shall coordinate and schedule a mutually agreed date for both meetings at Seller’s factory, with the goal of having them within two months after the design finalization meeting.  Seller shall document all mutually agreed adjustments to Exhibit J, issue the notes in letter form for review and agreement, and issue a final conformed letter  for subsequent endorsement by the parties and use as quality assurance guidelines.

EXHIBIT K  PROJECT PLANNINGtc \l1 "EXHIBIT K  PROJECT PLANNING
1  PURPOSE AND OBJECTIVES

1.1 Seller shall provide information and data required for development of a Project Schedule for the Work in accordance with the requirements of this Exhibit.  Seller’s information and data shall be provided electronically in a software which can be readily used in Purchaser’s “Primavera Project Planner” software which will be used by Purchaser to develop the Project Schedule.  The purpose of the Project Schedule shall be to:

(1)
assure adequate planning, scheduling and reporting during the prosecution and progress of the work by Seller in order to complete the work in accordance with any and all milestones;

(2)
assure coordination of the efforts of Seller, his various Vendors and Purchaser furnished equipment and materials, if any;

(3)
assist Seller, and Purchaser, in monitoring the progress of the work and in evaluating proposed changes to the Contract and the Project Schedule.

2  PROGRESS UPDATES
2.1  The Project Schedule shall be updated on a monthly basis and on a periodic basis throughout the duration of the work, and until Contract Completion.  Seller shall meet with Purchaser at the completion of each agreed upon period to review actual progress made through the date of the Schedule Update, including dates for activities actually started and/or completed, and to review the overall percentage of work actually completed.  The data date of each Schedule Update shall be the last Day of the month, or some other Day previously designated by Purchaser.  In case of disagreements at the Schedule Update meeting concerning actual progress to date, Purchaser’s determination shall govern. 

2.2  In addition to the Project Schedule updates, Seller shall submit a Monthly Contractor’s Progress Report containing the following minimum information as follows:

Monthly Contractor’s Progress Report
Timing:    Submitted 4 copies (4th of each Calendar month)

Contractor Name:

Reporting Month:
(1)  Management Summary (One Page)
‑  Overall Project Situation

‑  Major Activity

‑  Significant Problems

(2)  Progress Review
‑  Milestone Report

‑  Updated Bar Chart Schedule (Current vs. Target)

‑  Problems Affecting Progress

‑  Decisions and Actions

‑  Actions and Orientations required from Purchaser

(3)  Commercial Situation
‑  Payment Status

‑  Change Order Register

‑  Notice of Claims

3  RECOVERY SCHEDULE
3.1  Should the updated Project Schedule show at any time during Seller’s performance, in the sole opinion of Purchaser, that Seller is fourteen (14) or more days behind schedule for any Specific Date, Seller shall prepare a Recovery Schedule at no additional cost to Purchaser (unless Purchaser is solely responsible for the event or occurrence which has caused the schedule slippage) explaining and displaying how Seller intends to reschedule his work in order to regain compliance with the Project Schedule. 

4  PROJECT SCHEDULE REVISIONS
4.1  If, as a result of the monthly and periodic Project Schedule Update, it appears the Project Schedule no longer represents the actual prosecution and progress of the Work, Purchaser will request, and Seller shall submit, a revision to the Project Schedule. 

4.2  Seller may also request revisions to the Project Schedule in the event Seller’s planning for the Work is revised.  If Seller desires to make changes in the Project Schedule to reflect revisions in its method of operation and scheduling of the Work, Seller shall notify Purchaser in writing, stating the reason for the proposed revision.  In no case will notice to Purchaser of a request for schedule revision relieve Seller of any of his obligations under this Contract.  All Project Schedule revisions and updates shall conform to all provisions of the Contract documents contained herein. 

EXHIBIT L  EQUIPMENT REQUIRING INSURABILITY CERTIFICATEtc \l1 "EXHIBIT L  EQUIPMENT REQUIRING INSURABILITY CERTIFICATE
Gas Turbines

Generators

EXHIBIT M-1  SPARE PARTStc \l1 "EXHIBIT M-1  SPARE PARTS
SELLER’S OPERATING SPARES (ROUTINE) AND PRICES ARE ATTACHED HEREUNDER:

The prices as detailed under Exhibit M-1 are firm for those components ordered prior to the date stated in the footer, and will be updated by Seller for purchases after that date.

EXHIBIT M-2 COMMISSIONING SPARES AND SPECIAL TOOLStc \l1 "EXHIBIT M-2 COMMISSIONING SPARES AND SPECIAL TOOLS
1.
Sellers Start-up Commissioning Spares as required for the Scope of Work are:

· One (1) set of filters (except inlet filters); and

· One (1) set of gaskets.

2.
The following special tools are provided pursuant to Section 3.14.1:

Turbine maintenance tools (one (1) set per site):

· Guide pins (for removal or replacement of bearing caps, compressor casing and exhaust frame);

· Bearing and coupling disassembly fixture.

Generator maintenance tools (one (1) set per site):

· Rotor lifting slings;

· Rotor removal equipment including shoes, pans and pulling devices; and

· Rotor Jacking bolts.

Installation Equipment:

· Trunnion for generator (on loan basis only):

· Foundation/installation washer and shim packs; and

· Jacking bolts for generator.

EXHIBIT N-1  PURCHASE AMOUNT RECONCILIATIONtc \l1 "EXHIBIT N-1  PURCHASE AMOUNT RECONCILIATION
Item
U.S. Dollars

Base Price for the Unit

36,000,000

TDI - (162 manweeks)
Included

O & M Manuals (10)
Included

Maintenance Tools
Included

Second Battery Charger
Included

In/out Warranty obligation
Included

Delete Historian
(130,000)

Add Noise attenuation to 85 dB(A) Near Source
Included

Inlet System protative coating for high humidity
Included

Power Systems Stabilizer
Included

-20oF Protection for CO2 tank
19,000

Combustion System designed to accept 365oF fuel
Included

TOTAL (the “Purchase Amount”)
35,889,000

EXHIBIT N-2  OPTIONStc \l1 "EXHIBIT N-2  OPTIONS
Item
Quantity
Price in

U.S. Dollars

1.  Training as described in Exhibit H-2

     A.  GTG Maintenance

     B.  GTG Mark V Technician

     C.  EX2000 Excitation

Prices for these classes shall be escalated by 6% per year commencing January 1, 2002 and on the first day of January for each subsequent year thereafter that the option is exercised. 
1 Class (1 week)

1 Class (2 weeks)

1 Class (1 week)


$43,200

$72,000

$40,900

EXHIBIT O  HAZARDOUS MATERIAL NOTIFICATIONtc \l1 "EXHIBIT O  HAZARDOUS MATERIAL NOTIFICATION
HAZARDOUS AND TOXIC SUBSTANCES

DISCLOSURE REQUIREMENTS


CONTRACT NUMBER

Show the order identification 

on all correspondence

Seller:                                          

Attention:                                               

Address:                                      ZIP:        

Phone Number: (     )                                    

HAZARDOUS AND TOXIC SUBSTANCES DISCLOSURE REQUIREMENTS

The Occupational and Health Act (OSHA) of 1970, and OSHA regulation 29CFR 1910.20 contain hazardous and toxic substances reporting requirements.

Seller shall be required to provide the following documents, as applicable to Purchaser at the time of Contract, if possible, but not later than ten (10) days thereafter. A copy of the Material Safety Data Sheet, (Form OSHA‑20), or equivalent, must accompany each shipment of hazardous or toxic substances to Purchaser.  The following documents may be required for more than one item within the Contract.

MATERIAL SAFETY DATA SHEET

The Material Safety Data Sheet (Form OSHA-20), or equivalent is required for each material containing a chemical substance which: (i) is regulated by any Federal law or rule, (ii) is listed in the latest edition of the National Institute for Occupational Safety and Health Registry of Toxic Effects of Chemical Substances. (iii) testing has yielded positive evidence of an acute or chronic health hazard, or (iv) has a Material Safety Data Sheet available to Seller indicating that the material may pose a hazard to human health.

                                           ‑AND/OR‑   

SELLER DISCLAIMER STATEMENT

Seller may alternatively submit a disclaimer statement set forth below:

HAZARDOUS AND TOXIC SUBSTANCES DISCLAIMER

Seller hereby swears or affirms that the material furnished on this Purchase Order does not, to its best knowledge, contain any toxic substances or harmful physical agents as defined under 29CFR 1910.20.  In the event Seller discovers that such hazardous and toxic substances or agents are to be supplied, an appropriate Material Safety Data Sheet (Form OSHA-20), or equivalent shall be immediately supplied to Purchaser.  

Signature of Company Officer         Date:  _______________________________

____________________________                            

Title

NONCOMPLIANCE

Seller assumes all responsibility for its failure to supply Purchaser a completed Material Safety Data Sheet (Form OSHA-20), or equivalent or a Seller Disclaimer Statement as applicable.

EXHIBIT P  UNIT SERIAL NUMBERtc \l1 "EXHIBIT P  UNIT SERIAL NUMBER
UNIT’S SERIAL NUMBERS:
Gas Turbine
[---------]




Generator

[---------]



Seller shall provide the above serial numbers prior to the ODM.


EXHIBIT Q RESERVEDtc \l1 "EXHIBIT Q RESERVED



EXHIBIT R  OBSERVATION POINTStc \l1 "EXHIBIT R  OBSERVATION POINTS
Seller’s major observation points are as follows:

Gas Turbine
Full Speed No Load Test

Compressor Rotor Balance

Turbine Rotor Balance

Certify for Shipment

Generator
Stator Hi-Pot

Rotor Hi-Pot

Rotor Balance

Control System
Final Test

EXHIBIT S  FINAL WAIVER  OF LIENS FORMtc \l1 "EXHIBIT S  FINAL WAIVER  OF LIENS FORM
AFFIDAVIT AND RELEASE OF LIEN

THE STATE OF ________
§

COUNTY OF ___________
§

[Seller Name] hereby acknowledges the receipt and sufficiency of the sum of $                , (                                                           ), and other good and valuable consideration, in full payment for all design, labor, materials, equipment, supplies and services, for the supply of diesel GTG package for the [            project name                  ], (“the Project”) pursuant to the Purchase Contract No. [           ] dated [--------] , between [Seller Name] (the “Seller”) and [--------] (the “Purchaser”).

[Seller Name] hereby acknowledges and certifies that [--------] paid                                            , all sums owing and that it has no further claims against [-------], or any subsidiary, affiliate or parent of [-------] except for the outstanding unresolved Change Order listed in Appendix A to this Affidavit.  [if none, delete all of paragraph after “except for...”]  

[Seller Name] further covenants and warrants that the Project is free from all liens and claims for payment by any subcontractor, materialman or employee.

In consideration for such full payment, [Seller Name], on behalf of itself and its predecessors, employees, agents, officers, directors, shareholders, representatives, attorneys, successors, insurers and assigns, subcontractors and on behalf of any other persons claiming by, through or under [Seller Name], does hereby waive, release, and relinquish its rights to and discharge, release and acquit [-------], its subsidiaries, affiliates and parent and its employees, agents, officers, directors, shareholders, representatives, attorneys, successors, insurers, assigns and subcontractors, from any and all causes of action, claims, demands, debts, liabilities, expenses or costs of any kind and every character and nature whatsoever, including but not limited to any lien claims or rights, whether known or unknown, contingent or fixed, either in or arising out of the law of contracts, torts or property rights, whether arising under statutory law or common law, at law or in equity, with respect to the above-referenced property.  Furthermore, [Seller Name] agrees to Indemnify and hold harmless [Purchaser Name], its subsidiaries, affiliates and parent and all other persons or entities released by [Seller Name] above against the full amount of any liability, loss, claim, damage, or expense (including attorneys’ fees and any judgment required to be paid) in connection with any of the matters it has released in the event any person should assert against such released person or entity a claim under assignment or title derivative from [Seller Name] and in connection with any claims made in connection with or relating to [Seller Name] provision of design, labor, materials, equipment, supplies and/or services on the above-referenced property.

EXECUTED this _________ day of ______________________, 200[–].

[Seller Name]  
By:

 
Name:
 
Print or Type

Title:

 
SWORN TO AN SUBSCRIBED BEFORE ME, under my official hand and seal of office on this ____ day of ___________________, 200[–].

Notary Public in and for

the State of            
My Commission Expires:

(SEAL)

AFFIDAVIT
THE STATE OF ________
§

COUNTY OF ___________
§

BEFORE ME, the undersigned Notary Public, on this day personally came and appeared                                     known to me to be the individual whose name is subscribed to the foregoing RELEASE OF LIEN and being duly sworn, did state and acknowledge on his oath that he is the                           of                                            , is authorized to execute and deliver the foregoing on behalf of                                              as an act and deed of that entity for the purposes and consideration therein expressed.

GIVEN UNDER MY HAND AND SEAL OF OFFICE this _______ day of ________________, 200__.

      





Notary Public in and for 

the State of ___________.

(SEAL)

My Commission Expires:

CERTIFICATION
This is to certify that all work covered by Invoice No. [__________]  is complete and that the invoice is correct, authentic and the only one issued for the work described therein.


   [      NAME OF OFFICER      ]
A C K N O W L E D G E M E N T
(COUNTRY) [                       ]
(CITY)    [                       ]
Before me, a Notary Public for and in the City of [     CITY     ], [     COUNTRY     ], this [     DATE      ] personally appeared    [     NAME OF OFFICER    ], exhibiting to me his Residence Certificate No. [               ] issued at [                    ], [     NAME OF OFFICER    ] on [               ] to be the same person who executed the foregoing Certification acknowledged to me that the same is a free and voluntary act and deed and to me known as the same person who acknowledged this certification.

In witness hereof, I have hereunto set my hand and affixed my notarial seal this [     ] of [               ], 200[---] in 
[   NAME OF CITY   ] [     COUNTRY     ].

[       NAME OF NOTARY       ]
Notary Public, State of ______.

My Commission Expires __________

Doc. No. ____________

Page No. ____________

Book No. ____________

Series of 200   
W  I  T  N  E  S  S  :
[         NAME          ]
[          NAME          ]
EXHIBIT T  DOCUMENT DELIVERY SCHEDULE AND DOCUMENT DELIVERY STATUStc \l1 "EXHIBIT T  DOCUMENT DELIVERY SCHEDULE AND DOCUMENT DELIVERY STATUS
MPL or MLI

Title
Document Delivery Date (Weeks after ODM)

0040
MS/SCHEMATICS
10

0301*
OUTLINE, GT PACKAGE CONN-ELEC
14

0302*
OUTLINE, PURCH MOUNTED DEVICES
14

0306*
OUTLINE, MECH-GT & LOAD
12

0313*
OUTLINE, GT PACKAGE CONN-PIPING
14

0314
NOTES, GT PACKAGE CONN OUTLINE-PP
14

0323*
PL, FOUNDATION INTERFACE OUTLINE 
14

0330*
OUTLINE, FOUNDATION INTERFACE, OFF-BASE, ELECTRICAL
14

0326*
OUTLINE, FOUNDATION INTERFACE, OFF-BASE, MECHANICAL
20

0408
WT & CG, GAS TURBINE PACKAGE
14

0414
DEVICE SUMMARY
11

0438
DOCUMENT LIST, GTD TO CUSTOMER
6

0444*
DIAGRAM, ONE LINE
11

0463
DIAGRAM, BLOCK, CABLE
12

1603*
FOUNDATION BOLTING ARRANGEMENT
14

0403
ELEMENTARY CONNECTOR CONTROL PANEL
30 weeks prior to scheduled shipment

A068
FIRE PROTECTION SYSTEM, CO2
20

A130
AIR PROCESSING UNIT
20

EO25
COMPRESSOR & TURB WASHING SYSTEM
20

AO59
CONTROL CENTER PKG, OFF BASE
20

A111
GENERATOR TERMINAL ENCLOSURE
20

A141
TRANSFORMER, ISOLATION, STAT STR
20

A150
XFORMER, PWR POTENTIAL-OFF BASE
20

A192
LCI/EX2000 COMPT W/O HV
20

0
O & M INSTRUCTION MANUALS (10 final sets in English)
See Section 10.1.1 (85 days after delivery)

Drawings annotated with * are subject to Document Liquidated Damages.

DRAWING PROCESSING

A copy of each drawing reviewed will be returned to Seller as stipulated herein.  Copies of drawings returned to Seller will be in the form of a print with Purchaser’s marking.  The parties agree that the only document for which the assignment of Status 3 shall be applicable, will be the Electric One Line drawing.

A.
DEFINITION OF SELLER DOCUMENT REVIEW STATUS

The guidelines listed below are followed in assigning the document status number to Seller prints.  These status numbers serve as hold points for starting or continuing manufacture of the covered commodity.  The document and its transmittal letter indicate the reason for the status.

Status 1: Work may proceed.

The document conforms to Contract requirements.  The document requires no changes or additions.  Matters remaining to be resolved do not require document change and will be handled by correspondence.  Where it is known that the design information on a supplier document is not complete and resubmittals will be made, such as “hold” areas, the document is assigned another status number.

Status 2: Revise and resubmit.  Work may proceed subject to resolution of indicated comments.

The document is in basic conformance with Contract requirements.  Minor deviations from Contract requirements (not including minor changes for Purchaser’s convenience) have been noted or other minor technical or physical changes in the equipment are required.  Such changes may include those affecting dimensions, material, colors, etc.  Administrative type changes such as inclusion or equipment or tag numbers and shipping notes may be combined with technical changes in this status.  Seller shall resolve comments and resubmit documents prior to shipment of commodity.

Status 3: Revise and resubmit.  Work may not proceed.

Work may not proceed because the document:

·
The contents of the document do not reflect or materially contradict the requirements of this Contract or the document is not useable by Purchaser for its intended purpose.

Status 4: Review not required.  Work may proceed.

Document is not subject to Purchaser review.  Typical uses for this status are in the review of items that are supplier standard products, small internal parts of major equipment, or Seller standardized data.

Permission to proceed does not constitute acceptance or approval of design details, calculation analysis, test methods, or materials developed or selected by the supplier from full compliance with contractual obligations.

FINAL DRAWINGS

Upon receipt from Purchaser of drawings marked Status 1 or Status 4, Seller drawing shall be considered acceptable and no further corrective action shall be required.  After completion of fabrication and release for shipment, all drawings shall be resubmitted showing the “as installed” configuration of the Equipment.

The parties agree that the only document for which the assignment of the Status 3 shall be applicable, will be the Electrical One Line drawing.  Seller shall deliver eight (8) complete sets of drawings, to Purchaser, or as otherwise mutually agreed.

565773-3

565773-3

Purchaser _________          Seller _________

-v-

