West Coast Weekly Report #6

8 June 2001

Key Results of Past Week

1. Meeting with Messrs. McConnell and Shankman held on 7 June -  presented efforts to date & received approval to proceed with: a) 6-month pre-permitting effort with estimated cost of $1.5 million, b) Sempra JV discussions, and c) Western hemisphere supply development.

2. Messrs. McGarry & Cebryk conducted meetings with Socal, SDG&E, and URS to examine Long Beach, Ormond Beach, and Rosarito, Mexico terminal sites; plus, permitting schedules and issues.  Mike will distribute separate report of findings.

3. Akin Gump reported analysis of FERC issues involved with California LNG terminal.  Analysis concluded that offshore facility in California waters (within 3 miles of shore) would not be subject to FERC jurisdiction under the Natural Gas Act.  Analysis also concluded that open season can require binding commitment.

Action Plan for next Week

1. Evaluate potential sites on California coast and agree on criteria to select one site to permit.

2. Prepare detailed cost estimate for FRSU; capital and operating.

3. Prepare plan for engaging permitting consultant.

4. Finalize Sempra Confidentiality agreement.

5. Team meetings to discuss JV strategy with Sempra.

6. Meeting with Sempra international scheduled for 22 June 2001 in San Diego, CA.

KL/11June2001

