Hi Team,

Following are the items and timeline discussed in our last meeting.  Please send me any additions/corrections that are needed.

By 8/9/99:




· Purchase pencil boxes


Bert Hernandez & Lillian Villarreal

· Purchase Enron Pencils


Geneva Davis

· Purchase stick-on labels for boxes

N/A
· Print Labels for Pencil boxes

Sherry Butler, Kevin Hyatt

· Prepare memos to parents 


Lillian, Bert

· Get note printed in color


Kevin Hyatt will check with Xerox

· Prepare pencil boxes 


Committee

8/12/99





· Deliver pencil boxes/memos to school
Lillian

· Attend teacher meeting at school to inform them of the program and how they can help








Lillian, Bert

8/16/99





· Update/Revise Permission slip

Sandy Dutton

· Update/Revise sponsor packet

Lillian, Bert

· Provide any vendor discount info

Sharon Stringfellow

8/26 

· 6pm Attend Open House to inform parents 
Lillian, Bert

· Permission slips go out

Mid 9/99




· Get permission slips back


Lillian

· Begin to Update database


Pam Rhea, Bert Hernandez
· Obtain gift bag donation


Lillian

Early 10/99




· Take class pictures at school

Bert

· Arrange for transportation (Truck & busses)
Ruth Mann

Mid 10/99




· Have pictures numbered & identified by Teachers and


· Prepare Pictures for display


Bert

· Prepare Invites to Preview Party

Sharon Butler
· Work with Graphics group to get posters
Sandy Dutton

· Work with facilities to book lobby, display posters, table setup, gift storage

· Geneva Davis

· Get volunteers to man signup tables

Emitra Nelson/Dennis Lee

· By Oct 22




· Send out ccmails to Rachel Tobor

Lillian

· Send invites to preview party

Sharon Butler

· Schedule school band to perform in EB Lobby on 11/2
Lillian

· Send management email to Sharron Westbrook for distribution Lillian

10/25

· Send management solicitation email

Sharron Westbrook

10/28


· Prepare Packets in EB48C2 (11:30-2)
Volunteers

11/2





· Preview Party



Volunteers

11/2 - 11/12 (if needed)



· Sponsor sign-up



Volunteers

Mid 11/99




· Finalize uniform vendor & get students sized
Sharon Stringfellow

Early 12/99




· Print name tags & signup sheets for sponsors to use at school
Lorraine Becker

· Finalize snacks for students & volunteers
Daryl Kitchen


· Shopping Cmte finalizes any required shopping
Sharon Stringfellow & Lesli Campbell

12/6  - 12/10




· Gift dropoff (Body Shop & EB2802)

Volunteers

· Send reminder email with party schedule
Lillian





12/13





· Deliver Gifts & Snacks to school


Truck & Volunteers

· Shopping Cmte finalizes any required shopping
Sharon Stringfellow & Lesli Campbell

12/14





· Party Date!




Volunteers

· Shopping Cmte finalizes any required shopping
Sharon Stringfellow & Lesli Campbell

Early January, 2000



· Arrange for delivery of Uniforms


Sharon Stringfellow

Mid 1/2000




· Discuss extra funds



Committee


