
[image: image14.wmf]ID

Task Name

1

Drill EB 579 #1

2

Drill EB 579 #1 Sidetrack

3

Insurance Settlement

4

Sanction Project

5

Mob Rig

6

Drill Development Well #1

7

Complete Development Well #1

8

Drill Development Well #2

9

Complete Development Well #2

10

Demob Rig

11

Subsea Completion Equip

12

Production Controls

13

Umbilical System

14

Flowline System

15

Completion/WO System

16

Integration Testing

17

Platform

18

Production Facilities

19

Compression

20

Export System

21

Flowline/Umbilical Installation

22

Misc 

23

Initial Production

3/16

4/14

11/1

9/1

9/1

9/6

10/4

11/3

12/1

12/31

11/1

11/1

11/1

12/3

10/3

9/20

11/1

11/1

11/1

11/19

4/14

1/1

J

F

M

A

M

J

J

A

S

O

N

D

J

F

M

A

M

J

J

A

S

O

N

D

J

F

M

A

M

J

J

A

2001

2002

2003


Figure 7  - Falcon Production Forecast – Net Gas Production vs. Time.

            
[image: image2.wmf]Falcon Production Forecast

P(50) Volume 

(Mmboe)

0

1

2

3

4

5

6

7

2001

2002

2003

2004

2005

2006

2007

2008

Year

Net Production 

(Mmboe / yr)

0

5

10

15

20

25

30

35

Cumulative 

Gross 

Production 

(Mmboe)

Annual Net (Mmboe)

Cumulative Gross (Mmboe)


Figure 8  - Falcon Production Forecast – Net MMBOE vs. Time.

[image: image3.jpg]Falcon Project

Preliminary Capital Expenditure Schedule

Two Well, Mariner 1 Development - 300 Mmcfd

2001 2002 2003
Total M§ at az a3 a4 at az a3 Qs a1 az Qs a4
Development Well #1 Rig Activity and Lease Equipment (Development)
Drl Development Wl #1 5898 8858
[Complete Development Well #1 8870 8870
[Subsea Completion Equipment 1,585 200 250 400 735
Production Cantrols 156 i E3 4 75
Umbiical System %50 100 %0 250 250
Flowiine System 3852 265 400 108 1,0% 1,09
Flowine/\Jmbilcal Installation 1,260 0 %0
[CompletionWorkover System 1,076 243 243 590
Eil 200 200
Viscalansous 2200 % % 100 100 160 200 300 400 500 00
Total Gapex| 29,188 % 2 100 &2 1015 1,985 2899 | 20007 2,050 400 -
Devslopment Well #2 Rig Activity and Lease Equipment
[Drl Development Well #2. 8261 8251
(Complete Davelopment Well #2 917 8117
Subsea Complation Equipment 1,685 200 250 400 735
Production Controls 155 15 25 © 75
Ubilical System 990 00 180 250 450
Flowine System 3953 285 400 0% 1.0% 1,09
[Fiowine/Umbilcal nstallation 1,258 300 559
CompietionWorkaver System 1,077 243 243 £
s 200 200
Miscellansous 2,200 2% % 100 100 180 200 300 400 500 400
Total Capex| 28797 25 26 100 680 1,015 1,988 2,098 229 1928 00 z
Production System
Umbilcal System 507 60 & 140 222
Export Pipeiine System 20,465 4,000 4000 8000 10000 14468
[Production Canrols 805 ) 100 175 460
FPF 3191 2500 5,000 7500 12500 14500 191
FPF Installation 2,09 2,09
Expor Pipelne Terminaion Faciiles 1350 200 200 200 200 550
Compression (6500 HP) 5,000 1.000 1.000 1.000 2,000
iscelianeous 10584 )| 50 150 300 500 1.200 1,800 2800 2800 1,059
Total Capex| 114,085 26 50 0] 2930 5885 | 14215 24182 |  28500] 33099 1,089 .
Total for Two Well Development
Total Capex| 172,078 75 100 30|  a20] 1118|8188  2s880]  so7as|  sast 1,859
Cumuiative Gapex 75 175 525 4815 16730 | 34916 | e4@ss | 1isedz| 1m0213| 172078 | 172078
EB 579#1 Rig Activity and Lease Equipment (Development)
(Dol €8 578#1 [
Dl Sidetrack E8 579 #1 STK #1 2330 2330
Orl Sidetrack EB 578 #1 STK #2 50 2 25|
insurance Settiement 2.500) (2500)
Total Capex| 1203 1848|2355  (2,00) 5 - B = = : -
Total Full Gylce Development Cost
Grand Total Capex| 183281 11,423]  2456] (2160)]  4290] 11915] 1a,186| 29,980 s07a6] 64607 26 5
Cumulative Capex| 1425 | 18678 | 11728 | 16018| 27833 | 46119 | 76089 | qzmaas| tevazz| tesze1| tsnz8t

EREH

J Fist Production (1-4pr-03)

Abangonment Casts - 3 Wels = $10200M, Vessel/Risers(Mooring = S3500M

Salvage = $24030M





Figure 9  - Falcon Capital Expenditure Schedule.
[image: image1.wmf]Falcon Production Forecast

P(50) Volume 

(Bcf)

0

5

10

15

20

25

30

35

2001

2002

2003

2004

2005

2006

2007

2008

Year

Net Gas 

Production 

(Bcf)

0

15

30

45

60

75

90

105

Cumulative Net 

Gas Production 

(Bcf)

Annual Net (Bcf)

Cumulative Net (Bcf)


Figure 10A  - Falcon Monthly Operating Costs.

[image: image9.wmf]Reserve Category

Proven

Proven

Upside

Amplitude Area

H3.0

Splay

H2.5

Basic Geologic Paramaters

Trap Type

Stratigraphic

Statigraphic

Statigraphic

Average Depth (TVDSS)

8,100'

8,000'

7,000'

Most Likely Recovery Parameters

BHPi (psia)

4,475

4,450

4,200

BHT ('F)

155

152

122

Porosity (%)

29

28

28

Water Saturation (%)

20

20

20

Permeability (md)

500

200

200

Reservoir Drive

Combination

Depletion

Depletion

Recovery Efficiency (%)

65

65

65

Recovery Factor (Mcf/NAF)

1,775

1,710

2,286

Most Likely Volumetric Parameters

Net Pay (Maximum/Average)

130/50

30/21

40/18

Area (Acres)

2000

270

1000

Reservoir Volume (NAF)

100,000

5,670

18,000

Estimated Gas Recovery

Product of Most Likely Values

200

10.1

30

P50 from Monte Carlo Analysis

194

10.3

28.9

Falcon

Reserve Summary


Figure 10B  - Falcon Monthly Operating


[image: image4.wmf]Falcon Base Case - Cash Position Curve

-150

-75

0

75

150

225

2001

2002

2003

2004

2005

2006

2007

Year

Cumulative Net Cash Flow ($MM)


Figure 11  - Falcon Cash Position Curve

[image: image10.emf]FALCON PRODUCTION FACILITY

MONTHLY OPERATING EXPENSE  (Subsea - 175 Mmcfd)

Description Price Monthly Annual

Fixed Expenses

Labor (5 Positions)

  Operator (5)/IE $7,000 x 5 = $35,000 35,000 420,000

  Operator (5)/Mechanic $6,800 x 5 = $34,000 34,000 408,000

Subtotal $69,000 $828,000

 

Transportation  

  Boat (Supply - incl. with MeOH) 4 trips/mo = $12,000 0

  Helicopter (90 min/trip one-way) $4,000/day + $400/hr    

5 trips/mo + 15 hrs 25,775 309,300

Subtotal $25,775 $309,300

Catering  

  Food 5 x $30 = $150/day x 365 $4,560 $54,720

     

Communications $5,000 $60,000

Shore Base   $4,000 $48,000

Compressor Rental Purchase 6500 H.P. $0

Third Party & Maintenance  

  Engine PM (Generators, etc.) $6,000/mo 6,000 72,000

  Compressor Maintenance (one) $10,000 10,000 120,000

  Measurement Calibration $1,500 1,500 18,000

  Instrumentation Maintenance $3,000 3,000 36,000

  Facilities Inspections $1,000 1,000 12,000

  Painting $4,000 4,000 48,000

  Crane Maintenance $1,250 1,250 15,000

  Valve Repair and Maintenance $5,000 5,000 60,000

  Miscellaneous Electrical $3,000 3,000 36,000

Subtotal $34,750 $417,000


Figure 12  - Falcon Project Reserve Summary

Falcon Economic Summary

Development Type:
Two Well Subsea

Gross Reserves:

Gas 

(Bcf)


194

Condensate 
(MBbl)

581

Gross Capital:
($MM)

157

MEI Working Int.  (%)


  50

MMS Royalty
(%)


    0

Initial Gross Production Rate:

Gas 

(Mmcfd)

166

Condensate
(BPD)

500

Initial Production Date:


12-31-02

Product Pricing 2003:

Gas ($/MMBTU)


3.25

Condensate ($/Bbl)

21.00

Economics net to MEI 50% Working Interest

IRR


(%)


105

NPV-10

($MM)

142

VAI-10

(%)


2.88

Finding Cost
($/NBOE)

5.06

Payout (from sanction)




(years)

2.2

Figure 13  - Falcon Project Economic Summary

[image: image11.emf]Chemicals, Fuel & Oil

  Methanol   0

  Glycol 2,000 gal/mo x $5.00/gal 10,000 120,000

  Corrosion Inhibitor 100 gal/mo x $10.00/gal 1,000 12,000

  Antifreeze 200 gal/mo x $3.00/gal 600 7,200

  Potable Water 4,000 gal/mo x $.65/gal 2,600 31,200

  Diesel 3,600 gal/mo x $1.40/gal 5,000 60,000

  Lube Oil 1,100 gal/mo x $4.20/gal 4,620 55,440

Subtotal $23,820 $285,840

Inspections

  Subsea Inspection/ROV $4,000/mo $4,000 $48,000

Special Inspection Cost

  ABS Inspection &    

  Mooring System Inspection $10,000/mo $0

   

Insurance $100 mil value $50,000 $600,000

Overhead (12%) $28,000 $336,000

Contingency (10%) $25,000 $300,000

Total $273,905 $3,286,860

Subsea Intervention

  Rig Intervention (one $4 mil intervention/ 7 yrs.) $47,500 $570,000

  DSV Intervention (one $350,000 intervention/ 7 yrs.) $4,167 $50,000

Intervention Allowance (per well) $51,667 $620,000

Variable Expense

Chemicals - Parafin/Wax $0.230/Bbl

Chemicals - Methanol   $0.050/Mcf

Transportation - Gas $0.0653/Mcf

Transportation - Cond $1.025/Bbl

Basis Differential - NYMEX $-0.06/Mmbtu

Processing Fee - Gas

Processing Fee - Cond  


Figure 14  - Falcon Project Schedule.


[image: image5.wmf]Falcon Base Case Reserve 

Sensitivity

(Rate of Return / Net Present Value)

50

65

80

95

110

125

50

100

150

200

250

300

350

Gross Reserves (Bcf)

Rate of Return 

(%)

50

100

150

200

250

300

PV-10 @ 50% 

WI (MM$)

Rate of Return

Net Present Value


Figure 15  - Falcon Reserve Sensitivity.


[image: image6.wmf]Falcon Base Case Reserve 

Sensitivity

(Finding Cost / Value Added Index)

0

2

4

6

8

10

50

100

150

200

250

300

350

Gross Reserves (Bcf)

Finding Cost 

($ /Net Boe)

0

1

2

3

4

5

PV-10 Value 

Added Index

Finding Cost

PV-10 VAI


Figure 16  - Falcon Reserve Sensitivity.


[image: image7.wmf]Falcon Base Case Capex 

Sensitivity

(Net Present Value / Rate of Return)

50

75

100

125

150

175

0

15

30

45

60

75

90

105

120

Overrun (% of Forward  Capex)

PV-10 @ 50% WI 

($MM)

0

25

50

75

100

125

Rate of Return 

(%)

Net Present Value

Rate of Return


Figure 17  - Falcon Capex Sensitivity.


[image: image8.wmf]Falcon Base Case Capex 

Sensitivity

(Finding Cost / Value Added Index)

4

6

8

10

12

0

15

30

45

60

75

90

105

120

Overrun (% of Forward  Capex)

Finding Cost ($ / 

Net Boe)

0

1

2

3

4

PV-10 Value 

Added Index

Finding Cost

PV-10 VAI


Figure 18  - Falcon Capex Sensitivity.

� EMBED Excel.Sheet.8  ���








[image: image12.wmf]Reserve Category

Proven

Proven

Upside

Amplitude Area

H3.0

Splay

H2.5

Basic Geologic Paramaters

Trap Type

Stratigraphic

Statigraphic

Statigraphic

Average Depth (TVDSS)

8,100'

8,000'

7,000'

Most Likely Recovery Parameters

BHPi (psia)

4,475

4,450

4,200

BHT ('F)

155

152

122

Porosity (%)

29

28

28

Water Saturation (%)

20

20

20

Permeability (md)

500

200

200

Reservoir Drive

Combination

Depletion

Depletion

Recovery Efficiency (%)

65

65

65

Recovery Factor (Mcf/NAF)

1,775

1,710

2,286

Most Likely Volumetric Parameters

Net Pay (Maximum/Average)

130/50

30/21

40/18

Area (Acres)

2000

270

1000

Reservoir Volume (NAF)

100,000

5,670

18,000

Estimated Gas Recovery

Product of Most Likely Values

200

10.1

30

P50 from Monte Carlo Analysis

194

10.3

28.9

Falcon

Reserve Summary

[image: image13.png]'wo Well Subsea Shelf Platform

]

East Breaks 579, 623 - Falcon Project
Two Well Subsea Gas to Shelf Platform

o T P e S P v [
oo ssrs  sisten it
vurncs it int
sanaton popct

oo g

o Bovtopm ot 1
[compiots o wiopm ot i 1
ot Boviopm ot 2
[compiots o wiopm ot i 42
v

subte3 Compinton Equp
produston Cant
CEEE

ot 5 o
[compieniao ibm

g ton Tortng

Pt

produston it
[comprestion

esportssitm

oo umbica st

it productin

Wariner Eneray, In. Tie-Back Distance 50 Mies to B4 A105 | Temk T

o - Sonnns o

3 TouwTS ST

[Fages 151

Hstart || 1] & =3

RS

L D 1057pM

I
| [ElMcrosoft Pawerpoint - [P... [ E] Two well subsea shelr.




_1061714723.xls
CumCashCurve

		2001

		2002

		2003

		2004

		2005

		2006

		2007



Year

Cumulative Net Cash Flow ($MM)

Falcon Base Case - Cash Position Curve

-3.509

-79.75859

15.21655

89.36534

139.91486

179.01447

210.38255



ProductionNetBcf

		2001

		2002		0

		2003		29.606

		2004		52.921

		2005		70.081

		2006		82.786

		2007		91.663

		2008



Annual Net (Bcf)

Cumulative Net (Bcf)

Year

Net Gas Production (Bcf)

Cumulative Net Gas Production (Bcf)

Falcon Production Forecast
P(50) Volume (Bcf)

0

29.606

23.315

17.16

12.705

8.877



ProductionMmboe

		2001

		2002		0

		2003		10.2742616667

		2004		18.7833116667

		2005		25.0379133333

		2006		29.6353983333

		2007		32.84757

		2008



Annual Net (Mmboe)

Cumulative Gross (Mmboe)

Year

Net Production (Mmboe / yr)

Cumulative Gross Production (Mmboe)

Falcon Production Forecast
P(50) Volume (Mmboe)

0

5.0231533333

3.9557733333

2.91148

2.15562

1.50613



ROR-NPV-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



Net Present Value

Rate of Return

Gross Reserves (Bcf)

Rate of Return (%)

PV-10 @ 50% WI (MM$)

Falcon Base Case Reserve Sensitivity
(Rate of Return / Net Present Value)

49.959

66.19

105.001

94.43

141.999

104.72

187.048

112.62

260.569

119.88



VAI-FC-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



PV-10 VAI

Finding Cost

Gross Reserves (Bcf)

Finding Cost ($ /Net Boe)

PV-10 Value Added Index

Falcon Base Case Reserve Sensitivity
(Finding Cost / Value Added Index)

1.66

9.66

2.39

6.33

2.88

5.06

3.48

4.01

4.45

2.91



ROR-NPV-CapexSensitivity

		0		104.72

		15		86.74

		30		72.67

		45		61.38

		60		52.12

		75		44.39

		90		37.85

		105		32.22

		120		27.33



Net Present Value

Rate of Return

Overrun (% of Forward  Capex)

PV-10 @ 50% WI ($MM)

Rate of Return (%)

Falcon Base Case Capex Sensitivity
(Net Present Value / Rate of Return)

141.999

131.068

120.139

109.209

98.279

87.349

76.42

65.489

54.56



FC-VAI-CapexSensitivity

		0		2.88

		15		2.52

		30		2.23

		45		2.01

		60		1.82

		75		1.67

		90		1.54

		105		1.43

		120		1.33



Finding Cost

PV-10 VAI

Overrun (% of Forward  Capex)

Finding Cost ($ / Net Boe)

PV-10 Value Added Index

Falcon Base Case Capex Sensitivity
(Finding Cost / Value Added Index)

5.06

5.83

6.6

7.37

8.14

8.91

9.68

10.45

11.22



ChartData

		Falcon

		Reserves Sensitivity

						NPV		RoR		FC		VAI

		100		P(0)		49.959		66.19		9.66		1.66

		155		P(10)		105.001		94.43		6.33		2.39

		194		P(50)		141.999		104.72		5.06		2.88

		244		P(90)		187.048		112.62		4.01		3.48

		336		P(100)		260.569		119.88		2.91		4.45

		Capex Sensitivity

				%		PV10		IRR		FC		VAI

				0		141.999		104.72		5.06		2.88

				15		131.068		86.74		5.83		2.52

				30		120.139		72.67		6.60		2.23

				45		109.209		61.38		7.37		2.01

				60		98.279		52.12		8.14		1.82

				75		87.349		44.39		8.91		1.67

				90		76.42		37.85		9.68		1.54

				105		65.489		32.22		10.45		1.43

				120		54.56		27.33		11.22		1.33

		Production

				NET										GROSS

				Annual		Cum		Cond.		Annual				Annual		Cond.		Annual		Cum

				Bcf		Bcf		mmbo		mmboe				Bcf		mmbo		mmboe		mmboe

		2001

		2002		0		0		0		0				0		0		0		0

		2003		29.6		30		0.0888		5.02				60.55537		0.1817		10.274		10.27

		2004		23.3		53		0.0699		3.96				50.1513		0.1505		8.509		18.78

		2005		17.2		70		0.0515		2.91				36.86401		0.1106		6.255		25.04

		2006		12.7		83		0.0381		2.16				27.09711		0.0813		4.597		29.64

		2007		8.9		92		0.0266		1.51				18.93223		0.0568		3.212		32.85

		2008

				91.663				0.27499		15.55				193.60002		0.5809		32.848

		Cum Net Cash Flow (undiscounted)

		2001		-4

		2002		-80

		2003		15

		2004		89

		2005		140

		2006		179

		2007		210

		2008





Subsea - 300  Ph 1

		Falcon Project

		Preliminary Capital Expenditure Schedule

		Two Well Subsea, Shelf Platform, Tieback to BA A105 - 175 Mmcfd - Phase 1

						2001

														2002								2003

				Total M$		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4

		Development Well #1 Rig Activity and Lease Equipment (Development)

		Drill Development Well #1		8,898														8,898

		Complete Development Well #1		8,870														8,870

		Subsea Completion Equipment		2,343								212		425		625		1,081

		Production Controls		1,825								182		365		565		713

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,626														813		813

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1300

		Total Capex		30,575		25		25		- 0		787		1,476		2,644		22,555		3,063		- 0		- 0		- 0

		Development Well #2 Rig Activity and Lease Equipment (Development)

		Drill Development Well #2		8,261																8,261

		Complete Development Well #2		9,117																9,117

		Subsea Completion Equipment		2,344								212		425		625		1,082

		Production Controls		836								83		166		251		336

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,627														813		814

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1,300

		Total Capex		29,198		25		25		- 0		688		1,277		2,330		4,411		20,442		- 0		- 0		- 0

		Production System

		Umbilical System		13,181								1,272		2,546		2,546		6,817

		Export System		33,741								2,768		2,768		5,536		11,072		11,597

		Production Controls		530								53		106		106		265

		Production Manifold		2,495								250		500		750		995

		Platform		13,000										1,000		2,000		4,000		6,000

		Production Facilities		24,120								1,000		2,000		4,000		6,000		11,120

		Compression		- 0

		Flowline / Umbilical Installation		2,763																2,763

		Miscellaneous		7,099		25		50				200		400		600		1,800		4,024

		Total Capex		96,929		25		50		- 0		5,543		9,320		15,538		30,949		35,504		- 0		- 0		- 0

		Total for Two Well Development

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		East Breaks 579/623 #1 Well Rig Activity and Lease Equipment

		Drill EB 579 #1		11,323		11,323

		Drill Sidetrack EB 579 #1		2,330				2,330

		Miscellaneous		50		25		25

		Insurance Settlement		(2,500)						(2,500)

				- 0

				- 0

				- 0

				- 0

				- 0

				- 0

		Total Capex		11,203		11,348		2,355		(2,500)		- 0		- 0		- 0		- 0		- 0		- 0		- 0		- 0

		Total Full Cylce Development Cost

		Grand Total Capex		167,905		11,423		2,455		(2,500)		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				11,423		13,878		11,378		18,396		30,469		50,981		108,896		167,905		167,905		167,905		167,905

		Sunk Costs				First Production  (31-Dec-02)                                                                    Compression $6000M installed 1-Jan-05

						Abandonment Costs -  3 Wells = $10200M                                           Salvage = $17768M



&L&D&R&F




_1061722049.xls
CumCashCurve

		2001

		2002

		2003

		2004

		2005

		2006

		2007



Year

Cumulative Net Cash Flow ($MM)

Falcon Base Case - Cash Position Curve

-3.509

-79.75859

15.21655

89.36534

139.91486

179.01447

210.38255



ProductionNetBcf

		2001

		2002		0

		2003		29.606

		2004		52.921

		2005		70.081

		2006		82.786

		2007		91.663

		2008



Annual Net (Bcf)

Cumulative Net (Bcf)

Year

Net Gas Production (Bcf)

Cumulative Net Gas Production (Bcf)

Falcon Production Forecast
P(50) Volume (Bcf)

0

29.606

23.315

17.16

12.705

8.877



ProductionMmboe

		2001

		2002		0

		2003		10.2742616667

		2004		18.7833116667

		2005		25.0379133333

		2006		29.6353983333

		2007		32.84757

		2008



Annual Net (Mmboe)

Cumulative Gross (Mmboe)

Year

Net Production (Mmboe / yr)

Cumulative Gross Production (Mmboe)

Falcon Production Forecast
P(50) Volume (Mmboe)

0

5.0231533333

3.9557733333

2.91148

2.15562

1.50613



ROR-NPV-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



Net Present Value

Rate of Return

Gross Reserves (Bcf)

Rate of Return (%)

PV-10 @ 50% WI (MM$)

Falcon Base Case Reserve Sensitivity
(Rate of Return / Net Present Value)

49.959

66.19

105.001

94.43

141.999

104.72

187.048

112.62

260.569

119.88



VAI-FC-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



PV-10 VAI

Finding Cost

Gross Reserves (Bcf)

Finding Cost ($ /Net Boe)

PV-10 Value Added Index

Falcon Base Case Reserve Sensitivity
(Finding Cost / Value Added Index)

1.66

9.66

2.39

6.33

2.88

5.06

3.48

4.01

4.45

2.91



ROR-NPV-CapexSensitivity

		0		104.72

		15		86.74

		30		72.67

		45		61.38

		60		52.12

		75		44.39

		90		37.85

		105		32.22

		120		27.33



Net Present Value

Rate of Return

Overrun (% of Forward  Capex)

PV-10 @ 50% WI ($MM)

Rate of Return (%)

Falcon Base Case Capex Sensitivity
(Net Present Value / Rate of Return)

141.999

131.068

120.139

109.209

98.279

87.349

76.42

65.489

54.56



FC-VAI-CapexSensitivity

		0		2.88

		15		2.52

		30		2.23

		45		2.01

		60		1.82

		75		1.67

		90		1.54

		105		1.43

		120		1.33



Finding Cost

PV-10 VAI

Overrun (% of Forward  Capex)

Finding Cost ($ / Net Boe)

PV-10 Value Added Index

Falcon Base Case Capex Sensitivity
(Finding Cost / Value Added Index)

5.06

5.83

6.6

7.37

8.14

8.91

9.68

10.45

11.22



ChartData

		Falcon

		Reserves Sensitivity

						NPV		RoR		FC		VAI

		100		P(0)		49.959		66.19		9.66		1.66

		155		P(10)		105.001		94.43		6.33		2.39

		194		P(50)		141.999		104.72		5.06		2.88

		244		P(90)		187.048		112.62		4.01		3.48

		336		P(100)		260.569		119.88		2.91		4.45

		Capex Sensitivity

				%		PV10		IRR		FC		VAI

				0		141.999		104.72		5.06		2.88

				15		131.068		86.74		5.83		2.52

				30		120.139		72.67		6.60		2.23

				45		109.209		61.38		7.37		2.01

				60		98.279		52.12		8.14		1.82

				75		87.349		44.39		8.91		1.67

				90		76.42		37.85		9.68		1.54

				105		65.489		32.22		10.45		1.43

				120		54.56		27.33		11.22		1.33

		Production

				NET										GROSS

				Annual		Cum		Cond.		Annual				Annual		Cond.		Annual		Cum

				Bcf		Bcf		mmbo		mmboe				Bcf		mmbo		mmboe		mmboe

		2001

		2002		0		0		0		0				0		0		0		0

		2003		29.6		30		0.0888		5.02				60.55537		0.1817		10.274		10.27

		2004		23.3		53		0.0699		3.96				50.1513		0.1505		8.509		18.78

		2005		17.2		70		0.0515		2.91				36.86401		0.1106		6.255		25.04

		2006		12.7		83		0.0381		2.16				27.09711		0.0813		4.597		29.64

		2007		8.9		92		0.0266		1.51				18.93223		0.0568		3.212		32.85

		2008

				91.663				0.27499		15.55				193.60002		0.5809		32.848

		Cum Net Cash Flow (undiscounted)

		2001		-4

		2002		-80

		2003		15

		2004		89

		2005		140

		2006		179

		2007		210

		2008





Subsea - 300  Ph 1

		Falcon Project

		Preliminary Capital Expenditure Schedule

		Two Well Subsea, Shelf Platform, Tieback to BA A105 - 175 Mmcfd - Phase 1

						2001

														2002								2003

				Total M$		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4

		Development Well #1 Rig Activity and Lease Equipment (Development)

		Drill Development Well #1		8,898														8,898

		Complete Development Well #1		8,870														8,870

		Subsea Completion Equipment		2,343								212		425		625		1,081

		Production Controls		1,825								182		365		565		713

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,626														813		813

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1300

		Total Capex		30,575		25		25		- 0		787		1,476		2,644		22,555		3,063		- 0		- 0		- 0

		Development Well #2 Rig Activity and Lease Equipment (Development)

		Drill Development Well #2		8,261																8,261

		Complete Development Well #2		9,117																9,117

		Subsea Completion Equipment		2,344								212		425		625		1,082

		Production Controls		836								83		166		251		336

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,627														813		814

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1,300

		Total Capex		29,198		25		25		- 0		688		1,277		2,330		4,411		20,442		- 0		- 0		- 0

		Production System

		Umbilical System		13,181								1,272		2,546		2,546		6,817

		Export System		33,741								2,768		2,768		5,536		11,072		11,597

		Production Controls		530								53		106		106		265

		Production Manifold		2,495								250		500		750		995

		Platform		13,000										1,000		2,000		4,000		6,000

		Production Facilities		24,120								1,000		2,000		4,000		6,000		11,120

		Compression		- 0

		Flowline / Umbilical Installation		2,763																2,763

		Miscellaneous		7,099		25		50				200		400		600		1,800		4,024

		Total Capex		96,929		25		50		- 0		5,543		9,320		15,538		30,949		35,504		- 0		- 0		- 0

		Total for Two Well Development

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		East Breaks 579/623 #1 Well Rig Activity and Lease Equipment

		Drill EB 579 #1		11,323		11,323

		Drill Sidetrack EB 579 #1		2,330				2,330

		Miscellaneous		50		25		25

		Insurance Settlement		(2,500)						(2,500)

				- 0

				- 0

				- 0

				- 0

				- 0

				- 0

		Total Capex		11,203		11,348		2,355		(2,500)		- 0		- 0		- 0		- 0		- 0		- 0		- 0		- 0

		Total Full Cylce Development Cost

		Grand Total Capex		167,905		11,423		2,455		(2,500)		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				11,423		13,878		11,378		18,396		30,469		50,981		108,896		167,905		167,905		167,905		167,905

		Sunk Costs				First Production  (31-Dec-02)                                                                    Compression $6000M installed 1-Jan-05

						Abandonment Costs -  3 Wells = $10200M                                           Salvage = $17768M



&L&D&R&F




_1061722212.xls
CumCashCurve

		2001

		2002

		2003

		2004

		2005

		2006

		2007



Year

Cumulative Net Cash Flow ($MM)

Falcon Base Case - Cash Position Curve

-3.509

-79.75859

15.21655

89.36534

139.91486

179.01447

210.38255



ProductionNetBcf

		2001

		2002		0

		2003		29.606

		2004		52.921

		2005		70.081

		2006		82.786

		2007		91.663

		2008



Annual Net (Bcf)

Cumulative Net (Bcf)

Year

Net Gas Production (Bcf)

Cumulative Net Gas Production (Bcf)

Falcon Production Forecast
P(50) Volume (Bcf)

0

29.606

23.315

17.16

12.705

8.877



ProductionMmboe

		2001

		2002		0

		2003		10.2742616667

		2004		18.7833116667

		2005		25.0379133333

		2006		29.6353983333

		2007		32.84757

		2008



Annual Net (Mmboe)

Cumulative Gross (Mmboe)

Year

Net Production (Mmboe / yr)

Cumulative Gross Production (Mmboe)

Falcon Production Forecast
P(50) Volume (Mmboe)

0

5.0231533333

3.9557733333

2.91148

2.15562

1.50613



ROR-NPV-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



Net Present Value

Rate of Return

Gross Reserves (Bcf)

Rate of Return (%)

PV-10 @ 50% WI (MM$)

Falcon Base Case Reserve Sensitivity
(Rate of Return / Net Present Value)

49.959

66.19

105.001

94.43

141.999

104.72

187.048

112.62

260.569

119.88



VAI-FC-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



PV-10 VAI

Finding Cost

Gross Reserves (Bcf)

Finding Cost ($ /Net Boe)

PV-10 Value Added Index

Falcon Base Case Reserve Sensitivity
(Finding Cost / Value Added Index)

1.66

9.66

2.39

6.33

2.88

5.06

3.48

4.01

4.45

2.91



ROR-NPV-CapexSensitivity

		0		104.72

		15		86.74

		30		72.67

		45		61.38

		60		52.12

		75		44.39

		90		37.85

		105		32.22

		120		27.33



Net Present Value

Rate of Return

Overrun (% of Forward  Capex)

PV-10 @ 50% WI ($MM)

Rate of Return (%)

Falcon Base Case Capex Sensitivity
(Net Present Value / Rate of Return)

141.999

131.068

120.139

109.209

98.279

87.349

76.42

65.489

54.56



FC-VAI-CapexSensitivity

		0		2.88

		15		2.52

		30		2.23

		45		2.01

		60		1.82

		75		1.67

		90		1.54

		105		1.43

		120		1.33



Finding Cost

PV-10 VAI

Overrun (% of Forward  Capex)

Finding Cost ($ / Net Boe)

PV-10 Value Added Index

Falcon Base Case Capex Sensitivity
(Finding Cost / Value Added Index)

5.06

5.83

6.6

7.37

8.14

8.91

9.68

10.45

11.22



ChartData

		Falcon

		Reserves Sensitivity

						NPV		RoR		FC		VAI

		100		P(0)		49.959		66.19		9.66		1.66

		155		P(10)		105.001		94.43		6.33		2.39

		194		P(50)		141.999		104.72		5.06		2.88

		244		P(90)		187.048		112.62		4.01		3.48

		336		P(100)		260.569		119.88		2.91		4.45

		Capex Sensitivity

				%		PV10		IRR		FC		VAI

				0		141.999		104.72		5.06		2.88

				15		131.068		86.74		5.83		2.52

				30		120.139		72.67		6.60		2.23

				45		109.209		61.38		7.37		2.01

				60		98.279		52.12		8.14		1.82

				75		87.349		44.39		8.91		1.67

				90		76.42		37.85		9.68		1.54

				105		65.489		32.22		10.45		1.43

				120		54.56		27.33		11.22		1.33

		Production

				NET										GROSS

				Annual		Cum		Cond.		Annual				Annual		Cond.		Annual		Cum

				Bcf		Bcf		mmbo		mmboe				Bcf		mmbo		mmboe		mmboe

		2001

		2002		0		0		0		0				0		0		0		0

		2003		29.6		30		0.0888		5.02				60.55537		0.1817		10.274		10.27

		2004		23.3		53		0.0699		3.96				50.1513		0.1505		8.509		18.78

		2005		17.2		70		0.0515		2.91				36.86401		0.1106		6.255		25.04

		2006		12.7		83		0.0381		2.16				27.09711		0.0813		4.597		29.64

		2007		8.9		92		0.0266		1.51				18.93223		0.0568		3.212		32.85

		2008

				91.663				0.27499		15.55				193.60002		0.5809		32.848

		Cum Net Cash Flow (undiscounted)

		2001		-4

		2002		-80

		2003		15

		2004		89

		2005		140

		2006		179

		2007		210

		2008





Subsea - 300  Ph 1

		Falcon Project

		Preliminary Capital Expenditure Schedule

		Two Well Subsea, Shelf Platform, Tieback to BA A105 - 175 Mmcfd - Phase 1

						2001

														2002								2003

				Total M$		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4

		Development Well #1 Rig Activity and Lease Equipment (Development)

		Drill Development Well #1		8,898														8,898

		Complete Development Well #1		8,870														8,870

		Subsea Completion Equipment		2,343								212		425		625		1,081

		Production Controls		1,825								182		365		565		713

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,626														813		813

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1300

		Total Capex		30,575		25		25		- 0		787		1,476		2,644		22,555		3,063		- 0		- 0		- 0

		Development Well #2 Rig Activity and Lease Equipment (Development)

		Drill Development Well #2		8,261																8,261

		Complete Development Well #2		9,117																9,117

		Subsea Completion Equipment		2,344								212		425		625		1,082

		Production Controls		836								83		166		251		336

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,627														813		814

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1,300

		Total Capex		29,198		25		25		- 0		688		1,277		2,330		4,411		20,442		- 0		- 0		- 0

		Production System

		Umbilical System		13,181								1,272		2,546		2,546		6,817

		Export System		33,741								2,768		2,768		5,536		11,072		11,597

		Production Controls		530								53		106		106		265

		Production Manifold		2,495								250		500		750		995

		Platform		13,000										1,000		2,000		4,000		6,000

		Production Facilities		24,120								1,000		2,000		4,000		6,000		11,120

		Compression		- 0

		Flowline / Umbilical Installation		2,763																2,763

		Miscellaneous		7,099		25		50				200		400		600		1,800		4,024

		Total Capex		96,929		25		50		- 0		5,543		9,320		15,538		30,949		35,504		- 0		- 0		- 0

		Total for Two Well Development

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		East Breaks 579/623 #1 Well Rig Activity and Lease Equipment

		Drill EB 579 #1		11,323		11,323

		Drill Sidetrack EB 579 #1		2,330				2,330

		Miscellaneous		50		25		25

		Insurance Settlement		(2,500)						(2,500)

				- 0

				- 0

				- 0

				- 0

				- 0

				- 0

		Total Capex		11,203		11,348		2,355		(2,500)		- 0		- 0		- 0		- 0		- 0		- 0		- 0		- 0

		Total Full Cylce Development Cost

		Grand Total Capex		167,905		11,423		2,455		(2,500)		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				11,423		13,878		11,378		18,396		30,469		50,981		108,896		167,905		167,905		167,905		167,905

		Sunk Costs				First Production  (31-Dec-02)                                                                    Compression $6000M installed 1-Jan-05

						Abandonment Costs -  3 Wells = $10200M                                           Salvage = $17768M



&L&D&R&F




_1061789741.xls
CumCashCurve

		2001

		2002

		2003

		2004

		2005

		2006

		2007



Year

Cumulative Net Cash Flow ($MM)

Falcon Base Case - Cash Position Curve

-3.509

-79.75859

15.21655

89.36534

139.91486

179.01447

210.38255



ProductionNetBcf

		2001

		2002		0

		2003		29.606

		2004		52.921

		2005		70.081

		2006		82.786

		2007		91.663

		2008



Annual Net (Bcf)

Cumulative Net (Bcf)

Year

Net Gas Production (Bcf)

Cumulative Net Gas Production (Bcf)

Falcon Production Forecast
P(50) Volume (Bcf)

0

29.606

23.315

17.16

12.705

8.877



ProductionMmboe

		2001

		2002		0

		2003		10.2742616667

		2004		18.7833116667

		2005		25.0379133333

		2006		29.6353983333

		2007		32.84757

		2008



Annual Net (Mmboe)

Cumulative Gross (Mmboe)

Year

Net Production (Mmboe / yr)

Cumulative Gross Production (Mmboe)

Falcon Production Forecast
P(50) Volume (Mmboe)

0

5.0231533333

3.9557733333

2.91148

2.15562

1.50613



ROR-NPV-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



Net Present Value

Rate of Return

Gross Reserves (Bcf)

Rate of Return (%)

PV-10 @ 50% WI (MM$)

Falcon Base Case Reserve Sensitivity
(Rate of Return / Net Present Value)

49.959

66.19

105.001

94.43

141.999

104.72

187.048

112.62

260.569

119.88



VAI-FC-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



PV-10 VAI

Finding Cost

Gross Reserves (Bcf)

Finding Cost ($ /Net Boe)

PV-10 Value Added Index

Falcon Base Case Reserve Sensitivity
(Finding Cost / Value Added Index)

1.66

9.66

2.39

6.33

2.88

5.06

3.48

4.01

4.45

2.91



ROR-NPV-CapexSensitivity

		0		104.72

		15		86.74

		30		72.67

		45		61.38

		60		52.12

		75		44.39

		90		37.85

		105		32.22

		120		27.33



Net Present Value

Rate of Return

Overrun (% of Forward  Capex)

PV-10 @ 50% WI ($MM)

Rate of Return (%)

Falcon Base Case Capex Sensitivity
(Net Present Value / Rate of Return)

141.999

131.068

120.139

109.209

98.279

87.349

76.42

65.489

54.56



FC-VAI-CapexSensitivity

		0		2.88

		15		2.52

		30		2.23

		45		2.01

		60		1.82

		75		1.67

		90		1.54

		105		1.43

		120		1.33



Finding Cost

PV-10 VAI

Overrun (% of Forward  Capex)

Finding Cost ($ / Net Boe)

PV-10 Value Added Index

Falcon Base Case Capex Sensitivity
(Finding Cost / Value Added Index)

5.06

5.83

6.6

7.37

8.14

8.91

9.68

10.45

11.22



ChartData

		Falcon

		Reserves Sensitivity

						NPV		RoR		FC		VAI

		100		P(0)		49.959		66.19		9.66		1.66

		155		P(10)		105.001		94.43		6.33		2.39

		194		P(50)		141.999		104.72		5.06		2.88

		244		P(90)		187.048		112.62		4.01		3.48

		336		P(100)		260.569		119.88		2.91		4.45

		Capex Sensitivity

				%		PV10		IRR		FC		VAI

				0		141.999		104.72		5.06		2.88

				15		131.068		86.74		5.83		2.52

				30		120.139		72.67		6.60		2.23

				45		109.209		61.38		7.37		2.01

				60		98.279		52.12		8.14		1.82

				75		87.349		44.39		8.91		1.67

				90		76.42		37.85		9.68		1.54

				105		65.489		32.22		10.45		1.43

				120		54.56		27.33		11.22		1.33

		Production

				NET										GROSS

				Annual		Cum		Cond.		Annual				Annual		Cond.		Annual		Cum

				Bcf		Bcf		mmbo		mmboe				Bcf		mmbo		mmboe		mmboe

		2001

		2002		0		0		0		0				0		0		0		0

		2003		29.6		30		0.0888		5.02				60.55537		0.1817		10.274		10.27

		2004		23.3		53		0.0699		3.96				50.1513		0.1505		8.509		18.78

		2005		17.2		70		0.0515		2.91				36.86401		0.1106		6.255		25.04

		2006		12.7		83		0.0381		2.16				27.09711		0.0813		4.597		29.64

		2007		8.9		92		0.0266		1.51				18.93223		0.0568		3.212		32.85

		2008

				91.663				0.27499		15.55				193.60002		0.5809		32.848

		Cum Net Cash Flow (undiscounted)

		2001		-4

		2002		-80

		2003		15

		2004		89

		2005		140

		2006		179

		2007		210

		2008






_1061722192.xls
CumCashCurve

		2001

		2002

		2003

		2004

		2005

		2006

		2007



Year

Cumulative Net Cash Flow ($MM)

Falcon Base Case - Cash Position Curve

-3.509

-79.75859

15.21655

89.36534

139.91486

179.01447

210.38255



ProductionNetBcf

		2001

		2002		0

		2003		29.606

		2004		52.921

		2005		70.081

		2006		82.786

		2007		91.663

		2008



Annual Net (Bcf)

Cumulative Net (Bcf)

Year

Net Gas Production (Bcf)

Cumulative Net Gas Production (Bcf)

Falcon Production Forecast
P(50) Volume (Bcf)

0

29.606

23.315

17.16

12.705

8.877



ProductionMmboe

		2001

		2002		0

		2003		10.2742616667

		2004		18.7833116667

		2005		25.0379133333

		2006		29.6353983333

		2007		32.84757

		2008



Annual Net (Mmboe)

Cumulative Gross (Mmboe)

Year

Net Production (Mmboe / yr)

Cumulative Gross Production (Mmboe)

Falcon Production Forecast
P(50) Volume (Mmboe)

0

5.0231533333

3.9557733333

2.91148

2.15562

1.50613



ROR-NPV-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



Net Present Value

Rate of Return

Gross Reserves (Bcf)

Rate of Return (%)

PV-10 @ 50% WI (MM$)

Falcon Base Case Reserve Sensitivity
(Rate of Return / Net Present Value)

49.959

66.19

105.001

94.43

141.999

104.72

187.048

112.62

260.569

119.88



VAI-FC-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



PV-10 VAI

Finding Cost

Gross Reserves (Bcf)

Finding Cost ($ /Net Boe)

PV-10 Value Added Index

Falcon Base Case Reserve Sensitivity
(Finding Cost / Value Added Index)

1.66

9.66

2.39

6.33

2.88

5.06

3.48

4.01

4.45

2.91



ROR-NPV-CapexSensitivity

		0		104.72

		15		86.74

		30		72.67

		45		61.38

		60		52.12

		75		44.39

		90		37.85

		105		32.22

		120		27.33



Net Present Value

Rate of Return

Overrun (% of Forward  Capex)

PV-10 @ 50% WI ($MM)

Rate of Return (%)

Falcon Base Case Capex Sensitivity
(Net Present Value / Rate of Return)

141.999

131.068

120.139

109.209

98.279

87.349

76.42

65.489

54.56



FC-VAI-CapexSensitivity

		0		2.88

		15		2.52

		30		2.23

		45		2.01

		60		1.82

		75		1.67

		90		1.54

		105		1.43

		120		1.33



Finding Cost

PV-10 VAI

Overrun (% of Forward  Capex)

Finding Cost ($ / Net Boe)

PV-10 Value Added Index

Falcon Base Case Capex Sensitivity
(Finding Cost / Value Added Index)

5.06

5.83

6.6

7.37

8.14

8.91

9.68

10.45

11.22



ChartData

		Falcon

		Reserves Sensitivity

						NPV		RoR		FC		VAI

		100		P(0)		49.959		66.19		9.66		1.66

		155		P(10)		105.001		94.43		6.33		2.39

		194		P(50)		141.999		104.72		5.06		2.88

		244		P(90)		187.048		112.62		4.01		3.48

		336		P(100)		260.569		119.88		2.91		4.45

		Capex Sensitivity

				%		PV10		IRR		FC		VAI

				0		141.999		104.72		5.06		2.88

				15		131.068		86.74		5.83		2.52

				30		120.139		72.67		6.60		2.23

				45		109.209		61.38		7.37		2.01

				60		98.279		52.12		8.14		1.82

				75		87.349		44.39		8.91		1.67

				90		76.42		37.85		9.68		1.54

				105		65.489		32.22		10.45		1.43

				120		54.56		27.33		11.22		1.33

		Production

				NET										GROSS

				Annual		Cum		Cond.		Annual				Annual		Cond.		Annual		Cum

				Bcf		Bcf		mmbo		mmboe				Bcf		mmbo		mmboe		mmboe

		2001

		2002		0		0		0		0				0		0		0		0

		2003		29.6		30		0.0888		5.02				60.55537		0.1817		10.274		10.27

		2004		23.3		53		0.0699		3.96				50.1513		0.1505		8.509		18.78

		2005		17.2		70		0.0515		2.91				36.86401		0.1106		6.255		25.04

		2006		12.7		83		0.0381		2.16				27.09711		0.0813		4.597		29.64

		2007		8.9		92		0.0266		1.51				18.93223		0.0568		3.212		32.85

		2008

				91.663				0.27499		15.55				193.60002		0.5809		32.848

		Cum Net Cash Flow (undiscounted)

		2001		-4

		2002		-80

		2003		15

		2004		89

		2005		140

		2006		179

		2007		210

		2008





Subsea - 300  Ph 1

		Falcon Project

		Preliminary Capital Expenditure Schedule

		Two Well Subsea, Shelf Platform, Tieback to BA A105 - 175 Mmcfd - Phase 1

						2001

														2002								2003

				Total M$		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4

		Development Well #1 Rig Activity and Lease Equipment (Development)

		Drill Development Well #1		8,898														8,898

		Complete Development Well #1		8,870														8,870

		Subsea Completion Equipment		2,343								212		425		625		1,081

		Production Controls		1,825								182		365		565		713

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,626														813		813

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1300

		Total Capex		30,575		25		25		- 0		787		1,476		2,644		22,555		3,063		- 0		- 0		- 0

		Development Well #2 Rig Activity and Lease Equipment (Development)

		Drill Development Well #2		8,261																8,261

		Complete Development Well #2		9,117																9,117

		Subsea Completion Equipment		2,344								212		425		625		1,082

		Production Controls		836								83		166		251		336

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,627														813		814

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1,300

		Total Capex		29,198		25		25		- 0		688		1,277		2,330		4,411		20,442		- 0		- 0		- 0

		Production System

		Umbilical System		13,181								1,272		2,546		2,546		6,817

		Export System		33,741								2,768		2,768		5,536		11,072		11,597

		Production Controls		530								53		106		106		265

		Production Manifold		2,495								250		500		750		995

		Platform		13,000										1,000		2,000		4,000		6,000

		Production Facilities		24,120								1,000		2,000		4,000		6,000		11,120

		Compression		- 0

		Flowline / Umbilical Installation		2,763																2,763

		Miscellaneous		7,099		25		50				200		400		600		1,800		4,024

		Total Capex		96,929		25		50		- 0		5,543		9,320		15,538		30,949		35,504		- 0		- 0		- 0

		Total for Two Well Development

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		East Breaks 579/623 #1 Well Rig Activity and Lease Equipment

		Drill EB 579 #1		11,323		11,323

		Drill Sidetrack EB 579 #1		2,330				2,330

		Miscellaneous		50		25		25

		Insurance Settlement		(2,500)						(2,500)

				- 0

				- 0

				- 0

				- 0

				- 0

				- 0

		Total Capex		11,203		11,348		2,355		(2,500)		- 0		- 0		- 0		- 0		- 0		- 0		- 0		- 0

		Total Full Cylce Development Cost

		Grand Total Capex		167,905		11,423		2,455		(2,500)		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				11,423		13,878		11,378		18,396		30,469		50,981		108,896		167,905		167,905		167,905		167,905

		Sunk Costs				First Production  (31-Dec-02)                                                                    Compression $6000M installed 1-Jan-05

						Abandonment Costs -  3 Wells = $10200M                                           Salvage = $17768M



&L&D&R&F




_1061721684.xls
CumCashCurve

		2001

		2002

		2003

		2004

		2005

		2006

		2007



Year

Cumulative Net Cash Flow ($MM)

Falcon Base Case - Cash Position Curve

-3.509

-79.75859

15.21655

89.36534

139.91486

179.01447

210.38255



ProductionNetBcf

		2001

		2002		0

		2003		29.606

		2004		52.921

		2005		70.081

		2006		82.786

		2007		91.663

		2008



Annual Net (Bcf)

Cumulative Net (Bcf)

Year

Net Gas Production (Bcf)

Cumulative Net Gas Production (Bcf)

Falcon Production Forecast
P(50) Volume (Bcf)

0

29.606

23.315

17.16

12.705

8.877



ProductionMmboe

		2001

		2002		0

		2003		10.2742616667

		2004		18.7833116667

		2005		25.0379133333

		2006		29.6353983333

		2007		32.84757

		2008



Annual Net (Mmboe)

Cumulative Gross (Mmboe)

Year

Net Production (Mmboe / yr)

Cumulative Gross Production (Mmboe)

Falcon Production Forecast
P(50) Volume (Mmboe)

0

5.0231533333

3.9557733333

2.91148

2.15562

1.50613



ROR-NPV-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



Net Present Value

Rate of Return

Gross Reserves (Bcf)

Rate of Return (%)

PV-10 @ 50% WI (MM$)

Falcon Base Case Reserve Sensitivity
(Rate of Return / Net Present Value)

49.959

66.19

105.001

94.43

141.999

104.72

187.048

112.62

260.569

119.88



VAI-FC-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



PV-10 VAI

Finding Cost

Gross Reserves (Bcf)

Finding Cost ($ /Net Boe)

PV-10 Value Added Index

Falcon Base Case Reserve Sensitivity
(Finding Cost / Value Added Index)

1.66

9.66

2.39

6.33

2.88

5.06

3.48

4.01

4.45

2.91



ROR-NPV-CapexSensitivity

		0		104.72

		15		86.74

		30		72.67

		45		61.38

		60		52.12

		75		44.39

		90		37.85

		105		32.22

		120		27.33



Net Present Value

Rate of Return

Overrun (% of Forward  Capex)

PV-10 @ 50% WI ($MM)

Rate of Return (%)

Falcon Base Case Capex Sensitivity
(Net Present Value / Rate of Return)

141.999

131.068

120.139

109.209

98.279

87.349

76.42

65.489

54.56



FC-VAI-CapexSensitivity

		0		2.88

		15		2.52

		30		2.23

		45		2.01

		60		1.82

		75		1.67

		90		1.54

		105		1.43

		120		1.33



Finding Cost

PV-10 VAI

Overrun (% of Forward  Capex)

Finding Cost ($ / Net Boe)

PV-10 Value Added Index

Falcon Base Case Capex Sensitivity
(Finding Cost / Value Added Index)

5.06

5.83

6.6

7.37

8.14

8.91

9.68

10.45

11.22



ChartData

		Falcon

		Reserves Sensitivity

						NPV		RoR		FC		VAI

		100		P(0)		49.959		66.19		9.66		1.66

		155		P(10)		105.001		94.43		6.33		2.39

		194		P(50)		141.999		104.72		5.06		2.88

		244		P(90)		187.048		112.62		4.01		3.48

		336		P(100)		260.569		119.88		2.91		4.45

		Capex Sensitivity

				%		PV10		IRR		FC		VAI

				0		141.999		104.72		5.06		2.88

				15		131.068		86.74		5.83		2.52

				30		120.139		72.67		6.60		2.23

				45		109.209		61.38		7.37		2.01

				60		98.279		52.12		8.14		1.82

				75		87.349		44.39		8.91		1.67

				90		76.42		37.85		9.68		1.54

				105		65.489		32.22		10.45		1.43

				120		54.56		27.33		11.22		1.33

		Production

				NET										GROSS

				Annual		Cum		Cond.		Annual				Annual		Cond.		Annual		Cum

				Bcf		Bcf		mmbo		mmboe				Bcf		mmbo		mmboe		mmboe

		2001

		2002		0		0		0		0				0		0		0		0

		2003		29.6		30		0.0888		5.02				60.55537		0.1817		10.274		10.27

		2004		23.3		53		0.0699		3.96				50.1513		0.1505		8.509		18.78

		2005		17.2		70		0.0515		2.91				36.86401		0.1106		6.255		25.04

		2006		12.7		83		0.0381		2.16				27.09711		0.0813		4.597		29.64

		2007		8.9		92		0.0266		1.51				18.93223		0.0568		3.212		32.85

		2008

				91.663				0.27499		15.55				193.60002		0.5809		32.848

		Cum Net Cash Flow (undiscounted)

		2001		-4

		2002		-80

		2003		15

		2004		89

		2005		140

		2006		179

		2007		210

		2008





Subsea - 300  Ph 1

		Falcon Project

		Preliminary Capital Expenditure Schedule

		Two Well Subsea, Shelf Platform, Tieback to BA A105 - 175 Mmcfd - Phase 1

						2001

														2002								2003

				Total M$		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4		Q1		Q2		Q3		Q4

		Development Well #1 Rig Activity and Lease Equipment (Development)

		Drill Development Well #1		8,898														8,898

		Complete Development Well #1		8,870														8,870

		Subsea Completion Equipment		2,343								212		425		625		1,081

		Production Controls		1,825								182		365		565		713

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,626														813		813

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1300

		Total Capex		30,575		25		25		- 0		787		1,476		2,644		22,555		3,063		- 0		- 0		- 0

		Development Well #2 Rig Activity and Lease Equipment (Development)

		Drill Development Well #2		8,261																8,261

		Complete Development Well #2		9,117																9,117

		Subsea Completion Equipment		2,344								212		425		625		1,082

		Production Controls		836								83		166		251		336

		Umbilical System		750								100		100		200		350

		Flowline System		2,513								243		486		729		1,055

		Flowline/Umbilical Installation		750																750

		Completion/Workover System		1,627														813		814

		SIT		200																200

		Miscellaneous		2,800		25		25				50		100		525		775		1,300

		Total Capex		29,198		25		25		- 0		688		1,277		2,330		4,411		20,442		- 0		- 0		- 0

		Production System

		Umbilical System		13,181								1,272		2,546		2,546		6,817

		Export System		33,741								2,768		2,768		5,536		11,072		11,597

		Production Controls		530								53		106		106		265

		Production Manifold		2,495								250		500		750		995

		Platform		13,000										1,000		2,000		4,000		6,000

		Production Facilities		24,120								1,000		2,000		4,000		6,000		11,120

		Compression		- 0

		Flowline / Umbilical Installation		2,763																2,763

		Miscellaneous		7,099		25		50				200		400		600		1,800		4,024

		Total Capex		96,929		25		50		- 0		5,543		9,320		15,538		30,949		35,504		- 0		- 0		- 0

		Total for Two Well Development

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		Total Capex		156,702		75		100		- 0		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				75		175		175		7,193		19,266		39,778		97,693		156,702		156,702		156,702		156,702

		East Breaks 579/623 #1 Well Rig Activity and Lease Equipment

		Drill EB 579 #1		11,323		11,323

		Drill Sidetrack EB 579 #1		2,330				2,330

		Miscellaneous		50		25		25

		Insurance Settlement		(2,500)						(2,500)

				- 0

				- 0

				- 0

				- 0

				- 0

				- 0

		Total Capex		11,203		11,348		2,355		(2,500)		- 0		- 0		- 0		- 0		- 0		- 0		- 0		- 0

		Total Full Cylce Development Cost

		Grand Total Capex		167,905		11,423		2,455		(2,500)		7,018		12,073		20,512		57,915		59,009		- 0		- 0		- 0

		Cumulative Capex				11,423		13,878		11,378		18,396		30,469		50,981		108,896		167,905		167,905		167,905		167,905

		Sunk Costs				First Production  (31-Dec-02)                                                                    Compression $6000M installed 1-Jan-05

						Abandonment Costs -  3 Wells = $10200M                                           Salvage = $17768M



&L&D&R&F




_1061714602.xls
CumCashCurve

		2001

		2002

		2003

		2004

		2005

		2006

		2007



Year

Cumulative Net Cash Flow ($MM)

Falcon Base Case - Cash Position Curve

-3.509

-79.75859

15.21655

89.36534

139.91486

179.01447

210.38255



ProductionNetBcf

		2001

		2002		0

		2003		29.606

		2004		52.921

		2005		70.081

		2006		82.786

		2007		91.663

		2008



Annual Net (Bcf)

Cumulative Net (Bcf)

Year

Net Gas Production (Bcf)

Cumulative Net Gas Production (Bcf)

Falcon Production Forecast
P(50) Volume (Bcf)

0

29.606

23.315

17.16

12.705

8.877



ProductionMmboe

		2001

		2002		0

		2003		10.2742616667

		2004		18.7833116667

		2005		25.0379133333

		2006		29.6353983333

		2007		32.84757

		2008



Annual Net (Mmboe)

Cumulative Gross (Mmboe)

Year

Net Production (Mmboe / yr)

Cumulative Gross Production (Mmboe)

Falcon Production Forecast
P(50) Volume (Mmboe)

0

5.0231533333

3.9557733333

2.91148

2.15562

1.50613



ROR-NPV-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



Net Present Value

Rate of Return

Gross Reserves (Bcf)

Rate of Return (%)

PV-10 @ 50% WI (MM$)

Falcon Base Case Reserve Sensitivity
(Rate of Return / Net Present Value)

49.959

66.19

105.001

94.43

141.999

104.72

187.048

112.62

260.569

119.88



VAI-FC-ReserveSensitivity

		100.4		100.4

		154.6		154.6

		193.6		193.6

		244.3		244.3

		336.4		336.4



PV-10 VAI

Finding Cost

Gross Reserves (Bcf)

Finding Cost ($ /Net Boe)

PV-10 Value Added Index

Falcon Base Case Reserve Sensitivity
(Finding Cost / Value Added Index)

1.66

9.66

2.39

6.33

2.88

5.06

3.48

4.01

4.45

2.91



ROR-NPV-CapexSensitivity

		0		104.72

		15		86.74

		30		72.67

		45		61.38

		60		52.12

		75		44.39

		90		37.85

		105		32.22

		120		27.33



Net Present Value

Rate of Return

Overrun (% of Forward  Capex)

PV-10 @ 50% WI ($MM)

Rate of Return (%)

Falcon Base Case Capex Sensitivity
(Net Present Value / Rate of Return)

141.999

131.068

120.139

109.209

98.279

87.349

76.42

65.489

54.56



FC-VAI-CapexSensitivity

		0		2.88

		15		2.52

		30		2.23

		45		2.01

		60		1.82

		75		1.67

		90		1.54

		105		1.43

		120		1.33



Finding Cost

PV-10 VAI

Overrun (% of Forward  Capex)

Finding Cost ($ / Net Boe)

PV-10 Value Added Index

Falcon Base Case Capex Sensitivity
(Finding Cost / Value Added Index)

5.06

5.83

6.6

7.37

8.14

8.91

9.68

10.45

11.22



ChartData

		Falcon

		Reserves Sensitivity

						NPV		RoR		FC		VAI

		100		P(0)		49.959		66.19		9.66		1.66

		155		P(10)		105.001		94.43		6.33		2.39

		194		P(50)		141.999		104.72		5.06		2.88

		244		P(90)		187.048		112.62		4.01		3.48

		336		P(100)		260.569		119.88		2.91		4.45

		Capex Sensitivity

				%		PV10		IRR		FC		VAI

				0		141.999		104.72		5.06		2.88

				15		131.068		86.74		5.83		2.52

				30		120.139		72.67		6.60		2.23

				45		109.209		61.38		7.37		2.01

				60		98.279		52.12		8.14		1.82

				75		87.349		44.39		8.91		1.67

				90		76.42		37.85		9.68		1.54

				105		65.489		32.22		10.45		1.43

				120		54.56		27.33		11.22		1.33

		Production

				NET										GROSS

				Annual		Cum		Cond.		Annual				Annual		Cond.		Annual		Cum

				Bcf		Bcf		mmbo		mmboe				Bcf		mmbo		mmboe		mmboe

		2001

		2002		0		0		0		0				0		0		0		0

		2003		29.6		30		0.0888		5.02				60.55537		0.1817		10.274		10.27

		2004		23.3		53		0.0699		3.96				50.1513		0.1505		8.509		18.78

		2005		17.2		70		0.0515		2.91				36.86401		0.1106		6.255		25.04

		2006		12.7		83		0.0381		2.16				27.09711		0.0813		4.597		29.64

		2007		8.9		92		0.0266		1.51				18.93223		0.0568		3.212		32.85

		2008

				91.663				0.27499		15.55				193.60002		0.5809		32.848

		Cum Net Cash Flow (undiscounted)

		2001		-4

		2002		-80

		2003		15

		2004		89

		2005		140

		2006		179

		2007		210

		2008






_1061677074.xls
Sheet1

		

		Falcon Project Area

		Reserve Summary

				Falcon

		Reserve Category		Proven		Proven		Upside

		Amplitude Area		H3.0		Splay		H2.5

		Basic Geologic Paramaters

		Trap Type		Stratigraphic		Statigraphic		Statigraphic

		Average Depth (TVDSS)		8,100'		8,000'		7,000'

		Most Likely Recovery Parameters

		BHPi (psia)		4,475		4,450		4,200

		BHT ('F)		155		152		122

		Porosity (%)		29		28		28

		Water Saturation (%)		20		20		20

		Permeability (md)		500		200		200

		Reservoir Drive		Combination		Depletion		Depletion

		Recovery Efficiency (%)		65		65		65

		Recovery Factor (Mcf/NAF)		1,775		1,710		2,286

		Most Likely Volumetric Parameters

		Net Pay (Maximum/Average)		130/50		30/21		40/18

		Area (Acres)		2000		270		1000

		Reservoir Volume (NAF)		100,000		5,670		18,000

		Estimated Gas Recovery

		Product of Most Likely Values		200		10.1		30

		P50 from Monte Carlo Analysis		194		10.3		28.9





Sheet2

		





Sheet3

		






