
Gas Trading Vision II

Inception – Phase II

[image: image1.png]



[image: image13.wmf]PubCd A

IF-Tetco/US

NGI/Chi.Gate

PubCd B

NX1

NX1

May-01

Jun-01


On behalf of

Enron Net Works, LLC

	Document Classification:
	Released for Review

	Version:
	1.1

	Point of contact:
	Zhiyong Wei

	Date:
	April 20, 2001


Sign off
The signatories agree with the definitions, processes and recommendations stated in this document and agree for the first

 phase to begin based on this document.

[image: image4.wmf]Curve Shift

Gamma

Vega

Theta

ETA

Rho

Drift

May-01

Jun-01


 Business Sponsors
Name
Louise Kitchen
_______________________ 

Date ______________

Name
Geof Storey

_______________________ 

Date ______________

Name
Jeff Gossett

_______________________ 

Date ______________

 IT Sponsors

Name
Philippe Bibi

_______________________ 

Date ______________



Name
Beth Perlman

_______________________ 

Date ______________



Name
Steve Stock

_______________________ 

Date ______________



Name
Zhiyong Wei

_______________________ 

Date ______________


Name
Dave Nommensen

___________________ 

Date ___________



Name
Jim Ogg 

_______________________ 

Date _____________




Name
Bob McAuliffe

___________________ 

Date ___________

Contents

1
Management summary
4

2
phase ii TASKS
5

3     DEPENDENCIES AND RISK FACTORS……………………………………………………………….10

3.1      dependencies
10

3.2      risk factors
10

4
Project timeline
11

4.1
Estimated Schedule for Phase II 
11



1 Management summary

The purpose of this document is to present a revised set of requirements and timelines for the Phase II of the Gas Trading Vision-II project.  The purpose of the Gas Trading Vision-II project is to develop additional systems functionality and to modify the existing business processes to provide the natural gas businesses of Enron North America (US & Canada) with a consolidated position screen/report and enhanced position reporting tools for each of the various gas business units.

Phase I of the Gas Trading Vision-II project was commenced on March 21, 2001, with an estimated go-live date for June 4, 2001.  

The requirements and tasks for Phase II are being addressed in this document, along with the proposed IT development timeline.

2 Phase II Tasks

Task 1: Capability for desk roll-ups on an ad-hoc basis:

The roll-up capability with predefined desks has been available in the production environment of TDS. In this phase, traders need to have the ability of defining roll-up desks on an ad-hoc basis.  Also, the various portfolios do not need to be shared, and the portfolio calculation should be performed only on the actively viewed portfolios.

The IT development timeline for this task is provided towards the end of this document.

Task 2: Option Grid:
The Gas Trading group would like to have modifications made to the Option Grid that is currently in existence.  A screen shot of the existing Option Grid is as follows:


[image: image2.png]0Pt

=181

Reset A11_| Bofault Book | Save Dsfoult | Latest Book | Refresh Table| Prin Window |

W e

Shaw Field

Notional Values -

Rblications Filter : 1 No [

A Normalized K

ot
I Exch

7 Susption

4 1de Opt Only

P Call
T put

Strike Prices

# steps [ 14 Step Size [ 0,05

Ganna Factor [ 1 Fi

Postils [§ 1094413

Natural Gas Non-AFfiliate Suap Back
NG-PRICE.

Coment
Bk

Comodity Natural Gas

1o Opt Flg to

cop [y 03-#PR-2001

Suaps [ 85855, 21-JUN-1936 I Option ook (official basis)

Pr Range=>
Ref Period

Basis Entire

Susps
(rotional)  Portfolio

$0.000  SLESO  $.700  $1.750

SLEBI9 SLEW  SL79  SL7H

$1,800  $1.85  $1,900  SLI0 82,00  £2.050

SLBI9 SLEW  SLM9 L9 $2.049 82,009

#PR-2001

o

HAY-2001

JUN-2001

JuL-2001

AUIC-2001

SEP-2001

0cT-2001

Nov-2001

DEC-2001

Je-2002

FEB-2002

| =]





The modifications required by the Gas Trading group are to integrate the Option Grid into Excel.  The Gas Trading group also requires multiple step sizes in their output columns, and that no empty columns should be made visible.

The IT development timeline for this task is provided towards the end of this document.

Task 3:  Gas Daily Options:

The Gas Trading group had requested some modifications and reports for the Gas Daily Options.  The OSTRIP model has been adjusted to allow two inputs, NYMEX vol and GD vol.

The report that is currently being worked upon for the Gas Daily Options is as follows:

Option Delta Change Forward Month report:  This report also requires changes to the ERMS PortCalc application.

[image: image5.wmf]REPORT NO:

RSROPTDELTACHANGE

EGS RISK MANAGEMENT

PRINTED ON:

04-Apr-2001

OPTION SENSITIVITY REPORT - DELTA vs. CHANGES IN UNDERLYING PRICE

TIME:

6:17 PM

(PROMPT MONTH ONLY)

(MMBTUs)

POST ID:

1082693

BOOK:

GAS DAILY

PERIOD

PUB CODE

INDEX 

DELTA

DELTA 

FIXED 

PRICE

DELTA 

SCALAR 

INDEX 

ONLY

GAMMA 

FIXED ONLY

VEGA 

FORWARD 

VOL

GD VEGA 

FIXED -1.0

GD VEGA 

FIXED 

ONLY

GD VEGA 

FIXED +1.0

GD VEGA 

INDEX 

ONLY

THETA 

FIXED 

ONLY

CHARM

Apr-01

GD-PAN/TX/OK

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

16.618

0.000

Apr-01

GDP-CAL BORDER

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

158.309

0.002

Apr-01

GDP-CGT/APPALAC

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

58.549

0.001

Apr-01

GDP-CHI. GATE

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

31.301

0.001

Apr-01

GDP-COLGULF/LA

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

7.692

0.000

Apr-01

GDP-CONSUMERS

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

1.654

0.000

Apr-01

GDP-ELPO/PERM2

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

19.591

0.001

Apr-01

GDP-HEHUB

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

131.563

0.061

Apr-01

GDP-HPL/SHPCH

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

22.864

0.000

Apr-01

GDP-KERN/OPAL

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.0

0.000

0.000


The IT development timeline for this task is provided towards the end of this document.

Task 4: Basis Options:

The systems need to be enhanced to capture and value different kinds of spread options including Basis Options (off NYMEX).  Since the current system does not capture Basis Options, a new TAGG deal entry type will need to be created.  Currently, ERMS does not handle spread options; therefore, spread options will need to be added to PortCalc.  A correlation spreadsheet will also be developed to upload the correlation curves.  Additionally, the “Top Page” report in ERMS will also need to be modified to include additional sensitivities.

The IT development timeline for this task is provided towards the end of this document.
Task 5:  Options reports:

The Gas Trading group has also requested the development of Options reports that fall in the following two categories:

Sample PL reports:
Total PL:

[image: image6.wmf]Total

NX1

IF - Transco

NGI

May-01

Jun-01


Curve Shift:

[image: image7.wmf]Total

NX1

IF - Tetco/US

NGI/Chi.Gate

May-01

Jun-01


Gamma PL:

[image: image8.wmf]Total

PubCd A

IF-Tetco/US

NGI/Chi.Gate

PubCd B

NX1

NX1

May-01

Jun-01


Vega PL:
[image: image9.wmf]Scalar Delta

Gamma

Vega

Theta

Sigma Delta

Charm

May-01

Jun-01


ETA PL:
[image: image10.wmf]NX1

IF - Transco/Z6

NGI Socal

May-01

Jun-01


Sample Sensitivity reports:
Total Sensitivity:
[image: image11.wmf]Total

NX1

IF - Transco/Z6

May-01

Jun-01


Delta Positions:
[image: image12.wmf]Total

NX1

IF - Transco/Z6

NGI/Chi.Gate

May-01

Jun-01


Gamma Sensitivity:

Vega Sensitivity:

ETA Sensitivity:

The IT development timeline for these reports is provided towards the end of this document.

Task 6:  Transport Deal Capture & Valuation:
Based upon the requirements provided by the Gas Trading group, the Transport deals will be valued in the similar fashion as Basis Options in the PortCalc application of ERMS.  A new deal entry type will also be developed to capture the transport deals in TAGG.  

The additional fields that will be required to capture the new transport deal type in TAGG are as follows:

· Fuel percentage

· Commodity (strike)

· 2 Pub Codes (receipt/delivery pub codes)

· Demand charges

In addition to the creation of new deal entry type, and changes to the PortCalc application in ERMS, the curve structure will also need to be modified to handle correlation, and a correlation spreadsheet will also be developed for the correlation curves.

The IT development timeline for this task is provided towards the end of this document.

Task 7:  Single point of deal entry for term deals:

The issue of single point of deal entry has been addressed in two phases.  The Phase 1 of single deal entry allowed the users to enter simple types of physical deals at the time of deal creation.  

In this phase of the project, the users will be able to enter and edit all types of physical deals.  In order to handle the remaining types of physical deals, various tasks will need to be implemented.  The Graphical User Interface (GUI) needs to be defined, along with the detail mapping of the data elements.  Data delivery and monitoring mechanisms will also need to be designed.  

Sitara deal entry will be modified to incorporate the single deal entry functionality.  All physical deals will be entered through the new Sitara deal entry system.  The users will be able to view TAGG deals through the TAGG deal entry system; however, the “save” and “edit” capabilities will be disabled, once Sitara’s single deal entry functionality is ready.

The detailed IT development timeline for this task is provided towards the end of this document.

3 Dependencies And Risk Factors

3.1 Dependencies

The timely deployment of the deliverables for this project is also dependent upon the Gas Trading and Risk groups.  In addition to assisting in the refining of requirements, the designated representatives from these two groups will also be required for the user acceptance testing, which is a also a very critical part of this project.  

The appropriate signers from the above-mentioned groups have also been included in the project sign-off sheet of this document.

3.2 Risk Factors

There is a risk that the requirements gathering process is not sufficient to uncover all the user requirements prior to initial product delivery.  This risk, however, will be mitigated by the presence of domain experts (both IT and business) on the project team.

A risk factor may also arise during the detail design phase.  Once the detail design process is commenced, the IT development team may uncover additional areas of development, which may require necessary adjustments to the project timeline.

Another risk factor arises in the area of personnel.  The possibility arises that the project team may lose members to other projects or other companies.  This risk is difficult to mitigate and requires attention to personnel management.

The list of risk factors listed above is complete as of date.  As other risk factors arise, the GTV project team will bring them to the attention of the project stakeholders.

4 Project Timeline

4.1 Estimated Schedule for Phase II

[image: image3.wmf]ID

Task Name

Duration

Start

Finish

42

Phase II

194.15 days

Mon 3/26/01

Fri 12/21/01

43

Capability for desk roll-ups on an ad hoc basis

53 days

Mon 4/23/01

Wed 7/4/01

44

New process for roll-up aggregators

6 wks

Mon 4/23/01

Fri 6/1/01

45

Unit testing

2 days

Mon 6/4/01

Tue 6/5/01

46

Interfaces, admin. Screen, profiles

2 wks

Fri 6/8/01

Thu 6/21/01

47

Unit testing

2 days

Fri 6/22/01

Mon 6/25/01

48

Integration testing

2 days

Tue 6/26/01

Wed 6/27/01

49

User Acceptance Testing

1 wk

Thu 6/28/01

Wed 7/4/01

50

Option Grid

24 days

Wed 4/11/01

Mon 5/14/01

51

Changes to the existing Option Grid to meet immediate, urgent needs

3 days

Wed 4/11/01

Fri 4/13/01

52

Conversion from Motif into Powerbuilder

2 wks

Mon 4/16/01

Fri 4/27/01

53

Unit testing

2 days

Mon 4/30/01

Tue 5/1/01

54

Loading the grid into Excel

1 day

Wed 5/2/01

Wed 5/2/01

55

Integration testing

3 days

Thu 5/3/01

Mon 5/7/01

56

User Acceptance Testing

1 wk

Tue 5/8/01

Mon 5/14/01

57

Gas Daily Options

25 days

Mon 3/26/01

Fri 4/27/01

58

Changes to the ERMS PortCalc application

3 wks

Mon 3/26/01

Fri 4/13/01

59

Unit testing

3 days

Mon 4/16/01

Wed 4/18/01

60

Option Delta Change Forward Month Report

1 wk

Mon 4/9/01

Fri 4/13/01

61

Unit testing

1 wk

Mon 4/16/01

Fri 4/20/01

62

User Acceptance Testing

1 wk

Mon 4/23/01

Fri 4/27/01

63

Basis Options

72 days

Wed 5/2/01

Thu 8/9/01

64

Create deal entry type for Basis Options in TAGG

2 wks

Tue 5/8/01

Mon 5/21/01

65

Unit testing

2 days

Tue 5/22/01

Wed 5/23/01

66

Changes to the Translator

2 wks

Thu 5/24/01

Wed 6/6/01

67

Unit testing

2 days

Thu 6/7/01

Fri 6/8/01

68

Load correlation curves

1 wk

Tue 5/8/01

Mon 5/14/01

69

Unit testing

2 days

Tue 5/15/01

Wed 5/16/01

70

Change PortCalc to value spread options

9 wks

Wed 5/2/01

Tue 7/3/01

71

Unit testing

1 wk

Wed 7/4/01

Tue 7/10/01

72

Change Top-Page report to include ETA & additional PL

1 wk

Wed 7/11/01

Tue 7/17/01

73

Unit testing

2 days

Wed 7/18/01

Thu 7/19/01

74

Integration testing

1 wk

Fri 7/20/01

Thu 7/26/01

75

User Acceptance Testing

2 wks

Fri 7/27/01

Thu 8/9/01

76

Options reports

35 days

Thu 5/17/01

Wed 7/4/01

77

PL reports

10 days

Thu 5/17/01

Wed 5/30/01

78

Unit testing

5 days

Thu 5/31/01

Wed 6/6/01

79

Sensitivity reports

10 days

Thu 6/7/01

Wed 6/20/01

80

Unit testing

5 days

Thu 6/21/01

Wed 6/27/01

81

User Acceptance Testing

5 days

Thu 6/28/01

Wed 7/4/01

82

Transport Deal Capture & Valuation

86 days

Thu 5/24/01

Thu 9/20/01

83

Creation of new deal entry type & database changes

2 wks

Thu 5/24/01

Wed 6/6/01

84

Unit testing

1 wk

Thu 6/7/01

Wed 6/13/01

85

Changes to the Translator

3 wks

Thu 6/14/01

Wed 7/4/01

86

Unit testing

1 wk

Thu 7/5/01

Wed 7/11/01

87

Curve structure changes, correlation spreadsheet

2 wks

Fri 7/27/01

Thu 8/9/01

88

Unit testing

1 wk

Fri 8/10/01

Thu 8/16/01

89

Change PortCalc to value Transport deals

3 wks

Fri 7/27/01

Thu 8/16/01

90

Unit testing

1 wk

Fri 8/17/01

Thu 8/23/01

91

Integration testing

2 wks

Fri 8/24/01

Thu 9/6/01

92

User Acceptance Testing

2 wks

Fri 9/7/01

Thu 9/20/01

93

Single point of deal entry for term deals

172.15 days

Wed 4/25/01

Fri 12/21/01

94

GUI definition

4 wks

Wed 4/25/01

Tue 5/22/01

95

Detail design and mapping

3 wks

Wed 4/25/01

Tue 5/15/01

96

Data delivery / monitoring mechanism design

2 wks

Fri 8/17/01

Thu 8/30/01

97

Change Sitara hedge

1.33 wks

Wed 5/23/01

Thu 5/31/01

98

Unit testing

2 days

Thu 5/31/01

Mon 6/4/01

99

Block AEP deals

1 day

Mon 6/4/01

Tue 6/5/01

100

Unit testing

1 day

Tue 6/5/01

Wed 6/6/01

101

Scenario development

3 wks

Wed 4/25/01

Tue 5/15/01

102

Database mapping

3 wks

Wed 4/25/01

Tue 5/15/01

103

Sitara GUI development for regular deals

5 wks

Mon 6/4/01

Mon 7/9/01

104

Unit testing

3 days

Mon 7/9/01

Thu 7/12/01

105

Sitara GUI development for desk-to-desk deals

2 wks

Thu 7/12/01

Thu 7/26/01

106

Unit testing

2 days

Thu 7/26/01

Mon 7/30/01

107

Sitara hedge "mapper" for regular deals

4 wks

Mon 7/30/01

Mon 8/27/01

108

Unit testing

4 days

Mon 8/27/01

Fri 8/31/01

109

Sitara hedge "mapper" for desk-to-desk deals

1 wk

Fri 8/31/01

Fri 9/7/01

110

Unit testing

2 days

Fri 9/7/01

Tue 9/11/01

111

Develop outbound Sitara message

4 wks

Mon 7/30/01

Mon 8/27/01

112

Unit testing

2 days

Mon 8/27/01

Wed 8/29/01

113

Change CPR brigde

7 wks

Mon 6/4/01

Mon 7/23/01

114

Unit testing

1 wk

Mon 7/23/01

Mon 7/30/01

115

Develop inbound TAGG message

4 wks

Mon 7/30/01

Mon 8/27/01

116

Unit testing

1 wk

Wed 8/29/01

Wed 9/5/01

117

New TAGG server for incoming deal messages

5 wks

Wed 9/5/01

Wed 10/10/01

118

Unit testing

4 days

Wed 10/10/01

Tue 10/16/01

119

Disable TAGG "save" for physical deals

1 day

Tue 10/16/01

Wed 10/17/01

120

Unit testing

1 day

Wed 10/17/01

Thu 10/18/01

121

Develop monitoring mechanism

2.5 wks

Thu 10/18/01

Tue 11/6/01

122

Unit testing

3 days

Tue 11/6/01

Fri 11/9/01

123

Integration testing

3 wks

Fri 11/9/01

Fri 11/30/01

124

User Acceptance Testing

3 wks

Fri 11/30/01

Fri 12/21/01

125

User sign-off & Go-live

0 days

Fri 12/21/01

Fri 12/21/01

Bill Fortney

Bill Fortney

Nayan Dattani

Nayan Dattani

Bill Fortney,Nayan Dattani

Geoff Storey,Jeff Gossett

Francis Lim,Samer Khatib

Francis Lim,Oscar Rivera

Francis Lim,Oscar Rivera

Francis Lim,Samer Khatib

Francis Lim,Oscar Rivera,Samer Khatib

Geoff Storey,Jeff Gossett

Jeremy Wong,Sandy Chen

Jeremy Wong,Sandy Chen

Francis Lim

Francis Lim

Geoff Storey,Jeff Gossett

Francis Lim,Oscar Rivera

Francis Lim,Oscar Rivera

Francis Lim,Truong Vu

Francis Lim,Truong Vu

Francis Lim,Samer Khatib

Francis Lim,Samer Khatib

Jeremy Wong,Sandy Chen

Jeremy Wong,Sandy Chen

Francis Lim,Samer Khatib

Francis Lim,Samer Khatib

Jeremy Wong,Francis Lim

Geoff Storey,Jeff Gossett

Margie Nguyen,Francis Lim

Margie Nguyen,Francis Lim

Margie Nguyen,Francis Lim

Margie Nguyen,Francis Lim

Jeff Gossett,Geoff Storey

Oscar Rivera

Oscar Rivera

Truong Vu

Truong Vu

Francis Lim

Francis Lim

Jeremy Wong

Jeremy Wong

Francis Lim,Jeremy Wong,Truong Vu,Oscar Rivera

Geoff Stoery,Jeff Gossett

Narasim Kasaru

Zhuoming Lou

Jay Krish,Jeremy Wong

Narasim Kasaru

Narasim Kasaru

Gurdip

Gurdip

Russ Severson

Russ Severson,Jay Krish,DBA

Narasim Kasaru

Narasim Kasaru

Narasim Kasaru

Narasim Kasaru

Zhuoming Lou

Zhuoming Lou

Zhuoming Lou

Zhuoming Lou

Tim Zhu

Tim Zhu

Meena Jayant

Meena Jayant

Oscar Rivera

Oscar Rivera

Oscar Rivera

Oscar Rivera

Oscar Rivera

Oscar Rivera

Dat Truong

Dat Truong

Russ Severson

Russ Severson

12/21

3/18

3/25

4/1

4/8

4/15

4/22

4/29

5/6

5/13

5/20

5/27

6/3

6/10

6/17

6/24

7/1

7/8

7/15

7/22

7/29

8/5

8/12

8/19

8/26

9/2

9/9

9/16

9/23

9/30

10/7

10/14

10/21

10/28

11/4

11/11

11/18

11/25

12/2

12/9

12/16

12/23

12/30

1/6

March

April

May

June

July

August

September

October

November

December

January


Inception Document











Enron Net Works, LLC
11
Project Phase: Inception

