
[image: image1.wmf]



MEMORANDUM

____________________________________________________________________________


To:
Ken Kaase (Houston Pipeline)
Date:
February 7, 2001
From:

Tom Burns
  

CC:

L. Reed



R. West



J. Logan

SUBJECT:  Proposed Schedule for Smart Pigging of A/S Pipeline Section

The following is the proposed schedule for the in-line inspection and associated cleaning and facility modifications of the A/S Pipeline from valve 812-1A to valve 816. Please note that this schedule is the best estimate at this time and will be heavily dependent upon the condition of cleanliness of the pipeline.

In an effort to keep interruption of service to the minimum, the project will be completed in two segments. The segment from Lomax to valve 816 will be modified, cleaned and inspected followed by the section from valve 812-1A to Lomax. All aspects of the project have been planned to reduce downtime.

Project Schedule

February 5-15
Receive, evaluate and award cleaning and inspection contracts.

February 19

Complete evaluation and award construction contract.

February 22

Commence shop fabrication and pre-shut down field construction activities.

March 19
Isolate and depressurize first section from Lomax to valve 816 and modify facilities.

March 22
Commence cleaning on first section. Upon completion, a sizing tool will be run to ensure clearance.

March 29
Purge and pressure first section.

March 30
Smart-pig inspection of first section.

March 31
Confirm successful completion of first section.

April 1
Isolate and depressurize second section from valve 812-1A to Lomax and modify facilities.

April 4
Commence cleaning on second section. Upon completion, a sizing tool will be run to ensure clearance.



April 11
Purge and pressure first section.

April 12

Smart-pig inspection of second section.

April 13

Confirm successful completion of project.

Please realize that this schedule is heavily dependent upon the amount of time required to clean the line. Since the cleaning will be done on a 24- hour basis, it could possibly take less time than proposed. Any changes on this schedule will be forwarded at that time.



