# Value Maximization Strategy

Two primary options are being evaluated for realization of the maximum value of the non-terminated power contracts currently being served by Enron.  Each of these options can be pursued on a contract-by-contract basis, for a group of contracts, or for the entire portfolio.

Option I:  Pursue cash payments for the outright assignment of an individual contract or a portfolio of contracts.

Option II:  Pursue back-to-back supply contracts such that Enron remains the counterparty to the original contract, with a long-term supply agreement provided by a third party energy provider.  Payments to the supplier would be secured through a lock-box payment structure where back-to-back suppliers would have first call on the lock-box funds and the estate would sweep the residual funds.

Lockbox

Power

Power

$

$

Enron

Enron

Counterparty

Supplier

Residual Cash

It is expected that we will approach potential bidders with both options, allowing us to pick the highest value proposition for the estate.

Auction Process:

An auction process will be established to ensure an open and transparent process that will yield the highest value for the estate.  The general process will be structured as follows:

Phase 1:     4 weeks

- Identify Contracts

- Legal Review of Contracts

- Construct Data Room

- Identify Universe of Prospective Bidders

- Draft Teaser & Confidentiality Agreement

Phase 2 :    1 week

  - Make Initial Contacts

  - Send Teaser

  - Execute Confidentiality Agreements

Phase 3 :    4 –8 weeks

- Contract Review by Prospective Bidders

- Submission of Bids

- Selection of Final Bid or Bids

- Execution of Definitive Documents

Phase 4 :    TBD

- Approval of Bankruptcy Court, FERC and Hart, Scott, Rodino

# Commercial and Legal Constraints/ Risks

The plan for extracting the value from the portfolio is impacted by several commercial and legal constraints and risks.  A process is underway to optimize the value within these constraints and risks.  A list of some of the potential constraints and risks can be summarized as follows:

- Counterparties not exercising their right to terminate because they do not have economic access to cash to pay the termination amount [Query whether this isn’t the same as the next one?]

- Termination of contracts by Enron due to default from a counterparty may force the counterparty into bankruptcy and jeopardize value recovery for the estate

- Contract value is exposed to significant market risk until terminated or assigned

- The illiquidity of the long-term power market and the attendant difficulty of executing hedges of several long-term positions within the portfolio could negatively affect contract value

- Pursuing assignment of contracts in exchange for cash may be difficult in current tight capital market environment

- Assignment of contracts will require appropriate approvals including Bankruptcy Court, FERC and possibly Hart, Scott, Rodino

- Legal constraints, including but not limited to limitation on assignment rights, necessity of obtaining waivers of confidentiality, uncertainties associated with ongoing governmental review of all contracts between Enron and federal government agencies, and legal challenges that have been or may be raised by counterparties with respect to contracts