TIMELINE

Red = State Proceedings

Green = FERC

Blue = HSR, NRC, OREFSC

Plum = SEC

|  | Action | Resonsible | participants |
| --- | --- | --- | --- |
| 8.29 (AM) | OPUC all hands meeting in Portland. | Enron | Ackerman, Lesh, Kaufman, Morgan, NNG Counsel. |
| 8.30 (PM) | WUTC all hands meeting in Portland. | Enron | Ackerman, Lesh, Kaufman, Morgan, NNG Counsel. |
| 9.4 | FERC all hands meeting in Portland. | Enron | Susan Ackerman, Pamela Lesh, Mike Morgan, Paul Kaufman, Julie Solomon (or Bill Hieronymous), Adam Wenner, NNG FERC Counsel … ? |
| 9.5 (AM) | SEC all hands meeting in Portland. | Enron | Ackerman, Lesh, Kaufman, Morgan, Wenner, Joann Rutkowski, NNG SEC Counsel |
| 9.6 | Meeting with Chairman Hemmingway and Comm’r Beyer | NNG | Mark Dodson, Peggy Fowler, Kaufman |
| 9.6 | Meeting with Comm’r Smith. | NNG | Dodson, Fowler, Ackerman, Lesh |
| 9.7 | PR all hands meeting in Portland. | Enron | Dodson, Greg Kantor, Kaufman, Mark Palmer …? |
| 9.8 | Meetings with Governor’s office, Sen. Doerfler, Simmons | NNG | Dodson, Fowler, Kaufman |
| 9.8 | Phone call to WUTC Chair Showalter, Comm’r Hemstad, Oshie | NNG | Dodson |
| 9.8 | Phone calls to OR Congressional Delegation | NNG | Dodson |
| 9.10 | Meeting with Sparling, Helman, Nyegaard | NNG | Ackerman, Lesh, Kaufman |
| 9.10 | Phone calls to Cannon and Pyron | NNG | Dodson and Fowler |
| 9.10 | Follow-up with Congressional Offices—Press packet |  |  |
| 9.10 | Phone call to Jenks | NNG | Ackerman and Lesh |
| 9.10 | Phone call to Lott | NNG | Ackerman |
| 9.10 | Phone call to Public Counsel | NNG | Ackerman and NNG WA Counsel |
| 9.10 | Phone call to Mayor Katz | NNG | Dodson and Fowler |
| 9.10 | Press-release after market closes | NNG/Enron/PGE | Kantor, Palmer |
| 9.10 | Phone call to FERC Chairman and Comm’r Brownell | Enron | Rick Shapiro and Dodson |
| 9.10 | Phone call to FERC Merger Staff | Enron | Wenner and NNG Counsel |
| 9.10 | Phone call to SEC Staff | Enron | Rutkowski and NNG Counsel |
| 9.11 | Follow-up meeting with ICNU, CUB, NWIGU | NNG | Ackerman, Lesh, Kaufman |
| 9.21 | Draft WUTC/OPUC testimony due | NNG and PGE | Ackerman, Lesh, Kaufman, Morgan and NNG Counsel |
| 9.21 | Draft NRC and OREFSC | NNG and PGE | Ackerman, Lesh, Kaufman |
| 10.3 | All hands FERC meeting in D.C. | Enron | Ackerman, Lesh, PGE Team, Kaufman, Solomon (or Hieronymous), Wenner, NNG FERC Counsel … ? |
| 10.4 | All hands SEC meeting in D.C. | Enron | Ackerman, Lesh, Kaufman, Wenner, Rutkowski, NNG SEC Counsel … ? |
| 10.5 | Revised draft of WUTC/OPUC testimony | NNG and PGE | Ackerman, Lesh, Kaufman, Morgan and NNG Counsel |
| 10.5 | File WUTC/OPUC testimony and applications | NNG and PGE | Morgan and NNG Counsel |
| 10.5 | Open Data Room | NNG and PGE |  |
| 10.8 | Draft FERC filing | Enron | Ackerman, Lesh, PGE Team, Kaufman, Solomon (or Hieronymous), Wenner, NNG FERC Counsel … ? |
| 10.11 | Pre-filing meeting with FERC Staff | Enron | Ackerman, PGE Representative, Kaufman, Solomon (or Hieronymous), Wenner, NNG FERC Counsel … |
| 10.12 | Draft SEC Filing | Enron | Ackerman, Lesh, Kaufman, Wenner, Rutkowski, NNG SEC Counsel … ? |
| 10.16 | Special Meeting of OPUC | NNG and PGE |  |
| 10.17 | FERC all hands meeting in D.C. | Enron | Ackerman, Lesh, PGE Team, Kaufman, Solomon (or Hieronymous), Wenner, NNG FERC Counsel … |
| 10.18 | SEC all hands meeting in D.C. | Enron | Ackerman, Lesh, Kaufman, Wenner, Rutkowski, NNG SEC Counsel … |
| 10.19 | File NRC and OREFSEC | NNG and PGE | Ackerman, Lesh, Kaufman |
| 10.22 | OPUC Prehearing Conference | NNG and PGE | Ackerman, Lesh, Kaufman, Morgan, NNG Counsel |
| 10.22 | File FERC | NNG, PGE, Enron | Wenner and NNG FERC Counsel |
| 10.23 | WUTC Prehearing Conference | NNG, Enron | Ackerman, NNG Counsel, Morgan |
| 10.26 | File SEC | NNG, PGE, Enron | Rutkowski and NNG SEC Counsel |
| 10.26 | Assumed date for FERC notice |  |  |
| 11.16 | Draft OPUC NNG/PGE Rebuttal |  |  |
| 11.23 | OPUC—NNG/PGE file Rebuttal | NNG, PGE | Ackerman, Lesh, Kaufman, Morgan, NNG Counsel |
| 11.30 | OPUC—NNG/PGE, Staff/Intervenors Surrebuttal |  |  |
| 11.9 | OPUC—Staff/Intervenors File Reply Testimony |  |  |
| 12.17 | Draft HSR Filing Due | NNG, Enron |  |
| 12.21 | FERC approximate date for comments/protests | NNG, Enron | Wenner, NNG FERC Counsel |
| 12.3 | OPUC Hearings | NNG, PGE | Ackerman, Lesh, Kaufman, Morgan, NNG Counsel |
| 1.07.02 | FERC approximate date for NNG/Enron/PGE response to comments. |  |  |
| 1.16.02 | HSR Filing | NNG, Enron |  |
| 2.16.02 | HSR approximate date for second request. |  |  |

Decision time frames

3.02	FERC Decision—assuming no hearing

7.02	OPUC Decision

8.02	HSR Completion

10.02	SEC Decision—2 months after final state decision