WEEKLY SUMMARY

#### OCTOBER 19-25, 2001

- Aconcagua (Deepwater) (Mississippi Canyon 305) (25% WI) – Mariner has accepted Nippon’s bid for 25% WI.  Expect to close November 1.

- Yosemite/King Kong (Deepwater) (Green Canyon 516) (50% WI) – All wells have been completed.  One field umbilical laid.  Flowline installation will begin in early November.  Main umbilical will be installed in December.  Expect to come on line by yearend.

- Falcon (Deepwater) (East Breaks 690) (50% WI) – Evaluating a lump sum proposal for project.  Meeting with pipeline companies to access interest in building and owning the host platform and export system.  Final AFE for subsea long lead items has been approved.

- Viosca Knoll 962 #1 (Swordfish) - Exploration Plan and Application for Permit to Drill approvals received 10/22/01. The Noble Homer Ferrington began tow to location in the early hours of 10/25/01. It is anticipated the well will require approximately 30 days to drill and evaluate.

- Shasta (Deepwater) (Green Canyon 136) (25% WI) – Drilled #8 well to total depth.  Discovered 122 net feet of gas, 10-15 bcf recoverable.  Waiting on Texaco/Chevron partner meeting to finalize development plan.

- Roaring Fork (Shelf - 450' WD) (South Timbalier 316) (Planned WI 40% BCP, 20% ACP) – The exploration well reach total depth this week and logged 80 net feet of high quality oil pay.  Reserves are estimated at 8.1 MMBOE.  A delineation well will be drilled immediately.  Expect to come on stream in early 2003.

CONFIDENTIAL

# MANAGEMENT COORDINATION MEETING OF OCTOBER 25, 2001

HELD AT 580 WESTLAKE PARK BLVD., SUITE 1300

## HOUSTON, TEXAS

# PRESENT

| C. K. Burgess R. R. Clark D. M. Clement W. F. Fisher D. S. Huber A. D. Keel S. D. Josey M. A. Wichterich M. C. van den Bold K. D. Zelikovitz cc: G. K. Harless cc: T. E. Young |  | cc: M. A. Altobelli cc: J. S. Hudson cc: D. cc: C. L. Loegering |  | cc: R. Bowen – ENAC cc: C. Fox – ENAC cc: J. Melendrez – ENAC cc: T. Proffitt – ENAC cc: J. Sherrick – EGEP cc: J. Thompson – ENAC cc: G. Whalley – EWS Note: ENAC – Enron North America Corp. EWS – Enron Wholesale Services EGEP – Enron Global E&P |
| --- | --- | --- | --- | --- |

- OPERATIONS

1.1	Development/Key Producing Fields

- Aconcagua (Deepwater) (Mississippi Canyon 305) (25% WI) – Mariner has accepted Nippon’s bid for 25% WI.  Expect to close November 1.

- Yosemite/King Kong (Deepwater) (Green Canyon 516) (50% WI) – All wells have been completed.  One field umbilical laid.  Flowline installation will begin in early November.  Main umbilical will be installed in December.  Expect to come on line by yearend.

- Falcon (Deepwater) (East Breaks 690) (50% WI) – Evaluating a lump sum proposal for project.  Meeting with pipeline companies to access interest in building and owning the host platform and export system.  Final AFE for subsea long lead items has been approved.

- Vioska Knoll 962 #1 (Swordfish) - Exploration Plan and Application for Permit to Drill approvals received 10/22/01. The Noble Homer Ferrington began tow to location in the early hours of 10/25/01. It is anticipated the well will require approximately 30 days to drill and evaluate.

- Shasta (Deepwater) (Green Canyon 136) (25% WI) – Drilled #8 well to total depth.  Discovered 122 net feet of gas, 10-15 bcf recoverable.  Waiting on Texaco/Chevron partner meeting to finalize development plan.

-

- EXPLORATION, DEVELOPMENT & LAND

  - Swordfish (Deepwater) (Viosca Knoll 917, 961, 962) (Planned WI 30% BCP, 15% ACP) - The Homer Ferrington is anticipated to arrive on location and commence drilling early next week.  Mariner has laid off a portion of its 50% BCP, 25% ACP working interest.  Burlington has committed to WI 50% BCP, 25% ACP and Samedan has committed to WI 20% BCP, 10% ACP.  BP will retain a WI 50% ACP.

  - Roaring Fork (Shelf - 450' WD) (South Timbalier 316) (Planned WI 40% BCP, 20% ACP) – The exploration well reach total depth this week and logged 80 net feet of high quality oil pay.  Reserves are estimated at 8.1 MMBOE.  A delineation well will be drilled immediately.  Expect to come on stream in early 2003.

  - Texaco/Chevron Farmout - East Breaks - Finalizing agreements.

  - Western Gulf of Mexico Lease Sale - OCS Sale 180 – To date, seven blocks have been awarded with the remaining six blocks still being evaluated by the MMS.  Mariner was the high bidder on 13 deepwater blocks.  Twelve of the bids were with Pioneer 50% and the remaining bid was 100% Mariner.

  - Purchase of Noble Interest – We are formulating an initial bid to purchase all Noble working interest in Falcon, Yosemite, Crater Lake, and Mighty Joe Young, as well as 2 undrilled exploration prospects.

3.	FINANCE & ADMINISTRATION

  - Revolver Debt - At October 25, 2001, we have $9.3 million in borrowings against our $80 million Bank of America-led revolving credit facility, and we had short-term investments of $0.1 million.

Our mid-year borrowing base redetermination is currently in progress.  We have requested no change to the $80 million borrowing base at this time.  We expect to confirm this base by November 1, 2001.

  - Accounts Payable Imaging System – We are beginning implementation of a system to image and further automate our accounts payable processing system.  System is expected to be operational in the fourth quarter of 2001.

3.3	Budget – Budget timetable has been delayed one week with first due date occurring on November 7, 2001.

3.	FINANCE & ADMINISTRATION (CONTINUED)

  - Insurance – Working with Burlington on Monet/Hells Canyon claim.  We expect a $600K partial payment by yearend.

We have decided to change dental provider from Metlift to Fortis.  Expected change over date is December 1, 2001.

3.5	Document Retention Policy – Distributed document retention policy and currenting reviewing a plan for implementation.

4.	LEGAL

  - Aconcagua – Board approved sale on October 17, 2001.  Nippon currently conducting its due diligence.  Closing/funding expected to occur December 1.  Press release concerning purchase and sale agreement to be issued shortly.

  - Falcon – Revising purchase order for the purchase of the umbilical and 10” pipeline (long-lead items) from Coflexip.  Working with the Falcon team and Pioneer on a contract with Coflexip for the subsea pipeline system.

5.	GAS & OIL SALES

  - West Texas Intermediate posted prices:

WTI moved from $19.25 - $20.25 effective October 11.

WTI moved from $20.25 - $19.25 effective October 12.

WTI moved from $19.25 - $19.00 effective October 15.

WTI moved from $19.00 - $18.75 effective October 16.

WTI moved from $18.75 - $18.50 effective October 17.

WTI moved from $18.50 - $18.00 effective October 18.

WTI moved from $18.00 - $18.50 effective October 19.

WTI moved from $18.50 - $18.75 effective October 23.

WTI moved from $18.75 - $19.25 effective October 24.

  - NYMEX Gas.  The 12 month forward Nymex price as of October 24th is $3.23 per MMBTU; quotes by month are as follows:

| NOV. | DEC. | JAN. | FEB. | MAR. | APR. |
| --- | --- | --- | --- | --- | --- |
| $2.98 | $3.17 | $3.33 | $3.32 | $3.26 | $3.15 |

6.	PRODUCTION

Mariner’s oil and gas prices (restated net of transportation) and production are as follows:

|  | March Actual | April Actual |  |  | May Actual | June Actual | July Actual |  |  | August Actual |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ##### Monthly Pre-Hedge Prices: |  |  |  |  |  |  |  |  |  |  |
| Oil ($/bbl) | $22.54 |  | $23.67 | $25.04 |  | $23.97 |  | $23.90 | $23.69 |  |
| Gas ($/mcf) | $5.28 |  | $5.61 | $5.09 |  | $4.02 |  | $3.56 | $3.35 |  |
| Year-to-Date Weighted Average Gas Prices ($/MCF): |  |  |  |  |  |  |  |  |  |  |
| W/O Hedge | $7.31 |  | $6.86 | $6.48 |  | $6.15 |  | $5.84 | $5.58 |  |
| With Hedge | $5.40 |  | $5.22 | $5.07 |  | $4.88 |  | $4.74 | $4.61 |  |
| Production: |  |  |  |  |  |  |  |  |  |  |
| Oil (bbl/d) | 8,409 |  | 8,470 | 8,246 |  | 7,887 |  | 7,325 | 7,390 |  |
| Gas (mmcf/d) | 66.9 |  | 67.0 | 66.0 |  | 50.1 |  | 48.4 | 47.1 |  |

*Gas production decline in June reflects watering out of Apia field.