DRAFT (8/29/00)

Software Implementation Release for

ADS, BBS, MDAS, SI/SA

INSTALLATION SCHEDULE

SCHEDULE OF EVENTS:

| # | Time | Task | Responsibility |
| --- | --- | --- | --- |
| Monday, August 28, 2000 |  |  |  |
|  |  | - Alert Market Participants' metering contacts that STAR will be unavailable during the upgrade on 8/29/00. | - MDAS System Admin |
| Tuesday, August 29, 2000 |  |  |  |
|  | - By 1300 | - Send Installation Schedule to Market Participants, TSWG and Settlement Contacts | - CRCommunications |
|  | - 1200 - COB | - Begin configuring STAR metering systems for trade date 8/31. | - MDAS Team |
| By COB Wednesday, August 30, 2000 |  |  |  |
|  | 1330 | Conference Call to discuss Implementation | 10-Min Team/SCs |
|  |  | Complete deployment of Final ADS Client to MP’s. Verify connectivity and stability. | ADS Team |
|  | - by COB | - Complete configuration of STAR metering systems for trade date 8/31. | - MDAS Team |
| Thursday, August 31, 2000 |  |  |  |
|  | - by COB | - Clear up all MV90 communication problems with meters | - MDAS Technical Analyst |
|  | - by COB | - Send all available hourly data for 8/30/00 to STAR | - MDAS Technical Analyst |
|  | - by COB | - Remind MP's to manually read all appropriate meters on 9/1/00 | - MDAS Technical Analyst |
|  | 2200 -- 2245 | Run Markets for HE 0100 AND 0200 Close Real – Time Market for 2400 Put Real-Time Market for HE 0100 on HOLD. | HA GRC Market Ops |
|  | 2245 – 2300 | ## SI Unavailable to Market |  |
|  | 2245 | Download all supplemental energy intertie schedules for HE 0100 and 0200 (minimum – the rest of hours needs to be done after on-line) and convert to new format. Default all PRE_DISP_FLG to “YES”. | Market Ops |
|  | 2245 – 2300 | Apply upgraded SI Software to Production System | Market Ops |
|  | 2245 – 2300 | Upload all supplemental energy intertie schedules for HE 0100 and 0200. | Market Ops |
|  | 2300 | SI Available to Market |  |
|  | 2300 | Remind SCs to submit Intertie supplemental bids in new format (w/ PRE_DISP_FLG) |  |
|  | 2315 | Close Supplemental Market for HE 0100 | Market Ops |
|  | 2400 | Begin dispatching real-time markets using new 10-minute BEEP for HE 01 9/1/2000 | RT GRC |
| # Friday, September 1 |  |  |  |
|  |  | - Upgrade MDAS Online DB and Code | - Structure Consulting - Coordinated by MDAS System Admin |
| # Tuesday, September 5, 2000 |  |  |  |
|  | - by COB | - Import manually read files from SC's into MV90. Totalize data and send to STAR | - MDAS Technical Analyst |
|  | - by COB | - Change Summary Maps in MV90 to 10 Minute intervals (except for those to remain hourly and the outstanding ID's) | - MDAS System Admin |
| - Wednesday, September 6, 2000 |  |  |  |
|  | - by COB | - Start automatic 10 minute totalization in MV90 | - MDAS Team |
|  | - by COB | - Start automatic transfer of 10 minute data to STAR | - MDAS Team |
| # September 1 + 25 days |  |  |  |
|  | TBD | Run a “trial push” of a sample trade days with 10-minute energy calcs to Settlements. Run settlements batch for sample trade days. | DBA Market Ops Settlements |
| Monday, October 9, 2000 |  |  |  |
|  | - by COB | - Notify Market Participants that T+45 SQMD will be due on Monday, October 16, 2000 | - MDAS System Admin |
| Monday, October 16, 2000 |  |  |  |
|  |  | - SQMD data due for trade date 9/1/2000. | # Market Participants |
| # September 1 + 50 days |  |  |  |
|  | 1300 | Push September 1 trade day to Settlements | DBA |
|  |  | Run Preliminary Settlements for September 1 | Settlements |
| # Septemeber 1 + ? days |  |  |  |
|  |  | Preliminary Settlements for Septmeber 1 Available |  |