Timeline for Permitting Napoleonville Storage No.1 for Hydrocarbon Storage

| Notice of Intent | Required to be published at least 15 days prior to filing permit application, see Instructions to UIC-2 HSW at p.4 | Published in The Advocate on May 18, 2001 |
| --- | --- | --- |
| Permit Application | Filed at least 15 days after Notice of Intent | Pre-filed on May __, 2001. Deemed filed on June 1, 2001 |
| Letter advising (1) Application complete and (2) hearing date |  | Target date: June 4, 2001 |
| Public Hearing | On at least 10 days Legal Notice to Interested Parties. Regular hearings conducted on 2nd and 4th Thursday of each month. Special hearing may be conducted if auditorium available. | Target date: June 18 or 20, or Sometime the week of June 25 |
| Commissioner’s Findings of Fact | Issued after public hearing | Target date: 10 days after hearing |
| Commissioner’s Report to Natural Resources Committee of House and Senate | Required to submit to Natural Resources Committee for Comment. Comments/ recommendations are not binding on Commission. | Target date: 11 days after hearing |
| Natural Resources Committee’s Recommendations | By statute, Committee has only 15 days from receipt of Commissioner’s proposed findings of fact to meet and make recommendations. Statute requires a joint meeting of the House and Senate Natural Resources Committee. | Target date: 26 days after hearing |
| Final Order | Depends on availability of Commissioner | Target Date: 31 days after hearing |