SCHEDULE 5.04

- AUTHORIZATIONS FOR BUSINESSES UNDER DEVELOPMENT

1.	GCO received Gas importation permit on December 1, 1999.

2.	GCO received IPP license on June 6, 2000.

3.	GCO will obtain Previous Installation License by August 15, 2000.

4.	GCO will obtain ONS authorization for grid connection by September 14,

2000.

5.	GCO will receive Installation License by November 1, 2000.

6.	ECE will obtain MAE agreement by December 2002.

7.	GCO will obtain municipality construction authorization, fire department,

occupational, Health Secretarial, and plant operation license by December

2001.

8.	On April 15, 2000, we signed a GSA between TBSII and ECE and it was

submitted to ANP on May 2, 2000.