Dabhol Power Comany / Oman LNG

Implementation Procedures

Chapter 3

Annual Programme

and

Specific Lifting Schedule

(this chapter: 14 pages)

| # Procedures | Remarks |
| --- | --- |
| §1. Programming Information Exchange - DPC will inform OLNG of its intentions and requests for the Annual Programme (AP). - The estimated period to conduct maintenance inspection, and/or refurbishment for the LNG Ship and DPC's liquefied Natural Gas receiving facilities. (Attachment 1) - DPC’s intention to exercise its right of: (Attachment 2) - DPC Downward Flexibility Cargo pursuant to SPA 5.5.1 - Make-Up Cargoes pursuant to SPA 5.4.1 - Make-Good Cargoes pursuant to SPA 5.5.3 - Force Majeure Restoration Cargoes pursuant to SPA 14.5 - DPC Upward Flexibility Cargo pursuant to SPA 5.5.4 - Expectations of Carry Cargo from the preceding Contract Year pursuant to SPA 5.3.3 - Estimated Attribution - Any quantities of LNG which DPC is aware that it will not exercise its right to lift, whether for reasons of Force Majeure or otherwise. (Attachment 2) - DPC's proposed loading pattern in number of cargoes per month for each month (noting the requirements of SPA 8.2.3) and Estimated Average Filling Ratio. (Attachment 3) - Any proposal that DPC may have to use the LNG Ship for any liquefied Natural Gas transportation other than in respect of the SPA, provided that such proposal should not prejudice DPC's ability to fulfil its obligations to lift LNG under the SPA. (Attachment 4) | DPC ->OLNG. By fax and letter No less than 120 days before the start of each Contract Year SPA 8.1.1 and 8.2.3 |

| # Procedures | Remarks |
| --- | --- |
| - OLNG will inform DPC of its intentions and confirmations. - The estimated period to conduct maintenance, inspection and/or refurbishment for OLNG Facilities, the Upstream Facilities, and tug boats. (Attachment 5) - Estimated Density, Gross Heating Value and Cargo Conversion Factor of the cargoes to be delivered. (Attachment 5) - OLNG’s information after applying the Club Rules: (Attachment 6) - OLNG Downward Flexibility Cargo pursuant to SPA 5.6 - Make-Up Cargoes - Make-Good Cargoes - Force Majeure Restoration Cargoes - DPC Upward Flexibility Cargo - DPC Downward Flexibility Cargo - Expectations of Carry Cargo from the preceding Contract Year - Estimated Attribution - Proposed Annual Programme (Attachment 7) | OLNG -> DPC By fax and letter No less than 90 days before to the start of each Contract Year SPA 8.1.2 and 8.2.3 |
| - During the time of programming information exchange, OLNG and DPCwill communicate with each other and hold meetings if necessary. When there are changes in the information which had already been provided, OLNG and DPC will in each case promptly provide such information. | OLNG <-> DPC By fax and letter |

| # Procedures | Remarks |
| --- | --- |
| §2. AP Meeting and Agreement of AP - OLNG and DPC will discuss on the AP. The AP shall include the following information for each cargo: - Cargo number - The name of the LNG Ship - Estimated date of arrival at and departure from the Loading Port - Name and estimated date of arrival at and departure from the Unloading Port - Round Trip - Cooldown requirement for the LNG Ship The AP shall also include the scheduled maintenance and/or shutdown periods for the LNG Ship, DPCs liquefied Natural Gas receiving facilities and OLNG Facilities (SPA 8.2.4). (Attachment 7) OLNG shall furnish DPC with a statement of the AACC. (Attachment 8) | OLNG <-> DPC By fax and letter SPA 8.2.1, 8.2.3 and 8.2.4 |
| - OLNG and DPC shall consult in good faith and agree on the AP. OLNG shall issue the AP. (Attachment 7) | OLNG -> DPC By fax and letter No less than 30 days before the start of the Contract Year SPA 8.2.2 |
| - When there are changes in the information which had already been provided, OLNG and DPC will in each case promptly provide latest information. | OLNG <-> DPC By fax and letter SPA 8.3 |

| # Procedures | Remarks |
| --- | --- |
| §3. Changes to Annual Programme/Specific Lifting Schedule - OLNG and DPC will provide each other with the latest information relating to the AP. When there needs to be changes in the information which had already been provided under §1 and §2, OLNG and DPC will in each case promptly provide latest information. | OLNG <-> DPC By fax and letter SPA 8.3 |
| - OLNG and DPC shall discuss to examine whether the AP can be revised as soon as possible after notice have been received. | OLNG <-> DPC By fax and letter SPA 8.3 |
| - OLNG shall provide DPC with a Specific Lifting Schedule (SLS) showing three Month forward plan of lifting based on the current AP. If any change to the AP is agreed pursuant to SPA 8.3, OLNG shall as soon as practicable provide DPC with an update of the current SLS based on the current AP. (Attachment 9) | OLNG ->DPC By fax and letter Not later than the 15 Day of each month SPA 8.5 |

Attachment 1

###### Date:	DD/MM/YYYY

###### To:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

###### Sultanate of Oman

Facsimile Number:

###### Attention:	XXXXXX, [Name and Position]

###### From:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

Andheri ( East), Mumbai 400-090, India

###### Reference Number:

### Re: DPC’s Information

#### Maintenance / Inspection / Refurbishment Schedule of the LNG Ship:

| LNG Ship Name | Item* | Schedule | Remarks |
| --- | --- | --- | --- |

*: E.g. Dry-dock, Annual Survey, Delivery

#### Maintenance / Inspection / Refurbishment Schedule of DPCReceiving Facilities:

| #### Terminal Name | #### Facility Name | #### Schedule | #### Remarks |
| --- | --- | --- | --- |

[Signature]

[Name]

[Position]

Attachment 2

###### Date:	DD/MM/YYYY

###### To:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

###### Sultanate of Oman

Facsimile Number:

###### Attention:	XXXXXX, [Name and Position]

###### From:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

Andheri ( East), Mumbai 400-090, India

###### Reference Number:

### Re: DPC’s Information

### DPC’s Intention to Exercise Its Rights:

| #### DPC’s Rights | Number of Cargoes | #### Remarks |
| --- | --- | --- |
| Make-Up Cargoes |  |  |
| DPC Upward Flexibility Cargo |  |  |
| Make-Good Cargoes |  |  |
| Force Majeure Restoration Cargoes |  |  |
| Carry Cargo from the preceding Contract Year |  |  |
| DPC Downward Flexibility Cargo |  |  |

Estimated Attribution:

| #### Quantities | Number of Cargoes | #### Remarks |
| --- | --- | --- |
| (a) Annual Contract Cargoes |  |  |
| + Carry Cargo from the preceding Contract Year |  |  |
| + DPC Upward Flexibility Cargo |  |  |
| - DPC Downward Flexibility Cargo |  |  |
| (b) Make-Up Cargoes |  |  |
| (c) Make-Good Cargoes |  |  |
| (d) Force Majeure Restoration Cargoes |  |  |

#### Any Quantities of LNG under SPA 8.1.1 (e):

| # Quantities | Reasons |
| --- | --- |

[Signature]

[Name]

[Position]

Attachment 3

###### Date:	DD/MM/YYYY

###### To:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

###### Sultanate of Oman

Facsimile Number:

###### Attention:	XXXXXX, [Name and Position]

###### From:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

Andheri ( East), Mumbai 400-090, India

###### Reference Number:

### Re: DPC’s Information

#### DPC’s Proposed Loading Pattern:

| Month / Quarter | Number of Cargoes | Remarks |
| --- | --- | --- |
| January |  |  |
| February |  |  |
| March |  |  |
| 1st Quarter |  |  |
| April |  |  |
| May |  |  |
| June |  |  |
| 2nd Quarter |  |  |
| July |  |  |
| August |  |  |
| September |  |  |
| 3rd Quarter |  |  |
| October |  |  |
| November |  |  |
| December |  |  |
| 4th Quarter |  |  |
| Total |  |  |

Estimated Average Filling Ratio: [XX.X] %

Estimated Volume Per Cargo: [XXXXX] m3/cargo

[Signature]

[Name]

[Position]

Attachment 4

###### Date:	DD/MM/YYYY

###### To:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

###### Sultanate of Oman

Facsimile Number:

###### Attention:	XXXXXX, [Name and Position]

###### From:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

Andheri ( East), Mumbai 400-090, India

###### Reference Number:

### Re: DPC’s Information

#### Use of the LNG Ship other than for the SPA:

| #### Period | #### Proposal / Notes |
| --- | --- |

[Signature]

[Name]

[Position]

Attachment 5

###### Date:	DD/MM/YYYY

###### To:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

###### Andheri ( East), Mumbai 400-090, India

Facsimile Number:	+91 22288 1793/4

###### Attention:	 president [Name and Position]

###### From:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

Sultanate of Oman

###### Reference Number:

### Re: OLNG’s Information

#### Maintenance / Inspection / Refurbishment Schedule of OLNG Facilities, Upstream Facilities and tug boats:

| ##### Facility Name # Tug boats | Item* | Schedule | Remarks |
| --- | --- | --- | --- |

*: e.g. Gas Field, Pipeline, Production Train, Berth, Port

#### Estimated Density / GHV / C.C.F. of the Cargoes

| Estimated Density | [ ] kg/m3 |
| --- | --- |
| Estimated GHV | [ ] btu/scf |
| Estimated C.C.F. | [ ] Mt/cargo |

[           ] m3/cargo

[Signature]

[Name]

[Position]

Attachment 6

###### Date:	DD/MM/YYYY

###### To:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

###### Andheri ( East), Mumbai 400-090, India

Facsimile Number:

###### Attention:	 [Name and Position]

###### From:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

Sultanate of Oman

###### Reference Number:

### Re: OLNG’s Information

#### OLNG’s Intention and Confirmation to Supply LNG toDPC:

| #### Quantities | Number of Cargoes | #### Remarks |
| --- | --- | --- |
| Make-Up Cargoes |  |  |
| DPCUpward Flexibility Cargo |  |  |
| Make-Good Cargoes |  |  |
| Force Majeure Restoration Cargoes |  |  |
| Carry Cargo from the preceding Contract Year |  |  |
| DPC Downward Flexibility Cargo |  |  |
| OLNG Downward Flexibility Cargo |  |  |

Estimated Attribution:

| #### Quantities | Number of Cargoes | #### Remarks |
| --- | --- | --- |
| (a) Annual Contract Cargoes |  |  |
| + Carry Cargo from the preceding Contract Year |  |  |
| + DPC Upward Flexibility |  |  |
| - DPC Downward Flexibility Cargo |  |  |
| - OLNG Downward Flexibility Cargo |  |  |
| (b) Make-Up Cargoes |  |  |
| (c) Make-Good Cargoes |  |  |
| (d) Force Majeure Restoration Cargoes |  |  |

[Signature]

[Name]

[Position]

Attachment 7

###### Date:	DD/MM/YYYY

###### To:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

###### Andheri ( East), Mumbai 400-090, India

Facsimile Number:

###### Attention:	 [Name and Position]

###### From:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

Sultanate of Oman

###### Reference Number:

### Re: Proposed Annual Programme for Contract Year 20XX

| Cargo No. | Ship Name | Mina Qalhat |  | Unloading Port |  |  | Round Trip (days) | Cooldown1) | Remarks2) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ETA | ETD | Terminal | ETA | ETD |  |  |  |

- The estimated quantity of LNG required for cooling will be noticed immediately after the LNG Ship’s departure from the drydocking/repair port en route to the Loading Port

- Remarks e.g.: a. Information on drydocking      b. Maintenance schedule of related facilities

## Notice of Maintenance and/ or Shutdown Periods

|  | Periods | Remarks |
| --- | --- | --- |
| LNG Ship |  |  |
| Buyers LNG Receiving Facilities |  |  |
| OLNG’s Facilities |  |  |

[Signature]

[Name]

[Position]

Attachment 8

###### Date:	DD/MM/YYYY

###### To:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

###### Andheri ( East), Mumbai 400-090, India

Facsimile Number:

###### Attention:	 [Name and Position]

###### From:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

Sultanate of Oman

###### Reference Number:

### Re: Statement of AACC for Contract Year 20XX

| #### Quantities | Number of Cargoes | #### Remarks |
| --- | --- | --- |
| (a) Annual Contract Cargoes (ACC) |  |  |
| (b) DPC Upward Flexibility Cargo |  |  |
| (c) Make-Good Cargoes |  |  |
| (d) Force Majeure Restoration Cargoes |  |  |
| (e) Carry Cargo from the preceding Contract Year |  |  |
| (f) DPC Downward Flexibility Cargo |  |  |
| (g) OLNG Downward Flexibility Cargo |  |  |
| ###### Adjusted Annual Contract Cargoes (AACC) |  |  |
| ###### Make-Up Cargoes |  |  |

[Signature]

[Name]

[Position]

Attachment 9

###### Date:	DD/MM/YYYY

###### To:	 Dabhol Power Company611/613 Midas6th Floor, Sahar Plaza ComplexMathurdas Vassanji Road

###### Andheri ( East), Mumbai 400-090, India

Facsimile Number:

###### Attention:	 [Name and Position]

###### From:	Oman LNG L.L.C.

First Floor,

Ominvest Building,

CBD Area, Ruwi,

Sultanate of Oman

###### Reference Number:

### Re: Specific Lifting Schedule for MM, 20XX

| Cargo No. | Ship Name | Mina Qalhat |  | Unloading Port |  |  | Round Trip (days) | Cooldown | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ETA | ETD | Terminal | ETA | ETD |  |  |  |

Remarks will be made for change to the original AP schedule as shown on each issue of the Specific Lifting Schedule

Remarks sign for DPC’s request: (+)

Remarks sign for OLNG’s request: (++)

[Signature]

[Name]

[Position]