WEEKLY SUMMARY

#### MAY 4-17, 2001

- Hells Canyon Monet (Mississippi Canyon 561) (Burlington-operated) (16.7% WI) – Test well currently at 8953’ MD running the BOP’s, preparing to drill out.  Expect to reach TD in early/mid-June.

2.	Crater Lake (Mississippi Canyon 322/366) (40% WI) – Test well on this low risk exploratory prospect is expected to spud next week.  Most likely reserves are 40 BCF and the operator (Walters) expects to bring the field online in the fourth quarter 2001 if successful.

3.	King Kong (Deepwater) (Green Canyon 472) (50% WI) - Mariner received the Homer Ferrington rig on May 15 and the rig is currently under tow to the location.  The Millennium Eddy has rotated over the past week such that the Northern face is directly over the King Kong area and causing 2+ knots loop currents per buoy reports.  Pending loop current considerations, we hope to be setting anchors early next week.

- Yosemite (Deepwater) (Green Canyon 516 #1) ( 45% WI) – Exploratory prospect adjacent to King Kong with most likely reserves of 117 BCF and NPV10 addition of $65 million net to Mariner on success.  Transocean Millennium expected on location in late May.

- Argo Prospect (Deepwater Prospect – Western Gulf) – Negotiating a trade with Pioneer on the Argo Prospect (Mariner’s Mockingbird Prospect) in East Breaks 981 and Alaminos Canyon 13.  Pending agreement on the trade, Mariner would act as contract operator for the test well which could spud in late June.

Prospect is a large, continuous amplitude in the Glob alt interval with a mean reserve potential of 140 BCFG.  Development is projected to be two subsea wells tied back to an F&G semi.  Economic chance of success is 50%, risked IRR is 30% and risked VAI is 1.55 to 1.  If successful, the IRR is 37%, VAI is 1.73 to 1 and the full cycle finding cost is 6.72/BOE.

6.	Texaco Farmout – Expect response from Texaco early next week on “drill to earn deal” covering 8-16 deepwater blocks in the Western Gulf.

CONFIDENTIAL

# MANAGEMENT COORDINATION MEETING OF MAY 17, 2001

HELD AT 580 WESTLAKE PARK BLVD., SUITE 1300

## HOUSTON, TEXAS

# PRESENT

| R. E. Henderson W. H. Hodge D. S. Huber L. V. McGuire F. A. Pici - W. Strickler R. W. Webb T. E. Young cc: R. R. Clark cc: G. K. Harless cc: K. D. Zelikovitz |  | cc: M. A. Altobelli cc: C. K. Burgess cc: D. M. Clement cc: D. L. Faulkinberry cc: J. S. Hudson cc: D. cc: C. L. Loegering cc: J. L. Sheets cc: B. Watsky cc: M. A. Wichterich |  | cc: R. Bowen – ENAC cc: J. Donahue – EBS cc: C. Fox – ENAC cc: J. Melendrez – ENAC cc: T. Detmering – ENAC cc: T. Proffitt – ENAC cc: J. Sherrick – EGEP Note: ENAC – Enron North America Corp. EGEP – Enron Global E&P EBS – Enron Broadband Services |
| --- | --- | --- | --- | --- |

- OPERATIONS

  - Development/Key Producing Fields

- Aconcagua (Deepwater) (Mississippi Canyon 305) (25% WI) – Plan to begin marketing ½ of Mariner’s interest prior to mid-year.

- Pluto (Deepwater) (Mississippi Canyon 674/718) (Mariner 51% WI) –

The current flow rate is 41.7 MMCFD and 5,400 BCPD.  Flowline hydraulic performance improves following small methanol soak treatments during brief shut-in periods.

- Black Stone Minerals B-1 S/T #2 (Onshore) (40% WI) – A static bottom hole pressure survey was obtained from the well after it had been shut-in and stabilized. The BHP results verify the zone of crossflow influx has been isolated and the flow from the swabbing operations is from the EY-1 sand.  Plans are to begin flowing the well for a week or two and see if it will clean up and flow gas.

- King Kong (Deepwater) (Green Canyon 472) (50% WI) - Mariner received the Homer Ferrington rig on May 15 and the rig is currently under tow to the location.  The Millennium Eddy has rotated over the past week such that the Northern face is directly over the King Kong area and causing 2+ knots loop currents per buoy reports.  Pending loop current considerations, we hope to be setting anchors early next week.

1.	OPERATIONS (continued)

  - Development/Key Producing Fields (continued)

- Yosemite (Deepwater) (Green Canyon 516 #1) ( 45% WI) – Exploratory prospect adjacent to King Kong with most likely reserves of 117 BCF and NPV10 addition of $65 million net to Mariner on success.  Transocean Millennium expected on location in late May.

2.	EXPLORATION & LAND

  - Crater Lake (Mississippi Canyon 322/366) (40% WI) – Test well on this low risk exploratory prospect is expected to spud next week.  Most likely reserves are 40 BCF and the operator (Walters) expects to bring the field online in the fourth quarter 2001 if successful.

  - Hells Canyon Monet (Mississippi Canyon 561) (Burlington-operated) (16.7% WI) – Test well currently at 8953’ MD running the BOP’s, preparing to drill out.  Expect to reach TD in early/mid-June.

  - Eastern Gulf of Mexico Sale 181 (December 2001) – Negotiating a joint bidding partnership with Pioneer.  Expect to have an agreement in place by the end of May.  Soliciting a third company to join the partnership.

  - East Breaks AMI – Completing an AMI agreement for western East Breaks to encompass the prospective area around the Falcon discovery.  Expect to finalize by the end of May.

  - Texaco Farmout – Expect response from Texaco early next week on “drill to earn deal” covering 8-16 deepwater blocks in the Western Gulf.

  - Argo Prospect (Deepwater Prospect – Western Gulf) – Negotiating a trade with Pioneer on the Argo Prospect (Mariner’s Mockingbird Prospect) in East Breaks 981 and Alaminos Canyon 13.  Pending agreement on the trade, Mariner would act as contract operator for the test well which could spud in late June.

Prospect is a large, continuous amplitude in the Glob alt interval with a mean reserve potential of 140 BCFG.  Development is projected to be two subsea wells tied back to an F&G semi.  Economic chance of success is 50%, risked IRR is 30% and risked VAI is 1.55 to 1.  If successful, the IRR is 37%, VAI is 1.73 to 1 and the full cycle finding cost is 6.72/BOE.

3.	FINANCE

3.1	Revolver Debt - At May 16, 2001, the balance on the $70 million Bank of America-led revolving credit facility was zero due to the receipt of proceeds from the sale of Devils Tower, and we had a short-term cash investment of $22.7 million.  The bank group has approved the borrowing base increase from $70 million to $80 million.

  - Project Finance - Discussions continue with Enron North America, Bank One, Duke and Mitsubishi for the King Kong infrastructure financing. We are also studying the use of the MARAD Title XI guarantee program to finance a low cost floating production system (Mariner-1).

  - First Quarter 2001 Results, News Release and 10-Q – News release was issued May 10 and 10-Q filing was made with SEC on May 15.

  - Capital Markets – Meetings have been held with three investment bankers in the last week to discuss the current status of debt and equity capital markets.  More meetings are being scheduled for next week.

4.	LEGAL

  - Canyon Express Project  - Meeting occurring this week and next week to finalize Construction Management Agreement and Joint Operating Agreement.

  - Dulcimer Litigation – Depositions of Mariner representatives completed May 3 and 4.  The trial has been scheduled for late March 2002.

  - Seismic Acquisitions – Recently received counterproposal from TGS -- currently evaluating.

  - “Centurian” (portable infrastructure project f/k/a the “F&G”) Project Finance – Signed retainer agreement with John Graykowski.  Currently working with Fulbright to identify relevant loan covenants.

  - Farmin of Drilling Slot(s) – Re: The Transocean Millenium Deepwater Drillship – Will execute agreements with Burlington Resources et al to take an assignment of one or more drilling slots.  First slot will be for the drilling of the Yosemite #1 Well.

5.	GAS & OIL SALES

  - West Texas Intermediate posted prices:

WTI moved from $24.75 - $25.25 effective May 3.

WTI moved from $25.25 - $24.50 effective May 7.

WTI moved from $24.50 - $24.25 effective May 8.

WTI moved from $24.25 - $25.00 effective May 9.

WTI moved from $25.00 - $25.25 effective May 10.

WTI moved from $25.25 - $25.50 effective May 14.

WTI moved from $25.50 - $25.75 effective May 15.

  - NYMEX Gas.  The 12 month forward Nymex price as of May 16 is $4.54 per MMBTU; quotes by month are as follows:

| # JUNE | # JULY | AUG. | SEPT. | OCT. | NOV. |
| --- | --- | --- | --- | --- | --- |
| $4.30 | $4.40 | $4.50 | $4.50 | $4.51 | $4.69 |

- ADMINISTRATION

6.1	Insurance – Currently in the market for insurance renewals.  Working with brokers and underwriters.  Renewal date is June 1.

Adjustors have received all documents and information to finalize the Pluto tree builders risk claims.  Expect final summary of claim to submit to underwriters next week.  Continue to gather invoices on umbilical claim.

Met with adjustors to discuss Falcon underground blow-out claim.  Gathering required information to forward to adjustors.  Another meeting scheduled on May 21.

7.	PRODUCTION

Mariner’s oil and gas prices (restated net of transportation) and production are as follows:

|  | Nov. Actual | Dec. Actual |  |  | Jan. Actual | Feb. Actual | March Actual |  |  | April Fcst. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ##### Monthly Pre-Hedge Prices: |  |  |  |  |  |  |  |  |  |  |
| Oil ($/bbl) | $27.85 |  | $25.65 | $25.61 |  | $25.30 |  | $21.86 | $23.89 |  |
| Gas ($/mcf) | $4.74 |  | $6.46 | $10.38 |  | $6.59 |  | $4.93 | $5.73 |  |
| Year-to-Date Weighted Average Gas Prices ($/MCF): |  |  |  |  |  |  |  |  |  |  |
| W/O Hedge | $3.73 |  | $3.93 | $10.38 |  | $8.50 |  | $7.15 | $6.78 |  |
| With Hedge | $2.95 |  | $3.11 | $6.60 |  | $5.84 |  | $5.22 | $5.12 |  |
| Production: |  |  |  |  |  |  |  |  |  |  |
| Oil (bbl/d) | 8,134 |  | 8,596 | 8,941 |  | 8,125 |  | 8,133 | 8,100 |  |
| Gas (mmcf/d) | 63.6 |  | 60.3 | 56.9 |  | 64.2 |  | 67.1 | 64.7 |  |