Summary of Contract Terms

1 General Electric Frame 7EA Combustion Gas Turbine

Delivery Point:	Shall mean either (i) in the case of the turbine the Seller’s manufacturing facility in Greenville, South Carolina; (ii) in the case of material ship direct items, Vendor’s manufacturing facilities; or (iii) in the case of the generator, Purchaser designated U.S. Port of Import, as applicable.

Optional Delivery Point:	In the event Purchaser elects by Change Order to have a Unit delivered to a Site.

Delivery Date(s):	Gas Turbine and Generator	March 11, 2001

Remaining Major Components	March 31, 2001

Payment terms:	ENA shall assume the obligations of all remaining payments related to the turbine purchase price (including change orders), except those obligations arising after the closing date of the proposed transaction.

Retention Letter of Credit:	In the amount of $965,855, to be held by purchaser until final acceptance of the unit.  GE may replace with letter of credit in like amount.

Correction of Equipment:	GE is responsible for replacing or correcting any defective work or conditions prior to acceptance of the Unit.  GE must also correct punchlist items to Purchaser’s satisfaction not later than the Primary Warranty Period, or Purchaser may draw on Retention Letter of credit.

Document Liquidated

Damages	1-30 days late	$500.00/day

31-90 days late	$1,000.00/day

91+ days late	$5,000.00/day

Delivery of Final

O&M Instructions

Liquidated Damages	1-30 days late	$500.00/day

31-90 days late	$1,000.00/day

91+ days late	$5,000.00/day

if not delivered within 90 days after site delivery date of the Unit.

Delivery Liquidated Damages	day 1+		$14,500.00/day

Takeover Liquidated Damages	day 1+ 		$14,500 per day

Specific Performance

Near Source Sound Level

Guarantee	Near field average A-weighted sound pressure levels for each Unit < 85dB(A) (referenced to 20 micropascals) when measured at 1.5 meters above any working elevation and 1 meter from the surface.

Specific Performance

Exhaust Emissions Guarantee	Category		Load		Units of Measure

100%

NOx			9		ppmvd @ 15% O2

CO			25		ppmvd

Particulates (TSP)	5		lb/hr

PM10			n/a		lb/hr

UHC			7		ppmvw

VOC			n/a		ppmvw

Electrical Output Guarantee	Adjusted Electrical Output > 77,800 kW (net of Unit auxiliary loads).

Specific Performance Electrical

Output Guarantee	Adjusted Electrical Output > 75,466 kW (net of Unit auxiliary loads)

Heat Rate Guarantee	Adjusted Heat Rate not to exceed 10,720 BTU/kWh (LHV).

Specific Performance Heat

Rate Guarantee	Adjusted Heat Rate not to exceed 11,042 BTU/kWh (LHV).

Output Liquidated Damages	If the Unit achieves the Specific Performance Electrical Output Guarantee during Performance Test, but fails to achieve the Electrical Output Guarantee, that amount which is equal to the positive difference between the Electrical Output Guarantee and the Adjusted Electrical Output of the Unit multiplied by $708/kW.

Heat Rate Liquidated Damages	That amount which is equal to the positive difference between the Adjusted Heat Rate of the Unit and the Heat Rate Guarantee multiplied by $14,650 per BTU/kWh (LHV).

Maximum Document

Liquidated Damages	$100,000 per Unit

Max. Delivery Liquidated

Damages	 $1,931,710 per Unit

Max. Takeover Liquidated

Damages	$1,931,710 per Unit

Max. Output Liquidated

Damages	$1,931,710 per Unit

Max. Heat Rate Liquidated

Damages	$2,897,565 per Unit

Max. Aggregate Liquidated

Damages	$5,795,130 per Unit

Overall Liability Cap	$19,317,100

[Remainder of page left intentionally blank]