## March 30, 2000

98-10947-LO-035

### PG&E Company

705 P Street, Third Floor

Fresno, CA 93760

Attn: 	Mr. Don Fantz

Subject:    	115kV Substation, CSU Fresno

Reference:	PG&E Detailed Study Design Meeting at PG&E Learning Center

Dear  Don:

Enron Energy Services (EES) and California State University, Fresno (CSUF) were pleased that the designs completed by EES and PG&E for the Herndon/Bullard Substation Yard work are very similar. These designs reveal we were comparing “apples to apples” at the March 7th cost comparison meeting at our San Ramon office.  However, after PG&E’s Project Manager explained their costs, we are extremely disappointed with their comment implying that the costs for the Detailed Study are known to be “high” and the “worst case scenario” was determined for all installations.

The only breakout that has been provided to date was the listing of seventeen categories on the January 24, 2000 letter by PG&E.   EES and CSUF requested to obtain a copy of PG&E’s itemized man-hour costs, subcontractor costs, and material costs to review and substantiate their underlying practicality. However, PG&E stated at yesterday’s meeting that there is a policy refusing to grant access to this breakout.  EES is unfamiliar with any written policy that states this provision.  At this time, I am requesting that PG&E provide the complete breakout.

By PG&E figuring the “worst case scenario” for all installations, the inflated Interconnection Costs are having a detrimental affect on the Project.  In addition to PG&E utilizing these inflated costs, EES and CSUF have numerous issues in response to the costs as they were verbally explained at yesterday’s meeting.  Listed below are some of the most conspicuous points we observed.

- The substation engineering was described to take a total of 255 man-days to conduct.  We find it hard to comprehend that such a simple design would require this much time, even if the numerous branches within PG&E were utilized, as described by your Project Manager.

- Property improvement category was explained to have activities such as road repair and yard repair.  With a Project of this size, any repair of the sort would be none to minimal.  However, this category has a cost of $11,605 before applicable taxes.

- Land and land rights category was described as containing monies to acquire the land rights for overbuilding the existing line.  Since the route is in an existing franchise land system, PG&E has stated that it is their policy to acquire these rights upon installing a transmission level system.  EES and CSUF do not agree with this view and request to see where this is a written policy within PG&E.   This category has $52,569 worth of costs before applicable taxes.

- With the overbuild of the existing 12kV line, we inquired why all the poles were required to be removed and replaced.  We request that PG&E look at replacing every other pole to accommodate the new 115kV circuit.  The spanning requirement for the 115kV would allow this consideration.  This would help reduce the costs within the transmission line construction category.

At the end of the meeting, PG&E proposed that for an unknown percentage of the two Engineering categories (transmission line and substation) a more accurate estimate could be provided.  The figure of $25,000 and the three months duration (an approximation provided by PG&E) seem ridiculous to conduct an exercise of refining numbers on such a basic Project.

EES and CSUF feel that the conceptual estimating techniques described by PG&E to calculate costs are severely impacting this Project.  I was surprised to hear the level of accuracy behind the development of the costs for the Detailed Study.  It was our understanding that with the money the University paid for a Detailed Study, a more thorough and accurate cost would be provided

Should you have any question or comments, please feel free to contact me.

Sincerely,

## ENRON ENERGY SERVICES

Robert M. Cone

Lead Project Manager

cc:	Dick Smith, CSUF

Dirk van Ulden, EES

Richard Crevelt, EES

Jeff Dasovich, Enron

Andy Wu, EES

Bob Kinert, PG&E