To: 	Enron North America Corp.

1400 Smith Street

Houston, TX   77002

Attn:	Janet Dietrich

Subject:    Amendment to March 7, 2000 Transformer Purchase Option

Your Reference	Our Reference	Date

2000-2001 Projects	HU-Enron-LM6000	May 12, 2000

Dear Ms. Dietrich,

By this letter, Enron and ABB agree to extend the transformer purchase option dated as of March 7, 2000 between the parties (the “March 7 Purchase Option”), as amended April 6, 2000, April 20, 2000, and on May 8, 2000. In consideration of the payment of $430,000, Enron and ABB agree as follows:

1.	The “Outside Exercise Date” is extended to June 30, 2000.

2.	Corresponding to the extension of the Outside Exercise Date, the parties agree that Section 1.8 of the March 7 Purchase Option shall be amended and restated to indicate that the 10% Cancellation Payment is applicable for cancellations from the Outside Exercise Date to ABB’s order entry of copper and steel.  The first line of the Cancellation Schedule shall read as follows:

Cancellation 			Milestone

Payment

10%				Outside Exercise Date

ABB shall hold firm the 10 shipping slots, so that the units will be shipped ex-works from ABB St. Louis on Oct. 20, 2000 (two units), November 17, 2000 (two units), December 1, 2000 (two units), December 15, (two units), and August 1, 2001 (two units).

3.	Enron and ABB agree to amend the March 7 Purchase Option by the addition of Section 2, ABB GSU Performance Data Sheets, (inclusive of the Technical Data Sheets HU-Enron-1C, HU-Enron-2D-LS and HU-Enron-2C) which are part of the attached Schedule 1.

4.	Due to the changes in design reflected in the Data Sheets referenced above, Enron and ABB further agree to amend Section 2.0 of the Amendment to Purchase Option Agreement dated April 6, 2000, which amended and restated Section 3.1 of the March 7 Purchase Option, by the deletion, in its entirety, of Section 2.0 and its replacement with the Section 1.1, Equipment Pricing, which is part of the attached Schedule 1.

All terms and conditions of the March 7 Purchase Option (as amended) other than those specifically referenced herein remain unchanged, including transformer shipping dates. Please indicate your acceptance of this amendment by signing this letter where indicated.

Should you have any questions, please let me know.

Sincerely,

Mike Sandridge

# Accepted by Enron as of May 12, 2000

# By:  _____________________________

Janet Dietrich

Schedule 1

Section 1.1  Equipment Pricing.

| Table Item | Primary Voltage | ABB Neg. Number | ABB Data Sheet # | Price ($)/Each |
| --- | --- | --- | --- | --- |
| Item 1 (3 winding) Quantity = 2 | 138 to 13.8-13.8 (64/85/106) | FCC011400-2C | HU-Enron-2C | $562,300.00 |
| Item 2 (3 winding) Quantity = 6 | 230/115 kV to 13.8-13.8 kV (64/85/106) MVA | FC011400-1C | HU-Enron-1C | $786,000.00 |
| Item 3 (2 winding) Quantity = 2 | 138/13.8 kV (84/112/140) | FC011400-2D-LS | HU-Enron-2D-LS | $782,000.00 |

## Section 2 Performance Data Sheets

ABB GSU Performance Data Sheets, (inclusive of the Technical Data Sheets HU-Enron-1C, HU-Enron-2D-LS and HU-Enron-2C) are attached hereto as Schedules 1A, 1B, and 1C.

#### Schedule 1A

# Technical Data Sheet	ENRON	April 6, 2000

# City of Austin Project	GSU (3W) Transformer	Tender No.: HU-Enron-2C

## RATING

| Type | CP | Temp. rise |  | Cooling | HV winding |  | 2LV windings |  | TV winding |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phases | 3 | Wind & Oil |  | Class | 138 | kV | 13.8/13.8 | kV |  | kV |
| Frequency | 60 | 65 |  | OA | 64 | MVA | 32/32 | MVA |  | MVA |
| Connection |  | 65 |  | FOA | 85 | MVA | 42.5/42.5 | MVA |  | MVA |
| Standards | ANSI | 65 |  | FOA | 106 | MVA | 53/53 | MVA |  | MVA |
| Off circuit taps: |  |  | +/-2 X 2.5% of 138 kV |  |  |  |  |  |  |  |

## PERFORMANCE DATA

| Voltage | Impedance |  | Load Losses * |  | No Load |  |  | Sound L. | Auxiliary |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| kV | Base MVA | % | MVA | kW | % Volt. | kW | % Cur. | dB(A) | kW |
| 138 | 64 H/(X-Y) | 9.0 | 64 | 138.6 | 100 | 43.2 | 0.18 | 79/81/82 | 7.2 |
|  | X/Y | 18.0 |  |  |  |  |  |  | - |

* Based on 85°C winding temperature

## DIELECTRIC TESTS

| Applied to Ground |  |  | Over Voltage |  |  | Full Wave Impulse |  |  | Switching Impulse |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | kV |  |  | KV | H1, H2, H3 | 550 | kV |  |  | kV |
|  |  | kV |  |  | KV | X1, X2, X3 | 110 | kV |  |  | kV |
|  |  | kV |  |  |  | Y1,Y2,Y3 | 110 | kV |  | - | kV |

## DIMENSIONS (inches) AND WEIGHTS (lbs) **

| Outline drawing |  |  |  | Core & coils weight | 125700 |
| --- | --- | --- | --- | --- | --- |
| Total height | 236 | Untanking height | 323 | Tank & fittings weight | 49100 |
| Total length | 275 | Transport height | 184 | Oil weight | 63900 |
| Total width | 225 | Transport length | 185 | Total weight | 238700 |
| Height over cover | 173 | Transport width | 125 | Transport | 161100 |

** Approximate, not for construction purpose

## ADDITIONAL DATA

### HV Bushings will have 650 kV BIL

#### Schedule 1B

# Technical Data Sheet	ENRON	May 17, 2000

# Project—LM6000 Projects	GSU  (3W) Transformer	Tender No.: HU-Enron-1C

## RATING

| Type | CP | Temp. rise |  | Cooling | HV winding |  | LV winding |  | TV winding |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phases | 3 | Wind & Oil |  | Class | 230/115 | kV | 13.8/13.8 | kV |  | kV |
| Frequency | 60 | 65 |  | OA | 64 | MVA | 32/32 | MVA |  | MVA |
| Connection |  | 65 |  | FOA | 85 | MVA | 42.5/42.5 | MVA |  | MVA |
| Standards | ANSI | 65 |  | FOA | 106 | MVA | 53/53 | MVA |  | MVA |
| Off circuit taps: |  |  | +/- 2 X 2.5% of 230 and / or 115 kV |  |  |  |  |  |  |  |

## PERFORMANCE DATA

| Voltage | Impedance |  | Load Losses * |  | No Load |  |  | Sound L. | Auxiliary |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| kV | Base MVA | % | MVA | kW | % Volt. | kW | % Cur. | dB(A) | kW |
| 230/115 | 64-H/ (X – Y) | 10.0 | 60 | 149.7 | 100 | 52.5 | 0.22 | 80/82/83 | 7.2 |
|  | 64-(X/Y) | 20 |  |  |  |  |  |  | - |

* Based on 85°C winding temperature

## DIELECTRIC TESTS

| Applied to Ground |  |  | Over Voltage |  |  | Full Wave Impulse |  |  | Switching Impulse |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | kV |  |  | kV | H1, H2, H3 | 750/550 | kV |  |  | kV |
|  |  | kV |  |  | kV | X1, X2, X3 | 110 | kV |  |  | kV |
|  |  | kV |  |  |  | Y1,Y2,Y3 | 110 | kV |  |  | kV |

## DIMENSIONS (inches) AND WEIGHTS (lbs) **

| Outline drawing |  |  |  | Core & coils weight | 135600 |
| --- | --- | --- | --- | --- | --- |
| Total height | 275 | Untanking height | 330 | Tank & fittings weight | 57300 |
| Total length | 290 | Transport height | 189 | Oil weight | 84600 |
| Total width | 238 | Transport length | 200 | Total weight | 277500 |
| Height over cover | 178 | Transport width | 138 | Transport weight | 178200 |

** Approximate, not for construction purpose

## ADDITIONAL DATA

#### Schedule 1C

# Technical Data Sheet	ENRON	May 17, 2000

# ProjectLas Vegas Project	GSU (2W) Transformer	 HU-Enron-2D-LS (Lower Sound)

## RATING

| Type | CP | Temp. rise |  | Cooling | HV winding |  | LV winding |  | TV winding |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phases | 3 | Wind & Oil |  | Class | 138 | kV | 13.8 | kV |  | kV |
| Frequency | 60 | 65 |  | OA | 84 | MVA | 84 | MVA |  | MVA |
| Connection |  | 65 |  | FA | 112 | MVA | 112 | MVA |  | MVA |
| Standards | ANSI | 65 |  | FA | 140 | MVA | 140 | MVA |  | MVA |
| Off circuit taps: |  |  | +/-2 X 2.5% of 138 |  |  |  |  |  |  |  |

## PERFORMANCE DATA

| Voltage | Impedance |  | Load Losses * |  | No Load |  |  | Sound L. | Auxiliary |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| kV | Base MVA | % | MVA | kW | % Volt. | kW | % Cur. | dB(A) | kW |
| 138 | 84 H/X | 9.0 | 84 | 161.0 | 100 | 57.0 | 0.17 | 70/72/73 | 6.5 |

* Based on 85°C winding temperature

## DIELECTRIC TESTS

| Applied to Ground |  |  | Over Voltage |  |  | Full Wave Impulse |  |  | Switching Impulse |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | kV |  |  | kV | H1, H2, H3 | 650 | kV |  |  | kV |
|  |  | kV |  |  | kV | X1, X2, X3 | 110 | kV |  |  | kV |
|  |  | kV |  |  |  | Y1,Y2,Y3 | 110 | kV |  | - | kV |

## DIMENSIONS (inches) AND WEIGHTS (lbs) **

| Outline drawing |  |  |  | Core & coils weight | 158200 |
| --- | --- | --- | --- | --- | --- |
| Total height | 243 | Untanking height | 338 | Tank & fittings weight | 66600 |
| Total length | 350 | Transport height | 190 | Oil weight | 90200 |
| Total width | 195 | Transport length | 200 | Total weight | 315000 |
| Height over cover | 179 | Transport width | 143 | Transport | 200000 |

** Approximate, not for construction purpose

## ADDITIONAL DATA

### HV Bushings will have 650 kV BIL